## Slide 1
Risk Management
Notes: Advance Project Management - CPH
Module 4 - Risk Management
<number>

## Slide 2
35
Risk Definitions
Risk Management
The practice of dealing with project risk. It includes planning for risk, assessing risk, developing risk response strategies, and monitoring risk throughout the project life cycle.

## Slide 3
35
Risk Definitions
Risk
Uncertain event that has a positive or negative effect on at least one of the project objectives (scope, schedule, budget, quality).

## Slide 4
35
Risk Definitions
Threat
A project risk that has a negative effect.
Project Managers will look for ways to eliminate or reduce the effects of a threat.

## Slide 5
35
Risk Definitions
Opportunity
A project risk that has a positive effect.
Project Managers will look for ways to enhance, exploit, or share the effects of an opportunity.

## Slide 6
35
Risk Definitions
Risk Trigger
An indicator that a risk event is imminent.

## Slide 7
Risk Definitions
Risk Tolerance
Risk Adverse / Risk Averter
Risk Neutral
Risk Taker / Risk Seeker
35

## Slide 8
Risk Tolerance
U
$
Tolerance diminishes as more money is at stake.
Prefers a more certain outcome and will demand a premium to accept risk.
Risk Adverse / Risk Avoider
36

## Slide 9
36
Risk Tolerance
Risk Neutral
U
$
Utility rises at a constant rate.

## Slide 10
36
Risk Tolerance
Risk Taker / Risk Seeker
U
$
Tolerance increases as more money is at stake.
Prefers a more uncertain outcome and be willing to pay a penalty to take a risk.

## Slide 11
WSDOT Risk Policy
Executive Order 1032.00E
Project Management On-Line Guide
Risk Register
37
www.wsdot.wa.gov/Projects/ProjectMgmt/

## Slide 12
WSDOT Risk Policy
Cost Risk Estimating & Management (CREM)
CEVP – Cost Estimate Validation Process
CRA – Cost Risk Assessment
37
www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/

## Slide 13
38
Risk Planning Process
Risk Management Planning
The objectives of Risk Management Planning are to increase the probability and impact of positive events (opportunities) and decrease the probability and impact of adverse events (threats) to project objectives.

## Slide 14
Ignoring risk doesn’t make the risk go away!
38
Risk Management Planning
Protects project investments
Proactive management – early warning
Achieve project objectives
Risk Planning Process

## Slide 15
38
Risk Planning Process
Risk Management Planning Steps
Step 1 – Review Organization Risk Policy
Step 2 – Risk Identification
Step 3 – Qualitative Risk Analysis

## Slide 16
38
Risk Planning Process
Risk Management Planning Steps
Step 4 – Quantitative Risk Analysis
Step 5 – Develop Risk Response Strategy
Step 6 – Risk Monitoring & Control

## Slide 17
38
Risk Management Planning – Step 1
Review Organization Risk Policy
Does this project require assistance from the CREM office?
What direction and tools are given in the Project Management On-Line Guide?
What is the Risk Profile of the Agency and Project Team?

## Slide 18
38
Risk Management Planning – Step 2
Risk Identification
Brainstorming
Delphi Technique
Interviewing

## Slide 19
38
Risk Identification
Root Cause Identification
SWOT Analysis
Assumption Analysis
Diagramming Techniques
Risk Management Planning – Step 2

## Slide 20
39
Outcome: Risk Register
Status (active, dormant, retired)
ID#
Date identified & Project Phase
Risk Management Planning – Step 2

## Slide 21
39
Risk Management Planning – Step 2
Outcome: Risk Register
Functional Assignment
Risk Event (SMART Technique)
Risk Trigger

## Slide 22
39
Exercise – Risk Identification
Risk Identification Exercise
As a team identify risk events for either:
  A Caribbean vacation
  Building a custom home
As a group, select a project and identify potential risk events. Brainstorm potential risks events, use the SMART method to define the risks and root cause identification for the risk trigger. Record on Risk Register.

## Slide 23
40
Risk Management Planning – Step 3
Qualitative Risk Analysis
Prioritizing risks for subsequent further analysis or action by assessing and combining their probability of occurrence and impact.

## Slide 24
40
Risk Management Planning – Step 3
Impact/Probability Matrix
A common method/tool to determine whether a risk is considered low, moderate, or high by combining the two dimensions of a risk: its probability of occurrence, and its impact on objectives if it occurs.

## Slide 25
40
Risk Management Planning – Step 3
Impact/Probability Matrix
Incorrect: confusing or combining Impact & Probability
  “It is very unlikely, therefore the impact is low”
Correct: Keep Impact & Probability independent
  “Probability is low, but if it happens, the project will fail. Therefore the impact is high”

## Slide 26
Risk Management Planning – Step 3
40
Impact
Probability
Low
High
Low
High
Green: Low Risk (Passive Acceptance – workarounds)
Yellow: Moderate Risk (Active Acceptance – contingency)
Red: High Risk (Risk Response Planning)
Using a 2x2 Impact/Probability Matrix

## Slide 27
Impact
Risk: Key project team member with specialized skill leaves project team before work is done.
Impact: High
Probability: Low
Yellow Zone – Moderate Risk
2x2 Impact/Probability Matrix example
Impact
Probability
Low
High
Low
High
Risk Management Planning – Step 3
40
X

## Slide 28
Impact
Risk: Change to regulatory ordinance requires additional wetland mitigation, requiring additional R/W
Impact: High
Probability: High
2x2 Impact/Probability Matrix example
Impact
Probability
Low
High
Low
High
X
Risk Management Planning – Step 3
40
Red Zone – High Risk

## Slide 29
Impact
Risk: Mariners first World Series game is scheduled on the same date as the Environmental Hearing
Impact: Low
Probability: Low
2x2 Impact/Probability Matrix example
Impact
Probability
Low
High
Low
High
X
Risk Management Planning – Step 3
40
Green Zone – Low Risk

## Slide 30
Comparative Risk Rating
Risk Management Planning – Step 3
41
A
B
C
D
A
B
C
D
A
C
B
C
A
C
Risk A – 2
Risk B – 1
Risk C – 3
Risk D – 0
Priority Order:
C – A – B – D

## Slide 31
42
Exercise – Qualitative Risk Analysis
Qualitative Risk Analysis Exercise
Using a 2x2 impact & probability matrix, assess the risks identified in the last exercise.
  First, evaluate the impact of the risk event on the project objectives
  Then, with the risks identified as “high” impact, assess the probability of the risk event.
  Perform a comparative risk rating on the “high-high” (red zone) risk events

## Slide 32
Risk Management Planning – Step 4
43
Quantitative Risk Analysis
The process of numerically analyzing the effect of identified risks on the project’s objectives. (In particular, the project schedule and the project costs).

## Slide 33
Cost Risk Estimating & Management (CREM) Office
CRA: Cost Risk Assessment (pg.37)
  $25 million or more
  $5 million or more with specific characteristics
CEVP®: Cost Estimate Validation Process (pg.37)
  $100 million or more
Risk Management Planning – Step 4
43

## Slide 34
Quantitative Risk Analysis
  Quantify possible outcomes for the project
  Assess probability of achieving specific project objectives
  Identify risks requiring most attention
Risk Management Planning – Step 4
43

## Slide 35
43
Quantitative Risk Analysis
  Identify realistic and achievable cost, schedule, or scope targets, given project risks
  Determine best management decision when conditions or outcomes are uncertain
Risk Management Planning – Step 4

## Slide 36
43
Quantitative Risk Analysis tools
  Interviewing (SMEs)
  Decision Tree Analysis
  Monte Carlo Simulation
Risk Management Planning – Step 4

## Slide 37
43
Quantitative Risk Analysis products
  Updated Risk Register
  Probabilistic analysis for project success (time and cost)
  Updated priority of risk events
  Trends in risk analysis
Risk Management Planning – Step 4

## Slide 38
Risk Management Planning – Step 4
44
25%
50%
75%
100%
0%
$30m
$33m
$36m
$39m
$37.5m
90%
15%
COST
PROBABILITY
TOTAL PROJECT COSTS
Cumulative Chart
Contingency

## Slide 39
Risk Management Planning – Step 5
45
Risk Response Strategy
The process of developing options and actions to enhance opportunities and to reduce threats to the project objectives.

## Slide 40
Risk Management Planning – Step 5
45
Risk Response Strategy
Proactive, not reactive
Appropriate to significance of risk
Cost effective
Timely

## Slide 41
Risk Management Planning – Step 5
45
Risk Response Strategy
Realistic within project context
Agreed upon by project team and all parties involved
Assigned to / owned by a responsible person

## Slide 42
Risk Management Planning – Step 5
45
Risk Response Definitions
Avoidance – Changing a project objective to eliminate the threat posed by an adverse risk event.

## Slide 43
Risk Management Planning – Step 5
45
Risk Response Definitions
Transference – Shifting the negative impact of a threat, along with the ownership of the response, to a third party.

## Slide 44
Risk Management Planning – Step 5
45
Risk Response Definitions
Mitigation – Reducing the Probability or Impact of an adverse risk event (threat) to an acceptable threshold.

## Slide 45
Risk Response Definitions
Acceptance – The project team decides not to change project objectives to deal with the risk.
  Passive acceptance: no action , deal with threats as they occur (workarounds)
  Active acceptance: establish a contingency reserve to handle risks
Risk Management Planning – Step 5
45

## Slide 46
Impact
Probability
Low
High
Low
High
A
T
M
Passive
Acceptance
(workaround)
Active
Acceptance
(or
A – T – M)
Risk Response Strategy (threats)
Risk Management Planning – Step 5
45

## Slide 47
Risk Response Definitions
Exploit – This strategy seeks to eliminate the uncertainty with an opportunity by changing a project objective to ensure it happens.
Risk Management Planning – Step 5
46

## Slide 48
Risk Response Definitions
Share – Allocating ownership of the positive risk event to a third party who is best able to capture the opportunity for the project.
Risk Management Planning – Step 5
46

## Slide 49
Risk Response Definitions
Enhance – Increasing the probability and/or positive impact of an opportunity.
Risk Management Planning – Step 5
46

## Slide 50
Risk Response Definitions
Contingency – Not a risk response, but an output from risk planning. Developed for actively accepted project risks. This is typically defined as time or funds.
Risk Management Planning – Step 5
46

## Slide 51
47
Exercise – Qualitative Risk Analysis
Risk Response Strategy Exercise
Using the results from the qualitative analysis from the last exercise:
  Identify risk response strategies for the “high-high” (red zone) risk events.
  Decide who will be the responsible person to monitor the risk event and the effectiveness of the risk response
  Decide if active acceptance or further risk response planning will be required for the “high-low” (yellow zone) risk events.

## Slide 52
Risk Monitoring & Control
Managing the Risk Register during the “Work the Plan” phase of the project.
Recognize the probability and impact of risk events may change during the life of the project.
Also recognizing that additional risks events can be identified during the “Work the Plan”.
Risk Management Planning – Step 6
48

## Slide 53
Risk Monitoring & Control
Assign a responsible party (ownership) of the risk event.
Track risk event status
  Active/Dormant: risk is currently being monitored and analyzed
  Retired: risk event (trigger) no longer poses a threat to the project.
Risk Management Planning – Step 6
48

## Slide 54
Risk Monitoring & Control
Risk Registers should be a standing agenda item for project team meetings.
Risk reporting should be an standing reporting item for all project progress reporting
WSDOT tools for reporting (PDIS, QPR, GMAP).
Risk Management Planning – Step 6
48