## Costed Work Plan
Activities | Action Required | Timeline | Expected Output | Expected Outcome | Responsible Entity | Status | Budget (Php) |  |  |  | Budget (USD)
[7 empty] | GoP | Donors | Stakeholders | Total | GoP | Donors | Stakeholders | Total | Notes
OBJECTIVE 1: ESTABLISH COMMITMENT AND SUPPORT TO IMPLEMENT EITI | [5 empty] | OBJECTIVE 1: ESTABLISH COMMITMENT AND SUPPORT TO IMPLEMENT EITI
1.1 Philippines issues unequivocal public statement of its intention to implement the EITI | The Philippine Government issued Executive Order (EO) 79[i] , with a section explicitly stating its desire to participate in the EITI | July 2012 | A statement from the Philippine Government committing to implement EITI in the country | Demonstrated commitment of the Philippine Government implement EITI in the country | Office of the President (OP) | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 Appointment of a senior Philippine Government official to lead EITI implementation | Senior official appointed to lead PH-EITI | August 2012 | Sec. Elisea Gozun, Presidential Adviser on Climate Change, was appointed by the MICC[ii] with the approval of President “Aquino, to be the focal point person for EITI implementation | Provision of strategic leadership to the EITI process and implementation by Sec. Elisea Gozun | Mining Industry Coordinating Council (MICC), Office of the President | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 Government commitment to work with all stakeholders on EITI | Dialogue with the business sector and civil society organizations to work together for the implementation of EITI | August 2012 | Commitment from the business sector and the civil society organizations to implement EITI in the Philippines | Established collaboration among the stakeholders | Sec. Elisea Gozun, Office of the Presidential Adviser on Climate Change | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 Public announcement of the Government to implement EITI and work with all the stakeholders of the extractive industry | A press conference where the President or the Presidential Spokesperson will reiterate the commitment of the government to implement EITI and work with all the stakeholders. The president will announce in the same conference the appointment of senior official to lead EITI in the country | April 2013 | Public announcement of the appointment of the PH-EITI focal point person and the government’s commitment to implement EITI, work with all stakeholders | Increased awareness of the public regarding the implementation of EITI in the Philippines | PH-EITI Secretariat, Sec. Edwin Lacierda | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 Establish commitment from different stakeholders | Regional consultations of different members of civil society organizations to inform them about EITI and understand the implication of implementing EITI in the Philippines | October-December 2012 |  | Increased awareness and support for EITI implementation in the Philippines | Bantay Kita, PH-EITI interim Secretariat | Achieved | 275791.81 | 431273.18 | 0 | 707064.99 | 6894.7953 | 10781.8295 | 0 | 17676.6247 | CSO Regional Consultations to Five Provinces and Training of Trainors
| Outreach to specific sectors: government regional offices, church, local officials, indigenous peoples’ groups, academe | February 2013 | Commitment/ support from key stakeholders on the implementation of PH-EITI | Increased awareness and support for EITI implementation in the Philippines | Interim PH-EITI Secretariat, Sec. Elisea Gozun of the Office of the Presidential Adviser on Climate Change | Achieved | 0 | 214143 | 0 | 214143 | 0 | 5353.575 | 0 | 5353.575 | Approved budget by British Embassy but not the actual expenses (actual expenses still needs to be finalized by Bantay Kita)
OBJECTIVE TOTAL | [6 empty] | 275791.81 | 645416.18 | 0 | 921207.99 | 6894.7953 | 16135.4045 | 0 | 23030.1997
OBJECTIVE 2. FORM THE MULTI-STAKEHOLDER GROUP, DEVELOP AND PUBLISH THE TERMS OF REFERENCE OF THE MSG AND WORKPLAN OF EITI | [5 empty] | OBJECTIVE 2. FORM MSG, DEVELOP AND PUBLISH ITS TERMS OF REFERENCE AND THE EITI WORKPLAN
2.1 Formation of the Philippine EITI Multi-stakeholders Group (MSG) | The focal point person invites the Chamber of Mines and the Bantay Kita coalition to form the interim PH-EITI Multi-Stakeholder Group (PH-EITI MSG) | August 22, 2012 | Formation of the interim MSG with 3 representatives from the government, the industry and the CSOs | Commitment from Chamber of Mines and Bantay Kita to organize the MSG of PH-EITI and work on the draft TOR and workplan | Sec. Elisea Gozun of the Office of the Presidential Adviser on Climate Change, Bantay Kita, COMP, interim MSG, interim PH-EITI Secretariat | Achieved | 0 | 0 | - | 0 | 0 | 0 | - | 0
| Regular meeting of the interim MSG to plan for the selection of industry and civil society representatives in the MSG, work on the draft TOR and work plan | August –January 2013 | Plan for the selection of industry and civil society representatives in the MSG, draft TOR and workplan | Formation of the PH-EITI MSG | Chamber of Mines, Bantay Kita, Office of the Presidential Adviser on Climate Change | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | Food and Venue expenses were provided by DBM in kind. The meetings werejust considered DBM-AS supported meetings
| Consultations with industry stakeholders who are non-chamber members on the selection of representatives in the MSG of PH-EITI | August –January 2013 | Process of selecting industry representatives in the MSG for non-chamber members | Greater involvement from the non-chamber members of the extractive industry | Mr. Romualdo Aguilos, Mines and Geosciences Bureau (MGB), interim EITI Secretariat, and Sec. Elisea Gozun | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | This activity is part of the National Planning Workshop
| Consultations with industry stakeholders of oil and gas sector on their participation in PH-EITI and selection of representatives in the MSG of PH-EITI | January 2013 | Participation of oil and gas industry in the PH-EITI | Greater involvement from the oil and gas sector | Sec. Elisea Gozun, interim PH-EITI Secretariat | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Expenses were shouldered by the Petroleum Association of the Philippines
| Subnational consultations of Bantay Kita on the criteria and process of selection of CSO MSG representatives for PH-EITI | October-December 2012 | Criteria and process of selecting CSO representatives for the MSG of PH-EITI | Commitment and support to implement PH-EITI | Bantay Kita, PH-EITI interim secretariat | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Same with Regional Consultations
| Consultation among Chamber of Mines of the Philippines (COMP) members on the selection of the industry MSG representatives | January 2013 | Identification of representatives to the MSG of the Chamber of Mines | Commitment and support to implement PH-EITI | Chamber of Mines of the Philippines | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Selection of representative for oil and gas sector to the PH-EITI MSG | January 2013 | Identification of representative of the oil and gas industry | Commitment and support to implement PH-EITI | Petroleum Association of the Philippines | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Selection of official representatives from the mining industry and the civil society organizations to the MSG of PH-EITI | January 17-19, 2013 | Official representatives of the industry and civil society organizations to the MSG of PH-EITI | Commitment and support to implement PH-EITI | PH-EITI interim Secretariat, Sec. Elisea Gozun, interim MSG, Bantay Kita, COMP | Achieved | 392200 | 984414.13 | 0 | 1376614.13 | 9805 | 24610.3533 | 0 | 34415.3533 | CSO Congress and EITI National Planning Workshop
2.2 Development and publication of PH-EITI MSG TOR and work plan and submission to the International EITI Secretariat to satisfy the requirement for candidacy | Regular meeting of the interim MSG to draft the TOR and work plan for consultation | August 2012–January 2013 | Draft TOR of the MSG of PH-EITI and fully-costed work plan | Availability of draft TOR and work plan prepared by the interim MSG for consultation with stakeholders | Chamber of Mines, Bantay Kita, Office of the Presidential Adviser on Climate Change, interim PH-EITI Secreatiart, interim PH-EITI MSG | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Food and Venue expenses were provided by DBM in kind. The meetings werejust considered DBM-AS supported meetings
| Consultation with stakeholders on the draft work plan and TOR | January 18-19, 2013 | Inputs from all the stakeholders on the draft TOR and work plan | Broad-based support on the TOR and work plan of PH-EITI | Interim MSG, Office of the Presidential Adviser on Climate Change, interim PH-EITI Secretariat | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The expenses for this activity were incorporated into the item on CSO Congress and National Planning Workshop
| Planning Workshop by the MSG of the PH-EITI to finalize the TOR, work plan and application form for submission to EITI International Secretariat | January to March 2013 | Completed TOR and fully-costed workplan | Completion of requirements for candidacy of the Philippines to EITI | PH-EITI MSG, interim PH-EITI Secretariat | Achieved | 0 | 53000 | 0 | 53000 | - | 1325 | 0 | 1325 | Food and Venue expenses were provided by DBM in kind. The meetings werejust considered DBM-AS supported meetings | This is the detailed planning workshop by PH-EITI MSG to finalize the TOR and Work plan (the 1st and 2nd MSG meeting)
| Conduct of PH-EITI Official Launching to publicly announce Philippines’ application to EITI | April 2013 | Public announcement of Philippines’ application to EITI | Increased public awareness regarding EITI | Sec. Elisea Gozun and PH-EITI Secretariat | Achieved | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
2.3 Submission of Final Application for EITI Candidacy | Send completed application to EITI International Secretariat to become a candidate country | April 5, 2013 | Completed application of the Philippines for candidacy to EITI | Compliance to the requirement for EITI candidacy | PH-EITI Secretariat | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OBJECTIVE TOTAL | [6 empty] | 392200 | 1037414.13 | 0 | 1429614.13 | 9805 | 25935.3533 | 0 | 35740.3533
OBJECTIVE 3.INSTITUTIONALIZE PH-EITI | [5 empty] | OBJECTIVE 3.INSTITUTIONALIZE PH-EITI
3.1 Formal creation of PH-EITI and establishment of EITI National Secretariat | Set up an interim PH-EITI Secretariat (PMO) | August 2012 | Interim PH-EITI Secretariat | Initiation of work on PH-EITI | Sec. Elisea Gozun | Achieved | 0 | 0 |  | 0 | 0 | 0 | - | 0
| Define operational requirement of PH-EITI Secretariat (e.g. Secretariat staffing requirements, budget requirements, logistical requirements) | 2nd quarter, 2013 | Operational plan of the PH-EITI Secretariat | Institutionalization of PH-EITI Secretariat | Interim PH-EITI Secretariat, PH-EITI MSG | On-going | 6646554 | 1854000 | - | 8500554 | 166163.85 | 46350 | - | 212513.85 | The detailed costing for this is in a separate sheet
| Issuance of an Order creating an EITI Secretariat (PMO) | 3rd quarter 2013 | Order formally creating PH-EITI | Institutionalization of PH-EITI | Department of Finance or Office of the President | Pending | - | - | - | - | - | - | - | -
3.2 Identify sustainable sources of financing for PH-EITI implementation | Secure government funding and submit proposals to raise funds from donors including the EITI Multi-Donor Trust Fund (MDTF) to support PH-EITI implementation | 2nd to 3rd quarter, 2013 | Funds for PH-EITI Secretariat | Implementation of PH-EITI | PH-EITI MSG and Secretariat | On-going | 0 | 0 | - | 0 | 0 | 0 | - | 0
3.3 Strengthen PH-EITI Secretariat | Train PH-EITI Secretariat and PH-EITI TWG[iii] and MSG on EITI implementation | 3rd to 4th quarter, 2013 | Capable Secretariat, TWG and MSG of PH-EITI to support the EITI implementation | Implementation of PH-EITI | PH-EITI Secretariat, EITI International Secretariat | Pending | 601500 | 1272000 | 150000 | 2023500 | 15037.5 | 31800 | 3750 | 50587.5
3.4 Address barriers to implementation and institutionalize PH-EITI | Hire consultant to review the legal and administrative and other barriers in the implementation of PH-EITI and propose strategies to address the barriers | 3rd quarter, 2013 | Policy report on the barriers for PH-EITI implementation and possible policy reforms | Implementation of PH-EITI | Consultant, PH-EITI Secretariat | Pending | - | 100000 | - | 100000 | - | 2500 | - | 2500
| Engage the Legislative and the Executive branches of government to address barriers to the full implementation of EITI | Throughout 2013 | Proposed amendments to existing policies | Implementation of PH-EITI | PH-EITI MSG and Secretariat | Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Engage Congress to adopt a law that will institutionalize PH-EITI | 2013 onwards | Bill institutionalizing PH-EITI | Institutionalization of PH-EITI | PH-EITI MSG and Secretariat, EITI champions in Congress | Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5 Subnational implementation of PH-EITI | Hire consultant to (1) develop the module on harmonizing the implementation of EITI at the subnational level and the current government policies in increasing participatory public finance at the local government level (2)develop a plan to harmonize national and subnational EITI implementation | 3rd to 4th quarter, 2013 | Guide in implementing subnational PH-EIti | Expansion of PH-EITI implementation | Consultant, PH-EITI MSG and Secretariat | Pending | 0 | 200000 | - | 200000 | 0 | 5000 | - | 5000
| Provide technical assistance to pilot sites, capability building and institutional preparation for sub national implementation of EITI | 4th quarter of 2013 and continuing | Pilot sites for subnational implementation | Expansion of PH-EITI implementation | Consultant, PH-EITI MSG and Secretariat | Pending | 1750000 | 2537500 | 700000 | 4987500 | 43750 | 63437.5 | 17500 | 124687.5
3.6 Regular meeting of PH-EITI MSG | MSG members should meet once a month or as frequently as possible depending on the demand of EITI | May 2013 to 2014 | Decisions on critical issues related to implementation of EITI in the Philippines | Effective implementation of EITI in the Philippines | PH-EITI MSG and Secretariat | On-going | 1020000 | 1600000 | - | 2620000 | 25500 | 40000 | - | 65500
OBJECTIVE TOTAL | [6 empty] | 10018054 | 7563500 | 850000 | 18431554 | 250451.35 | 189087.5 | 21250 | 460788.85
OBJECTIVE 4: PREPARE TO IMPLEMENT AND MONITOR PH-EITI | [5 empty] | OBJECTIVE 4: PREPARATION IN IMPLEMENTING AND MONITORING PH-EITI
4.1 Prepare of reference materials for EITI implementation | Identify payment of companies to government and incentives provided by government to companies, map out sources of data and provide recommendation on the level of materiality in reporting. | 3rd quarter, 2013 | Scoping study on payments and incentives, sources of data for verification of reported payments and recommended templates for reporting with recommended level of materiality | MSG will have materials to level off on the level and scope of EITI reporting | PH-EITI National Secretariat, consultants | Pending | 0 | 600000 | - | 600000 | 0 | 15000 | - | 15000 | Expected output of the consultant: mapping out of sources of data, recommendations for materiality and template
| MSG to agree on scope, level of disaggregation and materiality of reporting. | 2nd quarter, 2013 | Parameters in reporting | Implementation of PH-EITI | PH-EITI MSG | Achieved | - | - | - | - | - | - | - | - | Included in the budget for the regular meeting of MSG
| Drafting of templates for reporting based on the level of disaggregation and materiality as agreed upon by the MSG | 3rd to 4th quarter, 2013 | Draft templates for reporting | Implementation of PH-EITI | PH-EITI Secretariat, Consultant | Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Included in the budget for scoping study
| Finalize reporting policies, mechanisms, and templates | 4th quarter, 2013 | Approved policies on reporting mechanisms and templates | Implementation of PH-EITI | PH-EITI MSG | Pending | - | - | - | - | - | - | - | -
4.2 Build the required capacity for EITI implementation, monitoring and reporting | Scoping study to assess the capacity of regulatory agencies and tax administration agencies, extractive industries in generating the data needed to produce the report and complete the template | 3rd to 4thquarter, 2013 | Scoping study on capacity assessment of stakeholders | Better and more reliable reports of PH-EITI | PH-EITI Secretariat, Consultant | Pending | 0 | 300000 | - | 300000 | 0 | 7500 | - | 7500
| Conduct training with government agencies on how to complete the reporting template | 4th quarter, 2013 onwards | Capacity building for government agencies | Better and more reliable reports of PH-EITI | PH-EITI Secretariat, Consultant | Pending | 110000 | 304000 | - | 414000 | 2750 | 7600 | - | 10350
| Conduct training with local government units on how to complete the reporting template | 4th quarter, 2013 onwards | Capacity building for local government units | Better and more reliable reports of PH-EITI | PH-EITI Secretariat, Consultant | Pending | 215000 | 802500 | - | 1017500 | 5375 | 20062.5 | - | 25437.5
| Conduct training with industry on how to complete the reporting template | 4th quarter, 2013 onwards | Capacity building for industry | Better and more reliable reports of PH-EITI | PH-EITI Secretariat, Consultant | Pending | 54000 | 144000 | - | 198000 | 1350 | 3600 | - | 4950
| Conduct training with CSOs to understand PH-EITI reporting (also includes media) | 4th quarter, 2013 onwards | Capacity building for CSO | Better and more reliable reports of PH-EITI | PH-EITI Secretariat, Consultant | Pending | 162500 | 515000 | - | 677500 | 4062.5 | 12875 | - | 16937.5
| Organize EITI Study Tour in an EITI implementing country | 3rd quarter to 4th, 2013 | Report on experiences and challenges of other countries in implementing EITI | Increased knowledge on EITI implementation | PH-EITI Secretariat with assistance from EITI International Secretariat | Pending | 0 | 2991000 | 0 | 2991000 | 0 | 74775 |  | 74775
| Submission of completed reporting templates | 1st quarter to 2nd quarter, 2014 | Completed reporting templates from the 35 mining sites and the government agencies concerned | Implementation of PH-EITI | Companies involved in the first EITI report, government agencies, PH-EITI Secretariat | Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OBJECTIVE TOTAL | [6 empty] | 541500 | 5656500 | 0 | 6198000 | 13537.5 | 141412.5 | 0 | 154950
OBJECTIVE 5: AUDIT/RECONCILE AND REPORT ON REVENUE FLOWS BETWEEN PHILIPPINE GOVERNMENT AND EXTRACTIVE INDUSTRIES | [5 empty] | OBJECTIVE 5: AUDIT/RECONCILE AND REPORT ON REVENUE FLOWS BETWEEN PHILIPPINE GOVERNMENT AND EXTRACTIVE INDUSTRIES
5.1 Hiring of independent reconciler | The MSG hires the reconciler for analyze the government and industry data for the EITI report | 2nd quarter, 2014 | Reconcilation of data and preparation of PH-EITI report | Implementation of PH-EITI | Independent reconciler | Pending | 3150000 | 0 | - | 3150000 | 78750 | 0 | 0 | 78750
5.2 Preparation and Publication of EITI report | Release of the draft PH-EITI report to the MSG | 3rd quarter, 2014 | Reviewed PH-EITI report | Implementation of PH-EITI | PH-EITI Secretariat | Pending | 0 | 0 |  | 0 | 0 | 0 |  | 0
| MSG discussion and approval of EITI report | 3rd quarter, 2014 | Reviewed and Approved first PH-EITI report | Implementation of PH-EITI | PH-EITI MSG | Pending | - | - | - | - | - | - | - | - | Included in the budget for the regular meeting of MSG
| Publication of 1st Philippine EITI report | 4th quarter, 2014 | Published first PH-EITI report | Implementation of PH-EITI | PH-EITI MSG and Secretariat | Pending | 2200000 | 1750000 | - | 3950000 | 55000 | 43750 | - | 98750
5.3 Independent validation of the EITI report | Validation of the progress of PH-EITI implementation | 2nd to 3rd quarter of 2014 | Independent validation of the PH-EITI report | Validation of the PH-EITI report | International Secretariat | Pending | - | - | - | - | - | - | - | -
| Preparation of EITI validation report | 3rd to 4th quarter, 2014 | Validated PH-EITI report | Validation of the PH-EITI report | International Secretariat | Pending
| Respond to validator’s assessment and recommendations | 3rd to 4thquarter, 2014 | Reconciliation of the gaps in the PH-EITI report | Validation of the PH-EITI report | PH-EITI TWG and MSG | Pending | - | - | - | - | - | - | - | - | Included in the budget for the regular meeting of MSG
OBJECTIVE TOTAL | [6 empty] | 5350000 | 1750000 | 0 | 7100000 | 133750 | 43750 | 0 | 177500
OBJECTIVE 6: COMMUNICATE, BUILD KNOWLEDGE, AND ENGAGE CITIZENS IN THE PH-EITI PROGRAM | [5 empty] | OBJECTIVE 6: COMMUNICATE, BUILD KNOWLEDGE, AND ENGAGE CITIZENS IN THE PH-EITI PROGRAM
6.1 Establish and maintain EITI website | Create and maintain an EITI website to make all information regarding PH-EITI accessible to the public and to engage the public on the plans and works of PH-EITI. | 2nd quarter, 2013 onwards | A dynamic website that will contain all the information pertaining to PH-EITI including minutes of PH-EITI MSG meetings, data, background materials, researches, etc. | Well-informed public on the works of PH-EITI. | PH-EITI Secretariat, Consultant | On-going | - | 236000 | - | 236000 | - | 5900 | - | 5900
6.2 Establish Management Information System for the extractive industry | Improve procedures and information infrastructures (including ICT system) for the transmission, consolidation, stewardship and publication of data from extractive industries | 3rd to 4th quarter, 2013 | Procedures and information infrastructure on extractive industry data | Improved access to information on extractive industry data | PH-EITI Secretariat, Consultant | Pending | 0 | 1600000 | - | 1600000 | 0 | 40000 | - | 40000
6.3 Sub-national, national and international outreach | Conduct continuous outreach activities, meetings and workshops with stakeholders to keep them informed and involved in PH-EITI | continuous | Increased awareness and support for PH-EITI | Better implementation of PH-EITI | Sec. Elisea Gozun, PH-EITI MSG and Secretariat | On-going | 70000 | 984000 | - | 1054000 | 1750 | 24600 | - | 26350
6.4 Media outreach | Release of statement and press briefings on PH-EITI activities including Workshop with media group on EITI | 2nd Quarter of 2012 and continuing | Increased awareness and support for PH-EITI | Better implementation of PH-EITI | Sec. Elisea Gozun , PH-EITI Secretariat | Pending | 360000 | - | - | 360000 | 9000 | - | - | 9000
6.5 Public dissemination of EITI report | Conduct a national conference to launch EITI report | 4th quarter 2014 | Increased awareness on the EITI report | Increased discussion and debate on the EITI report | PH-EITI Secretariat | Pending | 472000 | 340000 |  | 812000 | 11800 | 8500 |  | 20300
OBJECTIVE TOTAL | [6 empty] | 902000 | 3160000 | 0 | 4062000 | 22550 | 79000 | 0 | 101550
GRAND TOTAL | [6 empty] | 17479545.81 | 19812830.31 | 850000 | 38142376.12 | 436988.6453 | 495320.7577 | 21250 | 953559.403
Notes:
[i] E.O. 79, s. 2012, Institutionalizing and Implementing Reforms in the Philippine Mining Sector Providing Policies and Guidelines to Ensure Environmental Protection and Responsible Mining in the Utilization of Mineral Resources, Section 14 states, “Improving Transparency in the Industry by Joining the Extractive Industries Transparency Initiative. In order to improve transparency, accountability and governance in the sector, the government shall support and commit participation in the Extractive Industries Transparency Initiative (EITI). The DENR is mandated to ensure that mechanisms are established to operationalize the EITI in the mining sector, in consultation and coordination with the mining industry and other concerned stakeholders.” http://www.gov.ph/2012/07/06/executive-order-no-79-s-2012/
[ii] Mining Industry Coordinating Council (MICC) is an inter-agency forum that is responsible for the dialogue and coordination of the industry stakeholders.
[iii] PH-EITI TWG (technical working group) is composed of representatives of concerned government agencies in EITI. The group will provide technical support in the implementation of PH-EITI. Sec. Gozun convenes the group.

## Project Activities
3. INSTITUTIONALIZING PH-EITI
3.3 Strengthen PH-EITI Secretariat |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. Train PH-EITI Secretariat, PH-EITI TWG[iii] and MSG on EITI implementation |  |  |  | Php | Php | USD
1. Training on the purpose of EITI validation, validation requirements, validation process, including the procurement of a validator, the role of the MSG, and action planning for successful validation
| Accomodations | pax | 48 | 5000 | 240000 | 6000 |  | 190000 | 50000
| Meals for 2-day workshop | pax | 48 | 6000 | 288000 | 7200 | 144000 | 144000
| Transportation |  |  | 28500 | 50000 | 1250 |  | 50000
| NCR | gas mileage | 4 | 1000 | 4000 | 100
| Nueva Vizcaya | land fare | 1 | 3000 | 3000 | 75
| Romblon | air fare | 1 | 6000 | 6000 | 150
| In-transit from Luzon |  | 2 | 1500 | 3000 | 75
| Tranportation (Visayas) | air fare | 2 | 4000 | 8000 | 200
| In-transit from Visayas |  | 2 | 1500 | 3000 | 75
| Tranportation (Mindanao) | air fare | 2 | 10000 | 20000 | 500
| In-transit from Mindanao |  | 2 | 1500 | 3000 | 75
| Honorarium of speakers (2 pax, 2 days) | pax | 4 | 10000 | 40000 | 1000 |  | 40000
| Documentor Fee | pax | 1 | 10000 | 10000 | 250 | 10000
| Kits | pax | 33 | 500 | 16500 | 412.5 | 16500 |  |  | Transportation around Metro Manila
| Miscellaneous/Operational expense | pax |  | 30000 | 30000 | 750 | 30000 |  |  | Communication, local transportation for preparation
| Sub-total |  |  |  | 674500 | 16862.5 | 200500 | 424000 | 50000
2. Revenue Management and Template Analysis Workshop
| Accomodations | pax | 48 | 5000 | 240000 | 6000 |  | 190000 | 50000
| Meals for 2-day workshop | pax | 48 | 6000 | 288000 | 7200 | 144000 | 144000
| Transportation |  |  | 28500 | 50000 | 1250 |  | 50000
| NCR | gas mileage | 4 | 1000 | 4000 | 100
| Nueva Vizcaya | land fare | 1 | 3000 | 3000 | 75
| Romblon | air fare | 1 | 6000 | 6000 | 150
| In-transit from Luzon |  | 2 | 1500 | 3000 | 75
| Tranportation (Visayas) | air fare | 2 | 4000 | 8000 | 200
| In-transit from Visayas |  | 2 | 1500 | 3000 | 75
| Tranportation (Mindanao) | air fare | 2 | 10000 | 20000 | 500
| In-transit from Mindanao |  | 2 | 1500 | 3000 | 75
| Honorarium of speakers (2 pax, 2 days) | pax | 4 | 10000 | 40000 | 1000 |  | 40000
| Documentor Fee | pax | 1 | 10000 | 10000 | 250 | 10000
| Kits | pax | 33 | 500 | 16500 | 412.5 | 16500 |  |  | Transportation around Metro Manila
| Miscellaneous/Operational expense | pax |  | 30000 | 30000 | 750 | 30000 |  |  | Communication, local transportation for preparation
| Sub-total |  |  |  | 674500 | 16862.5 | 200500 | 424000 | 50000
3. Training on financial tracking in extractive industries
| Accomodations | pax | 48 | 5000 | 240000 | 6000 |  | 190000 | 50000
| Meals for 2-day workshop | pax | 48 | 6000 | 288000 | 7200 | 144000 | 144000
| Transportation |  |  | 28500 | 50000 | 1250 |  | 50000
| NCR | gas mileage | 4 | 1000 | 4000 | 100
| Nueva Vizcaya | land fare | 1 | 3000 | 3000 | 75
| Romblon | air fare | 1 | 6000 | 6000 | 150
| In-transit from Luzon |  | 2 | 1500 | 3000 | 75
| Tranportation (Visayas) | air fare | 2 | 4000 | 8000 | 200
| In-transit from Visayas |  | 2 | 1500 | 3000 | 75
| Tranportation (Mindanao) | air fare | 2 | 10000 | 20000 | 500
| In-transit from Mindanao |  | 2 | 1500 | 3000 | 75
| Honorarium of speakers (2 pax, 2 days) | pax | 4 | 10000 | 40000 | 1000 |  | 40000
| Documentor Fee | pax | 1 | 10000 | 10000 | 250 | 10000
| Kits | pax | 33 | 500 | 16500 | 412.5 | 16500 |  |  | Transportation around Metro Manila
| Miscellaneous/Operational expense | pax |  | 30000 | 30000 | 750 | 30000 |  |  | Communication, local transportation for preparation
| Sub-total |  |  |  | 674500 | 16862.5 | 200500 | 424000 | 50000
3.3 | TOTAL |  |  |  | 2023500 | 50587.5 | 601500 | 1272000 | 150000
3.4 Addressing barriers to implementation and institutionalizating PH-EITI |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. Review the legal and administrative and other barriers in the implementation of PH-EITI and propose strategies to address the barriers |  |  |  | Php | Php | USD
| Consultant | days | 10 | 10000 | 100000 | 2500 |  | 100000
3.4 | Total |  |  |  | 100000 | 2500 |  | 100000
3.5 Subnational implementation of PH-EITI |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. Develop the module on harmonizing the implementation of EITI at the subnational level and develop a plan to harmonize national and subnational EITI implementation |  |  |  | Php | Php | USD
| Consultant | days | 20 | 10000 | 200000 | 5000 |  | 200000
| Sub-total |  |  |  | 200000 | 5000 |  | 200000
B. Provide technical assistance to pilot sites, capability building and institutional preparation for sub national implementation of EITI
| Travel expense of speakers and secretariat |  | 5 | 8000 | 1400000 | 35000 |  | 1400000
| Venue and Food |  | 35 | 70000 | 2450000 | 61250 | 1750000 | - | 700000
| Lodging expense of speakers and secretariat |  | 5 | 2000 | 350000 | 8750 |  | 350000
| Honorarium of speakers |  | 3 | 5000 | 525000 | 13125 |  | 525000
| kits |  | 30 | 250 | 262500 | 6562.5 |  | 262500
3.5 | Sub-total |  |  |  | 4987500 | 124687.5 | 1750000 | 2537500 | 700000
3.6 Regular meeting of MSG |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. MSG members should meet once a month or as frequently as possible depending on the demand of EITI |  |  |  | Php | Php | USD
| Accomodations | pax | 6 | 5000 | 600000 | 15000 |  | 600000
| Meals | pax | 35 | 1000 | 700000 | 17500 | 700000
| Transportation |  |  | 28500 | 1000000 | 25000 |  | 1000000
| NCR | gas mileage | 4 | 1000 | 4000 | 100
| Nueva Vizcaya | land fare | 1 | 3000 | 3000 | 75
| Romblon | air fare | 1 | 6000 | 6000 | 150
| In-transit from Luzon |  | 2 | 1500 | 3000 | 75
| Tranportation (Visayas) | air fare | 2 | 4000 | 8000 | 200
| In-transit from Visayas |  | 2 | 1500 | 3000 | 75
| Tranportation (Mindanao) | air fare | 2 | 10000 | 20000 | 500
| In-transit from Mindanao |  | 2 | 1500 | 3000 | 75
| Kits | pax | 32 | 500 | 320000 | 8000 | 320000
3.6 | Total |  |  |  | 2620000 | 65500 | 1020000 | 1600000
4. PREPARATION IN IMPLEMENTING AND MONITORING PH-EITI
4.1 Preparation of reference materials for EITI implementation |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. Scoping study on payments and incentives in the extractive industry and materiality of these payments |  |  |  | Php | Php | USD
| Consultants (2 pax, 20 days each) | days | 40 | 15000 | 600000 | 15000 |  | 600000 |  | Expected output: mapping out of sources of data, recommendations for materiality and template
4.1 | TOTAL |  |  |  | 600000 | 15000 |  | 600000
4.2 Building the required capacity for EITI implementation, monitoring and reporting |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. Scoping study to assess the capacity of regulatory agencies, tax administration agencies and extractive industries in generating the data needed to produce the report |  |  |  | Php | Php | USD
| Consultant | days | 30 | 10000 | 300000 | 7500 |  |  |  | Agencies to be assesed: BIR, MGB, LGUs, PPA, Customs, etc.
| Sub-total |  |  |  | 300000 | 7500 |  | 300000
B. Conduct training with government agencies on how to complete the reporting template (2 days) |  |  |  | Php | Php | USD
| Accomodations | pax | 20 | 5000 | 100000 | 2500 |  | 100000
| Meals for 2-day workshop | pax | 20 | 6000 | 120000 | 3000 | 60000 | 60000
| Transportation |  |  | 23500 | 104000 | 2600 |  | 104000
| Tranportation (Luzon) |  | 7 | 4000 | 28000 | 700
| In-transit from Luzon |  | 7 | 1500 | 10500 | 262.5
| Tranportation (Visayas) | air fare | 3 | 5000 | 15000 | 375
| In-transit from Visayas |  | 3 | 1500 | 4500 | 112.5
| Tranportation (Mindanao) | air fare | 4 | 10000 | 40000 | 1000
| In-transit from Mindanao |  | 4 | 1500 | 6000 | 150
| Honorarium of speakers (2 pax, 2 days) | pax | 4 | 10000 | 40000 | 1000 |  | 40000
| Documentor Fee | pax | 1 | 10000 | 10000 | 250 | 10000
| Kits | pax | 20 | 500 | 10000 | 250 | 10000
| Miscellaneous/Operational expense | pax |  | 30000 | 30000 | 750 | 30000
| Sub-total |  |  |  | 414000 | 10350 | 110000 | 304000
C. Conduct training with local government units on how to complete the reporting template
| Accomodations | pax | 50 | 5000 | 250000 | 6250 |  | 250000 |  | Participants: treasurer or accountant of the municipality and province where the extractive industries are operating
| Meals for 2-day workshop | pax | 50 | 6000 | 300000 | 7500 | 150000 | 150000
| Transportation |  |  | 23500 | 362500 | 9062.5 |  | 362500
| Tranportation (Luzon) |  | 17 | 4000 | 68000 | 1700
| In-transit from Luzon |  | 17 | 1500 | 25500 | 637.5
| Tranportation (Visayas) | air fare | 6 | 5000 | 30000 | 750
| In-transit from Visayas |  | 6 | 1500 | 9000 | 225
| Tranportation (Mindanao) | air fare | 20 | 10000 | 200000 | 5000
| In-transit from Mindanao |  | 20 | 1500 | 30000 | 750
| Honorarium of speakers (2 pax, 2 days) | pax | 4 | 10000 | 40000 | 1000 |  | 40000 |  | 5,000 for two-day training
| Documentor Fee | pax | 1 | 10000 | 10000 | 250 | 10000 |  |  | 10,000 for two-day training
| Kits | pax | 50 | 500 | 25000 | 625 | 25000
| Miscellaneous/Operational expense | pax |  | 30000 | 30000 | 750 | 30000
| Sub-total |  |  |  | 1017500 | 25437.5 | 215000 | 802500
D. Conduct training with industry on how to complete the reporting template (2 days)
| Meals for meeting | pax | 35 | 1200 | 84000 | 2100 |  | 84000 |  | 35 large-scale mining companies with 1 representative each plus secrtariat and speakers
| Honorarium of speakers (2 pax, 2 days) | pax | 4 | 5000 | 40000 | 1000 |  | 40000 |  | 5,000 for two-day training
| Documentor Fee | pax | 1 | 10000 | 20000 | 500 |  | 20000 |  | 10,000 for two-day training
| Kits | pax | 40 | 300 | 24000 | 600 | 24000
| Miscellaneous/Operational expense | pax |  | 30000 | 30000 | 750 | 30000
| Sub-total |  |  |  | 198000 | 4950 | 54000 | 144000
E. Conduct training with CSOs to understand PH-EITI reporting (2 days)
| Accomodations | pax | 35 | 5000 | 175000 | 4375 |  | 175000
| Meals for 2-day workshop | pax | 35 | 6000 | 210000 | 5250 | 105000 | 105000
| Transportation |  |  | 19500 | 195000 | 4875 |  | 195000
| Tranportation (Luzon) | gas mileage | 10 | 1000 | 10000 | 250
| In-transit from Luzon |  | 10 | 1500 | 15000 | 375
| Tranportation (Visayas) | air fare | 10 | 4000 | 40000 | 1000
| In-transit from Visayas |  | 10 | 1500 | 15000 | 375
| Tranportation (Mindanao) | air fare | 10 | 10000 | 100000 | 2500
| In-transit from Mindanao |  | 10 | 1500 | 15000 | 375
| Honorarium of speakers (2 pax, 2 days) | pax | 4 | 10000 | 40000 | 1000 |  | 40000 |  | 5,000 for two-day training
| Documentor Fee | pax | 1 | 10000 | 10000 | 250 | 10000 |  |  | 10,000 for two-day training
| Kits | pax | 35 | 500 | 17500 | 437.5 | 17500
| Miscellaneous/Operational expense | pax |  | 30000 | 30000 | 750 | 30000
| Sub-total |  |  |  | 677500 | 16937.5 | 162500 | 515000
F. Organize EITI Study Tour in an EITI implementing country | [9 empty] | Participants: PH-EITI MSG
| Travel expense | pax | 15 | 60000 | 1800000 | 45000 |  | 1800000
| Lodging expense | pax | 15 | 20000 | 600000 | 15000 |  | 600000 |  | $250 per night* 2 nights
| Meal allowance | pax | 15 | 11200 | 336000 | 8400 |  | 336000 |  | 2 days actual study tour, 2 days travel. $70 per day
| In-transit expense | pax | 15 | 8000 | 240000 | 6000 |  | 240000
| Kits | pax | 15 | 500 | 15000 | 375 |  | 15000
| Sub-total |  |  |  | 2991000 | 74775 |  | 2991000
4.2 | TOTAL |  |  |  | 5598000 | 139950 |  | 5598000
5. AUDIT/RECONCILE AND REPORT ON REVENUE FLOWS BETWEEN PHILIPPINE GOVERNMENT AND EXTRACTIVE INDUSTRIES
5.1 Hiring of independent reconciler |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. The MSG hires the reconciler for analyze the government and industry data for the EITI report |  |  |  | Php | Php | USD
| Independent reconciler | pax | 1 | 3150000 | 3150000 | 78750 | 3150000
5.1 | Total |  |  |  | 3150000 | 78750 | 3150000
5.2 Preparation and Publication of EITI report |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
C. Publication of 1st Philippine EITI report
Publication of EITI report
| Writers | pax | 5 | 100000 | 500000 | 12500 |  | 500000
| Overall editor | pax | 1 | 300000 | 300000 | 7500 |  | 300000
| Data manager | pax | 2 | 100000 | 200000 | 5000 |  | 200000
| Translation (Tagalog) | pax | 1 | 100000 | 100000 | 2500 |  | 100000
| Layout/graphic artist | pax | 1 | 150000 | 150000 | 3750 |  | 150000
| Printing | publication | 1000 | 1500 | 1500000 | 37500 | 1500000
| CDs | pax | 2000 | 50 | 100000 | 2500 | 100000
| Sub-total |  |  |  | 2850000 | 71250 | 1600000 | 1250000
Publication of EITI report (popular version)
| Writer | pax | 1 | 150000 | 150000 | 3750 |  | 150000
| Editor | pax | 1 | 50000 | 50000 | 1250 |  | 50000
| Translation (5 dialects) | pax | 5 | 50000 | 250000 | 6250 |  | 250000
| Layout/graphic artist | pax | 1 | 50000 | 50000 | 1250 |  | 50000
| Printing | publication | 1000 | 500 | 500000 | 12500 | 500000
| CDs | pax | 2000 | 50 | 100000 | 2500 | 100000
| Sub-total |  |  |  | 1100000 | 27500 | 600000 | 500000
5.2 | Total |  |  |  | 3950000 | 98750 | 2200000 | 1750000
6. COMMUNICATE, BUILD KNOWLEDGE, AND ENGAGE CITIZENS IN THE PH-EITI PROGRAM
6.1 Establish and maintain EITI website |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. Development and maintenance of PH-EITI website |  |  |  | Php | Php | USD
| Website developer | pax | 1 | 50000 | 50000 | 1250 |  | 50000 |  | Output: Dynamic website with search engine that can generate report based on the completed EITI templates
| Back end data base programmer | pax | 1 | 100000 | 100000 | 2500 |  | 100000
| Web hosting charge | month | 24 | 1500 | 36000 | 900 |  | 36000
| Content developer | pax | 1 | 50000 | 50000 | 1250 |  | 50000
6.1 | Total |  |  |  | 236000 | 5900 |  | 236000
6.2 Establish Management Information System for the extractive industry |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. Improve procedures and information infrastructures for the transmission, consolidation, stewardship and publication of data from extractive industries |  |  |  | Php | Php | USD
| Programmers | days | 400 | 4000 | 1600000 | 40000 |  | 1600000 |  | The objective is to create an IT system to reconcile and manage paymements to govenrnment
6.2 | Sub-total |  |  |  | 1600000 | 40000 |  | 1600000
6.3 Sub-national, national and international outreach |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. Sub-national outreach |  |  |  | Php | Php | USD
| Local transportation | pax | 40 | 7000 | 280000 | 7000 | 70000 | 210000 |  | Overall budget for travel of secretariat and focal point person to sub-national areas for EITI outreach activities
| In transit expense | pax | 40 | 1500 | 60000 | 1500 |  | 60000
| Lodging expense | pax | 40 | 3000 | 120000 | 3000 |  | 120000
| Sub-total |  |  |  | 460000 | 11500 | 70000 | 390000
B. International outreach |  |  |  | Php | Php | USD
| Air fare | pax | 6 | 60000 | 360000 | 9000 |  | 360000
| In transit expense | pax | 6 | 15000 | 90000 | 2250 |  | 90000
| Lodging expense (2 days) | pax | 12 | 12000 | 144000 | 3600 |  | 144000
| Sub-total |  |  |  | 594000 | 14850 |  | 594000
6.3 | Total |  |  |  | 1054000 | 26350 | 70000 | 984000
6.4 Media outreach |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. Release of statement and press briefings on PH-EITI activities inluding Workshop with media group on EITI |  |  |  | Php | Php | USD
| Meal | pax | 100 | 500 | 300000 | 7500 | 300000
| Kit | pax | 100 | 100 | 60000 | 1500 | 60000
6.4 | Total |  |  |  | 360000 | 9000 | 360000
6.5 Public dissemination of EITI report |  | UNIT | NO. OF UNITS | UNIT COST | TOTAL COST |  | GoP | Donors | Stakeholders
A. Conduct a national conference to launch EITI report |  |  |  | Php | Php | USD
A. Honoraria and Professional Fees
| A.1. Speakers | pax | 5 | 5000 | 25000 | 625 | 25000
| A.2. Facilitators | pax | 2 | 10000 | 20000 | 500 |  | 20000
| A.3. Documentation | pax | 2 | 10000 | 20000 | 500 |  | 20000
| B. Venue and Food (150 pax x 2 days x P1,200) | pax | 300 | 1200 | 360000 | 9000 | 360000
| C. Accommodations (30 rooms x 2 nights) | rooms | 60 | 5000 | 300000 | 7500 |  | 300000
D. Miscellaneous
| D.1. Workshop Kits | pax | 150 | 100 | 15000 | 375 | 15000
| D.2. Supplies | supplies | 1 | 15000 | 15000 | 375 | 15000
| D.3. Incidental Expenses |  | 1 | 57000 | 57000 | 1425 | 57000
6.6 | Total |  |  |  | 812000 | 20300 | 472000 | 340000
|  |  |  | TOTAL | 27291000

## Secrteariat Budget
| Unit | Unit cost | No. of units | Total |  | GoP | Donors
|  |  |  | Php | USD
1. Program Management
1.1. National coordinator | Monthly salary | 100000 | 16 | 1600000 | 40000 |  | 1600000
1.2. Division Chief | Monthly salary | 49750 | 18 | 895500 | 22387.5 | 895500
1.3. Technical staff 1 | Monthly salary | 42652 | 18 | 767736 | 19193.4 | 767736
1.4. Technical staff 2 | Monthly salary | 31351 | 18 | 564318 | 14107.95 | 564318
1.5. Consultant | Monthly salary | 60000 | 18 | 1080000 | 27000 | 1080000
1.6. Consultant | Monthly salary | 60000 | 18 | 1080000 | 27000 | 1080000
1.7 Consultant | Monthly salary | 60000 | 18 | 1080000 | 27000 | 1080000
Subtotal |  |  |  | 7067554 | 176688.85 | 5467554 | 1600000
2. Operational Budget
2.1. Office rent | Monthly rent | 30000 | 18 | 540000 | 13500 | 540000
2.2. Transportation | Pax | 5000 | 18 | 90000 | 2250 | 45000 | 45000
2.2.1 Local transportation
2.3. Supplies |  | 10000 | 18 | 180000 | 4500 | 180000
2.4. Utilities |  | 20000 | 18 | 360000 | 9000 | 360000
2.5. Equipment |  | 105000 | - | 155000 | 3875 |  | 155000
2.5.1 Desktop computer | Pax | 25000 | 3 | 75000 | 1875
2.5.2 Laptop | Pax | 30000 | 1 | 30000 | 750
2.5.3 Printer and scanner | Pax | 10000 | 1 | 10000 | 250
2.5.4 Projector | Pax | 25000 | 1 | 25000 | 625
2.5.6 Telefax | Pax | 15000 | 1 | 15000 | 375
2.6 Communication |  | 6000 | 18 | 108000 | 2700 | 54000 | 54000
Subtotal |  |  |  | 1433000 | 35825 | 1179000 | 254000
Total |  |  |  | 8500554 | 212513.85 | 6646554 | 1854000