## Sheet1
Project Cost Profiles
Project Number(s): | xxxxx
Project Title: | Xxxx Xxxx
Date updated: | mm/dd/yyyy
TPC or range ($K):
Cost Element | ($K)
| FY PY-3 FY 2004 | FY PY-2 FY 2005 | FY PY-1 FY 2006 | FY PY FY 2007 | FY CY FY 2008 | Total Prior Years | FY BY FY 2009 | FY BY+1 FY 2010 | FY BY+2 FY 2011 | FY BY+3 FY 2012 | FY BY+4 FY 2013 | Outyears FY 2014 and beyond | Total Current Estimate | Total Previous Estimate | Original Validated Baseline
Critical Decision (approvals) | CD-0 |  | CD-1 | CD-2A/3A, 2B |  |  | CD-3B |  | CD-4A, 4B | [5 empty] | CD-2
Total Estimated Cost (TEC)
Design (PED)
Design |  |  | 4600 |  |  | 4600 | [6 empty] | 4600 | 4600 | 4600
Contingency |  |  | 400 |  |  | 400 | [6 empty] | 400 | 400 | 400
Total, PED | 0 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000
Appropriations |  |  | 5000 |  |  | 5000 | [6 empty] | 5000
Obligations |  |  | 5000 |  |  | 5000 | [6 empty] | 5000
Costs |  |  | 600 | 3000 | 1400 | 5000 | [6 empty] | 5000
Construction (Post CD-2)
Site Preparation | [5 empty] | 0 | 5000 | [5 empty] | 5000 | 5000 | 5000
Equipment |  |  |  |  | 700 | 700 | 2000 | 6100 | 2000 |  |  |  | 10800 | 10800 | 10800
All Other Construction | [5 empty] | 0 | 11100 | 24400 | 500 |  |  |  | 36000 | 36000 | 36000
Contingency | [5 empty] | 0 | 1000 | 1500 | 500 |  |  |  | 3000 | 3000 | 3000
Total, Construction | 0 | 0 | 0 | 0 | 700 | 700 | 19100 | 32000 | 3000 | 0 | 0 | 0 | 54800 | 54800 | 54800
Appropriations |  |  |  |  | 800 | 800 | 32000 | 22000 |  |  |  |  | 54800
Obligations |  |  |  |  | 800 | 800 | 32000 | 22000 |  |  |  |  | 54800
Costs |  |  |  |  | 700 | 700 | 19100 | 32000 | 3000 |  |  |  | 54800
Total, TEC (Post CD-2) | 0 | 0 | 5000 | 0 | 700 | 5700 | 19100 | 32000 | 3000 | 0 | 0 | 0 | 59800 | 59800 | 59800
Total, Contingency | 0 | 0 | 400 | 0 | 0 | 400 | 1000 | 1500 | 500 | 0 | 0 | 0 | 3400 | 3400 | 3400
Other Project Cost (OPC)
OPC except D&D
Conceptual Planning | [5 empty] | 0 | 1250 | [5 empty] | 1250 | 1250 | 1250
Conceptual Design | [5 empty] | 0 | 1250 | [5 empty] | 1250 | 1250 | 1250
Start-Up | [5 empty] | 0 | 7500 | [5 empty] | 7500 | 7500 | 7500
Contingency | [5 empty] | 0 | 2000 | [5 empty] | 2000 | 2000 | 2000
Total, OPC except D&D | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000
Appropriations | [5 empty] | 0 | 12000 | [5 empty] | 12000
Obligations | [5 empty] | 0 | 12000 | [5 empty] | 12000
Costs | [5 empty] | 0 | 12000 | [5 empty] | 12000
D&D (Post CD-2)
D&D | [5 empty] | 0 | 4000 | [5 empty] | 4000 | 4000 | 4000
Contingency | [5 empty] | 0 | 2000 | [5 empty] | 2000 | 2000 | 2000
Total, D&D | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 6000
Appropriations | [5 empty] | 0 | 10000 | [5 empty] | 10000
Obligations | [5 empty] | 0 | 10000 | [5 empty] | 10000
Costs | [5 empty] | 0 | 10000 | [5 empty] | 10000
Total, OPC | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | 18000 | 18000
Total, Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000
Total Project Cost (TPC) (Post CD-2)
Appropriations | 0 | 0 | 5000 | 0 | 800 |  | 54000 | 22000 | 0 | 0 | 0 | 0 | 81800
Obligations | 0 | 0 | 5000 | 0 | 800 |  | 54000 | 22000 | 0 | 0 | 0 | 0 | 81800
Costs | 0 | 0 | 600 | 3000 | 2100 |  | 41100 | 32000 | 3000 | 0 | 0 | 0 | 81800
Total, TPC (Post CD-2) | 0 | 0 | 5000 | 0 | 700 | 5700 | 37100 | 32000 | 3000 | 0 | 0 | 0 | 77800 | 77800 | 77800
Total, Contingency | 0 | 0 | 400 | 0 | 0 | 400 | 5000 | 1500 | 500 | 0 | 0 | 0 | 7400 | 7400 | 7400
Instructions:
• Provide spreadsheet for each line item and MIE project greater than or equal to $20M. PED & construction PDS information should be consolidated into one spreadsheet.
• Fill in shaded yellow cells. If available, fill in shaded gray cells.
• First FY PY column shall be the FY of the CD-0 approval. As such, insert or delete columns as necessary.
• The "Total Previous Estimate" column represents the last BCP approval; otherwise, shall be the same as the "Original Validated Baseline" column.
• Provide comments, e.g. long lead, using comment function. [Toolbar <Insert> then <Comment>]