## Project
Project name | Project calendar duration (days): | 60 | Project start date | Project end date | Hourly fee | Currency | USD | File output folder | c:\temp\
Enter project name | Start project in (days): | 5 | 2026-08-03 | 2026-10-02 | 80 | Default case type | General
| Total planned work hours: | 230 |  | Work cost estimate: | 18400 | Default case status | Not started
| Title | Task budget hours | Start date | End date | Description | Case owner | Case type | Case status
Milestone | SYSTEM DESIGNED
Task | Interview users | 10
Case | Interview 1
Case | Interview 2
Task | Design interface | 15
Case | Screen 1
Case | Screen 2
Task | Design database | 15
Case | Tables and relationships
Case | Indexes
Milestone | SYSTEM IMPLEMENTED
Task | Implement front office | 50
Case | Function 1
Case | Function 2
Task | Implement back-office | 80
Case | Function A
Case | Function B
Task | Test and finalize system | 60
Case | Test 1
Case | Test 2
Note on A5: Copy a project plan structure from one of the worksheets and paste it in cell A6.
Note on H5: ProjectCompanion user name
Export file
Generate dates
Format rows
INSTRUCTIONS
Copy a template from one of the sheets and paste it in cell A6 on this sheet (create templates that matches your projects).
Modify the specific project plan on this sheet. Use a hierarchy of Milestones, Tasks, Cases and Caseitems.
Set budgets on tasks. Check the total planned work hours and adjust the hourly fee.
Specify duration and in how many days the project is estimated to start.
Click Generate dates to set dates on milestones and tasks. Modify the dates as you want.
Switch to the project proposal sheet to add expenses to the project and calculate the project margin.
If the project is accepted, you click Export file, and import it to a new project
in ProjectCompanion.

## Project proposal
EXPENSES |  | FINANCIAL SUMMARY
Billable expenses total | 1000 | Expected result | 5900
Travel | 1000 | Expected margin | 51.3%
Material
Other expenses
PROJECT SETUP INFORMATION
Non billable expenses total | 1000 | Project start date | 2026-08-03
Travel |  | Project end date | 2026-10-02
Material
Other expenses | 1000 | Contract value | 19400
|  | Budget hours | 230
WORK COST | 11500 | Budget expenses | 1000
Average hourly cost for worked hours | 50 | Total budget | 13500
PROPOSAL SUMMARY
We estimate that the project will take 230 hours to complete.
Our hourly fee is USD 80 per hour, which leads to an estimated project work cost of USD 18400.
In addition, we estimate that we will have project expenses of approximately USD 1000.
The total cost of the project is therefore estimated to USD 19400.

## General project
General project
Milestone | MILESTONE 1
Task | Task 1
Case | Case 1
Case | Case 2
Task | Task 2
Case | Case 3
Case | Case 4
Milestone | MILESTONE 2
Task | Task 3
Case | Case 5
Case | Case 6
Task | Task 4
Case | Case 7
Case | Case 8

## System development
Development of information system
Milestone | SYSTEM DESIGNED
Task | Interview users
Case | Interview 1
Case | Interview 2
Task | Design interface
Case | Screen 1
Case | Screen 2
Task | Design database
Case | Tables and relationships
Case | Indexes
Milestone | SYSTEM IMPLEMENTED
Task | Implement front office
Case | Function 1
Case | Function 2
Task | Implement back-office
Case | Function A
Case | Function B
Task | Test and finalize system
Case | Test 1
Case | Test 2

## Report development
Report development
Milestone | REQUIREMENTS ANALYZED
Task | Interview users
Case | Interview 1
Case | Interview 2
Task | Design interface framework
Case | Screen 1
Case | Screen 2
Task | Analyze data structure
Case | Operative system data analysis
Case | Data cleaning requirements
Task | Use cases
Case | Describe use cases
Case | Prioritize use cases
Milestone | SYSTEM IMPLEMENTED
Task | Implement data layers in DB
Case | Data quality control
Case | Data views
Task | Report development
Case | Sales summary report
Caseitem | Sales by region
Caseitem | Sales by product
Case | Sales by week
Case | Sales by product
Case | Sales by reseller
Case | Filter by country, region and product group
Case | Preliminary tests of report functions
Caseitem | Alfa tests
Caseitem | Beta tests
Task | Scorecard development
Case | Sales by region
Case | Sales by product
Case | Sales by campaign
Case | Preliminary tests of scorecard
Caseitem | Alfa tests
Caseitem | Beta tests
Task | Final tests and modifications
Case | Reports tests
Caseitem | Sales reports - accuracy
Caseitem | Sales reports - readability
Caseitem | Filter functions
Case | Scorecard tests
Caseitem | Sales data - accuracy
Caseitem | Report readability
Task | System handover
Case | User training
Case | Final documentation

## Installation
Sales and installation of industrial machinery
Milestone | PLANNING
Task | PROJECT START
Case | Design solution
Case | Contact sub-contractors
Case | Send proposal to customer
Task | ORDER APPROVED
Case | Order signed
Case | Pre-invoice
Case | Order components
Case | Sub-contractors informed
Task | DETAIL PLANNING
Case | Installation planned
Case | Final solution approved by customer
Case | Installation checklist finished
Case | Site inspection performed
Milestone | IMPLEMENTATION
Task | DELIVERY
Case | Confirm delivery times
Case | Schedule installation
Task | INSTALLATION
Case | Installation
Case | Installation documentation completed
Case | Validate
Task | CLOSE-OUT
Case | Warranty agreement created
Case | Invoice installation

## Campaign
Campaigning for an issue
Milestone | CAMPAIGN PLANNING
Task | Identify decision-makers
Case | Bill Smith, Plant manager
Case | Mary Jones, President sierra club
Task | Identify allies
Case | Allie 1
Case | Allie 2
Task | Identify opponents
Case | Opponent 1
Case | Opponent 2
Task | Perform research
Case | Interview person 1
Case | Collect legal texts
Task | Obtain resources
Case | Raise money
Case | Check Newspaper 1 for interest
Milestone | CAMPAIGN EXECUTION
Task | Survey
Case | Create survey questions
Case | Contact respondents
Case | Summarize results
Task | Press communication
Case | Write pressrelease
Case | Contact Paul Ericsson at Daily
Task | Personal communication
Case | Identify targets
Case | Write letters
Milestone | CAMPAIGN EVALUATION
Task | Summarize results
Case | Write web site page
Case | Inform stakeholders
Case | Suggest further action

## Service strategy
Develop service offering
Milestone | SERVICE STRATEGY DEVELOPED
Task | Demand management
Case | Interview business unit managers
Case | Summarize goals and plans
Task | Strategy generation
Case | Scenario analysis
Case | Strategy draft
Task | Service portfolio management
Case | Identify required services
Case | Describe required services
Task | IT financial management
Case | Create a budget draft
Case | Send budget draft for comments
Milestone | SERVICE STRATEGY APPROVED
Task | Business unit acceptance
Case | Line manager approval
Case | Corporate approval
Task | IT unit approval
Case | IT development approval
Case | IT operations approval
Milestone | SERVICE DESIGNS INITIATED
Task | Describe services
Case | Describe server goal situation
Case | Acceptance inspection
Task | Staff design teams
Case | Specify teams
Case | Line manager approval
Case | Initiate projects

## Clinical trial
Clinical trial
Milestone | Clinical trial preparation
Task | Protocol Development
Case | Write Synopsis
Case | Synopsis Approved
Case | Clinical Supples Request
Case | Write Protocol
Case | Review and Approve Protocol
Case | QA Review
Case | Protocol Approved
Task | CRF
Case | Design and Approve CRF
Case | Develop and Approve CRF Instructions
Case | CRF Printing Assembly
Case | CRF Available To Ship
Task | CRO Start-UP Activities
Case | Prepare
Case | Review Bids and Capabilities
Case | Select Vendors
Case | CRO Kick-Off Meeting
Case | Contracts
Case | Vendor Contract Executed
Milestone | Site setup
Task | Clinical Site Start-Up
Case | Select Sites
Case | Finalize Site Contracts
Case | 1st Site Contract Approved
Case | All Sites Approved Contracts
Case | IRB Submission and Approval
Case | Reg Doc Collection
Case | 1st Reg Doc Packet Approval
Case | All Reg Docs Approved
Case | 1st Site Initiated
Case | All Sites Initiated
Task | Central Labs
Case | Lab Specs Approved
Case | Lab Supplies and Equipment Preparation
Case | All Sites Lab Supplies
Task | Investigator Meeting
Case | Select Site and Plan Meeting
Case | Conduct Meeting
Milestone | Clinical trial execution
Task | Clinical Trial Conduct
Case | All Sites Clinical Drug Shipments
Case | First Subject In
Case | Enrollment Targets
Case | Last Subject In
Case | Treatment Period
Case | Last Subject Out
Task | Data Management
Case | Build and Validate DB
Case | 1st CRF in Database
Case | First Site Query
Case | Last CRF in DB
Case | Last Query Resolved
Case | DB Close
Case | Lock DB
Task | Study Results
Case | Break Blind
Case | Flash Results
Case | Clinical Trial Report
Case | Final Report

## Industrial installation
Installation of industrial equipment (example pumping stations)
Milestone | PUMPING STATIONS
Task | Pumping station 1
Case | Order materials
Case | Transport
Case | Installtion
Case | Inspection
Caseitem | Inspection electrical
Caseitem | Inspection pump
Caseitem | Inspection sewer lines
Task | Pumping station 2
Case | Order materials
Case | Transport
Case | Installtion
Case | Inspection
Caseitem | Inspection electrical
Caseitem | Inspection pump
Caseitem | Inspection sewer lines
Task | Pumping station 3
Case | Order materials
Case | Transport
Case | Installtion
Case | Inspection
Caseitem | Inspection electrical
Caseitem | Inspection pump
Caseitem | Inspection sewer lines
Task | Pumping station 4
Case | Order materials
Case | Transport
Case | Installtion
Case | Inspection
Caseitem | Inspection electrical
Caseitem | Inspection pump
Caseitem | Inspection sewer lines

## Plant startup
Industrial plant startup
Milestone | PROJECT INITIATION
Task | Site selection
Case | Evaluate site 1
Case | Evaluate site 2
Task | Technology evaluation
Case | Initial sketch
Case | Reactor designs
Task | Contractor evaluation
Case | Contractor 1
Case | Contractor 2
Task | Financing
Case | Credits
Case | Investor alternative 1
Case | Investor alternative 2
Milestone | PLANT DESIGN AND APPROVAL
Task | Pumping station
Case | Approve drawing A
Case | Approve drawing B
Task | Reactors
Case | Approve drawing C
Case | Approve drawing D
Task | Tanks
Case | Tank supplier selection
Case | Approve drawing F
Case | Approve drawing G
Case | Software selection
Case | Filter design
Milestone | CONSTRUCTION SUPERVISION
Task | Pumping station
Case | Installation
Case | Acceptance inspection
Task | Reactors
Case | Installation
Case | Acceptance inspection
Task | Tanks
Case | Installation
Case | Acceptance inspection
Task | Final inspection
Case | Pumping station
Case | Reactors
Case | Tanks
Case | Electrical
Case | Software
Case | Plant acceptance
Milestone | PRODUCTION RAMP-UP
Task | Staff training
Case | Operator course
Case | Manager course
Task | Startup process
Case | Order materials
Case | Detail startup planning
Case | Process fine-tuning

## Service design
Implement new service offering
Milestone | SERVICE DESIGN SPECIFIED
Task | Service level management
Case | Write SLA
Case | Approve SLA
Task | Service catalog management
Case | Define service
Task | Capacity management
Case | Calculate requirements
Task | Availability management
Case | Describe availability requirements
Task | Security management
Task | Information security
Milestone | SERVICE DESIGN FINALIZED
Task | Approve design
Task | Service transition planned

## CSI
Crime scene investigation
Milestone | CRIME SCENE INVESTIGATED
Task | Initial site analysis
Case | Document actions and observations
Task | Preliminary documentation
Case | Scene assessment
Case | Walk-through and initial documentation
Task | Scene processing
Case | Contamination control
Case | Documentation
Case | Prioritize collection of evidence
Case | Submit evidence for processing
Task | Finalize scene documentation
Case | Prepare debriefing
Case | Final crime scene survey
Case | Final crime scene documentation

## Construction
Construction
Milestone | DESIGN
Task | General preparations
Case | Sign contract
Case | Insurance
Case | Scheduling
Case | Permits
Case | Drawings
Task | Drawings
Case | Approve drawings - foundation
Case | Approve drawings - elevator
Case | Approve drawings - plumbing
Case | Approve drawings - electrical
Milestone | CONSTRUCTION
Task | Site setup
Case | Power
Case | Water
Case | Office
Task | Foundations
Case | Concrete foundation
Case | Elevator shaft
Case | Steel columns
Task | Roofing
Case | Prepare roof
Case | Install roof
Task | Windows
Case | Window frames
Case | Windows
Task | Elevators
Case | Elevator mechanical
Case | Elevator electrical
Task | Plumbing
Case | Water pipes
Case | WC
Task | Electrical
Case | Wall installations
Case | Outlet
Case | Light installation
Task | Heating
Case | Electrical
Task | Final clean-up
Case | Clean walls and floors
Case | Remove debris
Case | Inspect facilities
Milestone | CLOSE-OUT
Task | Final inspections
Case | Building inspection
Caseitem | Entry
Caseitem | Floor 1
Caseitem | Floor 2
Case | Elevator inspection and certification
Caseitem | Mechanical installation
Caseitem | Electrical installation
Case | Fire inspection
Caseitem | Entry
Caseitem | Floor 1
Caseitem | Floor 2
Case | Prepare punchlist
Task | Handover
Case | Certificates
Case | Warranties

## Course
Performing a course
Milestone | PLANNING
Task | Curriculum
Case | Select books
Case | Compile articles
Case | Create course description
Task | Facilities
Case | Book lecture rooms
Case | Book examination room
Task | Teachers
Case | Teacher agreements
Case | Guest lecturers
Milestone | EXECUTION
Task | Lectures
Case | Lecture 1 - Introduction
Case | Lecture 2 - Businss planning
Case | Lecture 3 - Financial analysis
Case | Lecture 3 - Strategy
Task | Exams
Case | Exam 1
Case | Exam 2