## Normative
1
2 | Task Name | NEW INFO | NEW SCHEDULE | Duration | Start Date | End Date | Resources | Predecessors
3 | -Enter Project Name Here |  | -Enter Project Name Here | 255d | 5/7/2007 8:00 AM | 5/14/2008 5:00 PM
4 | -Informative Work |  | Project Scope Statement (PSS) | 40d | 5/7/2007 8:00 AM | 7/3/2007 8:00 AM
5 | Create/Complete PROJECT SCOPE STATEMENT (TTPL 5) | .1 | HL7 Protocol Specifications (1.3.1.1) | 5d | 5/7/2007 8:00 AM | 5/11/2007 5:00 PM
6 | MILESTONE: Create Project in Project Insight | Request to enhance/create/sunset product boxes | Enhance, create or sunset a product? |  | 5/14/2007 8:00 AM | 5/14/2007 8:00 AM |  | Create/Complete PROJECT SCOPE STATEMENT (TTPL 5)
7 | Steering Division Approval (TTPL 7) | .2 | Create/Complete PSS | 5d | 5/14/2007 8:00 AM | 5/18/2007 5:00 PM |  | MILESTONE: Create Project in Project Insight
8 | TSC Approval (TTPL 7) | .2 | Sponsoring Group Approves PSS (1.3.1.2) | 5d | 5/21/2007 8:00 AM | 5/25/2007 5:00 PM |  | Steering Division Approval (TTPL 7)
9 | PMO Approval (TTPL 7) | .2 | Submit PSS to Steering Division and PMO (1.3.1.2) | 5d | 5/29/2007 8:00 AM | 6/4/2007 5:00 PM | David Hamill (0.00%) | TSC Approval (TTPL 7)
10 | Define Requirements / QVSD (TTPL 8) | .5 (Project Initiation) | SD Approves PSS (1.3.1.2) | 10d | 5/14/2007 8:00 AM | 5/25/2007 5:00 PM |  | MILESTONE: Create Project in Project Insight
11 | Logical Design / QVSD (TTPL 9) | .7 | TSC Approves PSS (1.3.1.2) | 10d | 5/29/2007 8:00 AM | 6/11/2007 5:00 PM |  | Define Requirements / QVSD (TTPL 8)
12 | Draft Specification / QVSD (TTPL 10) | .8 | PMO Approves PSS (1.3.1.2) | 10d | 6/12/2007 8:00 AM | 6/25/2007 5:00 PM |  | Logical Design / QVSD (TTPL 9)
.9
| -Normative Work |  | Normative Work (HDF 1.3.1: HL7 Project Life Cycle for Product Development)
|  | .16 | Project Initiation (1.3.1.5)
13 | Complete/Submit Notification of Intent To Ballot (NIB) form for Normative Ballot | keep as same ('Seek Comments' .17) | Requirements Analysis (1.3.1.7) | 5d | 6/26/2007 8:00 AM | 7/2/2007 5:00 PM |  | Draft Specification / QVSD (TTPL 10)
14 | MILESTONE: Informative Ballot of a Candidate Standard (TTPL 11) | MILESTONE: Normative Ballot | Logical Design (1.3.1.8) |  | 7/3/2007 8:00 AM | 7/3/2007 8:00 AM |  | Complete/Submit Notification of Intent To Ballot (NIB) form for Informative Ballot
15 | -DSTU Work (for projects which will be normative standards) | N/A | Draft Specification (1.3.1.9) | 190d | 7/3/2007 8:00 AM | 4/9/2008 5:00 PM
16 | Candidate Standard (DSTU) Validation & Revisions / QVSD (TTPL 12&13) | N/A | Informative Work (HDF 1.3.1: HL7 Project Life Cycle for Product Development) | 15d | 7/3/2007 8:00 AM | 7/24/2007 5:00 PM |  | MILESTONE: Informative Ballot of a Candidate Standard (TTPL 11)
17 | Wider industry use of DSTU needed? (TTPL 14) | N/A | Project Initiation (1.3.1.5) | 15d | 7/25/2007 8:00 AM | 8/14/2007 5:00 PM |  | Candidate Standard (DSTU) Validation & Revisions / QVSD (TTPL 12&13)
18 | MILESTONE: DSTU Published on www.hl7.org Website | N/A | Requirements Analysis (1.3.1.7) |  | 8/15/2007 8:00 AM | 8/15/2007 8:00 AM |  | Wider industry use of DSTU needed? (TTPL 14)
19 | Revised DSTU Specifications and Training / QVSD (TTPL 15) | N/A | Logical Design (1.3.1.8) | 15d | 8/15/2007 8:00 AM | 9/5/2007 5:00 PM |  | MILESTONE: DSTU Published on www.hl7.org Website
20 | Industry Use of DSTU (TTPL 16) | N/A | Draft Specification (1.3.1.9) | 130d | 9/6/2007 8:00 AM | 3/19/2008 5:00 PM |  | Revised DSTU Specifications and Training / QVSD (TTPL 15)
21 | Produce Complete Specifications / QVSD (TTPL 17) | N/A | Informative Work (HDF 1.3.1: HL7 Project Life Cycle for Product Development) | 15d | 3/20/2008 8:00 AM | 4/9/2008 5:00 PM |  | Industry Use of DSTU (TTPL 16)
22 | -Normative Work |  | Project Initiation (1.3.1.5) | 5d | 4/10/2008 8:00 AM | 4/17/2008 8:00 AM
Requirements Analysis (1.3.1.7)
Logical Design (1.3.1.8)
Draft Specification (1.3.1.9)
23 | Complete/Submit NIB FORM for Normative Ballot |  | Informative Work (HDF 1.3.1: HL7 Project Life Cycle for Product Development) | 5d | 4/10/2008 8:00 AM | 4/16/2008 5:00 PM |  | Produce Complete Specifications / QVSD (TTPL 17)
24 | MILESTONE: Normative Ballot (TTPL 18) |  | Project Initiation (1.3.1.5) |  | 4/17/2008 8:00 AM | 4/17/2008 8:00 AM |  | Complete/Submit NIB FORM for Normative Ballot
25 | Complete/Submit NIB FORM for Informative Ballot, if applicable |  | Requirements Analysis (1.3.1.7) | 5d | 4/10/2008 8:00 AM | 4/16/2008 5:00 PM |  | Produce Complete Specifications / QVSD (TTPL 17)
26 | MILESTONE: Informative Ballot, if applicable (TTPL 18a) |  | Logical Design (1.3.1.8) |  | 4/17/2008 8:00 AM | 4/17/2008 8:00 AM |  | Complete/Submit NIB FORM for Informative Ballot, if applicable
27 | -Publish Standards Work |  | Draft Specification (1.3.1.9) | 20d | 4/17/2008 8:00 AM | 5/14/2008 5:00 PM
28 | Publish Final Specs, IG & Training Matl / QVSD (TTPL 19) | .21 (upon Ballot Approval) | Finalize Specification (1.3.1.16) | 20d | 4/17/2008 8:00 AM | 5/14/2008 5:00 PM |  | MILESTONE: Informative Ballot, if applicable (TTPL 18a) , MILESTONE: Normative Ballot (TTPL 18)
Ballot and Publish (Normative)
Submit Notification of Intent To Ballot (NIB) form (1.3.1.17)
MILESTONE: Normative Ballot (1.3.1.17)
Publish the Standard, Implementation Guide, and Training Material (1.3.1.21)
Mark Project 'To Be Archived' in Project Insight
29 | Mark Project 'To Be Archived' in Project Insight | keep as same |  | 1d | 5/14/2008 8:00 AM | 5/14/2008 5:00 PM | David Hamill | Publish Final Specs, IG & Training Matl / QVSD (TTPL 19) [FF]
30 | Project Total: |  |  | 255d | 5/7/2007 8:00 AM | 5/14/2008 5:00 PM
DURATION - HAVE TOTAL DURATION BE ABOUT 4 MONTHS TO COINCIDE WITH WGM TO WGM TIMEFRAME

## Informative
1
2 | Task Name | NEW INFO | NEW SCHEDULE | Duration | Start Date | End Date | Resources | Predecessors
3 | -Enter Project Name Here |  | -Enter Project Name Here | 255d | 5/7/2007 8:00 AM | 5/14/2008 5:00 PM
4 | -Informative Work |  | Project Scope Statement (PSS) | 40d | 5/7/2007 8:00 AM | 7/3/2007 8:00 AM
5 | Create/Complete PROJECT SCOPE STATEMENT (TTPL 5) | .1 | HL7 Protocol Specifications (1.3.1.1) | 5d | 5/7/2007 8:00 AM | 5/11/2007 5:00 PM
6 | MILESTONE: Create Project in Project Insight | Request to enhance/create/sunset product boxes | Enhance, create or sunset a product? |  | 5/14/2007 8:00 AM | 5/14/2007 8:00 AM |  | Create/Complete PROJECT SCOPE STATEMENT (TTPL 5)
Create/Complete PSS
Sponsoring Group Approves PSS (1.3.1.2)
Submit PSS to Steering Division and PMO (1.3.1.2)
7 | Steering Division Approval (TTPL 7) | .2 | SD Approves PSS (1.3.1.2) | 5d | 5/14/2007 8:00 AM | 5/18/2007 5:00 PM |  | MILESTONE: Create Project in Project Insight
8 | TSC Approval (TTPL 7) | .2 | TSC Approves PSS (1.3.1.2) | 5d | 5/21/2007 8:00 AM | 5/25/2007 5:00 PM |  | Steering Division Approval (TTPL 7)
9 | PMO Approval (TTPL 7) | .2 | PMO Approves PSS (1.3.1.2) | 5d | 5/29/2007 8:00 AM | 6/4/2007 5:00 PM | David Hamill (0.00%) | TSC Approval (TTPL 7)
10 | Define Requirements / QVSD (TTPL 8) | .5 (Project Initiation) |  | 10d | 5/14/2007 8:00 AM | 5/25/2007 5:00 PM |  | MILESTONE: Create Project in Project Insight
11 | Logical Design / QVSD (TTPL 9) | .7 | Informative Work (HDF 1.3.1: HL7 Project Life Cycle for Product Development) | 10d | 5/29/2007 8:00 AM | 6/11/2007 5:00 PM |  | Define Requirements / QVSD (TTPL 8)
12 | Draft Specification / QVSD (TTPL 10) | .8 | Project Initiation (1.3.1.5) | 10d | 6/12/2007 8:00 AM | 6/25/2007 5:00 PM |  | Logical Design / QVSD (TTPL 9)
|  | .9 | Requirements Analysis (1.3.1.7)
13 | Complete/Submit Notification of Intent To Ballot (NIB) form for Informative Ballot | keep as same ('Seek Comments' .10) | Logical Design (1.3.1.8) | 5d | 6/26/2007 8:00 AM | 7/2/2007 5:00 PM |  | Draft Specification / QVSD (TTPL 10)
14 | MILESTONE: Informative Ballot of a Candidate Standard (TTPL 11) | MILESTONE: Informative Ballot | Draft Specification (1.3.1.9) |  | 7/3/2007 8:00 AM | 7/3/2007 8:00 AM |  | Complete/Submit Notification of Intent To Ballot (NIB) form for Informative Ballot
15 | -DSTU Work (for projects which will be normative standards) | N/A |  | 190d | 7/3/2007 8:00 AM | 4/9/2008 5:00 PM
16 | Candidate Standard (DSTU) Validation & Revisions / QVSD (TTPL 12&13) | N/A |  | 15d | 7/3/2007 8:00 AM | 7/24/2007 5:00 PM |  | MILESTONE: Informative Ballot of a Candidate Standard (TTPL 11)
17 | Wider industry use of DSTU needed? (TTPL 14) | N/A |  | 15d | 7/25/2007 8:00 AM | 8/14/2007 5:00 PM |  | Candidate Standard (DSTU) Validation & Revisions / QVSD (TTPL 12&13)
18 | MILESTONE: DSTU Published on www.hl7.org Website | N/A |  |  | 8/15/2007 8:00 AM | 8/15/2007 8:00 AM |  | Wider industry use of DSTU needed? (TTPL 14)
19 | Revised DSTU Specifications and Training / QVSD (TTPL 15) | N/A |  | 15d | 8/15/2007 8:00 AM | 9/5/2007 5:00 PM |  | MILESTONE: DSTU Published on www.hl7.org Website
20 | Industry Use of DSTU (TTPL 16) | N/A |  | 130d | 9/6/2007 8:00 AM | 3/19/2008 5:00 PM |  | Revised DSTU Specifications and Training / QVSD (TTPL 15)
21 | Produce Complete Specifications / QVSD (TTPL 17) | N/A |  | 15d | 3/20/2008 8:00 AM | 4/9/2008 5:00 PM |  | Industry Use of DSTU (TTPL 16)
22 | -Normative Work | N/A |  | 5d | 4/10/2008 8:00 AM | 4/17/2008 8:00 AM
23 | Complete/Submit NIB FORM for Normative Ballot | N/A |  | 5d | 4/10/2008 8:00 AM | 4/16/2008 5:00 PM |  | Produce Complete Specifications / QVSD (TTPL 17)
24 | MILESTONE: Normative Ballot (TTPL 18) | N/A |  |  | 4/17/2008 8:00 AM | 4/17/2008 8:00 AM |  | Complete/Submit NIB FORM for Normative Ballot
25 | Complete/Submit NIB FORM for Informative Ballot, if applicable | N/A |  | 5d | 4/10/2008 8:00 AM | 4/16/2008 5:00 PM |  | Produce Complete Specifications / QVSD (TTPL 17)
26 | MILESTONE: Informative Ballot, if applicable (TTPL 18a) | N/A |  |  | 4/17/2008 8:00 AM | 4/17/2008 8:00 AM |  | Complete/Submit NIB FORM for Informative Ballot, if applicable
Ballot and Publish (Informative)
27 | -Publish Standards Work | Keep as same | Submit Notification of Intent To Ballot (NIB) form (1.3.1.10) | 20d | 4/17/2008 8:00 AM | 5/14/2008 5:00 PM
28 | Publish Final Specs, IG & Training Matl / QVSD (TTPL 19) | .21 (upon Ballot Approval) | MILESTONE: Informative Ballot (1.3.1.19) | 20d | 4/17/2008 8:00 AM | 5/14/2008 5:00 PM |  | MILESTONE: Informative Ballot, if applicable (TTPL 18a) , MILESTONE: Normative Ballot (TTPL 18)
Publish the Standard, Implementation Guide, and Training Material (1.3.1.21)
Mark Project 'To Be Archived' in Project Insight
29 | Mark Project 'To Be Archived' in Project Insight | Keep as same |  | 1d | 5/14/2008 8:00 AM | 5/14/2008 5:00 PM | David Hamill | Publish Final Specs, IG & Training Matl / QVSD (TTPL 19) [FF]
30 | Project Total: | N/A |  | 255d | 5/7/2007 8:00 AM | 5/14/2008 5:00 PM

## DSTU
1
2 | Task Name | NEW INFO | NEW SCHEDULE | Duration | Start Date | End Date | Resources | Predecessors
3 | -Enter Project Name Here |  | -Enter Project Name Here | 255d | 5/7/2007 8:00 AM | 5/14/2008 5:00 PM
4 | -Informative Work |  | Project Scope Statement (PSS) | 40d | 5/7/2007 8:00 AM | 7/3/2007 8:00 AM
5 | Create/Complete PROJECT SCOPE STATEMENT (TTPL 5) | .1 | HL7 Protocol Specifications (1.3.1.1) | 5d | 5/7/2007 8:00 AM | 5/11/2007 5:00 PM
6 | MILESTONE: Create Project in Project Insight | Request to enhance/create/sunset product boxes | Enhance, create or sunset a product? |  | 5/14/2007 8:00 AM | 5/14/2007 8:00 AM |  | Create/Complete PROJECT SCOPE STATEMENT (TTPL 5)
7 | Steering Division Approval (TTPL 7) | .2 | Create/Complete PSS | 5d | 5/14/2007 8:00 AM | 5/18/2007 5:00 PM |  | MILESTONE: Create Project in Project Insight
8 | TSC Approval (TTPL 7) | .2 | Sponsoring Group Approves PSS (1.3.1.2) | 5d | 5/21/2007 8:00 AM | 5/25/2007 5:00 PM |  | Steering Division Approval (TTPL 7)
9 | PMO Approval (TTPL 7) | .2 | Submit PSS to Steering Division and PMO (1.3.1.2) | 5d | 5/29/2007 8:00 AM | 6/4/2007 5:00 PM | David Hamill (0.00%) | TSC Approval (TTPL 7)
10 | Define Requirements / QVSD (TTPL 8) | .5 (Project Initiation) | SD Approves PSS (1.3.1.2) | 10d | 5/14/2007 8:00 AM | 5/25/2007 5:00 PM |  | MILESTONE: Create Project in Project Insight
11 | Logical Design / QVSD (TTPL 9) | .7 | TSC Approves PSS (1.3.1.2) | 10d | 5/29/2007 8:00 AM | 6/11/2007 5:00 PM |  | Define Requirements / QVSD (TTPL 8)
12 | Draft Specification / QVSD (TTPL 10) | .8 | PMO Approves PSS (1.3.1.2) | 10d | 6/12/2007 8:00 AM | 6/25/2007 5:00 PM |  | Logical Design / QVSD (TTPL 9)
.9
13 | Complete/Submit Notification of Intent To Ballot (NIB) form for Informative Ballot | keep as same ('Seek Comments' .10) | DSTU Work (HDF 1.3.1: HL7 Project Life Cycle for Product Development) | 5d | 6/26/2007 8:00 AM | 7/2/2007 5:00 PM |  | Draft Specification / QVSD (TTPL 10)
14 | MILESTONE: Informative Ballot of a Candidate Standard (TTPL 11) | DSTU Ballot .13 | Project Initiation (1.3.1.5) |  | 7/3/2007 8:00 AM | 7/3/2007 8:00 AM |  | Complete/Submit Notification of Intent To Ballot (NIB) form for Informative Ballot
15 | -DSTU Work (for projects which will be normative standards) |  | Requirements Analysis (1.3.1.7) | 190d | 7/3/2007 8:00 AM | 4/9/2008 5:00 PM
|  | .14 | Logical Design (1.3.1.8)
|  | .15 | Draft Specification (1.3.1.9)
.16
|  | .17 Complete/Submit Notification of Intent To Ballot (NIB) form for Normative Ballot | Ballot and Use DSTU
Submit Notification of Intent To Ballot (NIB) form (1.3.1.13)
MILESTONE: DSTU Ballot (1.3.1.13)
16 | Candidate Standard (DSTU) Validation & Revisions / QVSD (TTPL 12&13) |  | Specification and Training (1.3.1.14) | 15d | 7/3/2007 8:00 AM | 7/24/2007 5:00 PM |  | MILESTONE: Informative Ballot of a Candidate Standard (TTPL 11)
17 | Wider industry use of DSTU needed? (TTPL 14) |  | Industry Use (1.3.1.15) | 15d | 7/25/2007 8:00 AM | 8/14/2007 5:00 PM |  | Candidate Standard (DSTU) Validation & Revisions / QVSD (TTPL 12&13)
18 | MILESTONE: DSTU Published on www.hl7.org Website |  | Finalize Specification (1.3.1.16) |  | 8/15/2007 8:00 AM | 8/15/2007 8:00 AM |  | Wider industry use of DSTU needed? (TTPL 14)
19 | Revised DSTU Specifications and Training / QVSD (TTPL 15) |  |  | 15d | 8/15/2007 8:00 AM | 9/5/2007 5:00 PM |  | MILESTONE: DSTU Published on www.hl7.org Website
20 | Industry Use of DSTU (TTPL 16) |  | Ballot and Publish (Normative) | 130d | 9/6/2007 8:00 AM | 3/19/2008 5:00 PM |  | Revised DSTU Specifications and Training / QVSD (TTPL 15)
21 | Produce Complete Specifications / QVSD (TTPL 17) |  | Submit Notification of Intent To Ballot (NIB) form (1.3.1.17) | 15d | 3/20/2008 8:00 AM | 4/9/2008 5:00 PM |  | Industry Use of DSTU (TTPL 16)
22 | -Normative Work | N/A |  | 5d | 4/10/2008 8:00 AM | 4/17/2008 8:00 AM
23 | Complete/Submit NIB FORM for Normative Ballot | N/A |  | 5d | 4/10/2008 8:00 AM | 4/16/2008 5:00 PM |  | Produce Complete Specifications / QVSD (TTPL 17)
24 | MILESTONE: Normative Ballot (TTPL 18) | N/A |  |  | 4/17/2008 8:00 AM | 4/17/2008 8:00 AM |  | Complete/Submit NIB FORM for Normative Ballot
25 | Complete/Submit NIB FORM for Informative Ballot, if applicable | N/A |  | 5d | 4/10/2008 8:00 AM | 4/16/2008 5:00 PM |  | Produce Complete Specifications / QVSD (TTPL 17)
26 | MILESTONE: Informative Ballot, if applicable (TTPL 18a) | N/A |  |  | 4/17/2008 8:00 AM | 4/17/2008 8:00 AM |  | Complete/Submit NIB FORM for Informative Ballot, if applicable
MILESTONE: Normative Ballot (1.3.1.17)
27 | -Publish Standards Work | Keep as same | Publish the Standard, Implementation Guide, and Training Material (1.3.1.21) | 20d | 4/17/2008 8:00 AM | 5/14/2008 5:00 PM
28 | Publish Final Specs, IG & Training Matl / QVSD (TTPL 19) | .21 (upon Ballot Approval) | Mark Project 'To Be Archived' in Project Insight | 20d | 4/17/2008 8:00 AM | 5/14/2008 5:00 PM |  | MILESTONE: Informative Ballot, if applicable (TTPL 18a) , MILESTONE: Normative Ballot (TTPL 18)
29 | Mark Project 'To Be Archived' in Project Insight | Keep as same |  | 1d | 5/14/2008 8:00 AM | 5/14/2008 5:00 PM | David Hamill | Publish Final Specs, IG & Training Matl / QVSD (TTPL 19) [FF]
30 | Project Total: |  |  | 255d | 5/7/2007 8:00 AM | 5/14/2008 5:00 PM

## orig
Admin Options | Act. | Task Name | Duration | hh mm | Work Hours | Start Date | End Date | Resources | Predecessors
|  | -Enter Project Name Here | 255d |  | 4,408.00 | 5/7/2007 8:00 AM | 5/14/2008 5:00 PM
|  | -Informative Work | 40d |  | 560.00 | 5/7/2007 8:00 AM | 7/3/2007 8:00 AM
|  | Create/Complete PROJECT SCOPE STATEMENT (TTPL 5) | 5d |  | 40.00 | 5/7/2007 8:00 AM | 5/11/2007 5:00 PM
|  | MILESTONE: Create Project in Project Insight |  |  | 0.00 | 5/14/2007 8:00 AM | 5/14/2007 8:00 AM |  | Create/Complete PROJECT SCOPE STATEMENT (TTPL 5)
|  | Steering Division Approval (TTPL 7) | 5d |  | 240.00 | 5/14/2007 8:00 AM | 5/18/2007 5:00 PM |  | MILESTONE: Create Project in Project Insight
|  | TSC Approval (TTPL 7) | 5d |  | 0.00 | 5/21/2007 8:00 AM | 5/25/2007 5:00 PM |  | Steering Division Approval (TTPL 7)
|  | PMO Approval (TTPL 7) | 5d |  | 0.00 | 5/29/2007 8:00 AM | 6/4/2007 5:00 PM | David Hamill (0.00%) | TSC Approval (TTPL 7)
|  | Define Requirements / QVSD (TTPL 8) | 10d |  | 80.00 | 5/14/2007 8:00 AM | 5/25/2007 5:00 PM |  | MILESTONE: Create Project in Project Insight
|  | Logical Design / QVSD (TTPL 9) | 10d |  | 80.00 | 5/29/2007 8:00 AM | 6/11/2007 5:00 PM |  | Define Requirements / QVSD (TTPL 8)
|  | Draft Specification / QVSD (TTPL 10) | 10d |  | 80.00 | 6/12/2007 8:00 AM | 6/25/2007 5:00 PM |  | Logical Design / QVSD (TTPL 9)
|  | Complete/Submit Notification of Intent To Ballot (NIB) form for Informative Ballot | 5d |  | 40.00 | 6/26/2007 8:00 AM | 7/2/2007 5:00 PM |  | Draft Specification / QVSD (TTPL 10)
|  | MILESTONE: Informative Ballot of a Candidate Standard (TTPL 11) |  |  | 0.00 | 7/3/2007 8:00 AM | 7/3/2007 8:00 AM |  | Complete/Submit Notification of Intent To Ballot (NIB) form for Informative Ballot
|  | -DSTU Work (for projects which will be normative standards) | 190d |  | 3,520.00 | 7/3/2007 8:00 AM | 4/9/2008 5:00 PM
|  | Candidate Standard (DSTU) Validation & Revisions / QVSD (TTPL 12&13) | 15d |  | 160.00 | 7/3/2007 8:00 AM | 7/24/2007 5:00 PM |  | MILESTONE: Informative Ballot of a Candidate Standard (TTPL 11)
|  | Wider industry use of DSTU needed? (TTPL 14) | 15d |  | 160.00 | 7/25/2007 8:00 AM | 8/14/2007 5:00 PM |  | Candidate Standard (DSTU) Validation & Revisions / QVSD (TTPL 12&13)
|  | MILESTONE: DSTU Published on www.hl7.org Website |  |  | 0.00 | 8/15/2007 8:00 AM | 8/15/2007 8:00 AM |  | Wider industry use of DSTU needed? (TTPL 14)
|  | Revised DSTU Specifications and Training / QVSD (TTPL 15) | 15d |  | 160.00 | 8/15/2007 8:00 AM | 9/5/2007 5:00 PM |  | MILESTONE: DSTU Published on www.hl7.org Website
|  | Industry Use of DSTU (TTPL 16) | 130d |  | 2,880.00 | 9/6/2007 8:00 AM | 3/19/2008 5:00 PM |  | Revised DSTU Specifications and Training / QVSD (TTPL 15)
|  | Produce Complete Specifications / QVSD (TTPL 17) | 15d |  | 160.00 | 3/20/2008 8:00 AM | 4/9/2008 5:00 PM |  | Industry Use of DSTU (TTPL 16)
|  | -Normative Work | 5d |  | 160.00 | 4/10/2008 8:00 AM | 4/17/2008 8:00 AM
|  | Complete/Submit NIB FORM for Normative Ballot | 5d |  | 0.00 | 4/10/2008 8:00 AM | 4/16/2008 5:00 PM |  | Produce Complete Specifications / QVSD (TTPL 17)
|  | MILESTONE: Normative Ballot (TTPL 18) |  |  | 0.00 | 4/17/2008 8:00 AM | 4/17/2008 8:00 AM |  | Complete/Submit NIB FORM for Normative Ballot
|  | Complete/Submit NIB FORM for Informative Ballot, if applicable | 5d |  | 160.00 | 4/10/2008 8:00 AM | 4/16/2008 5:00 PM |  | Produce Complete Specifications / QVSD (TTPL 17)
|  | MILESTONE: Informative Ballot, if applicable (TTPL 18a) |  |  | 0.00 | 4/17/2008 8:00 AM | 4/17/2008 8:00 AM |  | Complete/Submit NIB FORM for Informative Ballot, if applicable
|  | -Publish Standards Work | 20d |  | 168.00 | 4/17/2008 8:00 AM | 5/14/2008 5:00 PM
|  | Publish Final Specs, IG & Training Matl / QVSD (TTPL 19) | 20d |  | 160.00 | 4/17/2008 8:00 AM | 5/14/2008 5:00 PM |  | MILESTONE: Informative Ballot, if applicable (TTPL 18a) , MILESTONE: Normative Ballot (TTPL 18)
|  | Mark Project 'To Be Archived' in Project Insight | 1d |  | 8.00 | 5/14/2008 8:00 AM | 5/14/2008 5:00 PM | David Hamill | Publish Final Specs, IG & Training Matl / QVSD (TTPL 19) [FF]
|  | Project Total: | 255d |  | 4,408.00 | 5/7/2007 8:00 AM | 5/14/2008 5:00 PM

## Combined
1 | Duration | Concurent | Dependencies | Normative | Informative | DSTU | Comment Only
2 |  |  |  | NEW SCHEDULE | NEW SCHEDULE | NEW SCHEDULE | NEW SCHEDULE
3 |  |  |  | -Enter Project Name Here | -Enter Project Name Here | -Enter Project Name Here | -Enter Project Name Here
4 |  |  |  | Project Scope Statement (PSS) | Project Scope Statement (PSS) | Project Scope Statement (PSS) | Project Scope Statement (PSS)
5 | 1 week | Yes |  | HL7 Protocol Specifications (1.3.1.1) | HL7 Protocol Specifications (1.3.1.1) | HL7 Protocol Specifications (1.3.1.1) | HL7 Protocol Specifications (1.3.1.1)
6 |  | with 5 |  | Enhance, create or sunset a product? | Enhance, create or sunset a product? | Enhance, create or sunset a product? | Enhance, create or sunset a product?
7 |  | with 5 & 6 | 5 & 6 | Create/Complete PSS | Create/Complete PSS | Create/Complete PSS | Create/Complete PSS
8 | 2 weeks |  | 7 | Sponsoring Group Approves PSS (1.3.1.2) | Sponsoring Group Approves PSS (1.3.1.2) | Sponsoring Group Approves PSS (1.3.1.2) | Sponsoring Group Approves PSS (1.3.1.2)
9 | New project scope deadline |  | 8 | Submit PSS to Steering Division and PMO (1.3.1.2) | Submit PSS to Steering Division and PMO (1.3.1.2) | Submit PSS to Steering Division and PMO (1.3.1.2) | Submit PSS to Steering Division and PMO (1.3.1.2)
10 | 1 wk |  | 9 | SD Approves PSS (1.3.1.2) | SD Approves PSS (1.3.1.2) | SD Approves PSS (1.3.1.2) | SD Approves PSS (1.3.1.2)
11 | 1 wk |  | 10 | TSC Approves PSS (1.3.1.2) | TSC Approves PSS (1.3.1.2) | TSC Approves PSS (1.3.1.2) | TSC Approves PSS (1.3.1.2)
12 | 1 wk |  | 11 | PMO Approves PSS (1.3.1.2) | PMO Approves PSS (1.3.1.2) | PMO Approves PSS (1.3.1.2) | PMO Approves PSS (1.3.1.2)
13
14 |  |  |  | Normative Work (HDF 1.3.1: HL7 Project Life Cycle for Product Development) | Informative Work (HDF 1.3.1: HL7 Project Life Cycle for Product Development) | DSTU Work (HDF 1.3.1: HL7 Project Life Cycle for Product Development) | Comment Only Work (HDF 1.3.1: HL7 Project Life Cycle for Product Development)
15 | 1 wk | Yes | 11 | Project Initiation (1.3.1.5) | Project Initiation (1.3.1.5) | Project Initiation (1.3.1.5) | Project Initiation (1.3.1.5)
16 | 1 wk | with 15 | 14 | Requirements Analysis (1.3.1.7) | Requirements Analysis (1.3.1.7) | Requirements Analysis (1.3.1.7) | Requirements Analysis (1.3.1.7)
17 | 1 wk | Yes | 15 | Logical Design (1.3.1.8) | Logical Design (1.3.1.8) | Logical Design (1.3.1.8) | Logical Design (1.3.1.8)
18 | 1 wk | With 17 | 16 | Draft Specification (1.3.1.9) | Draft Specification (1.3.1.9) | Draft Specification (1.3.1.9) | Draft Specification (1.3.1.9)
19
20 | [5 empty] | Ballot and Use DSTU
21 | 1 wk | Yes with 17 & 18 | 9 needs to be done 16 needs to be done and 18 needs to have started and be well along to clearly articulate the specification |  |  | Submit Notification of Intent To Ballot (NIB) form (1.3.1.13)
22 | [5 empty] | MILESTONE: DSTU Ballot (1.3.1.13)
23 | 4 wk |  | 22 |  |  | Specification and Training (1.3.1.14)
24 | 6 mn | Yes with 23 | 23 |  |  | Industry Use (1.3.1.15)
25 | 1 wk | Yes with 24 probably on-going throughout the use | 24 |  |  | Finalize Specification (1.3.1.16)
26
27 |  |  |  | Ballot and Publish (Normative) | Ballot and Publish (Informative) | Ballot and Publish (Normative) | Ballot (Comment Only)
28 | 1 wk | Yes with 25 | 18 for Norm and Inform, Comment. 25 for DSTU | Submit Notification of Intent To Ballot (NIB) form (1.3.1.17) | Submit Notification of Intent To Ballot (NIB) form (1.3.1.10) | Submit Notification of Intent To Ballot (NIB) form (1.3.1.17) | Seek Comments/Submit Notification of Intent To Ballot (NIB) form (1.3.1.10)
29 |  | Yes with 28 | 28 | MILESTONE: Normative Ballot (1.3.1.17) | MILESTONE: Informative Ballot (1.3.1.19) | MILESTONE: Normative Ballot (1.3.1.17) | MILESTONE: Ballot Type (1.3.1.11) - Decision: Go forward with Normative, Informative or DSTU? Go to Line 7 and Modify PSS in the appropriate column based on your decision. Work with the PMO to create a new Project Insight entry with the correct schedule template.
30 | 1 wk |  | 29 |  | Go Normative? (1.3.1.20)
31 | 4 wk |  | 30 |  | Specification and Training (1.3.1.14)
32 | 6 mn | Yes with 29 | 31 |  | Industry Use (1.3.1.15)
33 | 1 wk | Yes with 32 probably on-going throughout the use | 32 |  | Finalize Specification (1.3.1.16)
34 | 1 wk | Yes with 33 probably on-going throughout the use | 33 |  | Submit Notification of Intent To Ballot (NIB) form (1.3.1.17)
35 | 1 wk | Yes with 34 | 34 |  | MILESTONE: Normative Ballot (1.3.1.17)
36 | 2 mn |  | 29, 35 | Publish the Standard, Implementation Guide, and Training Material (1.3.1.21) | Publish the Standard, Implementation Guide, and Training Material (1.3.1.21) | Publish the Standard, Implementation Guide, and Training Material (1.3.1.21)
37 | 1 wk |  | 36 must be completed and archived | Mark Project 'To Be Archived' in Project Insight | Mark Project 'To Be Archived' in Project Insight | Mark Project 'To Be Archived' in Project Insight
Note on B1: Ken McCaslin: wk = Week - 5 business days mn = Month or 4.5 weeks This assumes a small project with limited scope and requirements. Larger projects may require addtitional time as defined by the Work Grou during the Discovery phase of the project.
Note on C1: Ken McCaslin: Can this run concurrent with another item and what is the item.
Note on D1: Ken McCaslin: Dependencies define items that must at least be started, potentially even completed before the current item can began. This assumes basic principles of smal projects with limited scope and requirements. Larger projects may have more restricted dependencies.