## Overview
ProjectConnections.com Template | Simple Portfolio Status Report
Introduction: Simple Portfolio Status Report
What This Is
The Simple Portfolio Status Report is a multi-project, high-level status format for visually conveying a quick look at the status of various on-going, soon-to-start, or dependent projects. It was developed by a medium-sized telecom company as a way of quickly reporting project portfolio status to executive staff members. By design, it does not contain much detail! Instead, it provides a way for high-level managers to identify critical problems in the portfolio, and then focus executives on those issues.
Why It's Useful
Common project planning tools like MS Project have roll-up methods to report status on the on-going project portfolio. At this telecom PMO, an analysis revealed that it was more costly to do a complete roll-up of all the projects to get a summary status sheet on a weekly basis. Even when that approach was used, it was always modified for the executive staff meetings anyway, into something easier to read, fitting the preferences of the executive staff. The simple Excel status format was created to highlight problem areas and critical issues on projects and within the project portfolio.
How to Use It
Project team leaders and project managers determine their weekly status from the project team and forward it to the PMO (Project Management Office), or whoever is creating a summary status for the executives. Four status criteria are used:
Green - The project is going well or very close to plan.
Yellow - Something on the project has become suspect and put the plan in jeopardy, or something is indeterminate and may put the project at risk.
Orange - Something is definitely amiss and the project plan has slipped. A change is required or an alteration to the plan.
Red - The project is experiencing critical problems and a plan review is required immediately. Changes to the plan are necessary—perhaps extreme changes.
Future status blocks are left blank.
An "X" in the block indicates project start dates that are delayed, but scheduled.
The status criteria are applied in the following areas:
Technology: These are risks to the planned technology. They may propagate into cost overruns and time delays, but they should show up first as technical issues. These are generally problems encountered by the design and execution teams, although things like licensing contract failures could manifest into a failed technology (e.g., cannot use technology of choice/design).
Costs: Budget overruns. These are usually— but not always—a symptom of an earlier technology problem or of time delays. The PMO should decide if dips into contingency or reserve project funds are within the yellow or red status zones or if these colors are only used after the reserve is consumed.
Time: Delays in time. Causes of this are varied, but use of the yellow status indicates that there is a risk of schedule delays.

## Executive Status
Project Name | Priority | Proj Mgr | Status | January |  |  |  | February |  |  |  | March |  |  |  | April |  | May
Software Maintenance | Low | R. Smith | technology
costs
time
System Maintenance | Medium | R. Smith | technology
costs
time
Middleware Maintenance | Medium | R. Smith | technology
costs
time
Installation Application Maint. | Low | R. Smith | technology
costs
time
Software Diagnostics | High | J. Thomas | technology
costs
time
Software Messaging Module | High | S. Jones | technology
costs
time
Software JSP Diagnostics Responder | High | J. Thomas | technology
costs
time
Software Msg Display Application | High | S. Jones | technology
costs
time
Software Release | Medium | V. Narayan | technology | X | X | X | X | X | X | X | X | X | X
|  |  | costs | X | X | X | X | X | X | X | X | X | X
|  |  | time | X | X | X | X | X | X | X | X | X | X
Client HW version 2 upgrade | Medium | N. Zhang | technology
costs
time
Client HW cost reduction | High | N. Zhang | technology
costs
time
Customized CD and install (Customer Big Money) | High | P. Williams | technology | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  | costs | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  | time | X | X | X | X | X | X | X | X | X | X | X | X | X
Customized CD and install (Customer Deep Pockets) | High | P. Williams | technology | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  | costs | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  | time | X | X | X | X | X | X | X | X | X | X | X | X | X | X
technology (Risk of technical failure)
costs (budget over run or potential)
time (resource shortage / delay)
Project status is "Good" | Green
Project status is "In Question" | Yellow
Project status is "Below Expectations" | Orange
Project status is "Critical" or "Bad" | Red
Project scheduled but not started | X | X