## TxDOT
Schedule Patch #1: Projects with TxDOT Funding
1.a: If TxDOT is participating in design costs, insert the following rows after Row 40 in the schedule template
MSP Line # | Task Name | Duration | Start | Finish | Predecessors
41 | Obtain TxDOT funding (if includes design costs) |  |  |  | 40
42 | Obtain Advance Funding Agreement from TxDOT | 10 days |  |  | 40
43 | Prepare RCA for approval of interlocal agreement | 45 days |  |  | 42
44 | After Council approval, return signed APA to TxDOT | 5 days |  |  | 43
1.b: Insert the following rows after Row 115 in the < $2M template or after Row 135 in the > $2M template
MSP Line # | Task Name | Duration | Start | Finish | Predecessors
116/136 | TxDOT Environmental Processing |  |  |  | 116/136
117/137 | Submit environmental documents to TxDOT for review | 5 days |  |  | 116/136
118/138 | Address environmental review comments from TxDOT | 30 days |  |  | 117/137
1.c: Insert the following rows after Row 231 in the < $2M template or after Row 251 in the > $2M template
MSP Line # | Task Name | Duration | Start | Finish | Predecessors
232/252 | TxDOT review of bid documents & project manual
233/253 | Submit 100% plans/manual to TxDOT for review | 1 day |  |  | 231/251
234/254 | Receive TxDOT comments | 180 days |  |  | 233/253
235/255 | Address TxDOT comments | 30 days |  |  | 234/254
236/256 | Obtain TxDOT Funding (if construction only)
237/257 | Obtain Advance Funding Agreement from TxDOT | 10 days |  |  | 235/255
238/258 | Prepare RCA for approval of interlocal agreement | 45 days |  |  | 237/257
239/259 | After Council approval, return signed APA to TxDOT | 5 days |  |  | 238/258

## Design-Build
Schedule Patch #2: Projects Using Design-Build Delivery Method
2.a: Insert the following rows after Row 75 in the Arch > $2M template
MSP Line # | Task Name | Duration | Start | Finish | Predecessors
76 | Determine Project Delivery Method (Bldg Projects Only)
77 | Determine project delivery options & formulate recommendation | 10 days |  |  | 75
78 | Prepare & conduct briefings for MWBE AdvCom & Council Subcmte | 5 days |  |  | 77
79 | Obtain Council approval of alternate delivery method | 20 days |  |  | 78
2.b: Replace section Preliminary- RFQ Process "RFQ Advertisement & Selection" in the Arch > $2M template with the following
(new line numbers based on patch 2.a above having been made)
MSP Line # | Task Name | Duration | Start | Finish | Predecessors
80 | RFQ/RFP Process (Design-Build)
81 | Conduct RFQ process | 150 days |  |  | 79
82 | Determine short-listed firms | 16 days |  |  | 79SS+120 days
83 | Prepare and issue RFP to short-listed firms | 10 days |  |  | 82
84 | Conduct pre-proposal conference | 1 day |  |  | 83SS+10 days
85 | Proposals received (time milestone only) | 1 day |  |  | 81FF
86 | Conduct evaluations, including interviews | 60 days |  |  | 85
87 | Compile final results | 1 day |  |  | 87
2.c: Insert the following rows after Design "Permitting process" in the Arch > $2M template
(new line numbers based on patches 2.a and 2.b above having been made)
MSP Line # | Task Name | Duration | Start | Finish | Predecessors
234 | Establish Guaranteed Maximum Price for Construction
235 | Design-Builder solicits trade subcontracts | 100 days |  |  | 233
236 | Review/approve subcontract recommendations | 30 days |  |  | 235
237 | Reach agreement on GMP | 10 days |  |  | 236
238 | Obtain Council approval of GMP | 20 days |  |  | 237
239 | Execute Amendment #1 with Design-Builder | 10 days |  |  | 238
2.d: Delete all task rows in "Bid/Award/Execution Phase" except PMO tasks (zero durations)

## CM at Risk
Schedule Patch #3: Projects Using Construction Manager at Risk (CMR) Delivery Method
3.a: Insert the following rows after Row 75 in the Arch > $2M template
MSP Line # | Task Name | Duration | Start | Finish | Predecessors
76 | Determine Project Delivery Method (Bldg Projects Only)
77 | Determine project delivery options & formulate recommendation | 10 days |  |  | 75
78 | Prepare & conduct briefings for MWBE AdvCom & Council Subcmte | 5 days |  |  | 77
79 | Obtain Council approval of alternate delivery method | 20 days |  |  | 78
3.b: Insert the following rows after Design "Issue Notice to Proceed with Design" task in the Arch > $2M template
(new line numbers based on patch 3.a above having been made)
MSP Line # | Task Name | Duration | Start | Finish | Predecessors
201 | Select & Contract with Construction Manager at Risk
202 | Prepare & issue RFQ (if using 2-step process) | 10 days |  |  | 200
203 | Conduct pre-response meeting | 1 day |  |  | 202
204 | RFQ responses received | 45 days |  |  | 203
205 | Conduct evaluations | 10 days |  |  | 204
206 | Determine short-listed firms | 1 day |  |  | 205
207 | Prepare & issue RFP to short-listed firms | 5 days |  |  | 206
208 | Conduct pre-proposal meeting | 10 days |  |  | 207
209 | Proposals received | 30 days |  |  | 208
210 | Conduct evaluations, including interviews | 10 days |  |  | 209
211 | Compile final results | 1 day |  |  | 210
212 | Obtain Council approval of CMR selection | 45 days |  |  | 211
213 | Negotiate and execute CMR contract | 10 days |  |  | 212
214 | Issue notice to proceed to CMR | 2 days |  |  | 213
215 | Conduct kick-off meeting with project team | 0 days |  |  | 214
3.c: Insert the following rows after Design "Permitting process" in the Arch > $2M template
(new line numbers based on patches 3.a and 3.b above having been made)
MSP Line # | Task Name | Duration | Start | Finish | Predecessors
261 | Establish Guaranteed Maximum Price for Construction
262 | Design-Builder solicits trade subcontracts | 100 days |  |  | 260
263 | Review/approve subcontract recommendations | 30 days |  |  | 262
264 | Reach agreement on GMP | 10 days |  |  | 263
265 | Obtain Council approval of GMP | 20 days |  |  | 264
266 | Execute Amendment #1 with Design-Builder | 10 days |  |  | 265
3.d: Delete all task rows in "Bid/Award/Execution Phase" except PMO tasks (zero durations)