## Instructions
Instructions
1) Add or Delete project roles as applicable to your project
2) Insert key tasks and deliverables by phase
3) For each task select the appropriate assignment based on the resources involvement in that particular task. (A legend is provided in cell A3)

## Consolidated RAM
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
Project Funding
Task/Deliverable 1
Task/Deliverable 2
Acquisition Planning
Task/Deliverable 1
Task/Deliverable 2
Contracting
Task/Deliverable 1
Task/Deliverable 2
Requirements Analysis
Task/Deliverable 1
Task/Deliverable 2
System Design
Task/Deliverable 1
Task/Deliverable 2
System Development
Task/Deliverable 1
Task/Deliverable 2
System Implementation
Task/Deliverable 1
Task/Deliverable 2
Resources
P
A
S
I

## Project Funding
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
Project Funding
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Resources
P
A
S
I

## Acquisition Planning
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
Acquisition Planning
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Resources
P
A
S
I

## Contracting
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
Contracting
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Resources
P
A
S
I

## Requirements Analysis
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
Requirements Analysis
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Resources
P
A
S
I

## System Design
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
System Design
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Resources
P
A
S
I

## System Development
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
System Development
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Resources
P
A
S
I

## System Implementation
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Procurement Manager | Risk Manager | Administrative Manager | Administrative Staff Support | Financial Analyst | Contract Manager | Project Librarian | Project Scheduler | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Application Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor | Executive Steering Committee | IPOC & IVV | Legal Counsel | DOF | DGS | Federal Partners
System Implementation
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Task/Deliverable
Resources
P
A
S
I