## Overview
Project Scorecard
Introduction: Project Scorecard
What This Is
This is a one page shared definition of project team success, the "finish line" for the entire team regardless of functional area or responsibilities of any individual. The process of creating the scorecard forces all stakeholders to clarify the meaning and measures of "success", and track status and progress vs. these shared definitions throughout the project.
Why It's Useful
Project Teams benefit from having shared goals and shared metrics of success. They need to all have the same understanding of where the "finish line" is in the project race. Individual functional area success does not always correlate with overall project success. Project status reports may state where a project is with respect to its deadlines, but they often overlook the more critical aspect: where is the project in relationship to its goals -- the reasons for doing the project in the first place? This overall project scorecard provides a high-level view of the project's status in relation to overall project or product development success criteria, both during development, and after final release. It includes a prioritized list of the metrics of success, minimum "Go/NoGo" criteria for the project being worth doing, and a "Red/Yellow/Green" status indication that enables "at a glance" status reviews throughout the project. In addition, it encourages a long-term perspective on the definition of success by encouraging the team to think about when the various metrics of success will be measurable and/or measured. Periodically sharing this one page "dashboard" with the team, executives and other stakeholders can assure that everyone has the same understanding of project status throughout the project, and provide early warnings of problems by catalyzing conversations about what could be a problem in the future even though it can't easily be measured today. If you can at least imagine how you WOULD measure it, you'll reduce ambiguity and misunderstandings about the goals, and increase your chances of success.
How to Use It - Expect resistance from people who don't feel comfortable guessing or discussing metrics!
1. Review the project scorecard example on the next worksheet as an example. The example illustrates what a completed scorecard might look like for a project partway through its development phase, but before the status has been updated. The sample project used is anticipating serious problems with product availability, and there may be concerns about meeting the goals for revenue, ROI, and overall impact on company success. Notice, however, that the top 3 prioritized goals -- Quality, Functionality, and Schedule -- are all classified green; in spite of the issues, the project is still meeting its most important major goals. Once you've oriented yourself to what good and bad projects would look like, use the Blank Scorecard on the last worksheet to build a scorecard for your own project.
2. Describe your development success criteria or high-level project goals in Column C. Your categories may be different. And people will certainly resist defining success metrics that they believe will be difficult or impossible to measure. It's important to remember that the CONVERSATIONS about exatly WHAT success is and the MEASURES of that success are more valuable than the actual finished scorecard.
3. List the Target and Minimum Acceptance Limit for each goal area in Columns E and D respectively. You should have a clear and measurable goal (target) for each major area listed, and each listed success criteria should have buy in from team members as well as from the project sponsor and concerned executives. Goals that aren't supported won't be met. Remember, the minimums you set in this column mean that you are willing to CANCEL the project if your team cannot achieve at least the minimum. This is your GO/NoGO criteria.
4. Use Column A to indicate at least the 3 or 4 most important criteria for this project, in order. Prioritize ruthlessly, choosing between heart, lung, and kidneys if necessary, and do not rank any more than 4 criteria. These priorities will help you determine where, or if, to concentrate your effort when the project slips from one of the targets. When tough trade off decisions must be made, team members should refer to these priorities and make decisions in alignment with them. Again, the conversations with various stakeholders around setting the relative priorities of the various requirements are far more valuable than the ranking. Don't just fill it out to save your team time!
5. Periodically review each success criteria with the team and key stakeholders and agree on a Red/Yellow/Green status based on the current situation vs. the targets. This assessment is somewhat subjective, so try to find a consistent way to make the judgment. For instance, green may be on or ahead of targets, yellow may be behind by 10% or more, red off target by 30% or more. Ideally, these thresholds should be consistent from project to project and department to department. Differences in opinions among various stakeholders on status are the most interesting. Remember that, prior to the Space Shuttle Challenger explosion, space shuttle engine failure likelihood was estimated by engineers to be 1 in 200 while execs estimated the likelihood at 1 in 100,000.
6. If corrective action is necessary to bring a goal back to Green status, record the Action Items and the Owners in the appropriate columns. These are the high priority actions that must be taken in order to get the project back on track. Clear accountability by the owners as well as follow up to track status and progress are important here, of course.
7. Review the scorecard periodically throughout the project to ensure that all stakeholders have a shared understanding of the status of areas key to success and that corrective action is taken immediately in the event that a key area is off track.

## Scorecard Example
Overall Project Scorecard – EXAMPLE | [7 empty] | Updated: 8/15/2003
It's vital that the Project Team have a shared definition of "done". The intention of this list is to assess product status in relation to overall project team success criteria both during the project and beyond. This checklist should be reviewed at all checkpoints starting with Phase 1, as well as at periodic intervals post-release.
* RYG Indicators RED = OFF TRACK or Worry! YELLOW = Worry a little. GREEN = No worries, mate!
Priority for this Project | Item & Status (RYG*) | Description | Minimum Acceptance Limit (Go/NoGo Criteria . . . A MUST for making it worth the effort.) | Target | How and When Will This B Measurable /Measured? | Status Comments | Action Items Required to Change Status to Green | Owner
2 | Functionality | At least the minimum viable features to be successful in the market. | All "MUST" functionality in the product requirements document. | All of the "MUST" and "HIGH WANTS" functionality in the product requirements document. | First prototype through product shipment.
3 | Schedule | Schedule hits the market window of opportunity. | Phase 1 schedule +/- 2 months, or the Plan of Record (POR) schedule after a scope change. | Phase 1 schedule +/- 2 weeks, or the Plan of Record (POR) schedule after a scope change. | Ongoing throughout project.
| Revenue | Revenues from sales, service, support meet or exceed minimum estimated to make this a viable product to develop. | Revenue matches forecast +/- 20% | Revenue matches forecast +/- 10% | During development this would be projected revenues based on the forecast and market competivness. After sales begin.
| ROI | ROI, cash-to-cash meets or exceeds targets. | ROI matches forecast +/- 3% | ROI matches forecast +/- 2% | During Development based on forecast. After FCS (First Customer Shipment) based on actuals. Ultimately 3 - 5 years after project project completion.
1 | Quality | Quality meets or exceeds customer expectations and our internal cost of quality goals. (Post-release serious and critical bugs, other SW metrics of quality, AFR, DOA, reliability etc.) | AFR rate half of previous product after 6 months shipping. | AFR rate 10% of previous product after 6 months shipping. | After first customers receive the prototypes, and thoughout the lifetime of the product.
| Supportability & Serviceability | We and our customers can effectively service and support the product in the field in the volumes shipped in a timely fashion, at or below our predicted support costs. | Support Staff rates this 2X as supportable as previous product. | Support Staff rates this 10X as supportable as previous product. | Throughout the supported lifetime of the product, especially in the first 3 - 6 months in order to assess corrective action requirements. During Development based on predictions using MTBF and AFR predictions comparing the product to similar products, SW defect find stats, test coverage, etc. After FCS/GA based on actuals.
| Usability | Customer experience of learning, using and supporting the product meets or exceeds their expectations for ease-of-use. | Customers can learn to use the product in leass than 20 minutes, getting their first data from a real sample in that timeframe. Customers rate this product as 2X more usable than previous product. | Customers can learn to use the product in leass than 20 minutes, getting their first data from a real sample in that timeframe, without referring to the user manual. 5X more usable than previous. | From the time we have mock-ups of the user interface and during the first 3 months of product shipments. During development based on internal testing, external field testing, out of box testing. After FCS/GA based on defect and failure reporting attributable to “user error.”
| Costs | Costs at or below target, including manufacturing, support, warranty costs, TCO. | Budget +/- 30% | Budget +/- 20% | Throughout the project and the entire product lifecycle. During development this is based on projections. After FCS all are based on actuals.
| Availability | Ability to ramp ahead of the demand curve with acceptable delivery times. | 95% of orders fulfilled within 4 weeks of receipt during 3 month ramp up, and within 2 weeks thereafter. | 100% of orders fulfilled within 1 week of receipt after 3 months ramp up. | During development this is based on a coordinated plan with the manufacturing partner. After FCS this is based on actuals. After sales begin.
4 | Company Success | Supports overall company success, including strategic, and fitting in with the rest of the product offering. | Reputation not tarnished by this product. Contribution to revenues and profits exceed previous product by 25%. | Reputation enhanced by this product. Contribution to revenues and profits exceed previous product by 50%. | Monitor the market and program during development to ensure market alignment. Assess actual sales/opportunities against the plan after FCS. Throughout the product shipment and support phase.

## Scorecard Template
Overall Project Scorecard for Project ________________________________________ | [7 empty] | Updated: 8/15/2003
It's vital that the Project Team have a shared definition of "done". The intention of this list is to assess product status in relation to overall project team success criteria both during the project and beyond. This checklist should be reviewed at all checkpoints starting with Phase 1, as well as at periodic intervals post-release.
* RYG Indicators RED = OFF TRACK or Worry! YELLOW = Worry a little. GREEN = No worries, mate!
Priority for this Project | Item & Status (RYG*) | Description | Minimum Acceptance Limit (Go/NoGo Criteria . . . A MUST for making it worth the effort.) | Target | How and When Will This B Measurable /Measured? | Status Comments | Action Items Required to Change Status to Green | Owner
Functionality
Schedule
Revenue
ROI
Quality
Supportability & Serviceability
Usability
Costs
Availability
Company Success