## Project Questions
| PMO Initial Risk and Complexity Assessment Instructions on using this spreadsheet: Read eachMajor Project Requirement and select whether your project fits the low, medium, or high risk description by choosing the correct option in the rating drop down list. After rating your project on all of the Major Project Requirements, review your project's risk score and recommended project category at the end of the spreadsheet. | [7 empty] | Project Name: Project Manager:
| Major Project Requirement | Weight | Rating Criteria |  |  |  |  | Rating | Reference Materials PC: Project Charter template PP: Project Plan (for Category D Projects) template PE - Project Excecution template
|  |  | Low Risk | Medium Risk | High Risk |  |  |  |  | Area
| Total team FTE (in person years) | 25 | < 1 | 1 to 2 | > 2 | 0 | 0 | high | PP - Resource Allocation, PP - Risk Management, Risk Register template, Risk Log template, Team Status Report template, Project Status Report template, Project Performance Report template. PE - Project Activity, PE - Issues Log, PE - Risk Activity | T
[6 empty] | 0 | 0
[6 empty] | 3 | 75
| Business process change | 5 | minimal change or extends systems in use | moderate change | significant change | 0 | 0 | high | PC - Project Scope Statement (Includes/Excludes), PP - Quality Management, PE - Communications Activity, PE - Quality Log | S | Important when scope is ill-defined or large
[6 empty] | 0 | 0
[6 empty] | 3 | 15
Quality Mgmt | Number of people (stakeholders) affected by the project | 5 | 1 to 3 | 4 to 10 | > 10 | 0 | 0 | high | PP - External Stakeholders, PP - Communication Management Approach, PP - Communication Stakeholders and Information Identification, PE - Communications Activity | S | Important when working with inexperienced PM
[6 empty] | 0 | 0
[6 empty] | 3 | 15
| Project timeline | 5 | < 6 months | 6months - 1 year | > 1 year | 0 | 0 | high | PP - Work Activities, PP - Schedule Allocation, PP - Major Project Milestones, PP - Critical Dates, Risk Register template, Risk Log template, PE - Project Activity, PE - Risk Activity | T
[6 empty] | 0 | 0
[6 empty] | 3 | 15
| Budget | 5 | < $100K | $100K - $250K | > $250K | 0 | 0 | high | PP - Budget Allocation, Risk Register template, Risk Log template, Project Performance Report template, PE - Budget Activity | C | Important if other risks are high
[6 empty] | 0 | 0
[6 empty] | 3 | 15
| End-user/stakeholder involvement | 4 | very involved | somewhat involved | little or no involvement | 0 | 0 | high | PP - Roles and Responsibilities, PP - Project Reviews & Assessments, PE - Communications Activity | Q, S | Important if requirments and success are customer-driven
[6 empty] | 0 | 0
[6 empty] | 3 | 12
| Project manager experience | 4 | very experienced with similar projects | moderate experience or has other similar project experience | no experience with this type of project or is new to project management | 0 | 0 | high | Project Charter template, Project Plan template, PP - Resource Training, Project Status Report template, Project Performance Report template, Project Execution template | Q | Important if other risks are high
[6 empty] | 0 | 0
[6 empty] | 3 | 12
| Level of complexity | 4 | standalone with very few processes | SaaS product and/or mid range complexity | extensive processes & reporting requirements | 0 | 0 | high | PP - Quality Objectives and Standards Identification, PP - Project Reviews and Assessments, PP - Deliverables Acceptance Criteria, PP - Process Improvement Approach, PE - Quality Activity | S
[6 empty] | 0 | 0
[6 empty] | 3 | 12
| Team experience | 4 | extensive experience with similar projects | some experience with similar projects | minimal or no experience with similar projects | 0 | 0 | high | PP - Resource Training | Q | Important if other risks are high
[6 empty] | 0 | 0
[6 empty] | 3 | 12
Risk Mgmt | Number of end-users | 4 | 1 to 100 | 101 to 1000 | > 1000 | 0 | 0 | high | PP - End-user Training and Security Plan, PP - Project System Performance Approach | S | Important when scope is ill-defined or large
[6 empty] | 0 | 0
[6 empty] | 3 | 12
| Project delivery date | 4 | derived by proper project management practices | best guess estimate | none, mandated and/or critical | 0 | 0 | high | PP - Work Activities, PP - Schedule Allocation, PP - Major Project Milestones, PP - Critical Dates, PE - Project Activity | T | Important if scope is not well-defined and/or poor/non-existant change management process
[6 empty] | 0 | 0
[6 empty] | 3 | 12
| Project requirements | 3 | clearly defined and reasonable | some ambiguity | vague, undefined, or unreasonable | 0 | 0 | high | PC - Project Scope Statement (Includes/Excludes), Texas Project Delivery Framework System Development Life Cycle Extension | S | Important when timeline is dictated or non-existant
[6 empty] | 0 | 0
[6 empty] | 3 | 9
| Number of work units involved | 2 | 1 | 2 to 5 | > 5 | 0 | 0 | high | PP - Work Activities, PP - Schedule Allocation, PP - Major Project Milestones, PP - Critical Dates, Risk Register template, Risk Log template, PE - Communications Activity | S | Contributes to complexity
[6 empty] | 0 | 0
[6 empty] | 3 | 6
Procurement Mgmt | Sponsorship | 2 | named high level executive | management support | no sponsor | 0 | 0 | high | PC - Critical Success Factors, PC - Assumptions, PC - Constraints, PC - Funding Authority, PC - Project Oversight Authority, PC - Project Facilities and Resources, PP -Roles and Responsibilities | T | Important when working with multiple work units and stakeholders
[6 empty] | 0 | 0
[6 empty] | 3 | 6
| Team skillset in relation to the project | 2 | good fit | moderate fit | poor fit | 0 | 0 | high | PP - Resource Training, Team Status Report template | Q
[6 empty] | 0 | 0
[6 empty] | 3 | 6
HR Mgmt | Change management process | 2 | well defined & approval process in place | not well defined and/or verbal approval | not defined | 0 | 0 | high | PP - Change Management Plan, Change Request template, PE - Change Log | S | Important when budget, quality, and timeline are not flexible
[6 empty] | 0 | 0
[6 empty] | 3 | 6
| SDLC (system development life cycle) approach | 2 | established, followed, and effective | not well defined or partially followed | not defined and/or not followed | 0 | 0 | high | Texas Project Delivery Framework System Development Lifecycle Extension | Q | Important when working with inexperienced PM or team
[6 empty] | 0 | 0
[6 empty] | 3 | 6
| Team member availability | 2 | in place and dedicated to the project | available with some expected turnover and interruption | high turnover or not available most of the time | 0 | 0 | high | PP - Resource Allocation, Team Status Report template, Project Status Report template, PE - Communications Activity | T | Important if mandated or no delivery date
[6 empty] | 0 | 0
[6 empty] | 3 | 6
Cost Mgmt | Assumptions | 1 | documented, verified, and/or conservative | documented but unverified and/or aggressive | undocumented, unverified, and/or aggressive | 0 | 0 | high | PC - Assumptions | S | Important when budget, quality, and timeline are not flexible
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| External hardware or software interfaces needed | 1 | little or none | some | extensive | 0 | 0 | high | PP- Configuration Management Plan, Configuration Register Log template, Configuration Status Accounting Report template, PE - Quality Activity, PE - Issue Activity | S | Contributes to complexity
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| Hardware platform | 1 | stable, no changes expected, capacity is sufficient | some changes under evolution, but controlled | platform under development along with software | 0 | 0 | high | PP - Configuration Management Plan, Configuration Register Log template, Configuration Status Accounting Report template, Change Request template, PE - Change Log | S | Contributes to complexity
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| Number of end-user roles | 1 | 1 to 3 | 4 to 10 | > 10 | 0 | 0 | high | Texas Project Delivery Framework System Development Lifecycle Extension | S | Contributes to complexity
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| Physical facilities | 1 | little or no modification needed | some modifications needed; some existent | major modifications needed, or facilities non-existent | 0 | 0 | high | PC - Project Facilities and Resources | S | Contributes to complexity
[6 empty] | 0 | 0
[6 empty] | 3 | 3
Communication Mgmt | Policies, procedures, and standards | 1 | well defined and followed | not well defined or partially followed | not defined and/or not followed | 0 | 0 | high | Project Charter template, Project Plan template, Project Execution template, Texas Project Delivery Framework System Development Lifecycle Extension | Q | Important when working with multiple work units and stakeholders or with an inexperienced PM or team
[6 empty] | 0 | 0
[6 empty] | 3 | 3
Scope Mgmt | Post implementation support funding | 1 | not applicable or secured | budgeted | not discussed | 0 | 0 | high | PC - Funding Authority | C
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| Project contingency fund | 1 | not applicable or secured | budgeted | not discussed | 0 | 0 | high | PC - Funding Authority | C | Important if assumptions not well-documented or change occurs
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| Project manager authority | 1 | official authority | influential but little authority | no authority or influence | 0 | 0 | high | PC - Project Oversight Authority, PP - Roles and Responsibilities, Team Status Report template, Project Status Report template, Project Performance Report template | T | Important if working with multiple work units and unavailable team members
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| Project team roles & responsibilities | 1 | well defined & followed | not well defined or partially followed | not defined and/or not followed | 0 | 0 | high | PP - Roles and Responsibilities, Team Status Report template, PE - Communications Activity | Q
[6 empty] | 0 | 0
[6 empty] | 3 | 3
Risk Mgmt | Quality assurance approach | 1 | established, followed, and effective | not well defined or partially followed | not defined and/or not followed | 0 | 0 | high | PP - Quality Management, PE - Quality Activity | Q | Imporant when inexperienced team or high level of complexity
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| Request for Proposal | 1 | Not required | Required but not extensive | Required and extensive | 0 | 0 | high | Texas A&M University Department of Procurement Services | S | Important when timeline is dictated. Contributes to complexity
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| Rollout approach | 1 | pilot or single work group | partial | full | 0 | 0 | high | PP - Project Transition | Q | Important when working with multiple work units and a high level of complexity
[6 empty] | 0 | 0
[6 empty] | 3 | 3
Time Mgmt | Team member identification | 1 | identified | partially identified | unknown | 0 | 0 | high | PP - Roles & Responsibilities | T | Important if mandated or no delivery date
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| Team training | 1 | training plan in place, training ongoing | training for some areas not available or training planned for future | no training plan or training not readily available | 0 | 0 | high | PP - Resource Training | Q | Important if not experienced or new/unproven technology solution
[6 empty] | 0 | 0
[6 empty] | 3 | 3
| Technological solution | 1 | proven and existing | proven but new locally | not proven and new locally | 0 | 0 | high | PP - Quality Management, PE - Quality Activity | S
[6 empty] | 0 | 0
[6 empty] | 3 | 3
|  | 100 |  |  |  |  | 300
|  |  | Project Risk Score | Project Category
300
Category D Project