## Settings
HOLIDAYS |  |  | Assiagn To
No. | Date | Description | Project 1
1 | 2017-04-14 | Offical Holidays |  | John Deodeo
2 | 2017-04-20 | Offical Holidays |  | John Deo | contact@template124.com
3 | 2017-04-25 |  |  | Jenifer
4 |  |  |  | Bruce Tailor
5 |  |  |  | Jaime Sonders
6 |  |  |  | Mark
7
8
9
10
11
12
13
14
15
Next

## Gantt Chart
| Project Name | Home Renovation
| Project Leader | Jhone
| Client's Name | John Deer
| Project Start Date | 2017-04-05 |  | Enter Project Start Date
| Project End Date | 2017-07-04 |  | Enter Project End Date
| Project Length | 91
Level | Task | Assiagn To | Start Date | End Date | Call Days | % Done | # of work Days | Remaining | time axis 2017-04-05 to 2017-07-04
1 | Meeting and site survey | John Deodeo | 2017-04-05 | 2017-04-06 | 3 | 66.67% | 2 | 1 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1.2 | Meeting with John Dee | Jenifer | 2017-04-05 | 2017-04-05 | 2 | 50% | 1 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1.3 | Site Survey | John Deo | 2017-04-05 | 2017-04-06 | 3 | 66.67% | 2 | 1 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1.4 | Design and Material calculations | Jenifer | 2017-04-07 | 2017-04-15 | 6 | 83.33% | 5 | 1 | 0 | 0 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
2 | Renovation desigh-1 | Bruce Tailor | 2017-04-07 | 2017-04-09 | 2 | 50% | 1 | 1 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
2.1 | Material calculation - 1 | Bruce Tailor | 2017-04-07 | 2017-04-10 | 2 | 100% | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
2.2 | Internal Review | John Deodeo | 2017-04-09 | 2017-04-11 | 2 | 100% | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
2.3 | Renovation desigh-2 | John Deodeo | 2017-04-11 | 2017-04-13 | 3 | 100% | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 1 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
2.4 | Material calculation - 2 | Jenifer | 2017-04-11 | 2017-04-14 | 3 | 100% | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 1 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
2.5 | Proposal | John Deodeo | 2017-04-13 | 2017-04-15 | 2 | 50% | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
3 | Design and Budget Approval | Bruce Tailor | 2017-04-15 | 2017-04-19 | 3 | 100% | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
3.1 | Meeting with John Deer | Jaime Sonders | 2017-04-16 | 2017-04-17 | 1 | 100% | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
3.2 | Design Approval | John Deodeo | 2017-04-16 | 2017-04-19 | 3 | 100% | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
3.3 | Preparation | Mark | 2017-04-16 | 2017-04-30 | 12 | 66.67% | 8 | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
3.4 | Vendor Preparation | Jaime Sonders | 2017-04-18 | 2017-04-25 | 7 | 57.14% | 4 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
3.5 | Material Preparation | John Deodeo | 2017-04-18 | 2017-04-25 | 7 | 57.14% | 4 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 1 | 1 | 3 | 1 | 2 | 2 | 1 | 3 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
4 | Worker Preparation | Mark | 2017-04-20 | 2017-04-30 | 7 | 71.43% | 5 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
4.1 | Renovation | Jaime Sonders | 2017-05-01 | 2017-07-04 | 49 | 95.92% | 47 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 0 | 2 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1
Back
Next

## Dashboard
Next
Back