## Overview
CEB IT Leadership Council for Midsized Companies
Project Status Report Template
I. How and When to Use this Tool
This tool allows you to communicate the status and business value of a project to its stakeholders. In this document, you will find an example of a completed project status report and a template to guide you in building your own status reports.
II. Instructions
See the 'PMOEC Completed Report' worksheet for a sample report, and use it as a guide for filling out the 'Template' worksheet with your project's information. Throughout the template, fill in your information in the gray, thick bordered cells. To complete the Schedule portion of the template, use the 'Schedule Builder' worksheet.
Please note that the CEB program names referenced in the document have changed since the time of publication.

## PMOEC Completed Report
Completed Project Status Report
This sheet shows a completed Project Status Report for a hypothetical project. Note that the purpose clearly calls out the value the project delivers to the organization. Additionally, the report is written using clear, non-technical language.
Purpose
The purpose of this project is to build a product to make trading channels more efficient. This project will add value to the firm by improving competitive positioning and providing cost savings through increased efficiencies.
Value Delivery
Project Spend to Date | [5 empty] | Financials
Costs
[7 empty] | 2011Q3 | 2011Q4 | 2012Q1 | 2012Q2 | 2012Q3 | 2012Q4
[6 empty] | One-Time Expense | 65 | 33 | 18 | 3 | 2 | 0
[6 empty] | Recurring Expense | 5 | 15 | 15 | 12 | 10 | 10
[6 empty] | Depreciation | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | P&L Impact | 70 | 48 | 33 | 15 | 12 | 10
Project Spend to Date
[7 empty] | 2011Q3 | 2011Q4 | 2012Q1 | 2012Q2 | 2012Q3 | 2012Q4
[6 empty] | Budgeted | 50 | 36 | 10 | 29 | 41 | 43
[6 empty] | Actual Spend | 70 | 48 | 33 | 15 | 12 | 10
Cumulative Business Value Delivery
[6 empty] | Value Category | Increase Revenue | Cost Avoidance | Cost Reduction | Revenue Retention | Gain/Loss on Asset Sale | Total Benefit
[6 empty] | Original ($M) | 0 | 0 | 76 | 0 | 0 | 76
[6 empty] | Revised ($M) | 0 | 0 | 37 | 0 | 0 | 37
Stakeholder Engagement
| Building organizational support with peers and stakeholders |  |  |  | Communicating effectively with project team and stakeholders |  |  |  | Managing projects actively and visibly
Overall | Sponsor provides organization-wide perspective ('the big picture') on issues facing the project team | Sponsor modeled new, desired behaviors ('walks the talk') | Sponsor communicates expectations and responsibilities to direct reports, implementation managers, and/or change agents | Sponsor keeps communication open with the management/ leadership team with frequent project updates and status information | Sponsor communicates the importance and value of the project to all levels of the organization | Sponsor communicates cross-capability status, information, risks, and best practices to the project team | Sponsor is visible and shows support within the project team and to the organization in driving the change | Sponsor initiates informal communication events to educate and inform stakeholders on the project and on issues | Sponsor attends all required project team meetings, stage-gate reviews, and critical pull-ups | Sponsor creates 'space' for the project and is easily accessible to the project team | Sponsor is involved with team progress in order to regularly and proactively identify issues | Sponsor reviews, offers feedback, and signs off on deliverables in a timely manner
Yellow | Green | Green | Green | Green | Green | Yellow | Yellow | Green | Yellow | Green | Green | Yellow
Comments
Project Health and Performance
Project Health Overview
Overall | Value Delivery | Budget | Schedule | Issues/ Risks | Scope
Yellow | Yellow | Green | Green | Yellow | Green
Burn Rate | [7 empty] | Burn Rate
Hours
[8 empty] | Hours of Work for 2012 | 500
[8 empty] | Cumulative Work Completed to Date | Q1 | Q2 | Q3 | Q4
[9 empty] | 100 | 155 | 355 | 500
[8 empty] | Remaining Work | 400 | 345 | 145 | 0
Budget (Dollars in millions)
[8 empty] | Allotted Budget 2012 | 48
[8 empty] | Cumulative Budget Used to Date | Q1 | Q2 | Q3 | Q4
[9 empty] | 20 | 35 | 45 | 48
[8 empty] | Remaining Budget | 28 | 13 | 3 | 0
Project Performance Log
| Open | Closed | Total during Project Lifecycle
Issues | 1 | 0 | 1
Risks | 0 | 1 | 1
Change Management | 0 | 1 | 1
Risks and Issues
Issues
Date | Type of Issue | Owner | Issue Description |  |  | Resolution Steps |  |  |  | Prior Experience |  | Status
2012-08-20 | Resource Availability | PM | We were unable to obtain key project resources. We are accessing the impact of this issue on the project and will adjust accordingly. |  |  | Step 1: PM contacts Tech department to explore alternative resources. Step 2: PM evaluates Tech department proposal and determines the potential project changes it will require. |  |  |  | On previous projects, Tech lead successful solved resource shortages. |  | Resolved
Risks
Date | Type of Risk | Owner | Probability | Impact | Risk Description |  |  | Mitigation Steps |  | Prior Experience |  | Status
2012-08-18 | Technical Risk | PM | High | High | With new trade channel setup, more employees will have access to customer data. Increased customer data visibility could lead to potential security concerns. |  |  | Step 1: PM works with security officer to increase new trade channel security. Step 2: Security officer reiterates customer data policies to new system users. |  | Security officer has been willing to brief employees on security policies in the past. |  | Work in Progress
Milestones
Key Milestones | Status | Scheduled Start Date | Scheduled Completion Date |  | Actual Start Date |  | Actual Date Completed |  | Overall Objective of Milestone
System build | Completed | 2012-01-05 | 2012-03-10 |  | 2012-01-05 |  | 2012-03-10 |  | Create system that will lead to reduced costs
System security review | Completed | 2012-03-12 | 2012-03-20 |  | 2012-03-12 |  | 2012-03-20 |  | Mitigate the security risks of new system
Testing | On Track | 2012-04-02 | 2012-10-25 |  | 2012-04-02
New user orientation |  | 2012-12-01 | 2012-12-31
Change Management
Date | Change Description | Scope Impact | Budget Impact |  | Schedule Impact |  | Value Delivery Impact
2012-08-20 | Appropriate key resources were not available and substitutions had to be made. | No change in scope | Overall budget increase of 2 million |  | No change in schedule |  | Trade channels will still offer increased incremental revenues and improved competitive positioning.
Schedule
| Q1 2013 |  |  | Q2 2013 |  |  | Q3 2013 |  |  | Q3 2013
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Create system requirements | bar: Q1 2013 Jan
Design system | bar: Q1 2013 Jan to Q1 2013 Feb
Implement system | bar: Q1 2013 Mar
System security review | bar: Q1 2013 Mar
Testing preparation | bar: Q2 2013 Apr
Alpha testing | bar: Q2 2013 May to Q3 2013 Jul
Beta testing | bar: Q3 2013 Aug to Q3 2013 Oct
Draft new user manual | bar: Q3 2013 Sep to Q3 2013 Nov
Revise new user manual | bar: Q3 2013 Oct to Q3 2013 Nov
New user orientation | bar: Q3 2013 Dec
Schedule Key
Critical path task
Tasks with slack
Please note that the CEB program names referenced in the document have changed since the time of publication.
Note on B33: Overall Stakeholder Engagement should reflect the lowest score of any project element. [Delete this note before sharing]
Note on B41: Overall project health should reflect the lowest score of any project element. [Delete this note before sharing]
Note on H25: Not all of these categories will be relevant for each project. [Delete this note before sharing]

## Template
Project Status Report Template | [12 empty] | Green
Instructions: This sheet is a template for creating an effective Project Status Report. Fill in the gray, thick bordered boxes with the relevant information and the charts and remaining cells will automatically update. Based on your project, the issue and risk logs may need to be expanded, and the timeline may need to be modified. Use the 'Schedule Builder' worksheet to create the schedule portion of this sheet. | [12 empty] | Yellow
Red
Purpose
Value Delivery
Project Spend to Date | [5 empty] | Financials
Costs
[7 empty] | 2011Q3 | 2011Q4 | 2012Q1 | 2012Q2 | 2012Q3 | 2012Q4
One-Time Expense
Recurring Expense
Depreciation
[6 empty] | P&L Impact | 0 | 0 | 0 | 0 | 0 | 0
Project Spend to Date
[7 empty] | 2011Q3 | 2011Q4 | 2012Q1 | 2012Q2 | 2012Q3 | 2012Q4
Budgeted
[6 empty] | Actual Spend | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Business Value Delivery
[6 empty] | Value Category | Increase Revenue | Cost Avoidance | Cost Reduction | Revenue Retention | Gain/Loss on Asset Sale | Total Benefit
[6 empty] | Original | [5 empty] | 0
[6 empty] | Revised | [5 empty] | 0
Stakeholder Engagement
| Building organizational support with peers and stakeholders |  |  |  | Communicating effectively with project team and stakeholders |  |  |  | Managing projects actively and visibly
Overall | Sponsor provides organization-wide perspective ('the big picture') on issues facing the project team | Sponsor modeled new, desired behaviors ('walks the talk') | Sponsor communicates expectations and responsibilities to direct reports, implementation managers, and/or change agents | Sponsor keeps communication open with the management/ leadership team with frequent project updates and status information | Sponsor communicates the importance and value of the project to all levels of the organization | Sponsor communicates cross-capability status, information, risks, and best practices to the project team | Sponsor is visible and shows support within the project team and to the organization in driving the change | Sponsor initiates informal communication events to educate and inform stakeholders on the project and on issues | Sponsor attends all required project team meetings, stage-gate reviews, and critical pull-ups | Sponsor creates 'space' for the project and is easily accessible to the project team | Sponsor is involved with team progress in order to regularly and proactively identify issues | Sponsor reviews, offers feedback, and signs off on deliverables in a timely manner
Green
Comments
Project Health and Performance
Project Health Overview
Overall | Value Delivery | Budget | Schedule | Issues/ Risks | Scope
Green
Burn Rate | [7 empty] | Burn Rate
Hours
Hours of Work for 2012
[9 empty] | Q1 | Q2 | Q3 | Q4
Cumulative Work Completed to Date
[8 empty] | Remaining Work | 0 | 0 | 0 | 0
Budget (Dollars in millions)
Allotted Budget 2012
[9 empty] | Q1 | Q2 | Q3 | Q4
Cumulative Budget Used to Date
[8 empty] | Remaining Budget | 0 | 0 | 0 | 0
Project Performance Log
| Open | Closed | Total during Project Lifecycle
Issues |  |  | 0
Risks |  |  | 0
Change Management |  |  | 0
Risks and Issues
Issues
Date | Type of Issue | Owner | Issue Description |  |  | Resolution Steps |  |  |  | Prior Experience |  | Status
Risks
Date | Type of Risk | Owner | Probability | Impact | Risk Description |  |  | Mitigation Steps |  | Prior Experience |  | Status
Milestones
Key Milestones | Status | Scheduled Start Date | Scheduled Completion Date |  | Actual Start Date |  | Actual Date Completed | Overall Objective of Milestone
Change Management
Date | Change Description | Scope Impact | Budget Impact |  | Schedule Impact |  |  | Value Delivery Impact
Schedule
|  | Q1 2013 |  |  | Q2 2013 |  |  | Q3 2013 |  |  | Q4 2013
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Schedule Key
Critical path task
Tasks with slack
Please note that the CEB program names referenced in the document have changed since the time of publication.
Note on B83: Use the Schedule Builder on the next sheet for this section. [Delete this note before sharing]

## Schedule Builder
Schedule Builder
Instructions: This sheet contains a form for creating the schedule for the Project Status Report. To complete the form, fill in the name of the task, check whether it is on the critical path, and check off the months during which your team will perform the task. You can also change the start month and quarter for the project by editing the text in the Quarter and Month rows. The schedule portion of the Project Status Report template will automatically update.
|  |  | Q1 2013 |  |  | Q2 2013 |  |  | Q3 2013 |  |  | Q4 2013
Task Name | Critical Path Task? | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Please note that the CEB program names referenced in the document have changed since the time of publication.

## Sheet2 (hidden)
Critical Path | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Project Health Overview (hidden)
Project Health Overview
Overall | Value Delivery | Budget | Schedule | Issues/ Risks | Scope
| 3 | 3 | 3 | 3 | 3
Stakeholder Engagement
Overall | Sponsor provides organization-wide perspective ('the big picture') on issues facing the project team | Sponsor modeled new, desired behaviors ('walks the talk') | Sponsor communicates expectations and responsibilities to direct reports, implementation managers, and/or change agents | Sponsor keeps communication open with the management/leadership team with frequent project updates and status information | Sponsor communicates the importance and value of the project to all levels of the organization | Sponsor communicates cross-capability status, information, risks, and best practices to the project team | Sponsor is visible and shows support within the project team and to the organization in driving the change | Sponsor initiates informal communication events to educate and inform stakeholders on the project and on issues | Sponsor attends all required project team meetings, stage-gate reviews, and critical pull-ups | Sponsor creates 'space' for the project and is easily accessible to the project team | Sponsor is involved with team progress in order to regularly and proactively identify issues | Sponsor reviews, offers feedback, and signs off on deliverables in a timely manner
| 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3