## Sheet1
| SH16 Causeway Alliance : Concrete Barrier Requirements - Slipform & Precast: Verges and Ramps only. | [7 empty] | Date Sequenced | [15 empty] | Rev 8 Status as of 30th Jan 15 |  |  |  | Green represents spill through's required.
[6 empty] | Barriers supplied by - |  | Site | Site | Site | Site | Wilco |  | Wilco |  | Wilco |  |  | Wilco | Wilco | Wilco | Wilco |  | Wilco | Site | Site
[8 empty] | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T
Item | Sheet | Area | Activity | Date | Start Ch. | End Ch. | Slipform | NTC (TL5) | NTC (TL5) | NTC (TL4) | NTC (TL4) | TL5 (Type D) | TL5 (Type E) | TL4 (Type B) | TL4 (Type C) | 4T5 | 4T5 | 5T4 | 5T4 | TL4 End Bl. | TL4 End Bl. | TL5 End Bl. | TL5 End Bl. | CTN (TL5) | CTN (TL5) | CTN (TL4) | CTN (TL4) | Description
[12 empty] | Barrier | Barrier | Barrier | Barrier | Transistion | Transistion | Transistion | Transistion | Departure | Departure | Departure | Departure
| No |  |  | Required |  |  | or PCC | (LHS) | (RHS) | (LHS) | (RHS) | (6 M long) | (6 M long) | (6 M long) | (6 M long) | (LHS) | (RHS) | (LHS) | (RHS) | (LHS) | (RHS) | (LHS) | (RHS) | (LHS) | (RHS) | (LHS) | (RHS)
29 | Sheet 6 | West | A20551 | 2015-01-30 | 3328 | 3416 | Pre cast | C: 1; G: 12; S: 1 | E/B SH16 LHS verge @ RW4
39 | Sheet 1 | West | A5990 | 2015-02-03 | 4888 | 4912 | Pre cast | A: 1; E: 3 | E/B Whau bridge approach. LHS verge.
6 | Sheet 14 | Area 8 | WB2400 | 2015-02-14 | 82 | 220 | Pre cast | B: 1; E: 12; G: 10; L: 1 | W/B on ramp. RHS Gantry P21
8 | Sheet 14 | Area 8 | WB2620 | 2015-02-16 | 364 | 524 | Pre cast | C: 1; G: 23; M: 1 | W/B SH16 LHS verge
| GNRI | Area 2 | A2053 | 2015-02-19
10 | Sheet 13 | Area 2 | A2053 | 2015-02-19 | 607 | 623 | Pre cast | [20 empty] | W/B on ramp. RHS noise wall approach | bar: A
5 | Sheet 15 | Area 8 | WB2430 | 2015-02-24 | 334 | 368 | Pre cast | B: 1; E: 2; R: 1 | W/B on ramp. RHS WCA pier protection
34 | Sheet 4 | West | A3450 | 2015-02-25 | 4014 | 4180 | NTC, TL4 & 4T5 trans pre-cast. Rest slip f? Space? | C: 1; G: 3; I: 1 | W/B SH16 LHS verge. Continous on sheet 3
35 | Sheet 3 | West | A3450 | 2015-02-25 | 4180 | 4426 | TL5 slip form. Working space? CTN pre-cast? | [20 empty] | W/B SH16 LHS verge. Continous on sheet 4 | bar: Q
32A | Sheet 5 | West | A3040 | 2015-02-27 | 95 | 92 | The off structure CTN barrier by CA. | [20 empty] | W/B Patiki on ramp. RHS verge
Wilco
11 | Sheet 12 | Z1 | A42460 | 2015-03-27 | 1275 | 1281 | 1st off structure CTN by CA | [20 empty] | W/B Causeway bridge departure. LHS
7 | Sheet 14 | Area 2 | A2083 | 2015-05-06 | 40 | 82 | Pre cast | G: 6; N: 1 | W/B on ramp. RHS.
4 | Sheet 16 | Area 10C | A5370 | 2015-05-12 | 441 | 499 | Pre cast | A: 1; E: 7; Q: 1 | W/B on ramp. LHS WCA pier protection. |  |  | With spill through
9 | Sheet 13 | Area 5 | A43290 | 2015-05-25 | 547 | 575 | Pre cast | B: 1; E: 2; R: 1 | E/B off ramp. RHS Gantry P18. |  |  | With spill through
30 | Sheet 5 | West | A42990 | 2015-05-26 | 3500 | 3775 | TL4, 4T5 transition & TL5 slip form? Space? | [20 empty] | W/B SH16 LHS verge. Rosebank. Continious on sheet 6 & 7
37 | Sheet 2 | West | A4220? | Jun 15? | 4665 | 4707 | 1st off structure one by CA, rest pre-cast | A: 1; E: 3 | W/B Whau bridge approach. LHS. Revised date needed?
12 | Sheet 12 | Z1 | ? | 2015-08-27 | 183 | 217 | Pre cast | A: 1; E: 2; Q: 1 | E/B off ramp. LHS Gantry P8 |  |  | With spill through
13 | Sheet 12 | Z1 | A42800 | 2015-08-27 | 1189 | 1195 | 1st off strucure CTN by CA | [20 empty] | E/B Causeway bridge depatrure. LHS
17 | Sheet 11 | Z1 | A42820 | 2015-09-03 | 1578 | 1618 | Pre cast | A: 1; E: 3; Q: 1 | E/B Causeway. LHS Gantry P7. |  |  | With spill through
18 | Sheet 10 | Z1 | A42820 | 2015-09-03 | 1833 | 1867 | Pre cast | A: 1; E: 2; Q: 1 | E/B Causeway. LHS road sign. |  |  | With spill through
38 | Sheet 2/1 | West | A3950? | 2015-09-04 | 4894 | 4954 | 1st off structure one by CA, rest pre-cast | G: 8; M: 1 | W/B Whau bridge departure. LHS. Beware, angled section! Revised date needed?
31 | Sheet 5 | West | A3040 | 2015-09-11 | 122 | 140 | 1st off structure one by CA, rest pre-cast | C: 1; G: 2 | W/B Patiki on ramp. LHS verge
31A | Sheet 5 | West | A3040 | 2015-09-11 | 44 | 98 | 1st off structure one by CA, rest pre-cast | G: 8; S: 1 | W/B Patiki on ramp. LHS verge
32 | Sheet 5 | West | A3040 | 2015-09-11 | 124 | 140 | 1st off structure one by CA, rest pre-cast | D: 1; G: 2 | W/B Patiki on ramp. RHS verge
26 | Sheet 7 | West | A43380 | 2015-09-11 | 3049 | 3120 | Slip form ? Working space? | [20 empty] | W/B SH16 LHS verge. Continues on sheet 6
28 | Sheet 6 | West | A43880 | 2015-09-11 | 3120 | 3500 | 4T5 tansition & TL4 & TL5 all slipform? | [20 empty] | W/B SH16 LHS verge. Continues on sheets 5 & 7
20 | Sheet 9 | Z1 | A42790 | 2015-09-18 | 2075 | 2109 | Pre cast | A: 1; E: 2; Q: 1 | W/B Causeway. LHS Gantry P6. |  | Revised date needed | With spill through
19 | Sheet 9 | Z1 | A42760 | 2015-09-28 | 2230 | 2264 | Pre cast | A: 1; E: 2; Q: 1 | W/B Causeway. LHS Gantry P1. |  |  | With spill through
21 | Sheet 8 | Z1 | A42760 | 2015-09-28 | 2424 | 2448 | Pre cast | G: 2; N: 1; S: 1 | W/B Causeway. LHS SH16 |  | Revised date needed
22 | Sheet 8 | Z1 | A42760 | 2015-09-28 | 2424 |  | Slip form or pre-cast. Settlement?? | [20 empty] | W/B Rosebank off ramp. RHS. RFI 404 says Precast only. Slip form! Revised dates?
23 | Sheet 8 | Z1 | A42760 | 2015-09-28 | 2658 | 2772 | Slip form or pre-cast. Settlement?? | [20 empty] | W/B Rosebank off ramp. RHS. RFI 404 says Precast only. Slip form! Revised dates?
23A | Sheet 8 | Z1 | A42760 | 2015-09-28 | 2425 | 2465 | Pre cast | A: 1; E: 3; O: 1 | E/B Rosebank on ramp. LHS. New pull in area. Revised date needed?
24 | Sheet 7 | Z1 | A42770 | 2015-09-30 | 2772 | 2820 | Slip form or pre-cast. Settlement?? | [20 empty] | W/B Rosebank off ramp. RHS. RFI 404 says Precast only. Slip form! Revised dates?
25 | Sheet 7 | Z1 | A42780 | 2015-10-01 | 2949 | 3049 | NTC pre cast, TL5 slip form? Working space? | [20 empty] | W/B SH16 LHS verge | bar: A
27 | Sheet 7 | Z1 | A42780 | 2015-10-01 | 2938 | 3062 | NTC & CTN pre-cast. TL5 slip form? | [20 empty] | E/B SH16 LHS verge. Beware of headroom if CTN is pre-cast: lifting? | bar: A; Q
14 | Sheet 12 | Z1 | A42810 | 2015-10-07 | 1277 | 1334 | 1st off structure by CA, rest pre-cast | G: 8; I: 1 | E/B Causeway bridge approach. LHS. Slip? |  |  | With spill through
16 | Sheet 11 | Z1 | A42810 | 2015-10-07 | 1334 | 1368 | Pre cast | A: 1; E: 2; Q: 1 | E/B Causeway. LHS Gantry P17. |  |  | With spill through
33 | Sheet 5 | West | A20911 | Jan 16? | 3740 | 3832 | Pre cast | A: 1; E: 15; O: 1 | E/B SH16 at Patiki. LHS verge. Headroom? Revised date? |  |  | With spill through
1 | Sheet 16 | Area 10E | A42320 | 2016-05-03 | 593 | 620 | Pre cast | B: 1; E: 2; R: 1 | E/B on ramp. RHS Gantry P20
36 | Sheet 3 | West | ? | Jun 16? | 4390 | 4412 | Pre cast | [20 empty] | E/B SH16 CCTV access way. Revised date needed? | bar: C; M
15 | Sheet 11 | Z1 | A42750 | 2016-06-15 | 1619 | 1653 | Pre cast | A: 1; E: 2; Q: 1 | W/B Causeway. LHS Gantry P10. |  | Revised date needed | With spill through
2 | Sheet 16 | Area 10F | A42330 | 2016-06-13 | 590 | 620 | Pre cast | A: 1; E: 2; Q: 1 | E/B on ramp. LHS Gantry P20
3 | Sheet 16 | Area 10F | A42330 | 2016-06-13 | 702 | 730 | Pre cast | [20 empty] | E/B on ramp. LHS Maintenance access. |  |  | With spill through | bar: C; G; M
| Sheet 2 | West |  |  | 4691 | 4900 | [21 empty] | E/B Whau bridge. Already procured
[5 empty] | Summation |  |  | 16 | 4 | 6 | 1 | 66 | 0 | 85 | 0 | 2 | 0 | 0 | 1 | 4 | 2 | 2 | 0 | 11 | 3 | 3 | 0