## Instructions
Definition:
This template can be used throught the project life. From Origination to Execution
In the Origination Phase the PM can use it to get an order of magnitute need for resources.
In the Initiation phase you can use the template to work with putting assigned resources to the phases of the plan and percentage of utilization.
In the other phases of the project you can use it to do "WHAT IF" scenerios when looking at new or changed resources prior to changing the Microsoft Project.
Usage:
Origination:
When starting the template you can put generic resources in the spreadsheet. i.e. Developer,tester,Project Mananger. The rate
for US resources is $65.00. Also, you can put any other hardware costs and consulting costs as best as you know them.
In the origination phase you should not really have to worry about when the resources will be within the phases of the plan or if they will be used more in April then June.
Initiation:
Go ahead and put names to the generic resources and work with percentages of hours needed.
Add any consultants in the template with the hourly costs as best the PM know it.
Hardware and Software Costs can now be further defined.
Execution:
As you need to make changes to your resources, whether hardware,software,or human resources
you can do "What if" scenerios and put the resources hours where you believe the resource is needed. This will help to start your change requests prior to putting the
changes in Microsoft Project.

## Schedule
Resource Planning Worksheet | [12 empty] | You May Enter Data in the light blue shaded areas .
Program Services | [12 empty] | Also, you may format the bars for the phase start and end dates.
Project Delivery Model | [5 empty] | Start Date | Jul | Aug | Sep | Oct | Nov | Dec | Phase End | Jul-2011 | Aug-2011 | Sep-2011 | Oct-2011 | Nov-2011 | Dec-2011 | Jan-2012y | Feb-2012 | Mar-2012 | Apr-2012 | May-2012 | Jun-2012 | Jul-2012 | Aug-2012 | Sep-2012 | Oct-2012 | Nov-2012 | Dec-2012 | Jan-2013 | Feb-2013 | Mar-2013 | Apr-2013 | May-2013
Project Solution Delivery Summary: |  |  |  |  | Project | 2011-07-01
Project Definition
Project Analysis/Requirements
Project Design
Project Development/Build
Project Testing
Project Deployment
Resource Requirements | [6 empty] | Jul: FY 2007
Organizational Area | Role | QTY | Rate | % | Name | Requested Start Date | Jul* | Aug | Sep* | Oct | Nov* | Dec* | Projected End date | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Total | Total Cost Allocated
[6 empty] | Days/Month | 20 | 20 | 23 | 20 | 22 | 22 |  | 21 | 23 | 22 | 21 | 22 | 22 | 22 | 21 | 22 | 21 | 23 | 21 | 22 | 23 | 20 | 23 | 22 | 21 | 23 | 20 | 21 | 22 | 23
FTE STAFFING (EMPLOYEES)
[6 empty] | Sub Total: | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INCREMENTAL STAFFING (CONSULTANTS)
SubTotal: | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S/W, H/W, SUPPORT, EQUIPMENT AND OTHER EXPENSES
0
0
0
SubTotal: | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
TOTAL PROJECT HOURS: | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | TOTAL HARDWARE AND SOFTWARE COST: | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | MANAGEMENT RESERVE @ : | 10% | 0% | [30 empty] | 0
TOTAL PROJECT COST: | [37 empty] | 0
Assumes full time to equal 40 hours/week of productive effort