## SRMM
ACTION PLAN FOR COMMUNICATION AND MEDIA REGULATION 2013-2014
ACTION PLAN FOR \ICT SRMM 2013-2014
Goal 1: Develop an Efficient, Effective and Productive Corporate Entity
Objective | Program | Output | Baseline | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Proposed Budget review | Source of Fund | Comments
Foster Regional / International cooperation and enhance Rwanda visibility to International regulatory bodies. | Conduct a proper preparation to the WRC-15 as EACO Coordinator and as a country | Harmonized country and Regionall position towards the preparation of RWC-15 | The work started in 2012 and will end in 2015 | Preparation meetings conducted at the country level (NPC meetings) | Every Quarter | Preliminary country position reported & progress report of consultation meetings available | Director, Planning officer | 3200000 | 3200000 | RURA
|  |  |  | Participate in the preparation meeting at the EACO level, and provide and support our position depending on the outcome of agreement made at the country level | As the invitation comes |  | Planning and Monitoring officer | 4384000 | 0 | RURA | This amount was re-allocated to other activities because all EACO Meetings are supposed to be held at EACO HQ, KIGALI
|  |  |  | Conduct meetings of WRC 15 Preparatory EACO Task Force | Q2 and Q4 | Meeting conducted | Director, Planning officer | 5560000 | 0 | RURA
| Participate /Organize other International Organization meetings (ITU, ATU, EACO …) Frequency and numbering related activities | RURA visibility is enhanced | Continuous task | Participate in ITU meetings | As per the ITU Study group participation plan | Contributions submited and presented to ITU meetings | All Concerned staffs | 20000000 | 49982000 | RURA | The amount allocated for EACO Meetings and one capacity building program were added to ITU Events
|  |  |  | Participate in ATU meetings on frequency related issues | As the invitation comes | Meeting partipated and the meeting report availed | Planning Officer and Monitoring Officer | 9990000 | 9990000 | RURA
|  |  |  | Participate in EACO Task forces of Numbering and BTTF | As the invitation comes | Report of the meetings presented | Numbering Officer | 6048000 | 0 | RURA | This amount was re-allocated to other activities because all EACO Meetings are supposed to be held at EACO HQ, KIGALI
|  |  |  | Conduct meeting of EACO BTTF | Q2 & Q4 | Meeting conducted | Director | 5560000 | 0 | RURA
|  |  |  | Attend Spectrum related International forums | As the invitation comes | Meetings attended and report submitted | Concerned Staff | 5925000 | 5925000 | RURA
|  |  |  | In house training in analysing DVB-T Signal and Quality of services | Q1 | Staffs trained in DVB-T spectrum monitoring and QoS | All Staff | 11471250 | 11471250 | RURA
[6 empty] | SubTotal per Goal |  | 80568250 | 80568250
Goal 2: Create, Strengthen and enforce the legal and regulatory framework
Objective | Program | Output | Baseline | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) |  | Source of Fund
Participate actively in the formulation of the sector policies and Laws; | Development of the Frequency Spectrun Policy | Policy Directives given to the Frequency utilization | The first draft is available | Conduct consultation with Stakeholders | Q2 | The final draft document with incorporated inputs and comments from stakeholders |  | 900000 | 900000 | RURA
|  |  |  | Submit the document to the Ministry for promulgation | Q2 | The final document approved and gazetted |  | N/A | 0 | N/A
Put in place or review regulations and guidelines in the utility sectors where required | Develop the regulation for the human protection from harmful Electromagnetic Field (EMF) radiation | The general public is protected against harmful EMF radiation | From scratch | Develop the first draft of the regulation | Q2 | draft document ready from ICT SRMM | Monitoring Officer, Director | N/A | 0 | N/A
|  |  |  | send the document to the Legal department for legal input | Q2 | The draft with incorporated inputs and comments from legal | Director | N/A | 0 | N/A
|  |  |  | Conduct a consultation meeting with stakeholders | Q3 | The final draft available with inputs from consultation meetings | Director | 900000 | 900000 | RURA
|  |  |  | Finalize the document and submission of the same to the Regulatory Board for approval | Q3 | All utility regulations are gazette or progressively reported for. | Director | N/A | 0 | N/A
| Develop the regulation for the Licensing of Satellite services in Rwanda | Clear framework for Satellite services in Rwanda | The first draft already developed | Work with LLE Unit to finalize the draft on Satellite Terrestrial Station regulations | Q1 | The final draft version available | Planning, License Officers | N/A | 0 | N/A
|  |  |  | Conduct consultation with Stakeholders | Q1 | The final draft version available with incorporated comments from consultation meetings | Directors, Planning and Licensing Offier | N/A (Consultation to be conducted on line) | 0 | N/A
|  |  | The first draft already developed | Work on the final version of the regulations and Submission of the document to the Regulatory Board for approval | Q2 | the final version approved by the board | Director, Planning and Licensing officer | N/A | 0 | N/A
|  |  |  | Finalize the draft on Licensing framework on VSAT ISP together with the LLE Unit | Q2 |  | Director, Planning and Licensing officer |  | 0
|  |  |  | Circulate the draft to stakeholders for input and validation |  |  | Director, Planning and Licensing officer |  | 0
|  |  |  | Submit the draft for Regulatory Board approval |  |  | Director, Planning and Licensing officer |  | 0
| Revise the board decision introducing short code fees and determinin short code allocation procedure | The short code allocation procedures are revised in line with Stakeholders views | The revision will be based on the procedures in force. | Preparation of the fisrt draft of the reviewd board decision | Q1 | first draft available and submitted to cross cutting departments | Numbering Officer | N/A | 0 | N/A
|  |  |  | share the first draft with other concerned directorate (legal, consumer and economic) for their inputs and comments | Q1 | the final draft available | Director and numbering Officer |  | 0
|  |  |  | Praparation of the final version and submit to the board fro approval | Q2 | the final version approved by the board | Director and numbering Officer |  | 0
| Develop regulation and licensing framework for mobile content providers | The mobile content are provided based on clear framework | the first draft available | share the draft documents to other concerned departments (Consumer, standars and QoS, media and Postal, Legal unit) | Q2 | The final draft version available | Numbering Officer | N/A | 0 | N/A
|  |  |  | preparation of the final draft version and submit to the regulatory board for approval | Q3 | the final version approved by the board | Director and numbering Officer |  | 0
Set up and implement an appropriate and proactive enforcement mechanism for compliance with Laws, regulations and license obligations | Regular inspection and monitoring of radiocommunication transmiters | License obligation in terms of Frequency utilization enforced | On going activity | Conduct a monitoring and inspection of all FM Broadcasting and Digital TV Stations | Q1 & Q2 | Report of the inspection available and recommendation for enforcement sent to the Legal Unit | Monitoring Officers, | 3864000 | 3864000 | RURA
|  |  |  | Enforce the compliance with Broadcasting on FM Stations | Q2 and Q3 | Enforcement letter is sent to the defaulters | Monitoring and Director | N/A | 0 | N/A
|  |  |  | Conduct a Frequency analysis of all Fixed Wireless Access and Intermational Mobile Telecommunication (IMT) of ISP and Telecom Network | Q3 & Q4 | Report of the inspection available and recommendation for enforcement sent to the Legal Unit | Monitoring and Director | 2070000 | 2070000 | RURA
| Strenghten RURA Spectrum Monitoring and Mnagement capability | Capability to monitor the delivery of Digital Television in accordance with International best practice | Tender document already prepared | Purchase of DVB-T2 TV analyzer | Q1 | DVB-T2 TV analyzer available | Director and numbering OfficerS | 80000000 | 80000000 | RURA
|  | Proper operation of Spectrum Monitoring Stations | On going activity | Operation and maintenance of spectrum monitoring stations - Rutsiro station - Munini Station - Kayonza station - Miyove station - Mont Kigali Station - Transportable station - Mobile stations | every month for each fixed and transportable station Every week for the mobile station | SMMS sites and tools well maintained and operating properly | Monitoring Officers | 2340000 | 2340000 | RURA
|  |  |  | Finalize the electrification of the SMMS sites | Q2 | All sites connected to the Electricity grid | Monitoring Officers | 110000000 | 110000000 | RURA
|  |  | New activity | Enter into an agreement with TCI for the maintenance of the SMMS | Q3 | Maintenance contract available | Monitoring Officers | 65000000 | 65000000 | RURA
|  | Enforcement of Law on illegal frequency usage |  | Identification of illegal spectrum usage and submit to LLE unit for enforcement -VHF/UHF spectrum band -GSM spectrum band -Unlicensed spectrum band | Q1, Q2 Q3 | Illegal spectrum use reported to LLE Unit | Monitoring Officers | N/A | 0 | N/A
|  | Proper operation of ASMS | On going activity | Operation and maintenance of Automated Spectrum Management System (ASMS) and its database | every month | ASMS operating properly | Monitoring Officers | N/A | 0 | N/A
|  | Reduced cost of Infrastructure sharing | From scratch | Find and alternative links to replace SMMS microwave links, using either VSAT or Fiber | Q1 | microwave network optimized, and the cost minimized at the lowest possible level | Monitoring Officers | 460000 | 460000 | RURA
| Establish Satellite communication management activities in the Unit | Improve capacity to handle Satellite coordination and management issues | New activity | Conduct a research on satellite coordination issues and propose the best way of responding to the incoming satellite coordinations | Q1 & Q2 | Satellite communication regulation understood | Planning Officer |  | 0
[6 empty] | SubTotal per Goal |  | 240534000 | 265534000
GOAL 4: Promote easy market entry, fair competition and support a market driven industry in the regulated utilities.
Objective | Program | Output | Baseline | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) |  | Source of Fund
Conduct regular market analysis to identify and reduce barriers to entry in a view to balance supply and demand in the regulated sectors. | Development of CBA for Mobile Number Portability | Decision to implement MNP or to use altenative strategy to stimulate competition in the mobile market | The tender process for the consultant is in on going | Assist the consultants in accessing all required data and reference documents needed for the successful outcome of the study | Q2 | Data and required documents availed to the consulting team | Director and Numbering Officer | 100000000 | 100000000 | RCIP
|  |  |  | Prepare and organize meeting with stakeholders whenever required | Q3 | Meetings prepared and conducted | Director and Numbering Officer | 900000 | 900000 | RURA
|  |  |  | Review and anayse different reports done by the consultant | Q3 | Final report of the study available | Director and Numbering Officer | N/A | 0 | N/A
|  |  |  | Conduct benchmarking and study tours to places where MNP has been implemented | Q2 | Benchmark conducted on MNP and report submitted | Director and Numbering Officer | 12768000 | 12768000 | RURA
[6 empty] | SubTotal per Goal |  | 113668000 | 113668000
GOAL 5: Ensure efficient and effective allocation of resources, safety and reliability of utilities services
Objective | Program | Output | Baseline | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) |  | Source of Fund
Develop and enforce operational service delivery standards and quality of service parameters in line with Internationally recognized norms for all regulated services | Maintain a reliable and secure usage of frequency | Coverage prediction of each broadcasting site to help broadcasters plan their network | Contunous task | Calculation and publication of the estimated radio&TV coverage of each broadcasting site. | Once per year | Coverage simulation done | Monitoring and Planning Officers | N/A | 0 | N/A
|  | Ensuring that the public is protected against harmful EMF Radiation |  | Measurement of human exposure to electromagnetic radiations | Q2 and Q4 | Complaints are effectively addressed and appropriate responses given Increased consumer confidence in the Authority | Monitoring Officers | 658000 | 658000 | RURA
|  | frequency and telecom numbers notification |  | Notification of new radio stations and TV stations, notification of existing unnotified stations, and notification of new, amended and non-notified numbering resources | Q2 | Resources in use published on the ITU website | Numbering Officer | 0 | 0 | N/A
|  | Frequency is used in an interference free environment |  | Assessing and solving reported interferences | Handled as received | Report of all solved interferences | Monitorign Officers | 376000 | 376000 | RURA
Put in place a mechanism to continually assess and follow the trend of the technology and accordingly set up a structure to adjust national scarce Resources plan for their use, management, planning and monitoring. | Assess the usage of the frequency to ensuring the efficient usage of the Frequency Spectrum | List of vacated frequencies | On going activity | Inspection of licensees with revoked license in order to ensure that the spectrum is no longer in use |  | Standards and quality of services disseminated and enforced | Monitoing and Licensing Officers | 920000 | 920000 | N/A
|  | Creation of an interference-free environment between Rwanda and neighboring countries |  | Handling incoming coordination requests from neighboring country and submit coordination requests to concerned administration when needed | Handled as received | Coordination requests done | Monitoring and Planning Officers | 0 | 0
|  | Free assignable frequencies identified for new applicants in line with International best practices |  | Identification of unused spectrum to help the planning and assignment section | Every 4 months | Free frequencies availed to potential operators | Monitoring and Licensing officers | 1380000 | 1380000 | RURA
|  | Proper and predictable utilization of frequency | New activity | Develop proper Band arrangement for all services (Fixed, Mobile, Radiolocation etc) based on ITU Recommendation | Q3 | Proper band available | Plannign officer | 0 | 0
| Audit of the Spectrum utilization in Rwanda to establish where possible frequency bands to refarm | The efficiency of the frequency is established | Start from Scratch | Conduct an audit of the frequency band is all the services Fixed Servces, Mobile services, Aeronautic, Radiolocation, Fixed satellites etc | Q2 | survey report available | Monitoring, Planning and Licensing officers | 1380000 | 1380000 | RURA
|  |  |  | Develop, based on the result of audit, develop recommendation for refarming | Q3 | Recommendation available | Monitoring, Planning and Licensing officers | 0 | 0
|  |  |  | Conduct consultations with stakeholders on the refarming recommendation | Q3 | Consultation meeting available | Monitoring, Planning and Licensing officers |  | 0
|  |  |  | Submit to report of the Spectrum Audit | Q4 | Report submitted | Monitoring, Planning and Licensing officers | 0 | 0
To set up mechanisms to foster the deployment of Broadband last mile connectivity | To develop a proper plan that allows frequency for the last mile connectivity | A proper frequency plan for immerging technologies | From scratch | Adopt the best channelization plan for the Digital Dividend frequency (700 and 800 MHz) | Q4 | Spectrum management strategy paper developed& new channelization plan available | Planning officer | 0 | 0 | RURA
|  | Proper utilization of the Unlicensed band | First draft obtained | Adopt the regulation for the usage of frequency in the Unlicensed (ISM) band and other | Q1 | Regulation adopted and in force | Monitoring and Planning Officers | 0 | 0 | RURA
[6 empty] | SubTotal per Goal |  | 4714000 | 4714000
Goal 6: Contribute to the national long term development by promoting the availability, accessibility and affordability of regulated services to all consumers including low income, rural and disadvantaged consumers
Objective | Program | Output | Baseline | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) |  | Source of Fund
To promote and support the development and deployment of appropriate technologies, services & content ensuring non-discrimination especially for people with disabilities | Promote self-training on Radiocommuniction in the Country | Amateur Radio Union established | Activity stated in 2011 | To get equipment for operations | Q1 | Radio Amateur constitution approved, Office established | Director and Monitoring officer | 15000000 | 15000000 | RURA
|  |  |  | To convene general assembly for radio amateur | Q2 | The ordinary general assembly held | Director and Monitoring officer
|  |  |  | Assist the amateur Radio union to start up the operations(including to get the statut, bureau) | Q2 | Equipment available | Director and Monitoring officer
[6 empty] | SubTotal per Goal |  | 471054250
GRAND TOTAL
1600670950
MEDIA AND POSTAL AFFAIRS
GOAL 7: Ensure a sustainable development of the Media sector that reflect a sense of Rwanda’s identity, character, cultural diversity and expression of content
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Proposed Budget review | Source of Fund
Establish mechanisms for Broadcasting Media monitoring and ensure storage of broadcast contents for any further use and analysis. | Put in place Broadcasting content monitoring mecanisms. | Technical Specification for media monitoring equipment and Plasma TV Developed | Compliance of TV and Radio programs with the laws and regulations. | 1.1. Drafting tender document | Q1 | Draft of the tender submitted to procurement office | Media Monitoring Team | 150000000 | 225000000 | RURA | The financial offer of Successful bidder was above the amount allocated to this tender, therefore there is a need of increase the amount from 150,000,000 RWF to 225,000,000 RWF
|  |  |  | 1.2. Training, Installation and commissioning of Media monitoring equipment | Q2 | Operational media monitoring equipment | MPA Director and Media Monitoring Team
|  |  |  | 1.3. Install Plasma TV set in MPA unit office with all subscription arrangements for real time Monitoring TV programs | Q1 | Operational plasma screens and decoders operational | Media Monitoring Team. | 4000000 | 4000000 | RURA
|  |  |  | 1.4. Broadcasting Media Monitoring, Analysis and reporting | Q2, Q3 & Q4 | Monitoring reports available | Media Monitoring Team. | 0 | 0 | RURA
Supporting and encourage the local content creation with the aim of having sufficient local production and encourage investment of local content production. | Support and promote local content production for audio and audio visual media | Theres't any initiative for supporting content production in place | More innovation, entrepreneurship and competitiveness in local content creation | 1.1. Identify local content producers | Q1 | Collected data available | Media Monitoring Team. | 0 | 0 | RURA | After assessment, the amount was reduced from 10,000,00 RWF to 1,000,000 RWF
|  |  |  | 1.2. Organise meetings and set modalities of promoting local content | Q1, Q2 | Modalities for promoting local content available | Media Monitoring Team. | 0 | 0
|  |  |  | 1.3. Arrange regular meetings with local content producers to discuss about challenges and progress. | Q1, Q2 | Meeting Report available | Media and postal Unit | 10000000 | 1000000
|  |  |  | 1.4 Conduct field visits to premises of local content producers and discuss possible support | Q2 & Q4 | Possible support identified | Media and postal Unit | 0 | 0
Put in place and support a framework of cooperation between Self Regulatory Body and RURA | Provide technical support to Self Regulatory Body and work together in handling audio, audio-visual and internet media related matters | Internal discussions on MOU was done | Joint Mechanisms to regulate media sector | 1.1.Organise consultation meetings Self regulatory Body | Q1 | Reports available | Media and Postal | 1000000 | 1000000 | RURA
|  |  |  | 1.2 Organise a joint retreat for drafting MoU | Q1 | Draft of the MoU available
|  |  |  | 1.3 Approval and Signature of the MoU | Q2 | MoU Signed
Develop and enforce the regulatory framework for media sector in line with the Media Reform in the country | Develop regulatory framework governing broadcasting services in Rwanda and enforce related international standards | Regulations drafted and internal consulataion done | Clear guidance for licensing procedures and compliance with law in broadcasting sector | 1.1. Conduct external consultation and with stakeholders | Q1 | Inputs and comments from stakeholders are available | Comm and Media and CLIA departments | 535000 | 535000 | RURA
|  |  |  | 1.2. Finalize the regulations, approval and publication | Q1 | Regulations are approved and published | Comm and Media Dept.
|  |  |  | 1.3. Draft the licensing template | Q1 | License template available
|  |  |  | 1.4. Analyse, process license applications and issue licenses for providing Broadcasting services licenses | Q1 | Licenses issued | Comm and Media Dept.
|  |  |  | 1.5. Acquire metal cupboard for rod folders to keep license applications documents | Q1 | Metal cabinet purchased | MPA UNIT | 1000000 | 3000000 | RURA | After assessment, we found the allocated amount is not enough for a cupboard which will support print media permits and other kind of licences, therefore we are requesting two (2) million extra budget
| Develop regulations governing subscription satellite television services |  | Licencing framework for providing satellite TV services in place | Develop regulations and conduct required consultations with stakeholders | Q1, Q2 | Regulations and Licenses approved by the Board,Procedures and requirements for providing sateelites TV services published on RURA website | Comm and Media and CLIA departments | 0 | 0 | RURA
| Develop Prime Minister order determining specific mission of RURA in regard to media | Draft was sent to PMO | Clear functions of RURA in media regulation | 1.1. Participate in the consultation on PM order on specific function of RURA in Media | Q1 | PM order submitted for approval | Comm and Media Dept. | 0 | 0
| Provide regulatory advice to broadcasting policy making process within the framework of TAM project (Telecom Advisory Mission ), South korea funded project | Media policy and Broadcasting policy are in place | Improved regulatory framework for converged broadcasting and telecommunication Services | 1.1.Take part in developing the business model for new media | Q1,Q2 | Business model developed | TAM+RURA | 1000000 | 1000000 | RURA
|  |  |  | 1.2. Take part in the development of business model for TV content as a new groth industry | Q1,Q2 | Business model developed | TAM+RURA |  |  | RURA
|  |  |  | 1.3.Take part in the development of Media policy for public service broadcasting | Q1,Q2 | Media policy for public service broadcasting developed | TAM+RURA |  |  | RURA
|  |  |  | 1.4.Take part in the development of the Guidelines on the regulatory framework in response to the convergence of telecommunications and Broadcasting | Q1,Q2 | regulatory framework developed | TAM+RURA |  |  | RURA
| Develop Regulations for "advertising and sponsorship" in broadcasting services | Media law was promulgated; RURA initiated the draft of the PM order in accordance with art 5 of RURA law | The way of advertsing and sponsorship regulated | 1.1 Collect data, Conduct study visit to Advertising Standards Authority of South Africa (ASA) to learn more about regulations and enforcement of advertising and sponsorship of TV programs | Q2 | All required material available | Staff in charge and Director | 6000000 | 6000000 | RURA
|  |  |  | 1.2. Develop the regulations | Q2 |  |  | 0 | 0
|  |  |  | 1.3. Conduct internal consultation with LLE Unit and with stakeholders | Q3 |  |  | 0 | 0
|  |  |  | 1.4. Finalize, approve and publish the regulations | Q4 |  |  | 0 | 0
| Develop Regulations on "Must Carry Obligations" in television broadcasting services | Media and new RURA laws in place | Universal accessibility of certain television channels in particular public television channel | 1. 1 Collect data, and develop the regulations; | Q1 | Draft is ready for consultation | Media and Postal affairs | 535000 | 535000 | RURA
|  |  |  | 1.2. Conduct internal consultation and with stakeholders | Q2 | Inputs and comments from stakeholders are available | Comm and Media and CLIA departments
|  |  |  | 1.3. Finalize the regulations, approval and publication | Q3 | Regulations are approved and published | Comm and Media Dept.
| Develop the regulatory framework for internet multimedia broadcasting services providers | Online benchmarking was done and somme provisional authorisation were issued | Local Internet broadcasters compliant with laws and regulations | 1.1. Benchmarking the regulatory framework in the region and developed countries (South Korea or Singapore) | Q3 | Benchmarks available | Director + staff in charge | 8000000 | 8000000 | RURA
|  |  |  | 1.2. Desk research on regulatory framework for Internet multimedia broadcasting | Q1 | Benchmarks available | Director + staff in charge | 0 | 0 | RURA
|  |  |  | 1.3. Draft the regulation for internet multimedia services providers | Q2 | Draft regulation available | staff in charge | 0 | 0 | RURA
|  |  |  | 1.5. Conduct internal and stakeholders consultation | Q4 | Legal and economic inputs available | Director+staff in charge + LLE | 1000000 | 1000000 | RURA
|  |  |  | 1.6. Finalise and validate regulations |  | Stakeholders comments and inputs considered
|  |  |  | 1.7. Approval and publication of the regulations | Q4 | Regulations approved and published | Media and Com. and CLIA departments | 100000 | 100000 | RURA
|  |  |  | 1.8. Field visits and collection of information on internet multimedia services providers in Rwanda | Q4 | Information about internet broadcasters available | staff in charge | 100000 | 100000 | RURA
GOAL 2: Create, Strenghen and enforce the legal and regulatory framework
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) |  | Source of Fund
Put in place or review regulations and guidelines in the utility sectors where required | Develop Guidelines for minimum requirements for internet connectivity in hotels in Rwanda and support the process of preparing related tender | Baseline survey was done countrywide, Guidelines drafted and terms of reference have been drafted and submitted to Association of hoteliers for further processing | Improved internet connection and enough bandwidth in hotels | 1.1. Finetune the terms of reference and tender document for internet connectivity in Rwanda | Q1 | ToR available and tender document | Comm and Media Dept. | 0 | 0
|  |  |  | 1.2. Take part in the evaluation and issuance of the tender | Q1 | Contract signed and tender issued | Comm and Media Dept. | 0 | 0
|  |  |  | 1.3. Finetune the guidelines | Q1 | Draft guideline available | Director+ staff in charge | 100000 | 100000 | RURA
|  |  |  | 1.4. Carry out the consultations | Q1 | consultation report available | Director + staff in charge | 535000 | 535000 | RURA
|  |  |  | 1.5. Validation of the guidelines | Q2 | Final guideline available | Director + staff in charge
| Develop regulatory and licensing framework for postal industry in Rwanda | Postal Regulations and Template of license for providing postal services drafted | Postal sector reorganised and postal operators compliant with laws | 1.1. Fine tune postal and courier Regulations with legal and economic inputs | Q1 | Regulations approved and published | Director + staff in charge | 835000 | 835000 | RURA
|  |  |  | 1.2.Organise validation workshop | Q1 | Minutes of the meeting available | Director + staff in charge
|  |  |  | 1.3.Approval and publication of postal regulations | Q1 |  | Director + staff in charge
|  |  |  | 1.4. Elaborate licensing requirements and procedures for postal and courriers operators | Q1 | Requirements and procedures published | Director + staff in charge
|  |  |  | 1.5. Fine tune license template proposal for postal and courrier operators and include legal and economic inputs | Q1 | Approved license format for postal services available | Director + staff in charge
|  |  |  | 1.6. Register courrier and postal operators, analyse and process license applications and issue licenses | Q2 | Data on sector development available | Director + staff in charge | 300000 | 300000 | RURA
| Enforce Rwanda Internet Exchange Point (RINEX) guidelines by Monitoring and ensuring its performance | Recommendation on how to improve RINEX management and ensure its sustainability was done | Local traffic kept local; Reduced cost and better usage of international bandwidth for the country | 1.1. Facilitate setting up appropriate management of RINEX as per recommendation from consultant report | Q1 | New model of RINEX management implemented | Director + staff in charge | 0
|  |  |  | 1.2. Carry out periodic monitoring | Q2,Q3,Q4 | Report availble | Staff in charge
|  |  |  | 1.3. Follow up and support the acquisition and installation of state of the art equipment | Q4 | Acquired infrastructure deployed and operational | Director + staff in charge+ Finance unit | 40000000 | 40000000 | UAF
| Enforce Internet resources management guidelines and monitor the performance of .rw registry | .rw domain was redelegated and managed locally with financial support from RURA (UAF) | Performance, affordability, competitivity, compliance with international standards of .rw top level domain | 1.1. Support financially the auditing and facilitate the development of relevant term of references | Q2 | Audited financial statement available | Director + staff in charge+ Finance unit + UAF | 15000000 | 15000000 | UAF
|  |  |  | 1.2. Carry out periodic monitoring | Q1 and Q4 | Report available | Director+staff in charge | 0 |  | RURA
|  |  |  | 1.3. Hiring consultancy services for developing RICTA business plan | Q2 | Business plan developed | Director + staff in charge | 150000000 | 150000000 | UAF
|  |  |  | 1.4. Analyse RICTA's reports and provide financial support RICTA operations | Q1 | Analysis report and recommendations available | Director+Staff in charge + UAF and Finance unit |  |  | UAF
| Ensure IPV6 deployment and compliance in public network | Status of the IPv6 deployment by ISPs and Operators available on RURA website | Implementation of international recommendations and getting ready with the new development in ICT | 1.1. Carry out the consultations with ISPs on the implementation of the IPv6 | Q2 | Consultation report available | Director + staff in charge | 0 |  | RURA
|  |  |  | 1.2. Develop the roadmap for implemantation of IPv6 | Q3 | Draft roadmap available | Director + staff in charge
|  |  |  | 1.3.Finalize,Validate and publish the roadmap | Q4 | Final roadmap available | Director + staff in charge | 535000 | 535000 | RURA
Goal 5: Ensure efficient and effective allocation, safety and reliability of utility services
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) |  | Source of Fund
Develop and enforce operational service delivery standards and Qos parameters inline with internationally recognised norms for all regulated services | Put in place mechanisms to ensure security and Quality of service of courrier and parcels | Develop QoS parameters for postal services | Improved service delivery and compliance to standards | 1.1. Develop QoS parameters for postal services | Q3 | QoS parameters available and enforced | MPA unit
|  |  |  | 1.2. Develop a check-list to be used in inspection of QoS and security of couriers and parcels |  | Check list document developped | MPA unit
|  |  |  | 1.3. Conduct regular inspection and monitoring of registered postal operators | Q2 | Monitoring Reports available | MPA unit | 1000000 | 1000000 | RURA
|  |  |  | 1.4. Online Benchmarking on the usage of Qos monitoring tool to measure the speed of a courrier from one location to another | Q4 | Benchimarking report and recommendations available | MPA unit
GOAL 1: Develop an Efficient, Effective and Productive Corporate Entity
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) |  | Source of Fund
Foster Regional / International cooperation and enhance Rwanda visibility to International regulatory bodies. | To enhance Rwanda visibility and cooperation with other countries, regulatory institutions and International organisation | Different working groups, study groups meetings have been attended. There is a need to continue previous work for consistency | Gaining confidence in ICT regulation, development of ICT standards and their enforcement | Participate to SG 6- ITU-R Broadcasting service:WP 6A Terrestrial Broadcasting Delivery |  | Mission report |  | 5000000 | 9000000 |  | The remaining amount from the budget allocated for supporting and encouraging the local content creation was added to ITU Events
|  |  |  | Participate in the formulation of internet multimedia standard in ITU-T SG 16 | Q2,Q4 | Contribution and report available | Two Staff in charge | 8000000 | 16000000 | RURA
|  |  |  | Participating in ITU Study Group 6 ITU R: Broadcasting service (WP 6C Program production and quality assessment) | Q2,Q4 | Contribution and Report Available | Designated staff | 4670000 | 6000000 | RURA+ ITU
|  |  |  | WTDC-14 | Q3 and Q4 | Report Available | Director | 5000000 | 5000000
|  |  |  | Attend ITU- TDAG meetings | Q2 | Report available | Director/Designated staff | 8000000 | 3000000 |  | The full budget was not utilized and the remaining portion is re-allocated to new activity regarding the international and regional meetings related to media development
|  |  |  | Participate ITU-D Study Group 1 | Q1 | Contribution and Report Available | Designated staff | 2800000 | 0 |  | No staff attended and this budget is allocated to the international and regional meetings related to media development
|  |  |  | Participate in ITU Study Group 6: Broadcasting service(WP 6B:Programme Production and Quality Assessment) | Q2,Q4 | Contribution and Report Available | Staff in charge | 2800000 | 6470000 |  | The remaining amount from the budget allocated for supporting and encouraging the local content creation was added to ITU Events
|  |  |  | Participate in preparatory meetings of WRC 15 | Q1 | Contribution and Report Available | Broadcasting regulation officer | 2000000 | 0 |  | No staff attended and this budget is re-allocated to the international and regional meetings related to media development
|  |  |  | Take part in the formulation and discussions of internet governance related policies in ICANN meetings (ICANN 47 -Durban-RSA, ICANN 48 and ICANN 49- Singapore,ICANN 50-London) | Q1,Q2,Q3 and Q4 | Report and recommendations of ICANN meetings available | Appointed Icann focal point | 8000000 | 8000000 | RURA and ICANN
|  |  |  | Attend AFRINIC (African internet registry) public policy meetings on Internet ressources management | Q4 | Report and recommendations available | Staff in charge and Director | 5000000 | 5000000 | RURA
|  |  |  | Attend East african (AfIGF) and African Internet governance forum (EAIGF) aiming at discussing internet development issues in the region | Q1,Q2 | Report available | Director + staff in charge | 4000000 | 1500000 | RURA | The full budget was not utilized and the remaining portion is re-allocated to ITU Meetings
|  |  |  | Organise East African internet exchange point taskforce meeting | Q2 | Report available | Director + MPA staff | 4000000 | 2000000 | RURA | The full budget was not utilized and the remaining portion is re-allocated to ITU Meetings
|  |  |  | Participate in meetings with regards to East African internet exchange point | Q3 | Report available | Director | 1500000 | 1500000 | RURA
|  |  |  | Attend EACO Broadcasting Taskforce, COMESA and other regional meetings and conferences pertaining regulation of broadcasting sector | Q2, Q3 | Report Available | Director and/or staff in charge | 10000000 | 10000000 | RURA
|  |  |  | Participate in Universal Postal Union (UPU), Panafrican Postal union (PAPU) events and professional meetings on postal services regulation | Q1 & Q2 | Minutes and reports available | HoD, Director and/or staff in charge | 10000000 | 7500000 | RURA | The full budget was not utilized and the remaining portion is re-allocated to ITU Meetings
|  |  |  | Participate in COMESA, East african Community and EACO Postal sub Sector Technical Committee and taskforces | Q1 & Q4 | Minutes and reports available | Director and staff in charge | 9000000 | 9000000 | RURA
|  |  |  | Attending international and regional meetings with regards to media development and digital migration | Q3,Q4 | Minutes and reports available | Director/ officers in charge of media monitoring | 8800000 | 8800000 | RURA | This is a new activity introduced because MEDIA Sector needs a particular attention
|  |  |  | Fourth annual Trends in Innovation in the Postal Market in Berne Switzerland | Q1 | Report available | Director or designated staff | 4000000 | 4000000 | RURA
Goal 2: Create, Strengthen and enforce the legal and regulatory framework
Objective | Program | Output | Baseline | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | Budget allocated (RwF) |  | Source of Fund
Participate actively in the formulation of the sector policies and Laws; | Support the process of postal policy elaboration | Postal sector liberalized and opened up to competition | The postal policy was developped by consultant 3 years ago and need to be reviewed and updated to consider the current trend of postal services market and to be compliant with the policy format prescribed by the cabinet | Form an ad hoc committee | Q1 | Members of ad hoc committee nominated | Members of ad hoc committee nominated | N/A | N/A
|  |  |  | develop related Terms of reference and Hire consultancy services of expert to facilitate the review of postal policy | Q1 | The draft document available | The draft document available | 6000000 | 6000000 | RURA
|  |  |  | Organise a retreat to review and finalise the policy document | Q1 | The final draft document with incorporated inputs and comments from stakeholders | The final draft document with incorporated inputs and comments from stakeholders | 2000000 | 2000000 | RURA
|  |  |  | Submit the document to the Ministry in charge of Youth for further step | Q1 | Report on postal policy development submitted to the minister by ad hoc team | Report on postal policy development submitted to the minister by ad hoc team | N/A | N/A | N/A
579535000
ACTION PLAN FOR ICT STANDARD AND QoS 2013-2014
Goal 5: Ensure efficient and effective allocation of resources, safety and reliability of utility services
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Proposed Budget review | Source of Fund
Develop and enforce operational service delivery standards and quality of service parameters in line with internationally recognized norms for all regulated services | Installation and Commissionning of a new Mobile Networks QoS Measurement Platforn | Selection of preferred bidder done | a Customized system | Commissionning the acquired Mobile Networks QoS Monitoring Platform | Q1 | Approved test report | Director + Officer in Charge | 90000000 | 90000000 | RURA
|  |  |  | Conduct Test Measurements in the City of Kigali | Q1 | Test Report Available,System well configured | Director + Officer in Charge | 3000000 | 3000000 | RURA
|  | The newly approved Mobile QoS Regulations are enforceable | Mobile Networks well monitored to ensure Compliance to the new Regulations standard parameters | Conduct Measurement Campains in Kigali City and all 4 Provinces | Q1,Q2,Q3,Q4 | Measurement Reports are available/ Presented to the Board | Director + Officer in Charge | 7000000 | 7000000 | RURA
|  | Contract Signed | QoS Team trainned to handle and use the New acquired System | TEMS System Provider Trainings | Q3 | Training Report Available | Director+QoS Team | 0 | 40000000 | RURA | This amount was proposed to meet RURA responsibility as per cntract between RURA and Successful Bidder
| Long Term Evolution (LTE) Readiness | Negotiations between different stakeholders and Preparation of Business model | Readiness of RURA to ensure QoS of Services provided over LTE Network, Monitor Network performance | Prepare Measurement scripts for LTE QoS Measurement and Scanning | Q4 | Scripts available | Director + Officer in Charge | 0 | 0 | RURA
|  |  |  | Prepare Quaterly Reporting Template for LTE | Q4 | Template available | Director + Officer in Charge | 0 | 0 | RURA
| Develop a Ranking Framework for Operators QoS Performance | There was no ranking of operator's performance | Ranking Frameworkdevelopped and Agreed with Licenced Operators | Online research with other regulators, at least 5 Models | Q3,Q4 | 5 Ranking Models available | Director + Officer in Charge | 0 | 0 | RURA
|  |  |  | Develop a draft Ranking Framework Model for RURA | Q4 | Draft Ranking Model for RURA available | Director + Officer in Charge | 0 | 0 | RURA
|  |  |  | Consultation with Operators | Q4 | Consultation Meeting with Operators take place | Director + Officer in Charge | 0 | 0 | RURA
|  |  |  | Submit Operator's Ranking Framework to the Board for Approval | Q4 | Proposal for Ranking framework available | Director+HoD | 0 | 0 | RURA
| Analyze and Review the CURRENT deployment of the EPITIRO System | Report from Study tour in Bahrain | proposal for the new setup | make an analysis of the existing EPITIRO System, Based on study tour findings | Q1 | Report available | Director + Officer in Charge | 0 | 0 | RURA
|  |  |  | Submit a proposal/Concept paper on how we can re-design and re-deploy the EXISTING system (EPITIRO) | Q1 | Concept paper available | Director + Officer in Charge | 0 | 0 | RURA
| re-deploy , Operate, Explore all features and highlight capacity and weakness of the system | Some probes were deployed | new setup deployed | Conduct a survey to all ISPs in order: - to know the Coverage in the country of each ISP and - to know also the most solde bandwidth packages. | Q1 | reports available | Director + Officer in Charge | 5000000 | 5000000 | RURA
|  |  |  | Deploy probes and operate the system (monitoring tools) currently at RURA. | Q2,Q3,Q4 | Regular reports (weekly, monthly, quarterly,…) available | Director + Officer in Charge | 48000000 | 48000000 | RURA
|  |  |  | produce a proposal/Concept paper for the future operations of the project | Q2 | Concept paper available | Director + Officer in Charge | 0 | 0 | RURA
| Enforcement of GUIDELINES FOR (FIBER OPTIC CABLES UNDERGROUND INSTALLATION & siting and sharing of Telecom Towers) | Guidelines on Towers siting/ sharing and Fiber Optics Installation available | Instalation of fiber optic is done in accordance with internation telecommunication standards and without damaging existing infrastructure | Prepare permit requests and followup to obtain authorization from REMA and Districts | Q.1, Q.2, Q.3, Q.4 | Installation permit provided to operators | Director + Officer in Charge | 0 | 0 | RURA
|  |  |  | Site survey for fiber optic cable and Tower installation | Q.1, Q.2, Q.3, Q.4 | Survey report | Director + Officer in Charge | 8000000 | 8000000 | RURA
|  |  |  | Site survey after the installation of fiber optics and Towers | Q.1, Q.2, Q.3, Q.4 | Survey report | Director + Officer in Charge | 8000000 | 8000000 | RURA
Develop and enforce operational service delivery standards and quality of service parameters in line with Internationally recognized norms for all regulated services | Public Key Infrastructure (PKI) Establishment | There was no Certification Authority to issue certificate and digital signature in Rwanda | Closely work with the PKI expert during PKI implementation and reporting back to RURA | Regular update to the RURA management on the Implementation process | Q1, Q2, Q3 and Q4 | regular report on the status of the project | Director + Officer in Charge | 0 | 0 | RURA
|  |  | Good Cordination and Active Participation | Participate in workshops and Awareness compaign regarding te Implementation of PKI | Q2 | Workshops conducted | Director + Officer in Charge | 0 | 0 | RURA
|  |  | Root Certification Authority (RCA) well implemented in Rwanda | Participate in Inspection and testing of the constructed infrastructure (PKI) | Q3 and Q4 | Test Report available | Director + Officer in Charge | 0 | 0 | RURA
|  |  | Legal framework for Public Key Infrastructure | Retreat to finalise the required documents (Regulation, Certificate Policy and Certificate Procedure Statement, etc) | TBD | All documents ready for approval | AD-HOC Team | 0 | 2000000 | RURA | AD-HOC team was formed to work on these documents and meet RURA commitment in PKI implementation
|  |  | Physical security for Root CA Keys | Procuring a small safe box to store the Root CA tokens | Q3 | Safe box available | Officer in charge | 0 | 500000 | RURA | Three "KEYS" will be distributed and there is need to get a safe box to keep them.
|  |  | Clear picture of the appoach to be used by Rwanda | Consultation with ITU Experts on OID Registration | Q3 | Report on the appoach to be used by Rwanda | Officer in charge | 0 | 10000000 | RURA | This is a new activity related to PKI project after consultation with KOREAN Experts
Goal 2: Create, Strengthen and enforce the legal and regulatory framework
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) |  | Source of Fund
Put in place or review regulations and guidelines in the utility sectors where require | E-WASTE MANAGEMENT PREPAREDNESS |  | Closely work with the all concerned stakeholders | Regular update to the RURA management on the Implementation of the E-waste management process in Rwanda | Q.1 | Draft Available | Director + Officer in Charge | 0 | 0 | RURA
|  |  |  | Participate in workshops and Awareness compaign regarding the E-waste management Implementation | Q2 | Concept Paper available | Director + Officer in Charge | 0 | 0 | RURA
Set up and implement an appropriate and proactive enforcement mechanism for compliance with Laws, regulations and license obligations | CYBERSECURITY PREPAREDNESS |  | Closely work with the all concerned stakeholders | Regular update to the RURA management on the Implementation process of cybersecurity projects | Q.2 | Report available | Director + Officer in Charge | 0 | 0 | RURA
|  |  |  | Participate in workshops and Awareness compaign regarding te Implementation of cybersecurity projects | Q1 | consultation report | Director + Officer in Charge | 0 | 0 | RURA
Goal 1: Develop an Efficient, Effective and Productive Corporate Entity
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) |  | Source of Fund
Foster Regional / International cooperation and enhance Rwanda visibility to International regulatory bodies. | participating in ITU - T Study Groups(5, 9, 11,12, 13, 15 & 17) and ITU Council | All staff are very active in ITU events | Good image for RURA | ITU-T SG13 Regional & International meetings (Future networks including cloud computing, mobile and next-generation networks) , | Q2 | Meeting Reports available | Director + Officer in Charge | 6000000 | 6000000 | RURA
|  |  |  | ITU-T SG12 QoS Meeting | Q2 | Meeting Reports available | Director + Officer in Charge | 4000000 | 4000000 | RURA
|  |  |  | Participation ITU –T SG17 Meeting on security | Q1-Q2 | Meating report available | Director + Officer in Charge | 10000000 | 10000000 | RURA
|  |  |  | Participate actively in SG11and SG 15 upon invitation accepted and fellowship provision | Q.1, Q2, Q3, Q4 | meeting report | Director + Officer in Charge | 5000000 | 14000000 | RURA | Transfer from EACO Activities
|  |  |  | Participation in ITU-T SG 9 | Q2 | Report available | Director + Officer in Charge | 3000000 | 6000000 | RURA | Transfer from EACO Activities
|  |  |  | Participate in 6th World Telecommunication Development Conference (WTDC-2014) in Egypt and Preparatory Meetings in Ghana and Zambia | Q2, Q3 | Prepare country contribution to be submittes to the conference and Report | HoD + Director | 10000000 | 15000000 | RURA
|  |  |  | Participate TDAG meeting and ITU Council | Q2 | Report available | Director + Officer in Charge | 5000000 | 0 | RURA
|  |  |  | Participation ITU –T SG5 Meeting | Q2 | Final Draft Avairable | Director + Officer in Charge | 4000000 | 4000000 | RURA
|  |  |  | Active participation in ITU-T SG 12 Events with relevant contributions | TBD | Reports available | Director + Officer in Charge | 4000000 | 4000000 | RURA
|  | RURA Commitement to take Leadership roles in ITU and EACO Activities |  | ITU-T SG 13 Rapporteur Meeting (Rapporteur Q4/13) | Q3 | Reports available | Director + Officer in Charge | 0 | 0 | RURA | This amount was proposed in order to meet RURA Commitement to take Leadership roles in ITU and EACO Activities
|  |  |  | 3GPP Metings | Q3,Q4 | Reports available | Director + Officer in Charge | 0 | 7000000 | RURA | This amount was proposed in order to meet RURA Commitement to take Leadership roles in ITU and EACO Activities
|  |  |  | EACO WG8 Benchmarking (Vice-chairperson) | Q3 | Report available | Director | 0 | 10000000 | RURA
|  |  |  | ITU-T SG 5 Meeting (Associate Rapporteur) | Q4 | Reports available | Director + Officer in Charge | 0 | 5000000 | RURA
| Participate in EACO events | CANCELLED | RURA visibility increased | Participation in the EACO E-wasteTask Force/Committee | TBD | Meeting Reports available | Director + Officer in Charge | 2000000 | 0 | RURA | Amount Transferred to ITU Events
|  |  |  | Active participation in EACO QoS TF Meetings with relevant contributions | TBD | Reports available | Director + Officer in Charge | 2000000 | 0 | RURA
|  |  |  | Participation in the EACO Cybersecurity Task Force/Committee | Q3 | Reports available | Director + Officer in Charge | 2000000 | 0 | RURA
|  |  |  | Participation in the EACO Infrastructure sharing Task Force/Committee | Q4 | Reports available | Director + Officer in Charge | 2000000 | 0 | RURA
|  |  | RURA visibility increased | Participation in the EACOBroadcastingTask Force/Committee | Q1 | Reports available | Director + Officer in Charge | 2000000 | 0 | RURA
|  |  |  | Participation in the EACO international traffic monitoringTask Force/Committee | Q2-Q3 | Meating reports available | Director + Officer in Charge | 2000000 | 0 | RURA
|  |  |  | Participation in EACO E-transaction taskforce | TBD | Taskforce report | Director + Officer in Charge | 2000000 | 0 | RURA
TOTAL (ICT STDs&QoS) | [7 empty] | 250500000
PROJECTS UNDER HoD/COMMUNICATION AND MEDIA (ALL UNITS)
Goal 2: Create, Strengthen and enforce the legal and regulatory framework
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) |  | Source of Fund
Participate actively in the formulation of the sector policies and laws | Participate & Support MYICT in "Telecommunications Advisory Mission (TAM)" Project | Consultant already hired to facilitate in the whole process | Avaibility of Business Models for the new meda, Policy | Provide inputs and facilitate an expert hired by MYICT to - Develop business Moldels for media, TV content as a new growth industry, Media policy for public service broadcasting, and to develop the policy to promote competition in the telecommunication services market | Q.1, Q.2, Q.3, Q.4 | Consultation report available | All ICT Units | 0 | 0 | RURA
[5 empty] | Q.1, Q.2, Q.3, Q.5 | Consultation report available | All ICT Units | 0 | 0 | RURA
[5 empty] | Q.1, Q.2, Q.3, Q.6 | Consultation report available | All ICT Units | 0 | 0 | RURA
[5 empty] | Q.1, Q.2, Q.3, Q.7 | Consultation report available | All ICT Units | 0 | 0 | RURA
[5 empty] | Q.1, Q.2, Q.3, Q.8 | Consultation report available | All ICT Units | 0 | 0 | RURA
Goal 5: Ensure efficient and effective allocation of resources, safety and reliability of utility services
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (USD) |  | Source of Fund
Develop and enforce operational service delivery standards and quality of service parameters in line with Internationally recognized norms for all regulated services | Supporting the Digital Migration Process | Draft available | Licensed signed | Finalize License for Pan Africa Network | Q.1 |  | All ICT Units | 0 | 0 | RURA
|  | Awareness started | Population informed | Awareness Compaign on Analog Switch off (ASO) Process | Q.1, Q.2, Q.3, |  | All ICT Units | 70000000 | 70000000 | RURA
|  |  | Smooth analogue TV Switched off | Monitoring ASO Process | Q.1, Q.2, Q.3,Q4 |  | All ICT Units | 5000000 | 5000000 | RURA
TOTAL (PROJECTS UNDER HoD/COMMUNICATION AND MEDIA) | [7 empty] | 75000000 | 75000000
INFORMATION SYSTEM
Goal 1:Develop an Efficient, Effective and Productive Corporate Entity
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Proposed Budget review | Source of Fund | Comments
Equip RURA with the best information technology tools with most reliable and cutting-edge information technology platform; | To computirize a number of forms to be used online | The contract for computerizing some forms was signed between RURA and Software development company. | RURA customers will be able to lodge their applications and requests online, hense speeding up their processing | To computerize and secure the following forms available on website: Type approval , Economic Data for ISPs, Economic Data for Telecom Operators, Consumer Complaints Tracking, Water and Sanitation Operators Management , Application to manage alarms station and Application to manage FM Broadcasting Radio | 1st and 2nd Quarters | Dynamic forms available on RURA website for online application | Chief Information System and software Engineer | 0 | 0 | RURA
|  |  |  | To draft the terms of reference, participate technical evaluation and follow-up the deployment of Salar PV database | 2nd and 3rd Quarters | the availabity of Salar PV database | IS and Energy unit | 0 | 0 | RURA
|  |  |  | To draft the terms of reference, participate techniacal evaluation and follow-up the deplayment of oil depot database | 2nd and 3rd Quarters | the availabity of oil depot database | IS and Energy unit | 0 | 0 | RURA
|  |  |  | To automate the remaining forms for ICT plus radio communication license handling system | 2nd and 3rd Quarters | Online submission for cellular mobile networks performance questionnaire, cellular mobile networks dimensioning data , fixed networks performance questionnaire and Interference Complaint Form plus online communication license handling system |  | 15000000 | 15000000 | RURA
| Improve the visibility platforms of the Authority | The contract to provide us the web design tools was signed and we are still waiting the delivery | User friendly platform for access to the RURA public information | To put in place Electronic display board and reception sign systems in RURA waiting areas | 2nd and 3rd Quarters | Electronic display board and reception sign systems in Place | Hardware Engineer | 10000000 | 10000000 | RURA
|  |  |  | To update and administrate the Web and email system on regulary basis | 1st,2nd,3rd and 4 quarters | Website updated on regular basis and the number of added online application features. Email system operational with rura.rw domain and annually hosting fee paid | Chief Information System and software Engineer | 3500000 | 3500000 | RURA
| Implementation of E-document Tracking and Workflow Management System | As of now we have started to utilize the system for testing while the RDB continue its customization | reduced paper works in RURA offices | To implement E-document Tracking and Workflow Management System | 1st and 2nd Quarters | Paper works reduced at 80% | Chief Information System and System Administrator | 0 | 70000000 | RURA | This amount is brought to Action Plan 2013-2014 from Action Plan 2012-2013 because the current action plan was done while this tender was under process and finally cancelled due to tender successful bidder failure to supply.
|  |  |  | To harmonize electronic archiving with physical archiving by putting in Place the archiving rooms | 1st and 2nd Quarters |  |  | 15000000 | 20000000 | RURA | The GIS has been judged better to be removed from action plan because there is no clear needs for the departments . Its budget has been added to E-doc project
|  |  |  | To follow the training for customizing and administrating the e-document and workflow system according to the RURA needs | 1st & 2nd Quarter |  |  | 7394000 | 7394000 | RURA
| Upgrade Road Transportation Licensing System | Currently the existing system is not normalized . There is a need of normalization, incroparating the water way transport and securing the system | To have a secure system for transport with the online application for licences/ authorization posibility | To incoporate transport of water ways in the Road Transportation Licensing System | 1st and 2nd quarters | Water ways licensing incorporated in the existing system of road transport | Software Engineer | 0 | 0 | RURA
|  |  |  | Normalization of RTLS System after data entry activity | 1st and 2nd quarters | Harmonized system data structure | Software Engineer | 0 | 0 | RURA
| Upgrade Road Transportation Licensing System | Currently the existing system is not normalized . There is a need of normalization, incroparating the water way transport and securing the system | To have a secure system for transport with the online application for licences/ authorization posibility | Developing transport operators module so that they can apply for transport authorization/license online. Including SMS near-end authorization/license validity notification components/enhincing ability of developing web applications look-and-feel features. | Second & Third Quarters | The possibility of operators to apply online | Software Engineer | 20000000 | 20000000 | RURA
|  |  |  | To participate in web based application development and security training | 3rd Quarter |  |  | 15000000 | 15000000 | RURA
|  |  |  | Awareness campain/ Transport operators training/Hosting….. | 4th Quarters | the number of compains conducted and the transport operators are aware on the system existence | Software Engineer | 7000000 | 7000000 | RURA
| Implemention of an integrated finance and admistration information systems | the existing system sage that currenly RURA is using is a stand alone system. | To have a centralized finance and admistration information systems | To participate in SAP adminstation and customization training as requested by SAP Provider | 1st and 2nd Quarter | SAP annual license fees are paid, the system is updated on regular basis | System Administartor and Software Engineer | 16753700 | 16753700 | RURA
|  |  |  | To pay SAP annual license fees, to set up an integrated finance and admistration information systems | 1st & 2nd Quarter |  |  | 4000000 | 4000000 | RURA
| To implement the call center in RURA | As now the existing one phone is not enough for information requests handling and phone complaints reception and it is not accessible easily | centralised location for information requests handling and phone complaints reception | To do the deap analysis on call center setup and proposing the requirement and design | 1st Quarter | concise report in place with Design of the center and implementation and related operations with cost effective of all system components (hardware, software, Data, organization and Users) | IS and ICA unit | 0 | 0 | RURA
|  |  |  | To implement the proposed solution | 2nd Quarter | the propsed solution implemented | IS and ICA unit | 15000000 | 15000000 | RURA
| Acquire auditing software and training | the auditing process is done on manual process, we have advertized this tender locally and we didn't got any offer and we have decided to advertize it on international level | Internal auditors are faciliated by computerized system in their daily activities | To follow-up the system deployment and Training | First Quarter | improved auditing activities and reporting | System Administartor and Software Engineer | 3000000 | 3000000 | RURA
| Acquire software applications to manage: ISP &Telecom Companies promotions, Fiber optics Infrastracture Database and Telecom operators BTS database. | the existing software designed by interns need to be redesigned | Improved management of ISP &Telecom Companies promotions, Fiber optics and Telecom operators BTS. | To computerize ISP &Telecom Companies promotions, Fiber Optics data and Telecom operators BTS data. | Second and Quarter | Availability of software applications to manage the said applications. | Chief Information System and software Engineer | 20000000 | 20000000 | RURA
| Upgrade and secure RURA Network | the IT and Offices materials are not in safe Invironment and are accessible only within RURA premise | Secured Office and IT equipments | To draft the terms of reference Security Monitoring system RURA for offices and participate in tender evaluation | 1st,2nd quarters | Security Monitoring System in place( camera, door access control ) | Hardware Engineer | 40000000 | 40000000 | RURA
|  |  |  | To follow-up the deployment of security Monitoring system | [5 empty] | RURA
|  |  |  | Data,power and voice cabling plus the network equipment like switches, Rack, Access Point, Etc ) | 1st quarter | Cabling activites done and new network equipment installed | Network Administrator | 36000000 | 36000000 | RURA
| Upgrade and secure RURA Network | the IT and Offices materials are not in safe Invironment and are accessible only within RURA premise | Secured Office and IT equipments | To acquire and deploy Antivirus in all RURA computer | 1st,2nd quarters | The intivirus installed in all computers | Network Administrator | 6000000 | 6000000 | RURA
|  |  |  | To assessing IT equipments need to be insured and put them into insurance | 3rd,4th quarters | Senzitive IT equiment insured | Hardware Engineer | 14000000 | 14000000 | RURA
|  |  |  | To acquire skills for implementing VPN and E1 (CISCO voice , Open VPN ) | 1st & 2nd Quarter | RURA computer system accessible outside of RURA(both data and voice) | Network Administrator | 8112000 | 8112000 | RURA
|  |  |  | Implement the VPN and E1 technology | 3rd and 4th quarters |  |  | 15000000 | 15000000 | RURA
|  | As of now each application is hosted in its server but with the virtualization technology it is possible for many applications to share one server | reduced numbers of servers we buy and effectively management of the existing servers | To acquire skills on server virtualization imvironment | 1st and 2nd quarters | Virtualised System in place | System Administrator | 7856000 | 7856000 | RURA
|  |  |  | To set-up Server virtualization imvironment | 1st & 2nd Quarter |  |  |  |  | RURA
|  | As of now the data are stored on staff PC there is no centralised storage for data backup and the tender for acquiring the license for server data center were done | RURA data well stored and managed | To acquire skills for implementing the file server and active dircetory(Server+ and Storage +) | 1st & 2nd Quarter | the secure location for data storage and backup in place | System Administrator and Network Administrator | 7856000 | 7856000 | RURA
|  |  |  | Create a secure location for data storage and backup for all RURA Units and offsite backup | 1st & 2nd Quarter |  |  |  |  | RURA
|  | Aquire consumables for Printers, Copiers, faxes and scanners) | Well functioning Printing system | To acquire the consumables for IT equipments (for Printers, Copiers, faxes and scanners) | 1st and 2nd quarters | Well functioning Printing system | Hardware Engineer | 15000000 | 15000000 | RURA
|  | ensure efficient and updated software and hardware | Well functioning IT equipment | To acquire new computers for replacing the old ones | 3rd and 4th quarter | all machines and softwares are running smoothly | Hardware Engineer | 30000000 | 30000000 | RURA
| Upgrade and secure RURA Network |  |  | To acquire wood made stands for Desktop Computers | 1st and 2nd quarter |  |  | 5000000 | 5000000 | RURA
|  |  |  | To Perform preventive and corrective maintenance (UPS, Printers, Air conditioners,Copiers and Computers) | 1st and 2nd quarters |  |  | 15000000 | 15000000 | RURA
Provide the required job- specific trainings to all RURA staff | Internal IT training | Staff need to updated with new technologies and on IT tools which are already in place | To ensure the effective protection and proper usage of the computer systems within RURA | group training for VPN connection, external communication through E1, E-document | 1st, 2nd, 3rd and 4th quarters | All RURA staff trained on VPN connection, external communication through E1, E-document | All IS Team | 300000 | 300000 | RURA
Provide RURA with modern documentation centre for library and record keeping; | E-library | As of now there is small physical library | A modern e-library accessible with RURA staff anywere in any computer | To do the deap analysis on e-librayr setup and proposing the requirement and design | 2nd quarter | concise report in place with Design of the center and requirements and related operations with cost effective of all system components | IS and Librarian | 0 | 0 | RURA
TOTAL | [7 empty] | 351771700 | 426771700 | 0

## IS_capacity_building
Department | Unit | Number | Nature of the training | Venues | Name of the training | Proposed period | Estimated cost |  |  |  |  | Number of Beneficiary | Source of fund | Remarks
[7 empty] | Training/School fees | Subsistance allowance | Transport | Total | Proposed Budget review
| IS | 1 | Academic qualification trainings – Long terms training | KIGALI-ULK | Master of Science in Internet Systems | 2013-2014 | 2400000 | 0 | 0 | 2400000 | 2400000 | 1 | RURA
|  | 2 | short time Training abroad | India | Newgen Omniflow Omnidocs Product Customization | 1st quarter | 2600000 | 3744000 | 1050000 | 7394000 | 7394000 | 1 | RURA
|  | 3 | Academic qualification trainings – Long terms training | Switzerland | Online MBA-Information Technology | 18 Months |  |  |  |  | 15459120 | 1 | RURA | An online course approved by senior management and recommended to be added to this budget review due to its enrollment that is supposed to start 6th Jan 2014.
|  | 4 | short time Training abroad | India | CCNA Voice + and Open VPN | 3rd quarter | 2400000 | 4662000 | 1050000 | 8112000 | 8112000 | 1 | RURA
[10 empty] | 15506000 | 33365120

## MPA
MEDIA AND POSTAL AFFAIRS
GOAL 7: Ensure a sustainable development of the Media sector that reflect a sense of Rwanda’s identity, character, cultural diversity and expression of content
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Source of Fund
Establish mechanisms for Broadcasting Media monitoring and ensure storage of broadcast contents for any further use and analysis. | Put in place Broadcasting content monitoring mecanisms. | Technical Specification for media monitoring equipment and Plasma TV Developed | Compliance of TV and Radio programs with the laws and regulations. | 1.1. Drafting tender document | Q1 | Draft of the tender submitted to procurement office | Media Monitoring Team | 225000000 | RURA
|  |  |  | 1.2. Training, Installation and commissioning of Media monitoring equipment | Q2 | Operational media monitoring equipment | MPA Director and Media Monitoring Team
|  |  |  | 1.3. Install Plasma TV set in MPA unit office with all subscription arrangements for real time Monitoring TV programs | Q1 | Operational plasma screens and decoders operational | Media Monitoring Team. | 4000000 | RURA
|  |  |  | 1.4. Broadcasting Media Monitoring, Analysis and reporting | Q2, Q3 & Q4 | Monitoring reports available | Media Monitoring Team. |  | RURA
Supporting and encourage the local content creation with the aim of having sufficient local production and encourage investment of local content production. | Support and promote local content production for audio and audio visual media | Theres't any initiative for supporting content production in place | More innovation, entrepreneurship and competitiveness in local content creation | 1.1. Identify local content producers | Q1 | Collected data available | Media Monitoring Team. | 1000000 | RURA
|  |  |  | 1.2. Organise meetings and set modalities of promoting local content | Q1, Q2 | Modalities for promoting local content available | Media Monitoring Team.
|  |  |  | 1.3. Arrange regular meetings with local content producers to discuss about challenges and progress. | Q1, Q2 | Meeting Report available | Media and postal Unit
|  |  |  | 1.4 Conduct field visits to premises of local content producers and discuss possible support | Q2 & Q4 | Possible support identified | Media and postal Unit
Put in place and support a framework of cooperation between Self Regulatory Body and RURA | Provide technical support to Self Regulatory Body and work together in handling audio, audio-visual and internet media related matters | Internal discussions on MOU was done | Joint Mechanisms to regulate media sector | 1.1.Organise consultation meetings Self regulatory Body | Q1 | Reports available | Media and Postal | 1000000 | RURA
|  |  |  | 1.2 Organise a joint retreat for drafting MoU | Q1 | Draft of the MoU available
|  |  |  | 1.3 Approval and Signature of the MoU | Q2 | MoU Signed
Develop and enforce the regulatory framework for media sector in line with the Media Reform in the country | Develop regulatory framework governing broadcasting services in Rwanda and enforce related international standards | Regulations drafted and internal consulataion done | Clear guidance for licensing procedures and compliance with law in broadcasting sector | 1.1. Conduct external consultation and with stakeholders | Q1 | Inputs and comments from stakeholders are available | Comm and Media and CLIA departments | 535000 | RURA
|  |  |  | 1.2. Finalize the regulations, approval and publication | Q1 | Regulations are approved and published | Comm and Media Dept.
|  |  |  | 1.3. Draft the licensing template | Q1 | License template available
|  |  |  | 1.4. Analyse, process license applications and issue licenses for providing Broadcasting services licenses | Q1 | Licenses issued | Comm and Media Dept.
|  |  |  | 1.5. Acquire metal cupboard for rod folders to keep license applications documents | Q1 | Metal cabinet purchased | MPA UNIT | 3000000
| Develop regulations governing subscription satellite television services |  | Licencing framework for providing satellite TV services in place | Develop regulations and conduct required consultations with stakeholders | Q1, Q2 | Regulations and Licenses approved by the Board,Procedures and requirements for providing sateelites TV services published on RURA website | Comm and Media and CLIA departments | 0 | RURA
| Develop Prime Minister order determining specific mission of RURA in regard to media | Draft was sent to PMO | Clear functions of RURA in media regulation | 1.1. Participate in the consultation on PM order on specific function of RURA in Media | Q1 | PM order submitted for approval | Comm and Media Dept.
| Provide regulatory advice to broadcasting policy making process within the framework of TAM project (Telecom Advisory Mission ), South korea funded project | Media policy and Broadcasting policy are in place | Improved regulatory framework for converged broadcasting and telecommunication Services | 1.1.Take part in developing the business model for new media | Q1,Q2 | Business model developed | TAM+RURA | 1000000 | RURA
|  |  |  | 1.2. Take part in the development of business model for TV content as a new groth industry | Q1,Q2 | Business model developed | TAM+RURA |  | RURA
|  |  |  | 1.3.Take part in the development of Media policy for public service broadcasting | Q1,Q2 | Media policy for public service broadcasting developed | TAM+RURA |  | RURA
|  |  |  | 1.4.Take part in the development of the Guidelines on the regulatory framework in response to the convergence of telecommunications and Broadcasting | Q1,Q2 | regulatory framework developed | TAM+RURA |  | RURA
| Develop Regulations for "advertising and sponsorship" in broadcasting services | Media law was promulgated; RURA initiated the draft of the PM order in accordance with art 5 of RURA law | The way of advertsing and sponsorship regulated | 1.1 Collect data, Conduct study visit to Advertising Standards Authority of South Africa (ASA) to learn more about regulations and enforcement of advertising and sponsorship of TV programs | Q2 | All required material available | Staff in charge and Director | 6000000 | RURA
|  |  |  | 1.2. Develop the regulations | Q2
|  |  |  | 1.3. Conduct internal consultation with LLE Unit and with stakeholders | Q3
|  |  |  | 1.4. Finalize, approve and publish the regulations | Q4
| Develop Regulations on "Must Carry Obligations" in television broadcasting services | Media and new RURA laws in place | Universal accessibility of certain television channels in particular public television channel | 1. 1 Collect data, and develop the regulations; | Q1 | Draft is ready for consultation | Media and Postal affairs | 535000 | RURA
|  |  |  | 1.2. Conduct internal consultation and with stakeholders | Q2 | Inputs and comments from stakeholders are available | Comm and Media and CLIA departments
|  |  |  | 1.3. Finalize the regulations, approval and publication | Q3 | Regulations are approved and published | Comm and Media Dept.
| Develop the regulatory framework for internet multimedia broadcasting services providers | Online benchmarking was done and somme provisional authorisation were issued | Local Internet broadcasters compliant with laws and regulations | 1.1. Benchmarking the regulatory framework in the region and developed countries (South Korea or Singapore) | Q3 | Benchmarks available | Director + staff in charge | 8000000 | RURA
|  |  |  | 1.2. Desk research on regulatory framework for Internet multimedia broadcasting | Q1 | Benchmarks available | Director + staff in charge | 0 | RURA
|  |  |  | 1.3. Draft the regulation for internet multimedia services providers | Q2 | Draft regulation available | staff in charge | 0 | RURA
|  |  |  | 1.5. Conduct internal and stakeholders consultation | Q4 | Legal and economic inputs available | Director+staff in charge + LLE | 1000000 | RURA
|  |  |  | 1.6. Finalise and validate regulations |  | Stakeholders comments and inputs considered
|  |  |  | 1.7. Approval and publication of the regulations | Q4 | Regulations approved and published | Media and Com. and CLIA departments | 100000 | RURA
|  |  |  | 1.8. Field visits and collection of information on internet multimedia services providers in Rwanda | Q4 | Information about internet broadcasters available | staff in charge | 100000 | RURA
GOAL 2: Create, Strenghen and enforce the legal and regulatory framework
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Source of Fund
Put in place or review regulations and guidelines in the utility sectors where required | Develop Guidelines for minimum requirements for internet connectivity in hotels in Rwanda and support the process of preparing related tender | Baseline survey was done countrywide, Guidelines drafted and terms of reference have been drafted and submitted to Association of hoteliers for further processing | Improved internet connection and enough bandwidth in hotels | 1.1. Finetune the terms of reference and tender document for internet connectivity in Rwanda | Q1 | ToR available and tender document | Comm and Media Dept.
|  |  |  | 1.2. Take part in the evaluation and issuance of the tender | Q1 | Contract signed and tender issued | Comm and Media Dept.
|  |  |  | 1.3. Finetune the guidelines | Q1 | Draft guideline available | Director+ staff in charge | 100000 | RURA
|  |  |  | 1.4. Carry out the consultations | Q1 | consultation report available | Director + staff in charge | 535000 | RURA
|  |  |  | 1.5. Validation of the guidelines | Q2 | Final guideline available | Director + staff in charge
| Develop regulatory and licensing framework for postal industry in Rwanda | Postal Regulations and Template of license for providing postal services drafted | Postal sector reorganised and postal operators compliant with laws | 1.1. Fine tune postal and courier Regulations with legal and economic inputs | Q1 | Regulations approved and published | Director + staff in charge | 835000 | RURA
|  |  |  | 1.2.Organise validation workshop | Q1 | Minutes of the meeting available | Director + staff in charge
|  |  |  | 1.3.Approval and publication of postal regulations | Q1 |  | Director + staff in charge
|  |  |  | 1.4. Elaborate licensing requirements and procedures for postal and courriers operators | Q1 | Requirements and procedures published | Director + staff in charge
|  |  |  | 1.5. Fine tune license template proposal for postal and courrier operators and include legal and economic inputs | Q1 | Approved license format for postal services available | Director + staff in charge
|  |  |  | 1.6. Register courrier and postal operators, analyse and process license applications and issue licenses | Q2 | Data on sector development available | Director + staff in charge | 300000 | RURA
| Enforce Rwanda Internet Exchange Point (RINEX) guidelines by Monitoring and ensuring its performance | Recommendation on how to improve RINEX management and ensure its sustainability was done | Local traffic kept local; Reduced cost and better usage of international bandwidth for the country | 1.1. Facilitate setting up appropriate management of RINEX as per recommendation from consultant report | Q1 | New model of RINEX management implemented | Director + staff in charge | 0
|  |  |  | 1.2. Carry out periodic monitoring | Q2,Q3,Q4 | Report availble | Staff in charge
|  |  |  | 1.3. Follow up and support the acquisition and installation of state of the art equipment | Q4 | Acquired infrastructure deployed and operational | Director + staff in charge+ Finance unit | 40000000 | UAF
| Enforce Internet resources management guidelines and monitor the performance of .rw registry | .rw domain was redelegated and managed locally with financial support from RURA (UAF) | Performance, affordability, competitivity, compliance with international standards of .rw top level domain | 1.1. Support financially the auditing and facilitate the development of relevant term of references | Q2 | Audited financial statement available | Director + staff in charge+ Finance unit + UAF | 15000000 | UAF
|  |  |  | 1.2. Carry out periodic monitoring | Q1 and Q4 | Report available | Director+staff in charge | 0 | RURA
|  |  |  | 1.3. Hiring consultancy services for developing RICTA business plan | Q2 | Business plan developed | Director + staff in charge | 150000000 | UAF
|  |  |  | 1.4. Analyse RICTA's reports and provide financial support RICTA operations | Q1 | Analysis report and recommendations available | Director+Staff in charge + UAF and Finance unit |  | UAF
| Ensure IPV6 deployment and compliance in public network | Status of the IPv6 deployment by ISPs and Operators available on RURA website | Implementation of international recommendations and getting ready with the new development in ICT | 1.1. Carry out the consultations with ISPs on the implementation of the IPv6 | Q2 | Consultation report available | Director + staff in charge | 0 | RURA
|  |  |  | 1.2. Develop the roadmap for implemantation of IPv6 | Q3 | Draft roadmap available | Director + staff in charge
|  |  |  | 1.3.Finalize,Validate and publish the roadmap | Q4 | Final roadmap available | Director + staff in charge | 535000 | RURA
Goal 5: Ensure efficient and effective allocation, safety and reliability of utility services
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Source of Fund
Develop and enforce operational service delivery standards and Qos parameters inline with internationally recognised norms for all regulated services | Put in place mechanisms to ensure security and Quality of service of courrier and parcels | Develop QoS parameters for postal services | Improved service delivery and compliance to standards | 1.1. Develop QoS parameters for postal services | Q3 | QoS parameters available and enforced | MPA unit
|  |  |  | 1.2. Develop a check-list to be used in inspection of QoS and security of couriers and parcels |  | Check list document developped | MPA unit
|  |  |  | 1.3. Conduct regular inspection and monitoring of registered postal operators | Q2 | Monitoring Reports available | MPA unit | 1000000 | RURA
|  |  |  | 1.4. Online Benchmarking on the usage of Qos monitoring tool to measure the speed of a courrier from one location to another | Q4 | Benchimarking report and recommendations available | MPA unit
GOAL 1: Develop an Efficient, Effective and Productive Corporate Entity
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Source of Fund
Foster Regional / International cooperation and enhance Rwanda visibility to International regulatory bodies. | To enhance Rwanda visibility and cooperation with other countries, regulatory institutions and International organisation | Different working groups, study groups meetings have been attended. There is a need to continue previous work for consistency | Gaining confidence in ICT regulation, development of ICT standards and their enforcement | Participate to SG 6- ITU-R Broadcasting service:WP 6A Terrestrial Broadcasting Delivery |  | Mission report |  | 9000000
|  |  |  | Participate in the formulation of internet multimedia standard in ITU-T SG 16 | Q2,Q4 | Contribution and report available | Two Staff in charge | 16000000 | RURA
|  |  |  | Participating in ITU Study Group 6 ITU R: Broadcasting service (WP 6C Program production and quality assessment) | Q2,Q4 | Contribution and Report Available | Designated staff | 6000000 | RURA+ ITU
|  |  |  | WTDC-14 | Q3 and Q4 | Report Available | Director | 5000000
|  |  |  | Attend ITU- TDAG meetings | Q2 | Report available | Director/Designated staff | 4000000
|  |  |  | Participate ITU-D Study Group 1 | Q1 | Contribution and Report Available | Designated staff | 0
|  |  |  | Participate in ITU Study Group 6: Broadcasting service(WP 6B:Programme Production and Quality Assessment) | Q2,Q4 | Contribution and Report Available | Staff in charge | 6470000
|  |  |  | Participate in preparatory meetings of WRC 15 | Q1 | Contribution and Report Available | Broadcasting regulation officer | 0
|  |  |  | Take part in the formulation and discussions of internet governance related policies in ICANN meetings (ICANN 47 -Durban-RSA, ICANN 48 and ICANN 49- Singapore,ICANN 50-London) | Q1,Q2,Q3 and Q4 | Report and recommendations of ICANN meetings available | Appointed Icann focal point | 8000000 | RURA and ICANN
|  |  |  | Attend AFRINIC (African internet registry) public policy meetings on Internet ressources management | Q4 | Report and recommendations available | Staff in charge and Director | 5000000 | RURA
|  |  |  | Attend East african (AfIGF) and African Internet governance forum (EAIGF) aiming at discussing internet development issues in the region | Q1,Q2 | Report available | Director + staff in charge | 1500000 | RURA
|  |  |  | Organise East African internet exchange point taskforce meeting | Q2 | Report available | Director + MPA staff | 2000000 | RURA
|  |  |  | Participate in meetings with regards to East African internet exchange point | Q3 | Report available | Director | 1500000 | RURA
|  |  |  | Attend EACO Broadcasting Taskforce, COMESA and other regional meetings and conferences pertaining regulation of broadcasting sector | Q2, Q3 | Report Available | Director and/or staff in charge | 10000000 | RURA
|  |  |  | Participate in Universal Postal Union (UPU), Panafrican Postal union (PAPU) events and professional meetings on postal services regulation | Q1 & Q2 | Minutes and reports available | HoD, Director and/or staff in charge | 7500000 | RURA
|  |  |  | Participate in COMESA, East african Community and EACO Postal sub Sector Technical Committee and taskforces | Q1 & Q4 | Minutes and reports available | Director and staff in charge | 9000000 | RURA
|  |  |  | Attending international and regional meetings with regards to media development and digital migration | Q3,Q4 | Minutes and reports available | Director/ officers in charge of media monitoring | 8800000 | RURA
|  |  |  | Fourth annual Trends in Innovation in the Postal Market in Berne Switzerland | Q1 | Report available | Director or designated staff | 4000000 | RURA
Goal 2: Create, Strengthen and enforce the legal and regulatory framework
Objective | Program | Output | Baseline | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | Budget allocated (RwF) | Source of Fund
Participate actively in the formulation of the sector policies and Laws; | Support the process of postal policy elaboration | Postal sector liberalized and opened up to competition | The postal policy was developped by consultant 3 years ago and need to be reviewed and updated to consider the current trend of postal services market and to be compliant with the policy format prescribed by the cabinet | Form an ad hoc committee | Q1 | Members of ad hoc committee nominated | Members of ad hoc committee nominated | N/A
|  |  |  | develop related Terms of reference and Hire consultancy services of expert to facilitate the review of postal policy | Q1 | The draft document available | The draft document available | 6000000 | RURA
|  |  |  | Organise a retreat to review and finalise the policy document | Q1 | The final draft document with incorporated inputs and comments from stakeholders | The final draft document with incorporated inputs and comments from stakeholders | 2000000 | RURA
|  |  |  | Submit the document to the Ministry in charge of Youth for further step | Q1 | Report on postal policy development submitted to the minister by ad hoc team | Report on postal policy development submitted to the minister by ad hoc team | N/A | N/A
579535000

## STDs&QoS
ACTION PLAN FOR COMMUNICATION AND MEDIA REGULATION 2013-2014
ACTION PLAN FOR ICT STANDARD AND QoS 2013-2014
Goal 5: Ensure efficient and effective allocation of resources, safety and reliability of utility services
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Source of Fund
Develop and enforce operational service delivery standards and quality of service parameters in line with internationally recognized norms for all regulated services | Installation and Commissionning of a new Mobile Networks QoS Measurement Platforn | Selection of preferred bidder done | a Customized system | Commissionning the acquired Mobile Networks QoS Monitoring Platform | Q1 | Approved test report | Director + Officer in Charge | 90000000 | RURA
|  |  |  | Conduct Test Measurements in the City of Kigali | Q1 | Test Report Available,System well configured | Director + Officer in Charge | 3000000 | RURA
|  | The newly approved Mobile QoS Regulations are enforceable | Mobile Networks well monitored to ensure Compliance to the new Regulations standard parameters | Conduct Measurement Campains in Kigali City and all 4 Provinces | Q1,Q2,Q3,Q4 | Measurement Reports are available/ Presented to the Board | Director + Officer in Charge | 7000000 | RURA
|  | Contract Signed | QoS Team trainned to handle and use the New acquired System | TEMS System Provider Trainings | Q3 | Training Report Available | Director+QoS Team | 40000000 | RURA | Trainings to be done with reference to RURA responsibilities under the contract
| Long Term Evolution (LTE) Readiness | Negotiations between different stakeholders and Preparation of Business model | Readiness of RURA to ensure QoS of Services provided over LTE Network, Monitor Network performance | Prepare Measurement scripts for LTE QoS Measurement and Scanning | Q4 | Scripts available | Director + Officer in Charge | 0 | RURA
|  |  |  | Prepare Quaterly Reporting Template for LTE | Q4 | Template available | Director + Officer in Charge | 0 | RURA
| Develop a Ranking Framework for Operators QoS Performance | There was no ranking of operator's performance | Ranking Frameworkdevelopped and Agreed with Licenced Operators | Online research with other regulators, at least 5 Models | Q3,Q4 | 5 Ranking Models available | Director + Officer in Charge | 0 | RURA
|  |  |  | Develop a draft Ranking Framework Model for RURA | Q4 | Draft Ranking Model for RURA available | Director + Officer in Charge | 0 | RURA
|  |  |  | Consultation with Operators | Q4 | Consultation Meeting with Operators take place | Director + Officer in Charge | 0 | RURA
|  |  |  | Submit Operator's Ranking Framework to the Board for Approval | Q4 | Proposal for Ranking framework available | Director+HoD | 0 | RURA
| Analyze and Review the CURRENT deployment of the EPITIRO System | Report from Study tour in Bahrain | proposal for the new setup | make an analysis of the existing EPITIRO System, Based on study tour findings | Q1 | Report available | Director + Officer in Charge | 0 | RURA
|  |  |  | Submit a proposal/Concept paper on how we can re-design and re-deploy the EXISTING system (EPITIRO) | Q1 | Concept paper available | Director + Officer in Charge | 0 | RURA
| re-deploy , Operate, Explore all features and highlight capacity and weakness of the system | Some probes were deployed | new setup deployed | Conduct a survey to all ISPs in order: - to know the Coverage in the country of each ISP and - to know also the most solde bandwidth packages. | Q1 | reports available | Director + Officer in Charge | 5000000 | RURA
|  |  |  | Deploy probes and operate the system (monitoring tools) currently at RURA. | Q2,Q3,Q4 | Regular reports (weekly, monthly, quarterly,…) available | Director + Officer in Charge | 48000000 | RURA
|  |  |  | produce a proposal/Concept paper for the future operations of the project | Q2 | Concept paper available | Director + Officer in Charge | 0 | RURA
| Enforcement of GUIDELINES FOR (FIBER OPTIC CABLES UNDERGROUND INSTALLATION & siting and sharing of Telecom Towers) | Guidelines on Towers siting/ sharing and Fiber Optics Installation available | Instalation of fiber optic is done in accordance with internation telecommunication standards and without damaging existing infrastructure | Prepare permit requests and followup to obtain authorization from REMA and Districts | Q.1, Q.2, Q.3, Q.4 | Installation permit provided to operators | Director + Officer in Charge | 0 | RURA
|  |  |  | Site survey for fiber optic cable and Tower installation | Q.1, Q.2, Q.3, Q.4 | Survey report | Director + Officer in Charge | 8000000 | RURA
|  |  |  | Site survey after the installation of fiber optics and Towers | Q.1, Q.2, Q.3, Q.4 | Survey report | Director + Officer in Charge | 8000000 | RURA
Develop and enforce operational service delivery standards and quality of service parameters in line with Internationally recognized norms for all regulated services | Public Key Infrastructure (PKI) Establishment | There was no Certification Authority to issue certificate and digital signature in Rwanda | Closely work with the PKI expert during PKI implementation and reporting back to RURA | Regular update to the RURA management on the Implementation process | Q1, Q2, Q3 and Q4 | regular report on the status of the project | Director + Officer in Charge | 0 | RURA
|  |  | Good Cordination and Active Participation | Participate in workshops and Awareness compaign regarding te Implementation of PKI | Q2 | Workshops conducted | Director + Officer in Charge | 0 | RURA
|  |  | Root Certification Authority (RCA) well implemented in Rwanda | Participate in Inspection and testing of the constructed infrastructure (PKI) | Q3 and Q4 | Test Report available | Director + Officer in Charge | 0 | RURA
|  |  | Legal framework for Public Key Infrastructure | Retreate to finalise the required documents (Regulation, Certificate Policy and Certificate Procedure Statement, etc) | TBD | All documents ready for approval | AD-HOC Team | 2000000 | RURA | AD-HOC team was formed to work on these documents and meet RURA commitment in PKI implementation
|  |  | Physical security for Root CA Keys | Procuring a small safe box to store the Root CA tokens | Q3 | Safe box available | Officer in charge | 100000 | RURA | Three "KEYS" will be distributed and there is need o safe box to keep them.
|  |  | Clear picture of the appoach to be used by Rwanda | Consultation with ITU Expert on OID Registration | Q3 | Report available | Officer in charge | 10000000 | RURA
Goal 2: Create, Strengthen and enforce the legal and regulatory framework
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Source of Fund
Put in place or review regulations and guidelines in the utility sectors where require | E-WASTE MANAGEMENT PREPAREDNESS |  | Closely work with the all concerned stakeholders | Regular update to the RURA management on the Implementation of the E-waste management process in Rwanda | Q.1 | Draft Available | Director + Officer in Charge | 0 | RURA
|  |  |  | Participate in workshops and Awareness compaign regarding the E-waste management Implementation | Q2 | Concept Paper available | Director + Officer in Charge | 0 | RURA
Set up and implement an appropriate and proactive enforcement mechanism for compliance with Laws, regulations and license obligations | CYBERSECURITY PREPAREDNESS |  | Closely work with the all concerned stakeholders | Regular update to the RURA management on the Implementation process of cybersecurity projects | Q.2 | Report available | Director + Officer in Charge | 0 | RURA
|  |  |  | Participate in workshops and Awareness compaign regarding te Implementation of cybersecurity projects | Q1 | consultation report | Director + Officer in Charge | 0 | RURA
Goal 1: Develop an Efficient, Effective and Productive Corporate Entity
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Source of Fund
Foster Regional / International cooperation and enhance Rwanda visibility to International regulatory bodies. | participating in ITU - T Study Groups(5, 9, 11,12, 13, 15 & 17) and ITU Council | All staff are very active in ITU events | Good image for RURA | ITU-T SG13 Regional & International meetings (Future networks including cloud computing, mobile and next-generation networks) , | Q2 | Meeting Reports available | Director + Officer in Charge | 6000000 | RURA
|  |  |  | ITU-T SG12 QoS Meeting | Q2 | Meeting Reports available | Director + Officer in Charge | 4000000 | RURA
|  |  |  | Participation ITU –T SG17 Meeting on security | Q1-Q2 | Meating report available | Director + Officer in Charge | 10000000 | RURA
|  |  |  | Participate actively in SG11and SG 15 upon invitation accepted and fellowship provision | Q.1, Q2, Q3, Q4 | meeting report | Director + Officer in Charge | 5000000+9000000 | RURA | Transfer from EACO Activities
|  |  |  | Participation in ITU-T SG 9 | Q2 | Report available | Director + Officer in Charge | 3000000+3000000 | RURA | Transfer from EACO Activities
|  |  |  | Participate in 6th World Telecommunication Development Conference (WTDC-2014) in Egypt and Preparatory Meeting in Ghana | Q2, Q3 | Prepare country contribution to be submittes to the conference and Report | HoD + Director | 10000000 | RURA
|  |  |  | Participate TDAG meeting and ITU Council | Q2 | Report available | Director + Officer in Charge | 5000000 | RURA
|  |  |  | Participation ITU –T SG5 Meeting | Q2 | Final Draft Avairable | Director + Officer in Charge | 4000000 | RURA
|  |  |  | Active participation in ITU-T SG 12 Events with relevant contributions | TBD | Reports available | Director + Officer in Charge | 4000000 | RURA
|  | RURA Commitement to take Leadership roles in ITU Activities |  | ITU-T SG 13 Rapporteur Meeting (Rapporteur Q4/13) | Q3 | Reports available | Director + Officer in Charge | 6500000 | RURA
|  |  |  | 3GPP Metings | Q3,Q4 | Reports available | Director + Officer in Charge | 7000000 | RURA
|  |  |  | EACO WG8 Benchmarking (Vice-chairperson) | Q3 | Report available | Director | 10000000 | RURA
|  |  |  | ITU-T SG 5 Meeting (Associate Rapporteur) | Q4 | Reports available | Director + Officer in Charge | 5000000 | RURA
| Participate in EACO events | CANCELLED | RURA visibility increased | Participation in the EACO E-wasteTask Force/Committee | TBD | Meeting Reports available | Director + Officer in Charge | 2000000 | RURA | Amount Transferred to ITU Events (Above)
|  |  |  | Active participation in EACO QoS TF Meetings with relevant contributions | TBD | Reports available | Director + Officer in Charge | 2000000 | RURA
|  |  |  | Participation in the EACO Cybersecurity Task Force/Committee | Q3 | Reports available | Director + Officer in Charge | 2000000 | RURA
|  |  |  | Participation in the EACO Infrastructure sharing Task Force/Committee | Q4 | Reports available | Director + Officer in Charge | 2000000 | RURA
|  |  | RURA visibility increased | Participation in the EACOBroadcastingTask Force/Committee | Q1 | Reports available | Director + Officer in Charge | 2000000 | RURA
|  |  |  | Participation in the EACO international traffic monitoringTask Force/Committee | Q2-Q3 | Meating reports available | Director + Officer in Charge | 2000000 | RURA
|  |  |  | Participation in EACO E-transaction taskforce | TBD | Taskforce report | Director + Officer in Charge | 2000000 | RURA
TOTAL (ICT STDs&QoS) | [7 empty] | 250500000
PROJECTS UNDER HoD/COMMUNICATION AND MEDIA (ALL UNITS)
Goal 2: Create, Strengthen and enforce the legal and regulatory framework
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (RwF) | Source of Fund
Participate actively in the formulation of the sector policies and laws | Participate & Support MYICT in "Telecommunications Advisory Mission (TAM)" Project | Consultant already hired to facilitate in the whole process | Avaibility of Business Models for the new meda, Policy | Provide inputs and facilitate an expert hired by MYICT to - Develop business Moldels for media, TV content as a new growth industry, Media policy for public service broadcasting, and to develop the policy to promote competition in the telecommunication services market | Q.1, Q.2, Q.3, Q.4 | Consultation report available | All ICT Units | 0 | RURA
[5 empty] | Q.1, Q.2, Q.3, Q.5 | Consultation report available | All ICT Units | 0 | RURA
[5 empty] | Q.1, Q.2, Q.3, Q.6 | Consultation report available | All ICT Units | 0 | RURA
[5 empty] | Q.1, Q.2, Q.3, Q.7 | Consultation report available | All ICT Units | 0 | RURA
[5 empty] | Q.1, Q.2, Q.3, Q.8 | Consultation report available | All ICT Units | 0 | RURA
Goal 5: Ensure efficient and effective allocation of resources, safety and reliability of utility services
Objective | Program/Project | Baseline | Output | Activities to deliver output | Timeline/ Quarterly basis | Indicator | Responsibility | BUDGET ALLOCATED (USD) | Source of Fund
Develop and enforce operational service delivery standards and quality of service parameters in line with Internationally recognized norms for all regulated services | Supporting the Digital Migration Process | Draft available | Licensed signed | Finalize License for Pan Africa Network | Q.1 |  | All ICT Units | 0 | RURA
|  | Awareness started | Population informed | Awareness Compaign on Analog Switch off (ASO) Process | Q.1, Q.2, Q.3, |  | All ICT Units | 70000000 | RURA
|  |  | Smooth analogue TV Switched off | Monitoring ASO Process | Q.1, Q.2, Q.3,Q4 |  | All ICT Units | 5000000 | RURA
TOTAL (PROJECTS UNDER HoD/COMMUNICATION AND MEDIA) | [7 empty] | 75000000
Note on E210: USER: New, replace what has been already happened and not attended