## Header
PMO Cost Trend Analysis Template
Published
Owner
PMO to populate data onto Cost Trend Analysis page
Please read instructions

## Instructions
PMO Cost Trend Analysis Template
INSTRUCTIONS
Objective | This template is used to consolidate the cost data from all of the projects within the portfolio so as to be able to produce a consolidate summary that can be included in the steering committee pack
Action | PMO to capture summary data from all of the Project Cost Tracker templates.
When to complete | Monthly submission based on PMO reporting calendar
Overview | Name | Description
The Cost Summary page is used to consolidate all of the project cost details to provide a total for the portfolio.
| Step 1 | Costs are copied from the xx page from each of the project submissions.
| Step 2 | Costs are inserted into the yellow cells on the Cost Summary page, 1 project for each row.
| Step 3 | Cost summary table at the top of the page is copied and inserted into the Cost page within the PMO Steering Committe deck.
Summary | Name | Description
| Prior Years | Calculated field that provides the total Prior Years Actuals for all projects
| Budget 2013 | Calculated field that provides the total current year Budget for all projects
| Actuals | Calculated field that provides the total current year to date Actuals for all projects
| Estimate to Complete (ETC) | Calculated field that provides the total current year ETC for all projects
| Variance | Calculated field that provides the variance for current year (Budget less Actuals less ETC) for all projects.
| 2014 | Calculated field used to capture the Budget for following year for all projects if required.
| 2015 + | Calculated field used to capture any remaining years Budget to provide a total cost of all projects, if required
| Total | This provides the total known / forecast cost for all projects (Prior Year Actuals + Current Year Actuals + Current Year ETC + Budget 2014 + Budget 2015 Onwards)
Project Cost Details (Row 8 onwards) | Name | Description
| Project | Used to insert the recognised project name
| Prior Years | Used to insert the Prior Years Actuals for project
| Budget 2013 | Used to insert current Year Budget for project
| Actuals 2013 | Used to insert year to date Actuals for project
| ETC 2013 | Used to insert current year ETC for project
| Variance 2013 | Used to insert the variance for current year (Budget less Actuals less ETC) for project.
| Budget 2014 | Used to insert next years Budget for project, if required
| Budget 2015 + | Used to insert any remaining years Budget to provide a total cost for project, if required
| Total Project Cost | This provides the total known / forecast cost for the project (Prior Year Actuals + Current Year Actuals + Current Year ETC + Budget 2014 + Budget 2015 Onwards)
Note: | If you are copying and pasting from each Cost Tracker Summary, remember to paste special as values

## Cost Trend Analysis
Cost Trend Analysis | [10 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Project Cost Data | [5 empty] | PMO Cost Trend Analysis
| <Year> | [5 empty] | <Year>
| Budget | YTD Actuals Previous Month | YTD Actuals Current Month | ETC | Revised Forecast | Variance (C - G) | Straight Line | Variance (G - J) | Weighted Latest Month | Variance (G - L)
| 1850 | 1040 | 1230 | 540 | 1770 | 80 | 3690 | -1920 | 2750 | -980
| Month | Mar | Apr | 4
Project | Budget | YTD Actuals Previous Month | YTD Actuals Current Month | ETC | Revised Forecast | Variance | Straight Line | Variance (G - J) | Weighted Latest Month | ETC
| 500 | 200 | 250 | 230 | 480 | 20 | 750 | -270 | 650 | -170
| 750 | 500 | 600 | 200 | 800 | -50 | 1800 | -1000 | 1400 | -600
| 200 | 150 | 180 | 10 | 190 | 10 | 540 | -350 | 420 | -230
| 400 | 190 | 200 | 100 | 300 | 100 | 600 | -300 | 280 | 20
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
Note on C6: User: Enter the total budget for current year
Note on D6: User: Enter the total budget for current year
Note on F6: User: This will be the total of the Forecast section. Make sure that you delete all old forecasts to get the correct calculation
Note on J6: User: Enter the total budget for current year
Note on K6: User: Enter the total budget for current year
Note on M6: User: This will be the total of the Forecast section. Make sure that you delete all old forecasts to get the correct calculation