## Template
Work-plan for: please list the period which the work-plan covers
Project ID and Project Name: Please list project ID followed by the full project name according the project document or the short name listed in ATLAS
EXPECTED OUTPUTS/OUTCOMES INDICATORS | PLANNED ACTIVITIES | TIMEFRAME | [7 empty] | RESPONSIBLE PARTY | PLANNED BUDGET
Output/outcome indicators and annual indicator targets/ benchmarks (if applicable) | List all activities to be undertaken (including evaluations and publications etc) | Q1 2014 | Q2 2014 | Q3 2014 | Q4 2014 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 |  | Source of Funds | COA | Description | Amount (year) | Amount (year)
Outcome 1 (please provide the full name of the Outcome as listed in the Project Document) | [15 empty] | Outcome 1
Indicators: List output/outcome indicators listed in the ProDoc, as well as the annual indicator targets or identified benchmarks etc. identified during the planning period (if applicable) | Activity 1.1 (Please provide the full name of the activity as listed in the Project Document) | [14 empty] | Fund | COA | Q1 2014 | Q2 2014 | Q3 2014 | Q4 2014 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | Please fill the % of annual budget for this activity in this quarter instead of an 'X' | % | % | % | % | % | % | % | Please list the institution which is responsible for the implementation of the activity | Please list to which funding source the activity cost is to be accredited. | Please list the budget code for the planned activity or part of activity (i.e. 71100, 71200, 72100 etc) | Please describe the actions to be taken under the individual budget code listed | Please list the ascribed cost related to the listed budget code | Please list the ascribed cost related to the listed budget code | Pleas | Pleas | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal | [11 empty] | Please list the budget code used in than above (i.e. 71100, 71200, 72100 etc) |  | Please list the total amount for each budget code per year | Please list the total amount for each budget code per year
Outcome 1 subtotal
Outcome 2 (please provide the full name of the Outcome as listed in the Project Document
| Activity 2.1 (Please provide the full name of the activity as listed in the Project Document) | [14 empty] | Fund | COA | Q1 of 2014 | Q2 of 2014 | Q3 of 2014 | Q4 of 2014 | Q1 of 2015 | Q2 of 2015 | Q3 of 2015 | Q4 of 2015
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity (please list the actual activity to be undertaken and not the "standard" sub-activity listed in the project document.) | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal | [11 empty] | Please list the budget code used in than above (i.e. 71100, 71200, 72100 etc) |  | Please list the total amount for each budget code per year | Please list the total amount for each budget code per year
Outcome 2 subtotal
Total | [11 empty] | Please list the budget code used in than above (i.e. 71100, 71200, 72100 etc) |  | Please list the total amount for each budget code per year | Please list the total amount for each budget code per year
Total

## Examples
Work-plan for: please list the period which the work-plan covers
Project ID and Project Name: Please list project ID followed by the full project name according the project document or the short name listed in ATLAS
EXPECTED OUTPUTS/OUTCOMES INDICATORS | PLANNED ACTIVITIES | TIMEFRAME | [7 empty] | RESPONSIBLE PARTY | PLANNED BUDGET
Output/outcome indicators and annual indicator targets/ benchmarks (if applicable) | List all activities to be undertaken (including evaluations and publications etc) | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 |  | Source of Funds | COA | Description | Amount 2012 | Amount 2013
Outcome 1: Voluntary agreements in three industries achieved | [15 empty] | Outcome 1
Indicators: No. of people voluntary agreements signed within the first two year of the project (2012 = 3 sector workshops held, 2013 = 12 enterprise have signed VA) | Activity 1.1: Nominate 12 enterprises from the Iron, steel and cement sectors. | [14 empty] | Fund | COA | Q1 2014 | Q2 2014 | Q3 2014 | Q4 2014 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015
| Activity: Develop propaganda materials/pamphlets for Voluntary Agreements (VA) related to the iron, steel and cement sectors | 10% | 20% | 30% | 40% | 50% | 50% |  |  | ABC | GOVT | 72100 | Three sub-contracts (one for each sector) contracted to prepare materials (as per assignment TOR). Each contract is estimated at 30.000 US $ Payments (03/12; 10/12; 04/13) | 72000 | 18000 | GOVT | 72100 | 7200 | 14400 | 21600 | 28800 | 36000 | 36000 | 0 | 0
| Activity Design and Print propaganda materials/pamphlets for Voluntary Agreements | TIMEFRAME Q3: 100% | ABC | GOVT | 71300 | A designer prepares and finalize uniform design for the three sector VA | 5000 |  | GOVT | 71300 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0
|  | TIMEFRAME Q3: 100% | UNDP | TRAC | 72100 | A sub-contractor contracted for printing of 3X500 copies of the three VA propaganda materials/pamphlets | 10000 |  | TRAC | 72100 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0
| Activity Hold workshops for enterprise representatives from the three sectors | TIMEFRAME Q8: 100% | ABC | GOVT | 72100 | A hotel is contracted to host three workshops (including meals rooms, conference hall etc.). Anticipated participation is 100 per workshop. |  | 25000 | GOVT | 72100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TIMEFRAME Q8: 100% | ABC | GOVT | 71600 | Travel for 150 participants for the workshops (100 local transportation at 10 US $ pp and 50 airfare at 150 US $ pp) |  | 8500 | GOVT | 71600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TIMEFRAME Q8: 100% | DEF | 3rd | 74500 | Miscellaneous expenses related to the workshop |  | 500
| Activity Signing of VA by interested enterprises. | TIMEFRAME Q6: 33%; TIMEFRAME Q7: 33%; TIMEFRAME Q8: 33% |  |  |  | PMO engages in correspondence with interested enterprises to ensure agreement signature (no cost) |  | 0
Subtotal | [11 empty] | 72100 |  | 82000 | 43000
[12 empty] | 71300 |  | 5000
[12 empty] | 71600 |  |  | 8500
[12 empty] | 74500 |  |  | 500
Outcome 1 Subtotal | [13 empty] | 87000 | 52000
Outcome 2: Institutional capacity of BVA and its staff in effective volunteer management and volunteer mobilization enhanced
Indicators: Users are actively utilizing the reconstructed IT platform. (2012 = IT platform tested and 100 MNB staff trained, 2013 = User survey shows 50% general satisfaction with IT platform) | Activity 2.1 Strengthening of online volunteer matching platform
| Activity Conduct problem analysis on current matching system | TIMEFRAME Q1: 50%; TIMEFRAME Q2: 50% | FGH | UNV | N/A | PMO analysis on currentl matching system and identifies inherit problems (no Cost) | 0
|  | TIMEFRAME Q2: 50%; TIMEFRAME Q3: 50% | FGH | UNV | 71200 | An Interantional consultant will review PMO analysis on currentl matching system and provide technical sound sugegstions to the PMO on a platform update (24 w/d x 500 US $ p/d) | 12000
| Activity Execute updates, test and launch updated platform | TIMEFRAME Q3: 50%; TIMEFRAME Q4: 50% | FGH | UNV | 72100 | Hired sub-contractor updates and test the applications of the platform and provides the fully functional updated platform to MNB (the subcontract is a combined contract with below - total cost 10 000 US $) Payments (07/12; 12/12) | 5000
| ActivityTrain MNB staff in IT platform maintenance | TIMEFRAME Q5: 100% | UNDP | TRAC | 72100 | The sub-contractor (please see above) also provides training in the platform usage to MNB (the subcontract is a combined contract with above - total cost 10 000 US $) Payments (03/13) |  | 5000
| Activity Organize outreach campaign targeting VIOs and prospective volunteers | TIMEFRAME Q6: 100% | WER | 3rd | 72100 | A design/printing company designs and prints 2000 copies of the outreach materials |  | 2000
|  | TIMEFRAME Q6: 100% | FGH | UNV | 72100 | 7 Local venues is hired to host the 7 PMO trainings on the voluntere matching and the use of the IT platform. For each venue cost for confrence roome and meals are covered (7 X 1000 US $) |  | 7000
|  | TIMEFRAME Q6: 100% | FGH | 3rd | 72100 | 2 Local venues is hired to host the 2 PMO trainings on the voluntere matching and the use of the IT platform. For each venue cost for confrence roome and meals are covered. (2 X 1000 US $) |  | 2000
| Activity Monitor platform rate of utilization and collect feedback from users | TIMEFRAME Q7: 50%; TIMEFRAME Q8: 50% | FGH | UNV | N/A | PMO monitor platform rate of utilization and collect feedback from users (No Cost) |  | 0
Subtotal | [11 empty] | 72100 |  | 5000 | 16000
[12 empty] | 71200 |  | 12000
Outcome 2 Subtotal | [13 empty] | 17000 | 16000
Total | [11 empty] | Please list the budget code used in than above (i.e. 71100, 71200, 72100 etc) |  | Please list the total amount for each budget code per year | Please list the total amount for each budget code per year
[12 empty] | 71200 |  | 12000 | 0
[12 empty] | 71300 |  | 5000 | 0
[12 empty] | 71600 |  | 0 | 8500
[12 empty] | 72100 |  | 87000 | 59000
[12 empty] | 74500 |  | 0 | 500
Total | [13 empty] | 104000 | 68000