## Introduction
Project Planning and Monitoring Tool
Purpose: This tool assists in organizing and monitoring project work. By using the task planning section, project milestones and tasks can accurately be planned out. Once the project begins, real-time progress is tracked and the project is monitored against the set baselines.
Instructions: This tool can be used for managing a project, starting with the planning stages right through to monitoring project progress. Refer to the boxes below to view each sections' instructions, and understand how each step is useful for managing projects. Alternatively, information entered in Microsoft Project can be copied and pasted into this tool to take advantage of its reporting capabilities. A simple copy and paste will work, however there is some preparation needed: 1. Ensure that the fields in MS Project are altered to match this tool. The order should be: Task Name, Start, Finish, and Resource Names. 2. Once pasted into this tool's Tab 2, reformat the start and finish columns to use a date format (within the Format menu, choose "Cells..." and select the desired date format). 3. Resource Names within MS Project must match the naming conventions used in this tool's Tab 1, table 1. Important Notice: Although this tool is capable of advanced functions, keep in mind that this is a light project management tool working within the limitations of Microsoft Excel. Pay close attention to any notices or warnings included within the individual tabs.
Getting Started: In chronological order, use the boxes below to navigate through the tool as the project progresses. Click the blue buttons to go directly to the section of choice, or use the worksheet tabs along the bottom of the spreadsheet screen. Some of the column headings in the sections include comments that offer additional instructions. Hover the mouse over the column headings to view these instructions.
| DATA ENTRY |  | PROJECT TASK PLANNING
| This section requires some basic data entry to get the project started. Information regarding project start and end dates, project team members and stakeholders, and non-work days is required. |  | Use this important section to plan out the project. Tasks should be entered, along with deadlines and task owners. Once hashed out and completed, copy and paste this plan into Tab 3 to begin monitoring project progress.
|  | Go to Data Entry |  | Go to Project Task Planning
| PROJECT MONITORING CHART |  | ISSUE LOG
| Copy and paste the project plan from Tab 2 into the first four columns of this Gantt chart. By entering the actual start and end dates for tasks, this chart allows you to view which tasks are on schedule, behind schedule or ahead of schedule. |  | If issues arise, use this area to log and ensure that problems are resolved.
|  | Go to Project Monitoring |  | Go to the Issue Log
CUSTOMIZED PROGRESS REPORT
Use this section to generate a custom progress report. Specify the time period that you would like to view and tasks during this time, ordered by task owner, will appear. This report is ideal for weekly meeting updates, or stakeholder progress reporting.
Go to Task Report
3
4
1
2
5

## 1. Data Entry
Basic Data Entry |  |  | Return to the Introduction
Fill in all of the white cells with the necessary information. To view additional instructions, hover your mouse over the table column headings.
Project Name | CRM Implementation
Estimated Project Start Date | 2009-06-01
Estimated Project End Date | 2009-07-20
Project Manager Name | Jane Doe
1. Project Team Members, Task Groups & Stakeholders | 2. Holidays / Time Off Project
Name | Date | Holiday
Jane Doe | 2009-04-10 | Good Friday
John Doe | 2009-04-13 | Easter Monday
Jane and John | 2009-04-15 | All Day Dept Meeting April
John Smith | 2009-05-18 | Canadian Victoria Day
Kim Lee | 2009-07-04 | US Independence Day
Chris Johnson | 2009-07-03 | Non-Project Work Day
Alex Singh | 2009-10-12 | Canadian Thanksgiving
Marketing Department | 2009-11-26 | US Thanksgiving
Production Team | 2009-12-25 | Christmas Day
| 2010-01-01 | New Year's Day
Note on B14: List all project participants and stakeholders. Include all project member names that will be actually involved with owning/implementing parts of the project. Feel free to insert multiple names of a team.
Note on D14: All dates in this list will not be made available in the project planning gantt chart. Make sure that ranges are printed out one date at a time. For example, if there is a week of non-project work, print out the five days as separate entries. Make sure to include only days that are not dedicated to the project as a whole. Remember, these dates will be blanked out completely.

## 2. Planning
Planning |  | Return to the Introduction
Use this section to work out the project plan. Feel free to add and delete rows as necessary, or move tasks around until the optimal project plan has been drafted. Once satisfied with the project plan, copy this information and paste it into the corresponding table in Tab 3. No changes can be made to the project plan within Tab 3, so ensure that if any changes are needed, the adjustments are made in this tab before re-copying and re-pasting the data into Tab 3. An example has been included below.
Project Task Information
Project Task | Estimated Start Date | Estimated Completion Date | Task Owner (MUST USE DROP DOWN MENU)
Project Feasibility Study | 2009-06-01 | 2009-06-03 | Alex Singh
Cost Benefit Analysis | 2009-06-02 | 2009-06-04 | Jane and John
Project Definition | 2009-06-06 | 2009-06-08 | Jane Doe
Assign Resources | 2009-06-08 | 2009-06-09 | John Smith
Create Project Plan | 2009-06-09 | 2009-06-16 | Kim Lee
Create Communications Plan | 2009-06-15 | 2009-06-17 | Jane Doe
Project Kick-Off Meeting | 2009-06-19 | 2009-06-19 | Jane Doe
Create Phase 1 Plan and Definition | 2009-06-22 | 2009-06-24 | Jane Doe
Phase 1 Execution Kick-Off | 2009-06-24 | 2009-06-24 | Jane Doe
Communicate Phase 1 Progress | 2009-06-25 | 2009-07-01 | John Doe
Change Control Processes | 2009-07-01 | 2009-07-02 | Jane and John
Close Phase 1 | 2009-07-02 | 2009-07-03 | Jane Doe
Create Phase 2 Plan and Definition | 2009-07-01 | 2009-07-03 | Chris Johnson
Phase 2 Execution Kick-Off | 2009-07-06 | 2009-07-06 | Chris Johnson
Communicate Phase 2 Progress | 2009-07-07 | 2009-07-09 | Chris Johnson
Change Control Processes | 2009-07-09 | 2009-07-10 | Chris Johnson
Close Phase 2 | 2009-07-13 | 2009-07-14 | Jane Doe
Project Delivery | 2009-07-15 | 2009-07-15 | Production Team
Project Closure Meeting | 2009-07-16 | 2009-07-16 | Jane Doe
Performance Appraisal | 2009-07-16 | 2009-07-18 | Jane Doe
Project Feedback Form | 2009-07-16 | 2009-07-18 | Kim Lee
Project Debrief Report | 2009-07-17 | 2009-07-20 | Jane Doe
Note on E8: Use only the drop down menu to select the owner of the corresponding task. Groups of people, individuals, or departments can be used, depending on the entries made in the Data Entry section.

## 3. Task Monitoring
Work Schedule Monitoring | [11 empty] | Return to the Introduction
IMPORTANT NOTICE: It is very important that tasks are entered with unique names. If task names are repeated, the data will not carry over correctly. Make sure to name each task differently. IMPORTANT NOTICE: Rows cannot be inserted or deleted from the table below. If changes are made to the project plan, make these changes in Tab 2. Planning, and copy and paste the changes into this sheet. Be aware that the actual start and end dates will not update when changes are copy and pasted into this sheet, so make adjustments to these last two columns as necessary. | [6 empty] | GANTT CHART LEGEND
Holiday / Vacation / No Work
Planned Project Work Day
Task Completed
COMPLETION STATUS LEGEND
Task Completed Ahead of Schedule
Task Completed Behind Schedule
Project Task Information | [6 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26
Project Task | Estimated Start Date | Estimated Completion Date | Task Owner | Actual Start Date | Actual Completion Date | Comments | 2009-06-01 |  |  |  |  | 2009-06-08 |  |  |  |  | 2009-06-15 |  |  |  |  | 2009-06-22 |  |  |  |  | 2009-06-29 |  |  |  |  | 2009-07-06 |  |  |  |  | 2009-07-13 |  |  |  |  | 2009-07-20 |  |  |  |  | 2009-07-27 |  |  |  |  | 2009-08-03 |  |  |  |  | 2009-08-10 |  |  |  |  | 2009-08-17 |  |  |  |  | 2009-08-24 |  |  |  |  | 2009-08-31 |  |  |  |  | 2009-09-07 |  |  |  |  | 2009-09-14 |  |  |  |  | 2009-09-21 |  |  |  |  | 2009-09-28 |  |  |  |  | 2009-10-05 |  |  |  |  | 2009-10-12 |  |  |  |  | 2009-10-19 |  |  |  |  | 2009-10-26 |  |  |  |  | 2009-11-02 |  |  |  |  | 2009-11-09 |  |  |  |  | 2009-11-16 |  |  |  |  | 2009-11-23
[7 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
Project Feasibility Study | 2009-06-01 | 2009-06-03 | John Doe | 2009-06-01 | 2009-06-02 | bar: 2009-06-01 1 M to 2009-06-01 3 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Cost Benefit Analysis | 2009-06-02 | 2009-06-04 | Jane and John | 2009-06-02 | 2009-06-03 | bar: 2009-06-01 2 T to 2009-06-01 4 T; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
Project Definition | 2009-06-06 | 2009-06-08 | Jane Doe | 2009-06-06 | 2009-06-09 | bar: 2009-06-08 8 M; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Assign Resources | 2009-06-08 | 2009-06-09 | John Smith | 2009-06-08 | bar: 2009-06-08 8 M to 2009-06-08 9 T; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Create Project Plan | 2009-06-09 | 2009-06-16 | Kim Lee | bar: 2009-06-08 9 T to 2009-06-15 16 T; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Create Communications Plan | 2009-06-15 | 2009-06-17 | Jane Doe | bar: 2009-06-15 15 M to 2009-06-15 17 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
Project Kick-Off Meeting | 2009-06-19 | 2009-06-19 | Jane Doe | bar: 2009-06-15 19 F; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
Create Phase 1 Plan and Definition | 2009-06-22 | 2009-06-24 | Jane Doe | bar: 2009-06-22 22 M to 2009-06-22 24 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Phase 1 Execution Kick-Off | 2009-06-24 | 2009-06-24 | Jane Doe | bar: 2009-06-22 24 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Communicate Phase 1 Progress | 2009-06-25 | 2009-07-01 | John Doe | bar: 2009-06-22 25 T to 2009-06-29 1 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Change Control Processes | 2009-07-01 | 2009-07-02 | Jane and John | bar: 2009-06-29 1 W to 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Close Phase 1 | 2009-07-02 | 2009-07-03 | Jane Doe | bar: 2009-06-29 2 T to 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
Create Phase 2 Plan and Definition | 2009-07-01 | 2009-07-03 | Chris Johnson | bar: 2009-06-29 1 W to 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Phase 2 Execution Kick-Off | 2009-07-06 | 2009-07-06 | Chris Johnson | bar: 2009-06-29 3 F to 2009-07-06 6 M; 2009-10-12 12 M; 2009-11-23 26 T
Communicate Phase 2 Progress | 2009-07-07 | 2009-07-09 | Chris Johnson | bar: 2009-06-29 3 F; 2009-07-06 7 T to 2009-07-06 9 T; 2009-10-12 12 M; 2009-11-23 26 T
Change Control Processes | 2009-07-09 | 2009-07-10 | Chris Johnson | bar: 2009-06-29 3 F; 2009-07-06 9 T to 2009-07-06 10 F; 2009-10-12 12 M; 2009-11-23 26 T
Close Phase 2 | 2009-07-13 | 2009-07-14 | Jane Doe | bar: 2009-06-29 3 F; 2009-07-13 13 M to 2009-07-13 14 T; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
Project Delivery | 2009-07-15 | 2009-07-15 | Production Team | bar: 2009-06-29 3 F; 2009-07-13 15 W; 2009-10-12 12 M; 2009-11-23 26 T
Project Closure Meeting | 2009-07-16 | 2009-07-16 | Jane Doe | bar: 2009-06-29 3 F; 2009-07-13 16 T; 2009-10-12 12 M; 2009-11-23 26 T
Performance Appraisal | 2009-07-16 | 2009-07-18 | Jane Doe | bar: 2009-06-29 3 F; 2009-07-13 16 T to 2009-07-13 17 F; 2009-10-12 12 M; 2009-11-23 26 T
Project Feedback Form | 2009-07-16 | 2009-07-18 | Kim Lee | bar: 2009-06-29 3 F; 2009-07-13 16 T to 2009-07-13 17 F; 2009-10-12 12 M; 2009-11-23 26 T
Project Debrief Report | 2009-07-17 | 2009-07-20 | Jane Doe | bar: 2009-06-29 3 F; 2009-07-13 17 F to 2009-07-20 20 M; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
Formulas:
Week 2 = [Week 1]+7
Week 3 = [Week 2]+7
Week 4 = [Week 3]+7
Week 5 = [Week 4]+7
Week 6 = [Week 5]+7
Week 7 = [Week 6]+7
Week 8 = [Week 7]+7
Week 9 = [Week 8]+7
Week 10 = [Week 9]+7
Week 11 = [Week 10]+7
Week 12 = [Week 11]+7
Week 13 = [Week 12]+7
Week 14 = [Week 13]+7
Week 15 = [Week 14]+7
Week 16 = [Week 15]+7
Week 17 = [Week 16]+7
Week 18 = [Week 17]+7
Week 19 = [Week 18]+7
Week 20 = [Week 19]+7
Week 21 = [Week 20]+7
Week 22 = [Week 21]+7
Week 23 = [Week 22]+7
Week 24 = [Week 23]+7
Week 25 = [Week 24]+7
Week 26 = [Week 25]+7
Note on B14: The first four columns of this table should be populated by copying and pasting the tasks that were planned out in Tab 2. The only new text that should be entered in this tab is the actual start and end dates.
Note on E14: Use ONLY the drop down menu to select the task owner name. Entering text that is not from the menu will result in reporting errors in Tab 4.
Note on H14: Insert task-specific comments as necessary. If useful, a hyperlink to a specific issue in Tab 4 can be created by hyperlinking within the document.

## 4. Issue Log
Issue Log |  |  | Return to the Introduction
Date | Issue | Comments | Resolution
2009-01-03 | Sample Issue

## 5. Reporting
Customized Progress Report |  |  |  | Return to the Introduction
To create a customized progress report, insert the desired timeframe for analysis in the start and end date boxes below. For a progress report of the entire project, insert the project's start and end dates. Consider running reports based on tasks for today, this week, or next week. IMPORTANT NOTICE: Task owner names must be selected from the drop down menus in Tabs 2 and 3 in order for this reporting page to work correctly. If errors occur on this page, return to the project planning stage and ensure that task owner names were selected from the menus, rather than typed in manually.
Enter Date to Start Progress Report | 2009-06-04 | Enter Date to End Progress Report |  | 2009-07-20
Analysis of On-Schedule Tasks to Date | Analysis of Task Completion to Date |  | Analysis of Project Time Management
Task Owner | Task to be Completed During Specified Period | Task Status | Scheduled Due Date | On Track Status
Jane Doe | Create Communications Plan | Task Not Yet Started | 2009-06-17 | Task is scheduled for work during this timeframe.
| Project Kick-Off Meeting | Task Not Yet Started | 2009-06-19 | Task is scheduled for work during this timeframe.
| Create Phase 1 Plan and Definition | Task Not Yet Started | 2009-06-24 | Task is scheduled for work during this timeframe.
| Phase 1 Execution Kick-Off | Task Not Yet Started | 2009-06-24 | Task is scheduled for work during this timeframe.
| Close Phase 1 | Task Not Yet Started | 2009-07-03 | Task is scheduled for work during this timeframe.
| Close Phase 2 | Task Not Yet Started | 2009-07-14 | Task is scheduled for work during this timeframe.
| Project Closure Meeting | Task Not Yet Started | 2009-07-16 | Task is scheduled for work during this timeframe.
| Performance Appraisal | Task Not Yet Started | 2009-07-18 | Task is scheduled for work during this timeframe.
| Project Debrief Report | Task Not Yet Started | 2009-07-20 | Task is scheduled for work during this timeframe.
Chris Johnson | Create Phase 2 Plan and Definition | Task Not Yet Started | 2009-07-03 | Task is scheduled for work during this timeframe.
| Phase 2 Execution Kick-Off | Task Not Yet Started | 2009-07-06 | Task is scheduled for work during this timeframe.
| Communicate Phase 2 Progress | Task Not Yet Started | 2009-07-09 | Task is scheduled for work during this timeframe.
| Change Control Processes | Task Not Yet Started | 2009-07-02 | Task is scheduled for work during this timeframe.
Kim Lee | Create Project Plan | Task Not Yet Started | 2009-06-16 | Task is scheduled for work during this timeframe.
| Project Feedback Form | Task Not Yet Started | 2009-07-18 | Task is scheduled for work during this timeframe.
John Doe | Communicate Phase 1 Progress | Task Not Yet Started | 2009-07-01 | Task is scheduled for work during this timeframe.
Jane and John | Change Control Processes | Task Not Yet Started | 2009-07-02 | Task is scheduled for work during this timeframe.
John Smith | Assign Resources | Task In Progress | 2009-06-09 | Task is scheduled for work during this timeframe.
Production Team | Project Delivery | Task Not Yet Started | 2009-07-15 | Task is scheduled for work during this timeframe.

## Hidden (hidden)
| Variables> | "Stats" |  | Members | Date | Holiday Name
| actual | Not Yet Started | Team--> | Jane Doe | 39913 | Good Friday | Jane Doe
| completion | In Progress |  | John Doe | 39916 | Easter Monday | John Doe
| status | Completed |  | Jane and John | 39918 | All Day Dept Meeting April | Jane and John
|  | Cancelled |  | John Smith | 39951 | Canadian Victoria Day | John Smith
|  |  |  | Kim Lee | 39998 | US Independence Day | Kim Lee
|  |  |  | Chris Johnson | 39997 | Non-Project Work Day | Chris Johnson
|  |  |  | Alex Singh | 40098 | Canadian Thanksgiving | Alex Singh
|  |  |  | Marketing Department | 40143 | US Thanksgiving | Marketing Department
| Status Var> | "Track" |  | Production Team | 40172 | Christmas Day | Production Team
|  | Not Yet Started |  |  | 40179 | New Year's Day
| on track | Completed On Time
| completion | Completed Behind Schedule
| status | Completed Ahead of Schedule
In Progress
Cancelled
LINK PROJECT START DATE TO THE MONDAY BEFORE (For Gantt Chart)
[16 empty] | Which wkday is it? |  |  | Find what day it is | Convert it to Monday
[13 empty] | Start Date | 2009-06-01 |  | Monday |  |  | Sunday
[13 empty] | The Monday | 2009-06-01 |  | Monday |  |  | Monday | 39965
Tuesday
Wednesday
Thursday
Friday
Saturday
#For Tab 5 - Schedule Plan
#NO WORK HOLIDAY DATES
Week of | 2009-06-01 |  |  |  |  | 2009-06-08 |  |  |  |  | 2009-06-15 |  |  |  |  | 2009-06-22 |  |  |  |  | 2009-06-29 |  |  |  |  | 2009-07-06 |  |  |  |  | 2009-07-13 |  |  |  |  | 2009-07-20 |  |  |  |  | 2009-07-27 |  |  |  |  | 2009-08-03 |  |  |  |  | 2009-08-10 |  |  |  |  | 2009-08-17 |  |  |  |  | 2009-08-24 |  |  |  |  | 2009-08-31 |  |  |  |  | 2009-09-07 |  |  |  |  | 2009-09-14 |  |  |  |  | 2009-09-21 |  |  |  |  | 2009-09-28 |  |  |  |  | 2009-10-05 |  |  |  |  | 2009-10-12 |  |  |  |  | 2009-10-19 |  |  |  |  | 2009-10-26 |  |  |  |  | 2009-11-02 |  |  |  |  | 2009-11-09 |  |  |  |  | 2009-11-16 |  |  |  |  | 2009-11-23
Day Date | 39965 | 39966 | 39967 | 39968 | 39969 | 39972 | 39973 | 39974 | 39975 | 39976 | 39979 | 39980 | 39981 | 39982 | 39983 | 39986 | 39987 | 39988 | 39989 | 39990 | 39993 | 39994 | 39995 | 39996 | 39997 | 40000 | 40001 | 40002 | 40003 | 40004 | 40007 | 40008 | 40009 | 40010 | 40011 | 40014 | 40015 | 40016 | 40017 | 40018 | 40021 | 40022 | 40023 | 40024 | 40025 | 40028 | 40029 | 40030 | 40031 | 40032 | 40035 | 40036 | 40037 | 40038 | 40039 | 40042 | 40043 | 40044 | 40045 | 40046 | 40049 | 40050 | 40051 | 40052 | 40053 | 40056 | 40057 | 40058 | 40059 | 40060 | 40063 | 40064 | 40065 | 40066 | 40067 | 40070 | 40071 | 40072 | 40073 | 40074 | 40077 | 40078 | 40079 | 40080 | 40081 | 40084 | 40085 | 40086 | 40087 | 40088 | 40091 | 40092 | 40093 | 40094 | 40095 | 40098 | 40099 | 40100 | 40101 | 40102 | 40105 | 40106 | 40107 | 40108 | 40109 | 40112 | 40113 | 40114 | 40115 | 40116 | 40119 | 40120 | 40121 | 40122 | 40123 | 40126 | 40127 | 40128 | 40129 | 40130 | 40133 | 40134 | 40135 | 40136 | 40137 | 40140 | 40141 | 40142 | 40143 | 40144
HOLIDAY? | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No
39913
39916
39918
39951
39998
39997 | [24 empty] | X
40098 | [95 empty] | X
40143 | [128 empty] | X
40172
40179
|  | SUM: | [5 empty] | For Pie chart 2 in Today's View - TOTAL PROJECT |  |  |  | For Pie chart 1 in Today - Today's Tasks |  |  |  | For Time Line in Today |  |  | Not subtracting weekends & holidays… | [6 empty] | Task is underway but is behind schedule.
|  | #REF! |  | Today | 2026-07-29 | CODE TASKS FOR THIS WEEK…. Ugh/ |  | Tasks Completed | 13.64% |  |  | Behind Schedule Tasks - Started | 0 |  |  | Project Start | 39965 |  | Project Days Passed | 6267 | 12790% |  |  |  |  | Task is late and has not yet been started.
[8 empty] | Tasks In Progress | 4.545% |  |  | Behind Schedule Tasks - Not Yet Started | 0 |  |  | Today | 46232 |  | Project Days Left | -6218 | -12690%
|  | AMOUNT | [5 empty] | Tasks Not Yet Started | 81.82% |  |  | Regularly Scheduled Tasks | 1 |  |  | Project End | 40014
|  | 19 |  |  | Total tasks | 22 | [5 empty] | QC | 1 | [5 empty] | QC | 49
[8 empty] | QC | 100% | [10 empty] | 49
Note on N30: From user input
Note on N31: The Monday of the first week of project commencement...

## HiddenWkly (hidden)
"Weekly" (or whatever) task view | [10 empty] | Task Not Yet Started |  |  | Task is underway but is behind schedule.
[11 empty] | Task Complete |  |  | Task is late and has not yet been started.
start date entry | 2009-06-04 | [9 empty] | Task In Progress |  |  | Task is scheduled for work during this timeframe.
End date entry | 2009-07-20
[26 empty] | TO ORDER BY TASK OWNER |  |  |  |  | Actual list for Tab
TASK NUMBER | ID for Task | "Rank" to list | Repeat Task for VLOOKUP | TASK | Estimated Start Date | Estimated End Date | Owner | Owner for List | Actual Start Date | Actual End Date |  | On Track Status | Task should be done - Started | Task Should be done - Not Yet Started | Reg Scheduled Task during this time | Sum | Unique Rank for Owners, by task | Owner Rank | Task Owner | List of tasks | Task Name | Est Start Date | Est End Date - DUE DATE | Completion Status | On Track Status | Possible Owner | Task Number | Yes to tasks | Unique Rank |  | RANK | Owner | Owner for Tab | Task | Task Status | Due Date | Completion Status
1 | [14 empty] | No | 1 | 18 | 6 | John Smith | 1 | Assign Resources | 39972 | 39973 | Task In Progress | Task is scheduled for work during this timeframe. | Unassigned | 0 |  |  | Jane Doe | 1 | Jane Doe | Jane Doe | Create Communications Plan | Task Not Yet Started | 2009-06-17 | Task is scheduled for work during this timeframe.
2 | [14 empty] | No | 3 | 14 | 3 | Kim Lee | 2 | Create Project Plan | 39973 | 39980 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Jane Doe | 9 | 9 | 1 | John Doe | 2 | Jane Doe |  | Project Kick-Off Meeting | Task Not Yet Started | 2009-06-19 | Task is scheduled for work during this timeframe.
3 |  |  |  | Project Feasibility Study | 39965 | 39967 | John Doe | John Doe | 2009-06-01 | 2009-06-02 | Task Complete |  | No | No | No | 6 | 1 | 1 | Jane Doe | 3 | Create Communications Plan | 39979 | 39981 | Task Not Yet Started | Task is scheduled for work during this timeframe. | John Doe | 1 | 1 | 4 | Jane and John | 3 | Jane Doe |  | Create Phase 1 Plan and Definition | Task Not Yet Started | 2009-06-24 | Task is scheduled for work during this timeframe.
4 |  |  |  | Cost Benefit Analysis | 39966 | 39968 | Jane and John | Jane and John | 2009-06-02 | 2009-06-03 | Task Complete |  | No | No | No | 10 | 2 | 1 | Jane Doe | 4 | Project Kick-Off Meeting | 39983 | 39983 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Jane and John | 1 | 1 | 5 | John Smith | 4 | Jane Doe |  | Phase 1 Execution Kick-Off | Task Not Yet Started | 2009-06-24 | Task is scheduled for work during this timeframe.
5 | [14 empty] | No | 15 | 3 | 1 | Jane Doe | 5 | Create Phase 1 Plan and Definition | 39986 | 39988 | Task Not Yet Started | Task is scheduled for work during this timeframe. | John Smith | 1 | 1 | 6 | Kim Lee | 5 | Jane Doe |  | Close Phase 1 | Task Not Yet Started | 2009-07-03 | Task is scheduled for work during this timeframe.
6 |  |  |  | Project Definition | 39970 | 39972 | Jane Doe | Jane Doe | 2009-06-06 | 2009-06-09 | Task Complete |  | No | No | No | 21 | 4 | 1 | Jane Doe | 6 | Phase 1 Execution Kick-Off | 39988 | 39988 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Kim Lee | 2 | 2 | 3 | Chris Johnson | 6 | Jane Doe |  | Close Phase 2 | Task Not Yet Started | 2009-07-14 | Task is scheduled for work during this timeframe.
7 | 7 | 1 | Assign Resources | Assign Resources | 39972 | 39973 | John Smith | John Smith | 2009-06-08 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 28 | 16 | 4 | John Doe | 7 | Communicate Phase 1 Progress | 39989 | 39995 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Chris Johnson | 4 | 4 | 2 | Alex Singh | 7 | Jane Doe |  | Project Closure Meeting | Task Not Yet Started | 2009-07-16 | Task is scheduled for work during this timeframe.
8 | 8 | 2 | Create Project Plan | Create Project Plan | 39973 | 39980 | Kim Lee | Kim Lee |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 36 | 17 | 5 | Jane and John | 8 | Change Control Processes | 39995 | 39996 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Alex Singh | 0 |  |  | Marketing Department | 8 | Jane Doe |  | Performance Appraisal | Task Not Yet Started | 2009-07-18 | Task is scheduled for work during this timeframe.
9 | 9 | 3 | Create Communications Plan | Create Communications Plan | 39979 | 39981 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 45 | 5 | 1 | Jane Doe | 9 | Close Phase 1 | 39996 | 39997 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Marketing Department | 0 |  |  | Production Team | 9 | Jane Doe |  | Project Debrief Report | Task Not Yet Started | 2009-07-20 | Task is scheduled for work during this timeframe.
10 | [14 empty] | No | 55 | 10 | 2 | Chris Johnson | 10 | Create Phase 2 Plan and Definition | 39995 | 39997 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Production Team | 1 | 1 | 7 | 0 | 10 | Chris Johnson | Chris Johnson | Create Phase 2 Plan and Definition | Task Not Yet Started | 2009-07-03 | Task is scheduled for work during this timeframe.
11 | 11 | 4 | Project Kick-Off Meeting | Project Kick-Off Meeting | 39983 | 39983 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 66 | 11 | 2 | Chris Johnson | 11 | Phase 2 Execution Kick-Off | 40000 | 40000 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 11 | Chris Johnson |  | Phase 2 Execution Kick-Off | Task Not Yet Started | 2009-07-06 | Task is scheduled for work during this timeframe.
12 | [14 empty] | No | 78 | 12 | 2 | Chris Johnson | 12 | Communicate Phase 2 Progress | 40001 | 40003 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 12 | Chris Johnson |  | Communicate Phase 2 Progress | Task Not Yet Started | 2009-07-09 | Task is scheduled for work during this timeframe.
13 | 13 | 5 | Create Phase 1 Plan and Definition | Create Phase 1 Plan and Definition | 39986 | 39988 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 91 | 13 | 2 | Chris Johnson | 13 | Change Control Processes | 39995 | 39996 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 13 | Chris Johnson |  | Change Control Processes | Task Not Yet Started | 2009-07-02 | Task is scheduled for work during this timeframe.
14 | 14 | 6 | Phase 1 Execution Kick-Off | Phase 1 Execution Kick-Off | 39988 | 39988 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 105 | 6 | 1 | Jane Doe | 14 | Close Phase 2 | 40007 | 40008 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 14 | Kim Lee | Kim Lee | Create Project Plan | Task Not Yet Started | 2009-06-16 | Task is scheduled for work during this timeframe.
15 | 15 | 7 | Communicate Phase 1 Progress | Communicate Phase 1 Progress | 39989 | 39995 | John Doe | John Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 120 | 19 | 7 | Production Team | 15 | Project Delivery | 40009 | 40009 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 15 | Kim Lee |  | Project Feedback Form | Task Not Yet Started | 2009-07-18 | Task is scheduled for work during this timeframe.
16 | 16 | 8 | Change Control Processes | Change Control Processes | 39995 | 39996 | Jane and John | Jane and John |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 136 | 7 | 1 | Jane Doe | 16 | Project Closure Meeting | 40010 | 40010 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 16 | John Doe | John Doe | Communicate Phase 1 Progress | Task Not Yet Started | 2009-07-01 | Task is scheduled for work during this timeframe.
17 | 17 | 9 | Close Phase 1 | Close Phase 1 | 39996 | 39997 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 153 | 8 | 1 | Jane Doe | 17 | Performance Appraisal | 40010 | 40012 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 17 | Jane and John | Jane and John | Change Control Processes | Task Not Yet Started | 2009-07-02 | Task is scheduled for work during this timeframe.
18 | [14 empty] | No | 171 | 15 | 3 | Kim Lee | 18 | Project Feedback Form | 40010 | 40012 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 18 | John Smith | John Smith | Assign Resources | Task In Progress | 2009-06-09 | Task is scheduled for work during this timeframe.
19 | 19 | 10 | Create Phase 2 Plan and Definition | Create Phase 2 Plan and Definition | 39995 | 39997 | Chris Johnson | Chris Johnson |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 190 | 9 | 1 | Jane Doe | 19 | Project Debrief Report | 40011 | 40014 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 19 | Production Team | Production Team | Project Delivery | Task Not Yet Started | 2009-07-15 | Task is scheduled for work during this timeframe.
20 | 20 | 11 | Phase 2 Execution Kick-Off | Phase 2 Execution Kick-Off | 40000 | 40000 | Chris Johnson | Chris Johnson |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 210 | [9 empty] | 0 |  |  |  | 0 | 20
21 | 21 | 12 | Communicate Phase 2 Progress | Communicate Phase 2 Progress | 40001 | 40003 | Chris Johnson | Chris Johnson |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 231 | [9 empty] | 0 |  |  |  | 0 | 21
22 | 22 | 13 | Change Control Processes | Change Control Processes | 40003 | 40004 | Chris Johnson | Chris Johnson |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 253 | [9 empty] | 0 |  |  |  | 0 | 22
23 | 23 | 14 | Close Phase 2 | Close Phase 2 | 40007 | 40008 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 276 | [9 empty] | 0 |  |  |  | 0 | 23
24 | [14 empty] | No | 300 | [9 empty] | 0 |  |  |  | 0 | 24
25 | 25 | 15 | Project Delivery | Project Delivery | 40009 | 40009 | Production Team | Production Team |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 325 | [9 empty] | 0 |  |  |  | 0 | 25
26 | 26 | 16 | Project Closure Meeting | Project Closure Meeting | 40010 | 40010 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 351 | [9 empty] | 0 |  |  |  | 0 | 26
27 | 27 | 17 | Performance Appraisal | Performance Appraisal | 40010 | 40012 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 378 | [9 empty] | 0 |  |  |  | 0 | 27
28 | 28 | 18 | Project Feedback Form | Project Feedback Form | 40010 | 40012 | Kim Lee | Kim Lee |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 406 | [9 empty] | 0 |  |  |  | 0 | 28
29 | 29 | 19 | Project Debrief Report | Project Debrief Report | 40011 | 40014 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 435 | [9 empty] | 0 |  |  |  | 0 | 29
30 | [14 empty] | No | 465 | [9 empty] | 0 |  |  |  | 0 | 30
31 | [14 empty] | No | 496 | [9 empty] | 0 |  |  |  | 0 | 31
32 | [14 empty] | No | 528 | [9 empty] | 0 |  |  |  | 0 | 32
33 | [14 empty] | No | 561 | [9 empty] | 0 |  |  |  | 0 | 33
34 | [14 empty] | No | 595 | [9 empty] | 0 |  |  |  | 0 | 34
35 | [14 empty] | No | 630 | [9 empty] | 0 |  |  |  | 0 | 35
36 | [14 empty] | No | 666 | [9 empty] | 0 |  |  |  | 0 | 36
37 | [14 empty] | No | 703 | [9 empty] | 0 |  |  |  | 0 | 37
38 | [14 empty] | No | 741 | [9 empty] | 0 |  |  |  | 0 | 38
39 | [14 empty] | No | 780 | [9 empty] | 0 |  |  |  | 0 | 39
40 | [14 empty] | No | 820 | [9 empty] | 0 |  |  |  | 0 | 40
41 | [14 empty] | No | 861 | [9 empty] | 0 |  |  |  | 0 | 41
42 | [14 empty] | No | 903 | [14 empty] | 42
43 | [14 empty] | No | 946 | [14 empty] | 43
44 | [14 empty] | No | 990 | [14 empty] | 44
45 | [14 empty] | No | 1035 | [14 empty] | 45
46 | [14 empty] | No | 1081 | [14 empty] | 46
47 | [14 empty] | No | 1128 | [14 empty] | 47
48 | [14 empty] | No | 1176 | [14 empty] | 48
49 | [14 empty] | No | 1225 | [14 empty] | 49
50 | [14 empty] | No | 1275 | [14 empty] | 50
51 | [14 empty] | No | 1326 | [14 empty] | 51
52 | [14 empty] | No | 1378 | [14 empty] | 52
53 | [14 empty] | No | 1431 | [14 empty] | 53
54 | [14 empty] | No | 1485 | [14 empty] | 54
55 | [14 empty] | No | 1540 | [14 empty] | 55
56 | [14 empty] | No | 1596 | [14 empty] | 56
57 | [14 empty] | No | 1653 | [14 empty] | 57
58 | [14 empty] | No | 1711 | [14 empty] | 58
59 | [14 empty] | No | 1770 | [14 empty] | 59
60 | [14 empty] | No | 1830 | [14 empty] | 60
61 | [14 empty] | No | 1891 | [14 empty] | 61
62 | [14 empty] | No | 1953 | [14 empty] | 62
63 | [14 empty] | No | 2016 | [14 empty] | 63
64 | [14 empty] | No | 2080 | [14 empty] | 64
65 | [14 empty] | No | 2145 | [14 empty] | 65
66 | [14 empty] | No | 2211 | [14 empty] | 66
67 | [14 empty] | No | 2278 | [14 empty] | 67
68 | [14 empty] | No | 2346 | [14 empty] | 68
69 | [14 empty] | No | 2415 | [14 empty] | 69
70 | [14 empty] | No | 2485 | [14 empty] | 70
71 | [14 empty] | No | 2556 | [14 empty] | 71
72 | [14 empty] | No | 2628 | [14 empty] | 72
73 | [14 empty] | No | 2701 | [14 empty] | 73
74 | [14 empty] | No | 2775 | [14 empty] | 74
75 | [14 empty] | No | 2850 | [14 empty] | 75
76 | [14 empty] | No | 2926 | [14 empty] | 76
77 | [14 empty] | No | 3003 | [14 empty] | 77
78 | [14 empty] | No | 3081 | [14 empty] | 78
79 | [14 empty] | No | 3160 | [14 empty] | 79
80 | [14 empty] | No | 3240 | [14 empty] | 80
81 | [14 empty] | No | 3321 | [14 empty] | 81
82 | [14 empty] | No | 3403 | [14 empty] | 82
83 | [14 empty] | No | 3486 | [14 empty] | 83
84 | [14 empty] | No | 3570 | [14 empty] | 84
85 | [14 empty] | No | 3655 | [14 empty] | 85
86 | [14 empty] | No | 3741 | [14 empty] | 86
87 | [14 empty] | No | 3828 | [14 empty] | 87
88 | [14 empty] | No | 3916 | [14 empty] | 88
89 | [14 empty] | No | 4005 | [14 empty] | 89
90 | [14 empty] | No | 4095 | [14 empty] | 90
91 | [14 empty] | No | 4186 | [14 empty] | 91
92 | [14 empty] | No | 4278 | [14 empty] | 92
93 | [14 empty] | No | 4371 | [14 empty] | 93
94 | [14 empty] | No | 4465 | [14 empty] | 94
95 | [14 empty] | No | 4560 | [14 empty] | 95
96 | [14 empty] | No | 4656 | [14 empty] | 96
97 | [14 empty] | No | 4753 | [14 empty] | 97
98 | [14 empty] | No | 4851 | [14 empty] | 98
99 | [14 empty] | No | 4950 | [14 empty] | 99
100 | [14 empty] | No | 5050 | [14 empty] | 100
Formulas:
Due Date = IF(SUM(S10:S109)<[Sum],"",VLOOKUP([RANK],S10:AA109,7,FALSE()))