## Instructions
Project Process Agreement (PPA)
Introduction The PPA is a key artifact in the eXpedited Life Cycle (XLC) that documents the agreement between the key stakeholders regarding which reviews will be conducted for the project, which artifacts are appropriate, and which tests are necessary. The PPA contains a complexity worksheet, a list of artifacts, a list of reviews, a list of tests, and a signature sheet. The signature sheet is populated with the selected items from each list. The PPA can be provided to a contractor as part of a request for proposal. As a proposal input, the PPA helps scope the expected work and timeframe for completion. Consider engaging someone with IT development experience to help determine your project's complexity and complete your draft PPA. Potential sources of support include Division of IT Governance (DITG), and Project Consultants assigned by the CMS Intake Review Team (CIRT). The CIRT reviews your IT Intake Request Form which starts the XLC process and can coordinate resources. Instructions Note: Tab specific instructions are provided in red boxes on each tab. Cells with a green background can be edited and are used to tailor the PPA to your project. 1. Complete the Complexity Worksheet tab to select an XLC lane. Completing the Complexity Worksheet identifies a Project Complexity Level: Complexity Level 1, Complexity Level 2 or Complexity Level 3. 2. The XLC lane (see CMS Expedited Life Cycle Process: Detailed Description, Figure 3, The Expedited Life Cycle Model) identifies a set of stage gate reviews for your project based on its complexity. Use the reviews in the selected XLC lane to guide completion of the XLC PPA - Stage Gates tab. 3. Each review has a set of supporting artifacts as shown in Table 4, CMS XLC Artifacts by Phase (see CMS Expedited Life Cycle Process: Detailed Description). Use the artifacts listed to guide completion of the XLC PPA - Artifacts tab. 4. Complete the XLC PPA - Testing Functions tab based on the requirements of your project. 5. Get signatures. The XLC PPA - Signature tab automatically fills in information gathered from the other 4 tabs. Print the signature tab and obtain the needed signatures.

## Complexity Worksheet
|  | PROJECT PROCESS AGREEMENT |  | Provide (New) | Hold
|  | Complexity Worksheet |  | Provide (Update) | Waive
| Project Name |  | Directions: Enter Information into green cells | Waive | Combine
| Project Description |  | 1. Enter Project Name, Description, and Release to the left.
| Release |  | 2. Review project characteristics, rating guidance and enter a
complexity level (1, 2 or 3) for each characteristic.
Project Characteristic | Complexity Level | Rating Guidance | Your Project’s Level? 1, 2, or 3
Shared Services Implications | 3 | Creating new shared service(s)
| 2 | Modifying existing shared service(s)
| 1 | Using existing shared service(s) as is
Program / Business Process Profile (with Design / Development Implications) | 3 | New business process model, or process that may lead to significant cross program coordination and/or significant coordination with external business partners and/or developing new code on a new or existing system
| 2 | Some new requirements and information flows, minor changes to code in an existing system
| 1 | Requirements and information flows are similar to current programs, no new code
Privacy Implications | 3 | New system, service or environment with any Personally Identifiable Information (PII), Personal Health Information (PHI), or Federal Taxpayer Information (FTI) data that is used, accessed, stored, or transmitted OR Changes to a system, service or environment that has implications to PII, PHI, or FTI data that is used, accessed, stored, or transmitted
| 2 | N/A – Privacy is either Complexity Level 1 or 3
| 1 | No PII, PHI, or FTI data OR Changes to a system, service or environment that has no implications to PII, PHI, or FTI data that is used, accessed, stored, or transmitted
Security Implications (based on Information Type [1] processed, accessed, stored, or transmitted) | 3 | New system, service or environment with any: § Investigation, intelligence-related, and security information § Mission-critical information OR Changes to existing service, system or environment that affects the state of any: § Investigation, intelligence-related, and security information § Mission-critical information
| 2 | New system, service or environment with any:  Information about persons  Financial, budgetary, commercial, proprietary or trade secret information  Internal administration  Other Federal agency information  New technology or controlled scientific information  Operational information  System configuration management information OR Changes to existing service, system or environment that affects the state of any:  Information about persons  Financial, budgetary, commercial, proprietary or trade secret information  Internal administration  Other Federal agency information  New technology or controlled scientific information  Operational information  System configuration management information
| 1 | New system, service or environment with any:  Other sensitive information  Public information OR Changes to existing service, system or environment that affects the state of any:  Other sensitive information  Public information OR No implications to any security controls
Data Complexity (ties to data’s financial implications) | 3 | § Completely new data for the agency § Data is serving as a corporate asset
| 2 | Some new data is introduced
| 1 | § Data is similar to existing agency systems § Data scope focused on one service/system/domain
Interface Complexity | 3 | New interface or change(s) to an existing interface that involves: § Interaction with non-Federal agencies in business rules § Data access via internet § Extensive interaction with other systems, especially external organizations and agencies § Shared service or system access via internet § Extensive interactions with other systems, databases, or new / updated COTS products
| 2 | New interface or change(s) to an existing interface that involves: § Interaction with other Federal agencies in business rules § Data access via extranet § Moderate interaction with other systems, especially external organizations and agencies § Shared service or system access via extranet § Moderate interaction with other systems, especially external organizations and agencies
| 1 | New interface or change(s) to an existing interface that involves: § No interaction w/ external organization in business rules § Data access via internal HHS network access only § No interaction with other systems, especially external organizations and agencies § Shared service or system access via internal HHS network access only § No interaction with other systems, databases, or new / updated COTS products OR No changes to any interface
Project Complexity
[1] Information Type definitions are from CMS System Security and e-Authentication Assurance Levels by Information Type

## XLC PPA - Artifacts
| PROJECT PROCESS AGREEMENT -- | ARTIFACTS |  |  |  |  | Provide (New) | Hold
|  |  |  | Directions: Enter Information into green cells |  |  | Provide (Update) | Waive
| Project Name | 0 |  | Review artifacts list & details in column A-D. Add any project defined artifacts in row 50-52. |  |  | Waive | Combine
| Project Description | 0 |  | Record agreement for the project's initial release in column E and F. |  |  | Combine
| Release | 0 |  | Provide justifications for Waive or Combine in column G.
Complexity Level
A | B | C | D | E | F | G
# | ARTIFACT | Domain | ARTIFACT DEFINITION | CMS IT PROJECT
|  |  |  | PROJECT AGREEMENT | AUTHOR (specific for Project) | JUSTIFICATION and/or NOTES
1 | IT Intake Request Form | Systems Development | Collect basic new project information from a Business Owner | Provide (New)
2 | Enterprise Architecture Analysis Artifacts | Systems Development | Consists of models, diagrams, tables, and narrative, which show the proposed solution's integration into CMS operations from both a logical and technical perspective. | Provide (New)
3 | Business Case | Systems Development | Describes the basic aspects of the proposed IT project; why, what, when, and how. | Provide (New)
4 | Requirements Document | Systems Development | Identifies the business and technical capabilities and constraints of the IT project. | Provide (New)
5 | High-Level Technical Design | Systems Development | Conceptual functions and stakeholder interactions | Provide (New)
6 | Section 508 Product Assessment Package | Systems Development | Provides information regarding compliance with required accessibility standards. | Provide (New)
7 | Acquisition Strategy | Project Management | The overall objective of an Acquisition Strategy is to document and inform stakeholders about how acquisitions will be planned, executed, and managed throughout the life of a project or investment. | Provide (New)
8 | Project Process Agreement | Project Management | Authorizes and documents the justifications for using, not using, or combining specific stage gate reviews and the selection of specific work products. | Provide (New)
9 | Project Charter | Project Management | Authorizes the existence of a project and provides the authority to proceed and apply organizational resources. | Provide (New)
10 | Information Security Risk Assessment | Security | Contains a list of threats and vulnerabilities, an evaluation of current security controls, their resulting risk levels, and any recommended safeguards to reduce risk exposure. | Provide (New)
11 | System Security Plan | Security | Documents the system's security level and describes managerial, technical and operational security controls. | Provide (New)
12 | Privacy Impact Assessment | Security | Ensures no collection, storage, access, use or dissemination of identifiable respondent information that is not both needed and permitted. | Provide (New)
13 | Logical Data Model | Systems Development | Represents CMS data within the scope of a system development project and shows the specific entities, attributes, and relationships involved in a business function's view of information | Provide (New)
14 | Release Plan | Systems Development | Describes what portions of the system functionality will be implemented in which release and why. | Provide (New)
15 | Project Management Plan | Project Management | Provides detailed plans, processes, and procedures for managing and controlling the life cycle activities. | Provide (New)
16 | System of Records | Systems Development | Informs the public of collection of information about its citizens from which data are retrieved by a unique identifier. | Provide (New)
17 | Test Plan | Systems Development | Describes the overall scope, technical and management approach, resources, and schedule for all intended test activities associated with validation testing. | Provide (New)
18 | Performance Test Plan and Results | Systems Development | Performance tests help to determine a system’s and application’s limitations, as well as the maximum number of active users utilizing the application throughout servers. | Provide (New)
19 | Project Schedule | Project Management | Integrated Master Schedule showing all activities required to complete a project and their interdependencies. | Provide (New)
20 | Risk Register | Project Management | Captures the results of a qualitative and quantitative risk analysis and the results of planning for response. | Provide (New)
21 | Issues List | Project Management | Keeps a record of all issues that occur during the life of a project. | Provide (New)
22 | Action Items | Project Management | Record and manage assignments that generally result from meeting discussions. | Provide (New)
23 | Decision Log | Project Management | Documents the decisions made over the course of the project. | Provide (New)
24 | Lessons Learned Log | Project Management | Identifies and records lessons learned and future recommendations. | Provide (New)
25 | Contingency Plan | Security | Describes the strategy for ensuring system recovery in accordance with stated recovery time and recovery point objectives. | Provide (New)
26 | System Design Document | Systems Development | Documents both high-level system design and low-level detailed design specifications. | Provide (New)
27 | Database Design Document | Systems Development | Describes the design of a database and the software units used to access or manipulate the data. | Provide (New)
28 | Physical Database / Model | Systems Development | represents CMS data within the scope of a system development project and shows the specific tables, columns, and constraints involved in a physical implementation's view of information. | Provide (New)
29 | Interface Control Document | Systems Development | Describes the relationship between a source system and a target system. | Provide (New)
30 | Data Use Agreement | Systems Development | Informs data users of confidentiality requirements and obtains their agreement to abide by these requirements. | Provide (New)
31 | Test Case Specification | Systems Development | Describes the purpose of a specific test, identifies the required inputs and expected results, provides step-by-step procedures for executing the test, and outlines the pass/fail criteria for determining acceptance. | Provide (New)
32 | Data Conversion Plan | Systems Development | Describes the strategies involved in converting data from an existing system/application to another hardware and/or software environment. | Provide (New)
33 | Computer Match/Interagency Agreements | Systems Development | Documents agreements permitting computerized comparison of systems of records which contain personally identifiable information. | Provide (New)
34 | Implementation Plan | Systems Development | Describes how the automated system/application or IT situation will be installed, deployed and transitioned into an operational system or situation. | Provide (New)
35 | User Manual | Systems Development | Explains how a novice business user is to use the automated system or application from a business function perspective. | Provide (New)
36 | Operations & Maintenance Manual | Systems Development | Guides those who maintain, support and/or use the system in a day-to-day operations environment. | Provide (New)
37 | Business Product/Code | Systems Development | The implemented system (hardware, software, and trained personnel) that addresses a business need. | Provide (New)
38 | Version Description Document | Systems Development | Identifies, tracks and controls versions of automated systems and/or applications to be released to the operational environment. | Provide (New)
39 | Training Plan | Systems Development | Describes the overall goals, learning objectives, and activities that are to be performed to develop, conduct, control, and evaluate instruction. | Provide (New)
40 | Test Summary Report | Systems Development | Summarizes test activities and results including any variances from expected behavior. | Provide (New)
41 | Training Artifacts | Systems Development | Products required to satisfy the training plan which may include, web-based instruction, instructor guides, student guides, exercise materials, and training records. | Provide (New)
42 | Contingency Test Plan (tabletop) | Security | Documents planned tests of strategies, personnel, procedures, and resources that respond to a supported applications/system interruption. | Provide (New)
43 | Security Assessment | Security | Describes the completed assessment phases following established assessment procedure and reporting procedures. | Provide (New)
44 | Authorization Package | Security | Demonstrates and to validates that appropriate security controls exist to safeguard the system. | Provide (New)
45 | Plan of Action & Milestones | Security | Reports the status of known security weaknesses with associated Plan of Action and Milestones. | Provide (New)
46 | CMS CIO Provided Authorization To Operate | Security | CIO approval of System Certification and System Accreditation authorizing the system to become operational. | Provide (New)
47 | System Disposition Plan | Systems Development | Addresses how the various components of an automated system are handled at the completion of operations. | Provide (New)
48 | Post Implementation Report | Systems Development | Describes the performance of a system/application during normal operations. | Provide (New)
49 | Annual Operational Analysis Report | Systems Development | Combines elements from the CPIC evaluation and performance of the system/application during normal operations. | Provide (New)
50 | Project Closeout Report | Project Management | Assesses the project, ensures completion, and derives lessons learned and best practices to be applied to future projects. | Provide (New)
51 | Monitoring Reports | Systems Development | Documents and reports security assessment results. | Provide (New)
52 | Project Defined Artifact 1 |  | A project defined artifact that …
53 | Project Defined Artifact 2 |  | A project defined artifact that …
54 | Project Defined Artifact 3 |  | A project defined artifact that …
|  | ARTIFACTS TO PROVIDE NEW DOCUMENTS: |  | 51
|  | ARTIFACTS TO PROVIDE UPDATES TO EXISTING DOCS: |  | 0
|  | ARTIFACTS COMBINED: |  | 0
|  | ARTIFACTS WAIVED: |  | 0

## XLC PPA - Stage Gates
| PROJECT PROCESS AGREEMENT | -- STAGE GATES |  | Directions: Enter Information into green cells |  |  | Perform | Hold
|  |  |  | Review stage gate list & details in column A-D. Add any project defined reviews in row 14&15. |  |  | Delegate | Waive
| Project Name | 0 |  | Record agreement for the project's initial release in column E and F. |  |  | Waive | Combine
| Project Description | 0 |  | Provide justifications for Waive or Combine in column G. |  |  | Combine
| Release | 0 |  | Consider risks in column H, provide mitigation in justifications for combined or waived reviews
Complexity Level
A | B | C | D | E | F | G | H
# | STAGE GATE REVIEW | CMS Governance / Delegated to Projects | STAGE GATE DEFINITION | CMS IT PROJECT |  |  | RISK OF WAIVING REVIEW
|  |  |  | PROJECT AGREEMENT | AUTHOR (specific for Project) | JUSTIFICATION and/or NOTES
1 | Architecture Review (AR) | Governance | Determine whether the proposed project potentially duplicates, interferes, contradicts or can leverage another investment that already exists, is proposed, under development, or planned for near-term disposition. The business need is assessed to determine if it is sound and conforms to the CMS Enterprise Architecture. | Perform |  |  | When AR is waived then high level technical design begins with incomplete understanding of desired solution and its relationship to existing systems. This usually leads to unnecessary redundancy and missed opportunity to leverage other IT efforts. It often leads to solutions that conflict with CMS IT strategy. This review is a governance level review.
2 | Investment Selection Review (ISR) | Governance | Determine if it is a sound, viable, and worthy of funding, support and inclusion in the organization's IT Investment Portfolio. The business need and objectives are reviewed to ensure the effort supports CMS' overall mission and objectives and will not comprise initiatives on the horizon. | Perform |  |  | When ISR is waived then project is added to CMS portfolio and funds are committed without an assessment of soundness, viability, and worthiness. This review is a governance level review.
3 | Project Baseline Review (PBR) | May be Delegated | Obtain management approval that the scope, cost and schedule that have been established for the project are adequately documented and that the project management strategy is appropriate for moving the project forward in the life cycle. The PBR includes review of the budget, risk, and user requirements for the investment; emphasis should be on the total cost of ownership and not just development or acquisition costs. | Perform |  |  | When PBR is waived then work begins without a baselined plan complicating ability to provide direction and track progress against integrated cost, schedule, and technical baselines.
4 | Requirements Review (RR) | May be Delegated | Verify that the requirements are complete, accurate, consistent and problem-free; evaluate the responsiveness to the business requirements; ensure that the requirements are a suitable basis for subsequent design activities; ensure traceability between the business and system requirements; and affirm final agreement regarding the content of the Requirements Document by the business owner. | Perform |  |  | When RR is waived then design begins without requirement reconciliation with business need and there is no assurance that the solution can be verified in the test phase. Without a RR, any unexpected requirements issues that drive cost and schedule variances are likely to drive further variances later in the lifecycle.
5 | Preliminary Design Review (PDR) | Governance | Verify the preliminary design satisfies the functional and nonfunctional requirements and is in conformance with CMS's Technical Reference Architecture (TRA); determine technical solution's completeness and consistency with CMS standards; raise and resolve any technical and/or project-related issues, to identify and mitigate project, technical, security, and/or business risks affecting continued detailed design and subsequent development, testing, implementation, and operations and maintenance activities. | Perform |  |  | When PDR is waived then detailed design begins without high level application architectural review to validate software and external interfaces or verification that design satisfies functional and non-functional requirements. Without a PDR, any unexpected high level design issues that drive cost and schedule variances are likely to drive further variances later in the lifecycle. This review is a governance level review.
6 | Detailed Design Review (DDR) | Governance | Verify the final design satisfies the functional and nonfunctional requirements and is in conformance with CMS's Technical Reference Architecture (TRA); determine technical solution's completeness and consistency with CMS standards; raise and resolve any technical and/or project-related issues, to identify and mitigate project, technical, security, and/or business risks affecting continued detailed design and subsequent development, testing, implementation, and operations and maintenance activities. | Perform |  |  | When DDR is waived then development begins without assurance that design meets stated business needs. Solutions developed from incomplete or unworkable design are likely to have performance gaps that will require unexpected time and money to fix. Without a DDR, any unexpected detailed design issues that drive cost and schedule variances are likely to drive further variances in development, integration, and verification. This review is a governance level review.
7 | Validation Readiness Review (VRR) | May be Delegated | Ensure the system/application completed thorough Development Testing and is ready for turnover to the formal, controlled test environment for Validation testing. | Perform |  |  | When VRR is waived then the system/application begins testing without a formal hand off from development to test or rules for communication. This usually includes a controlled baseline, clear statement of what function is and is not working, formal turnover of any required work-around, or initiation of formal configuration management procedures. Waiving VRR often leads to an uncontrolled baseline with errors that cannot be reproduced. Without a VRR, any unexpected development issues that drive cost and schedule variances often drive further variances in integration, and verification.
8 | Implementation Readiness Rev (IRR) | May be Delegated | Ensure the system/application completed thorough Integration Testing and is ready for turnover to the formal, controlled test environment for Production Readiness | Perform |  |  | When IRR is waived then the system/application begins testing without a formal hand off from validation to implementation or rules for communication. This usually includes a controlled baseline, clear statement of what function is and is not working, formal turnover of any required work-around, or initiation of formal configuration management procedures. Waiving IRR often leads to an uncontrolled baseline with errors that cannot be reproduced. Without a IRR, any unexpected development issues that drive cost and schedule variances often drive further variances in integration, and verification.
7 | Production Readiness Review (PRR) | May be Delegated | Ensure the system/application completed its implementation processes according to plan and that it is ready for turnover to the Operations & Maintenance team and operational release into the Production environment. | Perform |  |  | When PRR is waived then the system/application moves to the production environment without without a formal handoff from implementation or rules for communication. Handoff usually includes verification that it meets performance requirements, clear statement of what function is and is not working, formal turnover of any required work-around, and reconciliation with operations and maintenance procedures. Without a PRR, any unexpected integration and verification issues that drive cost and schedule variances may drive further variances in the next level of testing as well as production.
9 | Operational Readiness Review (ORR) | Governance | Ensure the system/application completed its implementation processes according to plan and that it is ready for turnover to the Operations & Maintenance team and operational release into the Production environment. | Perform |  |  | When ORR is waived then the system/application is put into production without verification that it meets performance requirements and that operation and maintenance procedures ensure prompt system recovery without loss of data. Security is a significant component of ORR must be satisfied for the CIO to grant Authority to Operate. This review is a governance level review.
10 | Post Implementation Review (PIR) | Governance/Delegated (see Stage Gate Definition for more information) | The purpose of the PIR is twofold: (1) To ascertain the degree of success from the project; in particular, the extent to which it met its objectives, delivered planned levels of performance, and addressed the specific requirements as originally defined; (2) To enable the team, and future teams, to learn lessons from the project to improve future CMS work and solutions. In that context, the PIR examines whether the team achieved the results it planned for, what those results actually were, and what caused the results to be different from those planned for (if they are different). Newly-operational systems are required to schedule a Governance-level PIR with the Technical Review Board (TRB) within 6 to 12 months of going into production. Subsequent PIRs (e.g., for each release) should be conducted at the project level (i.e., as a delegated review) unless the system has undergone a total redesign. | Perform |  |  | When PIR is waived then a project's effectiveness is not evaluated. Did the project meet the expectations of the stakeholders? Did the project provide value? Any increasing operational costs or decreasing capability is not assessed, updates or workarounds are not considered, and inefficient solutions continue to operate. Any decreasing operational costs or improvements are not shared so other efforts can reap similar benefits. This review is a governance level review.
11 | Annual Operational Analysis (AOA) | May be Delegated | Review project performance to evaluate: Customer Satisfaction, Strategic and Business Results, Financial Performance, and Innovation. | Perform |  |  | When AOA is waived then a project's continued effectiveness is not evaluated. Any increasing operational costs or decreasing capability is not assessed, updates or work arounds are not considered, and inefficient solutions continue to operate. Any decreasing operational costs or improvements are not shared so other efforts can reap similar benefits.
12 | Disposition Review (DR) | May be Delegated | Ensure project has been completely and appropriately transitioned/disposed, thereby ending the lifecycle of the IT project. | Perform |  |  | When DR is waived, then a project is shut down without proper coordination of technical and contractual obligations. This can allow costs to accumulate for a system no longer in production.
13 | Project Defined Review 1 | May be Delegated | A project defined review that … |  |  |  | When Project Defined Review 1 is waived then ...
14 | Project Defined Review 2 | May be Delegated | A project defined review that … |  |  |  | When Project Defined Review 2 is waived then ...
15 | Project Defined Review 2 | May be Delegated | A project defined review that … |  |  |  | When Project Defined Review 2 is waived then ...
Note: Agreed upon artifacts are expected for all stage gate reviews, regardless of who conducts them
|  | GOVERNANCE STAGE GATE REVIEWS: |  | 13
|  | DELEGATED STAGE GATE REVIEWS: |  | 0
|  | WAIVED STAGE GATE REVIEW: |  | 0
|  | COMBINED STAGE GATE REVIEW: |  | 0

## XLC PPA - Testing Functions
| PROJECT PROCESS AGREEMENT -- | TESTS |  | Directions: Enter Information into green cells |  |  | Conducted | Hold
|  |  |  | Review test list & details in column A-D. Add any project defined tests in row 21&22. |  |  | Not Conducted | Waive
| Project Name | 0 |  | Record agreement for the project's initial release in column E and F. |  |  | Combine | Combine
| Project Description | 0 |  | Provide justifications for Waive or Combine in column G.
| Release | 0
Complexity Level
A | B | C | D | E | F | G
# | TEST | Business App, Infrastructure, or Both | TEST DEFINITION | CMS IT PROJECT
|  |  |  | PROJECT AGREEMENT | AUTHOR (specific for Project) | JUSTIFICATION and/or NOTES
Development Testing
1 | Unit Testing | Business App | Assesses and corrects the functionality and data of a business application’s individual code modules | Conducted
2 | Application Integration Testing | Business App | Assesses the interfaces, data, and interoperability of modules and systems within a single business application. | Conducted
3 | Section 508 Testing | Business App | Ensures that the Electronic Information Technology (EIT) product is compliant with applicable Section 508 Accessibility Standards. | Conducted
Validation Testing
4 | System Testing | Business App | Assesses the functionality and interoperability of a business application and multiple systems, such as databases, hardware, software, or communication devices, and their integration with infrastructure into an overall integrated system. | Conducted
5 | Functional Testing | Business App | Assesses the input/output functions of a business application against pre-defined functional and data requirements. | Conducted
6 | End-to-End Integration Testing | Business App | Evaluates whether the business applications and systems interoperate correctly, pass data and control correctly to one another, and store data correctly. | Conducted
7 | User Acceptance Testing | Business App | Assesses the overall functionality and interoperability of a business application’s solution in an operational mode. | Conducted
8 | Regression Testing | Both | Validates that modifications have not caused unintended functional or data results and that the application still complies with its specific requirements. Similarly, validates that infrastructure changes have not compromised dependent business applications. | Conducted
9 | Section 508 Testing | Both | Ensure that the EIT product is compliant with applicable Section 508 Accessibility Standards. | Conducted
10 | Infrastructure Testing | Infrastructure | Assesses the interfaces and interoperability of new or modified infrastructure with other infrastructure and system components, such as databases, hardware, software, or communication devices. | Conducted
Implementation Testing
11 | System Acceptance Testing | Both | Assesses the solution’s functionality, architecture, and configuration in a production-like environment. | Conducted
12 | Performance Testing (includes load testing, volume testing, stress testing, and longevity testing). | Both | Performance tests help to determine a system’s and application’s limitations, as well as the maximum of active users utilizing the application throughout servers. | Conducted
13 | Initial Security Control Assessment (SCA) | Both | Determines the extent to which the security controls in the business application or infrastructure are implemented correctly, operate as intended, and produce the desired outcome with respect to meeting the security requirements for the application or infrastructure. | Conducted
14 | Final Integration Testing | Both | Confirms that a business application or infrastructure solution works correctly from end to end in an environment configured the same as a production environment and with the same security settings. | Conducted
15 | Initial Contingency Planning Testing | Both | Ensures the personnel are knowledgeable and capable of performing the notification/activation requirements and procedures as outlined in the CP, in a timely manner. | Conducted
Operational Testing
16 | Production Ready Testing | Both | Confirms that a production-ready business application or infrastructure has been installed and configured correctly in a production environment and is ready for operational use. | Conducted
17 | Monitoring & Reliability Testing | Both | Ensures that the implemented application or infrastructure performs as expected in production. | Conducted
18 | Operational Security Control Assessment (SCA) | Both | Determines the extent to which the security controls in the business application or infrastructure are implemented correctly, operate as intended, and produce the desired outcome with respect to meeting the security requirements for the business application or infrastructure. | Conducted
19 | Audits | Both | Ensures a business application or infrastructure complies with prescribed auditing requirements and operating standards. Assures accuracy of operating statistics and reporting, risk analysis, information security, disaster recovery and contingency planning, corrective action planning, and quality assurance of all procedures. | Conducted
20 | Operational Contingency Planning Testing | Both | Ensures the personnel are knowledgeable and capable of performing the notification/activation requirements and procedures as outlined in the CP, in a timely manner. | Conducted
Project Defined Testing
21 | Project Defined Test 1 | Both | A project defined test that…
22 | Project Defined Test 2 | Both | A project defined test that…
Note: Agreed upon test plans and reports are expected for all stage gate reviews, regardless of who conducts them
|  | CONDUCTED TESTS: |  | 20
|  | NOT CONDUCTED TESTS: |  | 0
|  | COMBINE TESTS: |  | 0

## XLC PPA for Signatures
Project Process Agreement
Project Name | 0
Project Description | 0
Release | 0
Complexity Level
IT Intake Request Form | Provide (New) | Physical Database / Model | Provide (New)
Enterprise Architecture Analysis Artifacts | Provide (New) | Interface Control Document | Provide (New)
Business Case | Provide (New) | Data Use Agreement | Provide (New)
Requirements Document | Provide (New) | Test Case Specification | Provide (New)
High-Level Technical Design | Provide (New) | Data Conversion Plan | Provide (New)
Section 508 Product Assessment Package | Provide (New) | Computer Match/Interagency Agreements | Provide (New)
Acquisition Strategy | Provide (New) | Implementation Plan | Provide (New)
Project Process Agreement | Provide (New) | User Manual | Provide (New)
Project Charter | Provide (New) | Operations & Maintenance Manual | Provide (New)
Information Security Risk Assessment | Provide (New) | Business Product/Code | Provide (New)
System Security Plan | Provide (New) | Version Description Document | Provide (New)
Privacy Impact Assessment | Provide (New) | Training Plan | Provide (New)
Logical Data Model | Provide (New) | Test Summary Report | Provide (New)
Release Plan | Provide (New) | Training Artifacts | Provide (New)
Project Management Plan | Provide (New) | Contingency Test Plan (tabletop) | Provide (New)
System of Records | Provide (New) | Security Assessment | Provide (New)
Test Plan | Provide (New) | Authorization Package | Provide (New)
Performance Test Plan and Results | Provide (New) | Plan of Action & Milestones | Provide (New)
Project Schedule | Provide (New) | CMS CIO Provided Authorization To Operate | Provide (New)
Risk Register | Provide (New) | System Disposition Plan | Provide (New)
Issues List | Provide (New) | Post Implementation Report | Provide (New)
Action Items | Provide (New) | Annual Operational Analysis Report | Provide (New)
Decision Log | Provide (New) | Project Closeout Report | Provide (New)
Lessons Learned Log | Provide (New) | Monitoring Reports | Provide (New)
Contingency Plan | Provide (New)
System Design Document | Provide (New)
Database Design Document | Provide (New)
Stage Gates
Architecture Review (AR) | Perform | Implementation Readiness Rev (IRR) | Perform
Investment Selection Review (ISR) | Perform | Production Readiness Review (PRR) | Perform
Project Baseline Review (PBR) | Perform | Operational Readiness Review (ORR) | Perform
Requirements Review (RR) | Perform | Post Implementation Review (PIR) | Perform
Preliminary Design Review (PDR) | Perform | Annual Operational Analysis (AOA) | Perform
Detailed Design Review (DDR) | Perform | Disposition Review (DR) | Perform
Validation Readiness Review (VRR) | Perform
Tests
Unit Testing | Conducted | System Acceptance Testing | Conducted
Application Integration Testing | Conducted | Performance Testing (includes load testing, volume testing, stress testing, and longevity testing). | Conducted
Section 508 Testing | Conducted | Initial Security Control Assessment (SCA) | Conducted
System Testing | Conducted | Final Integration Testing | Conducted
Functional Testing | Conducted | Initial Contingency Planning Testing | Conducted
End-to-End Integration Testing | Conducted | Production Ready Testing | Conducted
User Acceptance Testing | Conducted | Monitoring & Reliability Testing | Conducted
Regression Testing | Conducted | Operational Security Control Assessment (SCA) | Conducted
Section 508 Testing | Conducted | Audits | Conducted
Infrastructure Testing | Conducted | Operational Contingency Planning Testing | Conducted
APPROVALS:
IT Project Manager | Print Name |  | Date
Business Project Manager | Print Name |  | Date
CMS IT Governance / PMO | Print Name |  | Date
CMS Executive Sponsor | Print Name |  | Date