## Introduction
This assessment is designed to measure an individual or an organization's level of maturity
in implementing and practicing project management.
You may find some questions do not match directly with terminology or manager descriptions
used within your organization. When this occurs, answer the question considering your similar
terminology or manager descriptions.
At the conclusion of each set of questions, a summary or interpretation of your results is provided.
Also, the worksheet of this assessment provides a graphical representation of your results.
If you have any questions or problems utilizing this assessment, do not hesitate to contact us at
info@pmmilestone.com. Also, do not hesitate to contact us to modify this assessment
to custom fit your organization.
Project Management
Maturity Assessment
Model

## Common Language
LEVEL |  | Answer the following questions by placing a "10" in the box of your answer. Scoring results will be discussed at the end of
ONE |  | the questions.
Question |  |  | Question |  |  | Question |  |  | Question |  |  | Question |  |  | Question |  |  | Question |  |  | Question |  |  | Question |  |  | Question |  |  |  | Scope |  | Time |  | Cost |  | Human Resources |  | Procurement |  | Quality |  | Risk |  | Communication
1. |  | A comprehensive definition of scope management would be: | 6. |  | A variance envelope has been established on a project. The envelope goes from plus/minus 30 percent in R&D to | 10. |  | In which of the following circumstance(s) would you most likely to buy goods or services instead of [producing them in-house? | 14. |  | Power games, withholding information, and hidden agendas are examples of: | 18. |  | A project can best be defined as: | 22. |  | Project cash reserves are often used for adjustments in escalation factors, which may be beyond the control of the project | 26. |  | In today's view quality, who defines quality? | 31. |  | The ultimate purpose for risk management is: | 35. |  | The swiftest and most effective communications take place among people with: | 39. |  | A company dedicated to quality usually provides training for: |  | Management |  | Management |  | Management |  | Management |  | Management |  | Management |  | Management |  | Management |  | Your Score | Benchmark
| A. | Managing a project in terms of its objectives through all life cycle phases and processes |  |  | plus/minus 5 percent during manufacturing. The most common reason for the change in the "thickness" of the envelope |  | A. | Your company has excess capacity and your company can produce the goods or services |  | A. | Feedback |  | A. | A series of non-related activities designed to accomplish single or multiple objectives |  |  | Manager. Other than possible financing (interest) costs and taxes, the three most common escalation factors involve |  | A. | Senior management |  | A. | Analysis |  | A. | Common points of view |  | A. | Senior management | 1 | 0 | 8 | 0 | 2 | 0 | 5 | 0 | 3 | 0 | 4 | 0 | 11 | 0 | 7 | 0 | Scope | 0 | 30
| B. | Approval of the scope baseline |  |  | is because: |  | B. | Your company has no excess capacity and cannot produce the goods or services |  | B. | Communication barriers |  | B. | A coordinated effort of related activities designed to accomplish a goal without a well-established end point |  |  | changes in: |  | B. | project management |  | B. | Mitigation |  | B. | Dissimilar interests |  | B. | Hourly workers | [16 empty] | Time | 0 | 30
| C. | Approval of the detailed project charter |  | A. | The management reserve has been used up |  | C. | There are many reliable vendors for the goods or services that you are attempting to procure but the vendors cannot achieve |  | C. | Indirect communication |  | C. | Cradle-to-grave activities that must be accomplished in less than one year and consume human and nonhuman resources |  | A. | Overhead rates, labor rates, and material costs |  | C. | Functional management |  | C. | Assessment |  | C. | Advanced degrees |  | C. | Salaried workers | 16 | 0 | 9 | 0 | 6 | 0 | 13 | 0 | 10 | 0 | 26 | 0 | 19 | 0 | 14 | 0 | Cost | 0 | 30
| D. | Configuration Control |  | B. | The accuracy of the estimates in manufacturing is worse than the accuracy of estimates in R&D |  |  | your level of quality |  | D. | Mixed messages |  | D. | Any undertaking with a definable time frame and well-defined objectives that consumes both human and nonhuman |  | B. | Overhead rates, schedule slippages, rework |  | D. | Workers |  | D. | Contingency planning |  | D. | The ability to reduce perception barriers |  | D. | All employees | [16 empty] | Human Resources | 0 | 30
| E. | Approved detailed planning including budgets, resource allocation, linear responsibility charts, and management sponsorship |  | C. | Tighter controls are always needed as a project begins to wind down |  | D. | A and B |  | E. | All of the above |  |  | resources with certain constraints |  | C. | Rework, cost-of-living adjustments, overtime |  | E. | Customers |  | E. | All of the above |  | E. | Good encoding skills |  | E. | Project managers | 18 | 0 | 23 | 0 | 12 | 0 | 20 | 0 | 17 | 0 | 33 | 0 | 25 | 0 | 15 | 0 | Procurement | 0 | 30
|  |  |  | D. | The personal desires of the project sponsor are an issue |  | E. | A and C |  |  |  |  | E. | All of the above |  | D. | Material costs, shipping cost, and scope changes | [28 empty] | Quality | 0 | 30
2. |  | The most effective means of determining the cost of a project is to price out the: |  | E. | None of the above |  |  |  | 15. |  | The basic elements of a communication model include: |  |  |  |  | E. | Labor rates, material costs, and cost reporting | 27. |  | Project managers need exceptionally good communication and negotiation skills primarily because: | 32. |  | Which of the following is not a factor to consider when selecting a contract type? | 36. |  | Assigning resources in an attempt to find the shortest project schedule consistent with fixed resource limits is called: | 40. |  | During a project review meeting, we discover that our $25,000 project has negative (behind) schedule variance of $2,500, | 21 | 0 | 30 | 0 | 22 | 0 | 24 | 0 | 32 | 0 | 37 | 0 | 31 | 0 | 28 | 0 | Risk | 0 | 30
| A. | Work Breakdown Structure |  |  |  | 11. |  | Project risk is typically defined as a function consisting of reducing: |  | A. | Listening, talking, and sign language | 19. |  | Risk management decision-making falls into three broad categories: |  |  |  |  | A. | They may be leading a team over which they have no direct control |  | A. | The type/complexity of the requirement |  | A. | Resource allocation |  |  | which equates to 12 percent of the work scheduled to this point of time. We can therefore conclude that: | [16 empty] | Communications | 0 | 30
| B. | Linear responsibility chart | 7. |  | An informal communication network on a project and within an organization is called: |  | A. | Uncertainty |  | B. | Communicator, encoding, message, medium, decoding, receiver, and feedback |  | A. | Certainty, risk, and uncertainty | 23. |  | The critical path in a project network is the path that: |  | B. | Procurement activities mandate this |  | B. | The urgency of the requirement |  | B. | Resource partioning |  | A. | The project will be completed late | 29 | 0 | 36 | 0 | 40 | 0 | 27 | 0 | 34 | 0 | 39 | 0 | 38 | 0 | 35 | 0
| C. | Project Charter |  | A. | A free upward flow |  | B. | Damage |  | C. | Clarity of speech and good listening habits |  | B. | Probability, risk, and uncertainty |  | A. | Has the greatest degree of risk |  | C. | They are expected to be technical experts |  | C. | The cost/price analysis |  | C. | Resource leveling |  | B. | The critical path has been lengthened
| D. | Scope Statement |  | B. | A free horizontal flow |  | C. | Time |  | D. | Reading, writing, and listening |  | C. | Probability, risk event, and uncertainty |  | B. | Will elongate the project if the activities on this path take longer than anticipated |  | D. | They must provide executive/customer/sponsor briefings |  | D. | The extent of price competition |  | D. | Resource quantification |  | C. | The costs are being overrun |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| E. | Management plan |  | C. | An unrestricted communication flow |  | D. | Cost |  | E. | All of the above |  | D. | Hazard, risk event, and uncertainty |  | C. | Must be completed before all other paths |  | E. | All of the above |  | E. | All are factors to consider |  | E. | None of the above |  | D. | Overtime will b required to maintain the original critical path |  | Total |  | Total |  | Total |  | Total |  | Total |  | Total |  | Total |  | Total
|  |  |  | D. | A grapevine |  | E. | A and B |  |  |  |  | E. | A and D |  | D. | All of the above | [10 empty] | E. | None of the above
3. |  | A written or pictorial document that describes, defines, or specifies the services or items to be procured is: |  | E. | An open network |  |  |  | 16. |  | Good project objectives must be: |  |  |  |  | E. | A and B only | 28. |  | For effective communication, the message should be oriented to: | 33. |  | Which of the following is not indicitative of today's views of the quality management process? | 37 |  | Which of the following is true of modern quality management?
| A. | A specification document |  |  |  | 12. |  | Typically, during which phase in a project life cycle are most of the project expenses incurred? |  | A. | General rather than specific | 20. |  | Which of the following types of power comes through the organizational hierarchy? |  |  |  |  | A. | The initiator |  | A. | Defects should be highlighted |  | A. | Quality is defined by the customer |  |  |  |  | Overall Total |  |  |  | 0
| B. | A gantt chart | 8. |  | Smoothing out resource requirements from period to period is called: |  | A. | Concept phase |  | B. | Established without considering resource constraints |  | A. | Coercive, legitimate, referent | 24. |  | The major difference between project and line management is that the project manager may not have any control over which |  | B. | The receiver |  | B. | Focus should be on written specifications |  | B. | Quality has become a competitive weapon
| C. | A blueprint |  | A. | Resource allocation |  | B. | Development or design phase |  | C. | Realistic and attainable |  | B. | Reward, coercive, expert |  |  | basic management function? |  | C. | The media |  | C. | The responsibility for quality lies primarily with management but everyone should be involved |  | C. | Quality is now an integral part of strategic planning
| D. | A risk analysis |  | B. | Resource partitioning |  | C. | Execution phase |  | D. | Overly complex |  | C. | Referent, expert, legitimate |  | A. | Decision-making |  | D. | The management style |  | D. | Quality saves money |  | D. | Quality is linked with profitability on both the market and cost sides |  |  |  |  | 30 or more points in each of the eight categories | [6 empty] | You have a reasonable knowledge of the basic principles of project
| E. | None of the above |  | C. | Resource leveling |  | D. | Termination phase |  | E. | Measurable, intangible, and verifiable |  | D. | Legitimate, coercive, reward |  | B. | Staffing |  | E. | The corporate culture |  | E. | Problem identification leads to cooperative solutions |  | E. | All are true | [11 empty] | management.
|  |  |  | D. | resource quantification |  | E. | None of the above |  |  |  |  | E. | Expert, coercive, referent |  | C. | Rewarding
4. |  | The costs of nonconformance include: |  | E. | None of the above |  |  |  | 17. |  | In which type of contract arrangement is the contractor most likely to control costs? |  |  |  |  | D. | Tracking/monitoring | 29. |  | The financial closeout of a project dictates that: | 34. |  | The document that describes the details of the task in terms of physical characteristics and places the risk of performance | 38. |  | The techniques and methods used to reduce or control risk are known as: |  |  |  |  | 30 or more points in all but one or two categories | [6 empty] | You and your organization still possess all the knowledge you need of
| A. | Prevention costs |  |  |  | 13. |  | Conflict management requires problem solving. Which of the following is often referred to as a problem-solving technique and |  | A. | Cost plus percentage of cost | 21. |  | The most common definition of project success is: |  | E. | Reviewing |  | A. | All project funds have been spent |  |  | on the buyer is: |  | A. | Risk identification | [11 empty] | basic principles, but that one or two of the categories may not apply
| B. | Internal failure costs | 9. |  | The major disadvantage of a bar chart is: |  |  | used extensively in conflict resolution? |  | B. | Firm-fixed price |  | A. | Within time |  |  |  |  | B. | No charge numbers have been overrun |  | A. | A design specification |  | B. | Risk response | [11 empty] | directly to your circumstances.
| C. | External failure costs |  | A. | Lack of time phasing |  | A. | Confrontation |  | C. | Time and materials |  | B. | Within time and cost | 25. |  | During which phase of a project is the uncertainty the greatest? |  | C. | No follow-on work from this client is possible |  | B. | A functional specification |  | C. | Lessons learned or control
| D. | B and C only |  | B. | Cannot be related to calendar dates |  | B. | Compromise |  | D. | Firm-fixed price with economic price adjustment |  | C. | Within time, cost, and technical performance requirements |  | A. | Design |  | D. | No further charges can be made against the project |  | C. | A performance specification |  | D. | Risk quantification |  |  |  |  | Less than 30 in any category | [6 empty] | A deficiency exists in that category. If the score is less than 10, a rigorous
| E. | A, B, and C |  | C. | Does not show activity interrelationships |  | C. | Smoothing |  | E. | Fixed-price incentive firm target |  | D. | Within time, cost, performance, and acceptance by the customer/user |  | B. | Development/execution |  | E. | All of the above |  | D. | A project specification |  | E. | None of the above | [11 empty] | training program on basic principles may be necessary.
|  |  |  | D. | Cannot be related to manpower planning |  | D. | Forcing |  |  |  |  | E. | None of the above |  | C. | Concept |  |  |  |  | E. | All of the above
5. |  | Perhaps the biggest problem facing the project manager during integration activities within a matrix structure is: |  | E. | Cannot be related to cost estimates |  | E. | Withdrawal | [7 empty] | D. | Phase-out | 30. |  | The major difference between PERT and CPM networks is:
| A. | Coping with employees who report to multiple bosses | [13 empty] | E. | All of the above |  | A. | PERT requires three time estimates whereas CPM requires one time estimate | [10 empty] | Total score between 300 and 400 | [6 empty] | Your organization is positioned to begin work on Level Two of the Maturity
| B. | Too much sponsorship involvement | [16 empty] | B. | PERT is used for construction projects whereas CPM is used for R&D | [17 empty] | model.
| C. | Unclear functional understanding of the technical requirements | [16 empty] | C. | PERT addresses only time whereas CPM also includes costs and resource availability
| D. | Escalating project costs | [16 empty] | D. | PERT requires computer solutions whereas CPM is manual technique | [10 empty] | Total score less than 300 | [6 empty] | There may exist pockets of project management with different levels of
| E. | All of the above | [16 empty] | E. | PERT is measured in days whereas CPM uses weeks or months | [17 empty] | knowledge. Project-driven pockets will generally possess more knowledge.

## Common Processes
LEVEL | The following 20 questions explore how mature you believe your organization to be in regard to Level 2 - Common Processes. | [56 empty] | High scores (usually |  | Phases with very low
TWO | Beside each question you will enter the number that corresonds to your opinion based on the following key | [56 empty] | +6 or greater) indicates |  | numbers have not been
[58 empty] | this phase has been |  | achieved yet.
|  |  | Your | Strongly | Disagree | Slightly | No | Slightly | Agree | Strongly |  |  |  | Your | Strongly | Disagree | Slightly | No | Slightly | Agree | Strongly |  |  |  | Your | Strongly | Disagree | Slightly | No | Slightly | Agree | Strongly |  |  |  |  | Your | Strongly | Disagree | Slightly | No | Slightly | Agree | Strongly | [13 empty] | achieved or at least
|  |  | Opinion | Disagree |  | Disagree | Opinion | Agree |  | Agree |  |  |  | Opinion | Disagree |  | Disagree | Opinion | Agree |  | Agree |  |  |  | Opinion | Disagree |  | Disagree | Opinion | Agree |  | Agree |  |  |  |  | Opinion | Disagree |  | Disagree | Opinion | Agree |  | Agree | [13 empty] | you are in this phase.
Question |  |  | Enter | -3 | -2 | -1 | 0 | 1 | 2 | 3 |  | Question |  | Enter | -3 | -2 | -1 | 0 | 1 | 2 | 3 |  | Question |  | Enter | -3 | -2 | -1 | 0 | 1 | 2 | 3 |  | Question |  |  | Enter | -3 | -2 | -1 | 0 | 1 | 2 | 3
Life Cycles for Level Two (cont)
1. |  | My company recognizes the need for | [9 empty] | 6. | My company is committed to quality upfront | [9 empty] | 13. | Our executives both understand project | [9 empty] | 20. | Our executives have demonstrated a
|  | project management. This need is | [10 empty] | planning. We try to do the best we can at | [10 empty] | sponsorship and serve as project sponsors | [10 empty] | willingness to change our way of doing | [12 empty] | Initial Maturity Phase |  |  | - The development of a management cost/schedule system
|  | recognized at all levels of management, | [10 empty] | planning. | [8 empty] | 0 |  | on selected projects. | [8 empty] | 0 |  | business in order to mature in project | [15 empty] | - Integration of schedule and cost control
|  | including senior management. | [8 empty] | 0 | [23 empty] | management. | [9 empty] | 0 | [5 empty] | - Development of an ongoing educational cirriculum to support project management and enhance individual skills
[12 empty] | 7. | Our lower - and middle - level managers | [9 empty] | 14. | Our executives have recognized or
2. |  | My company has a system in place to | [10 empty] | totally and visibliy support the project | [10 empty] | identified the applications of project
|  | manage both cost and schedule. The | [10 empty] | management process. | [8 empty] | 0 |  | management to various parts of our | [9 empty] | Life Cycles for Level Two | [11 empty] | SCORING |  | Transpose your scores for each question below. (If you are taking the computer version of this assessment,
|  | system requires charge numbers and cost | [21 empty] | business. | [8 empty] | 0 | [14 empty] | the scores should appear below.)
|  | account codes. The system reports | [9 empty] | 8. | My company is doing everything possible | [21 empty] | Embryonic Phase | - Recognizing the need for project management
|  | variances from planned targets. | [8 empty] | 0 |  | to minimize "scope creep" (I.e. scope | [9 empty] | 15. | My company has successfully integrated | [11 empty] | -Recognizing the potential benefits of project management | [11 empty] | Embryonic |  | Executive |  | Middle/Lower Management |  | Growth |  | Maturity
[13 empty] | changes) on our projects. | [8 empty] | 0 |  | cost and schedul control for both managing | [11 empty] | -Recognizing the applications of project management to various parts of the business | [11 empty] | 1. | 0 | 5. | 0 | 7. | 0 | 4. | 0 | 2. | 0 |  |  |  | Your Score | Benchmark
3. |  | My company has recognized the benefits | [21 empty] | projects and reporting status. | [8 empty] | 0 |  |  | -Recognizing some fo the changes necessary to implement project management | [11 empty] | 3. | 0 | 10. | 0 | 9. | 0 | 6. | 0 | 15. | 0 |  | Maturity |  | 0 | 6
|  | that are possible from implementing | [9 empty] | 9. | Our lower - and middle- level managers are | [34 empty] | 14. | 0 | 13. | 0 | 12. | 0 | 8. | 0 | 16. | 0 |  | Growth |  | 0 | 6
|  | project management. These benefits have | [10 empty] | committed not only to project management, | [9 empty] | 16. | My company has developed a project | [10 empty] | Executive Management | -Visible executive support | [11 empty] | 17. | 0 | 20. | 0 | 19. | 0 | 11. | 0 | 18. | 0 |  | Middle/Lower Management |  | 0 | 6
|  | been recognized at all levels of | [10 empty] | but also to the promises made to project | [10 empty] | management curriculum (I.e. more than | [10 empty] | Acceptance Phase | -Executive understanding of project management | [10 empty] | TOTAL |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Executive |  | 0 | 6
|  | management, including senior | [10 empty] | managers for deliverables. | [8 empty] | 0 |  | one or two courses) to enhance the | [11 empty] | -Project sponsorship | [22 empty] | Embryonic |  | 0 | 6
|  | management. | [8 empty] | 0 | [12 empty] | project management skills of our employees. | [8 empty] | 0 |  |  | -Willingness to change the way the company does business
[12 empty] | 10. | The excutives in my organization have a
4. |  | My company (or division) has a well- | [10 empty] | good understanding of the principles of project | [9 empty] | 17. | Our executives have recognized what | [10 empty] | Middle/Lower- Level | -Visible Middle/Lower management support
|  | definable project management | [10 empty] | management. | [8 empty] | 0 |  | must be done in order to achieve maturity | [10 empty] | Management | -Middle/Lower management commitment to project management
|  | methodology using life cycle phases. | [8 empty] | 0 | [12 empty] | in project management. | [8 empty] | 0 |  | Acceptance Phase | -Middle/Lower management education
[12 empty] | 11. | My company has selected one or more | [22 empty] | -Release of employees/staff for project management training programs
5. |  | Our executives visibly support project | [10 empty] | project management software packages | [9 empty] | 18. | My company views and treats project
|  | management through executive | [10 empty] | to be used as the project tracking system. | [8 empty] | 0 |  | management as a profession rather | [10 empty] | Growth Phase | -Development of company project management life cycles
|  | presentations, correspondence, and by | [21 empty] | than a part-time assignment. | [8 empty] | 0 |  |  | -Development of a project management methodology
|  | occasionally attending project team | [9 empty] | 12. | Our lower - and middle - level managers | [22 empty] | -A commitment to effective planning
|  | meetings/briefings | [8 empty] | 0 |  | have been trained and educated in | [9 empty] | 19. | Our lower- and middle-level managers | [11 empty] | -Minimization of scope changes (I.e., scope creep)
[13 empty] | project management. | [8 empty] | 0 |  | are willing to release their employees | [11 empty] | -Selection of software to support a Project Managmenet Information System
[24 empty] | for project management training. | [8 empty] | 0 |  | This phase is the beginning of the creation of the project management process.

## Singular Methodology
LEVEL |  | The following multiple choice questions will allow you to compare your organization against other | [34 empty] | Interpretation of your score:
THREE |  | companies with regard to the level 3 "Hexagon of Excellence". Scoring will be provided at the end
|  | of the questions. | Your | Question |  |  | Your | Question |  |  | Your | Question |  |  | Your | Question |  |  | Your | Question |  |  | Your | Question |  |  | Your | Question | Your | Enter Points | [7 empty] | Overall Total |  | 0
Question |  | Enter corresponding letter for your answer. | Answer |  |  |  | Answer |  |  |  | Answer |  |  |  | Answer |  |  |  | Answer |  |  |  | Answer |  |  |  | Answer |  | Answer | For Answer | A. | B. | C. | D. | E. | F.
|  |  |  | 7. |  | How many different project management methodologies exist in your |  | 13. |  | Our culture seems based upon: |  | 19. |  | In our company, the project manager's authority comes from: |  | 25. |  | My company believes that training should be: |  | 31. |  | The culture within our organization is best described as: |  | 38. |  | The skills that will probably be most important for my company's project |  | 1 | 0 |  | 2 | 2 | 4 | 2 | 4 | 5 |  | Points |  | Interpretation
[6 empty] | organization (i.e., consider a systems development methodology for MIS |  |  | A. | Policies |  |  | A. | Within himself/herself, whatever he or she can get away with |  |  | A. | Performed at the request of employees |  |  | A. | Informal project management based upon trust, communication, and cooperation |  |  |  | managers as we move into the 21st century are: |  | 2 | 0 |  | 0 | 0 | 1 | 3 | 4 | 5 |  | 169 - 210 |  | Your company compares very well to other companies at Level 3.
[6 empty] | projects different than a product development project management |  |  | B. | Procedures (including forms to be filled out) |  |  | B. | The immediate superior to the project manager |  |  | B. | Performed to satisfy a short-term need |  |  | B. | Formality based upon policies and procedures for everything |  |  | A. | Technical knowledge and leadership |  | 3 | 0 |  | 0 | 0 | 3 | 4 | 5 | 5 |  |  |  | You are on the right track for excellence, assuming that you not
[6 empty] | methodology)? |  |  | C. | Policies and procedures |  |  | C. | Documented job descriptions |  |  | C. | Performed to satisfy both long and short - term needs |  |  | C. | Project management thrives on formal authority relationships |  |  | B. | Risk management and knowledge of the business |  | 4 | 0 |  | 0 | 1 | 3 | 4 | 5 | 5 |  |  |  | achieved it yet.
1. |  | My company actively uses the following processes: |  |  | A. | We have no methodologies |  |  | D. | Guidelines |  |  | D. | Informally through the project sponsor in the form of a project charter or |  |  | D. | Performed only if there exists a return on investment in training dollars |  |  | D. | Executive meddling, which forces an overabundance of documentation |  |  | C. | Integration skills and risk management |  | 5 | 0 |  | 0 | 2 | 2 | 2 | 5
| A. | Total quality management (TQM) only |  |  | B. | 1 |  |  | E. | Polices, procedures, and guidelines |  |  |  | appointment letter | [6 empty] | E. | Nobody trusting the decisions of our project managers |  |  | D. | Integration skills and knowledge of the business |  | 6 | 0 |  | 0 | 2 | 4 | 5 |  |  |  | 147 - 168 |  | Your company is going in the right direction, but more work is needed.
| B. | Concurrent engineering (shortening deliverable development time) only |  |  | C. | 2 - 3 | [9 empty] | 26. |  | My company believes that the content of training courses is best determined by: | [6 empty] | E. | Communication skills and technical understanding |  | 7 | 0 |  | 0 | 5 | 4 | 2 | 0 |  |  |  |  | Project management is not totally perceived as a profession. It is also
| C. | TQM and concurrent engineering only |  |  | D. | 4 - 5 |  | 14. |  | Cultures are either quantitative (policies, procedures, forms, and guidelines), |  | 20. |  | After project go-ahead, our project sponsor tend to: |  |  | A. | The instructor |  | 32. |  | What percentage of the project manager's time each week is spent preparing | [5 empty] | 8 | 0 |  | 0 | 2 | 3 | 5 | [5 empty] | possible that your organization simply does not fully understand project
| D. | Risk management only |  |  | E. | More than 5 |  |  |  | behavioral, or a compromise. The culture in my company is probably _____ |  |  | A. | Become invisible, even when needed |  |  | B. | The Human Resources Department |  |  |  | reports? |  | 39. |  | In my organization, the people assigned as project leaders are usually: |  | 9 | 0 |  | 1 | 3 | 4 | 4 | 5 | 5 |  |  |  | management. Emphasis is probably more toward being non-project
| E. | Risk management and concurrent engineering only | [7 empty] | percent behavioral. |  |  | B. | Micromanage |  |  | C. | Management |  |  | A. | 5 - 10 percent |  |  | A. | Middle managers |  | 10 | 0 |  | 1 | 5 | 4 | 0 | [5 empty] | driven than project driven.
| F. | Risk management, concurrent engineering, and TQM |  | 8. |  | With regard to benchmarking: |  |  | A. | 10 - 25 percent |  |  | C. | Expect summary-level briefings once a week |  |  | D. | Employees who will receive the training |  |  | B. | 10 - 20 percent |  |  | B. | Lower managers |  | 11 | 0 |  | 3 | 3 | 3 | 5 | 0 | 4
[5 empty] | A. | My company has never tried to use benchmarking |  |  | B. | 25 - 60 percent |  |  | D. | Expect summary-level briefings once every two weeks |  |  | E. | Customization after an audit with the employees and managers |  |  | C. | 20 - 40 percent |  |  | C. | Any level of management |  | 12 | 0 |  | 1 | 5 | 5 | 3 |  |  |  | 80 - 146 |  | The company is probably just providing lip service to project management.
2. |  | On what percentage of your projects do you use the principles of total |  |  | B. | My company has performed benchmarking and implemented changes but |  |  | C. | 50 - 60 percent |  |  | E. | Get involved only when a critical problem occurs or at the request of the project | [6 empty] | D. | 40 - 60 percent |  |  | D. | Usually nonmanagement employees |  | 13 | 0 |  | 2 | 3 | 4 | 5 | 4 |  |  |  |  | Support is minimal. The company believes that it is the right thing to do,
|  | quality management? |  |  |  | not for project management |  |  | D. | 60 - 75 percent |  |  |  | manager or middle/lower managers |  | 27. |  | What percentage of the training courses in project management contain |  |  | E. | Greater than 60 percent |  |  | E. | Anyone in the company |  | 14 | 0 |  | 2 | 3 | 4 | 5 | 5 |  |  |  |  | but has not figured out the true benefits or what they, the executives, should
| A. | 0 percent |  |  | C. | My company has performed project management benchmarking but no |  |  | E. | Greater than 75 percent | [7 empty] | documented lessons learned case studies from other projects within your | [9 empty] | 15 | 0 |  | 1 | 5 | 5 | 5 | 0 |  |  |  |  | be doing. The company still operates very functionally.
| B. | 5 - 10 percent |  |  |  | changes were made | [5 empty] | 21. |  | What percentage of your projects have sponsors who are at the director level |  |  |  | company? |  | 33. |  | During project planning, most of our activities are accomplished using: |  | 40. |  | The project managers in my organization have undergone at least some degree |  | 16 | 0 |  | 2 | 3 | 5 | 0 | 2
| C. | 10 - 25 percent |  |  | D. | My company has performed project management benchmarking and |  | 15. |  | Our organizational structure is: |  |  |  | or above? |  |  | A. | None |  |  | A. | Policies |  |  |  | of training in: |  | 17 | 0 |  | 4 | 2 | 5 | 1 | 0 |  |  | Below 79 |  | The company does not understand project management, nor does it have
| D. | 25 - 50 percent |  |  |  | changes were made |  |  | A. | Traditional (predominantly vertical) |  |  | A. | 10 - 25 percent |  |  | B. | Less than 10 percent |  |  | B. | Procedures |  |  | A. | Feasibility studies |  | 18 | 0 |  | 2 | 3 | 5 | 0 | 3 |  |  |  |  | a desire to change. The managers feel their existing power base may be
| E. | 50 - 75 percent | [6 empty] | B. | A strong matrix (i.e., project manager provides most of the technical direction) |  |  | B. | 25 - 60 percent |  |  | C. | 10 - 25 percent |  |  | C. | Guidelines |  |  | B. | Cost-benefit analysis |  | 19 | 0 |  | 1 | 2 | 2 | 4 | 5 |  |  |  |  | threatened by project management.
| F. | 75 - 100 percent |  | 9. |  | My company's corporate culture is best described by the concept of: |  |  | C. | A weak matrix (i.e., managers provide most of the technical direction) |  |  | C. | 50 - 60 percent |  |  | D. | 25 - 50 percent |  |  | D. | Checklists |  |  | C. | Both A and B |  | 20 | 0 |  | 1 | 1 | 3 | 4 | 5
[5 empty] | A. | Single-boss reporting |  |  | D. | We use collocated teams |  |  | D. | 60 - 75 percent |  |  | E. | More than 50 percent |  |  | E. | None of the above |  |  | D. | Our project managers are typically brought on board after project approval/award |  | 21 | 0 |  | 1 | 3 | 5 | 4 | 4
3. |  | On what percent of your projects do you use the principles of risk management? |  |  | B. | Multiple-boss reporting |  |  | E. | I don't know what the structure is: management changes on a daily basis |  |  | E. | Greater than 75 percent | [13 empty] | 22 | 0 |  | 1 | 3 | 5 | 5 | 5
| A. | 0 percent |  |  | C. | Dedicated teams without empowerment | [9 empty] | 28. |  | What percentage of the executives in functional (not corporate) organization |  | 34. |  | The typical time duration for a project status review meeting with senior |  | 41. |  | Our project managers are encouraged to: |  | 23 | 0 |  | 0 | 2 | 4 | 5 | 5
| B. | 5 - 10 percent |  |  | D. | Nondedicated teams without empowerment |  | 16. |  | When assigned as a project leader, our project manager obtains resources by: |  | 22. |  | My company offers approximately how many different internal training courses |  |  |  | have attended training programs or executive briefings specifically designed to |  |  |  | management is: |  |  | A. | Take risks |  | 24 | 0 |  | 0 | 3 | 4 | 5 | 0
| C. | 10 - 25 percent |  |  | E. | Dedicated teams with empowerment |  |  | A. | "Fighting" for the best people available |  |  |  | for employees (courses that can be regarded as project-related)? |  |  |  | show executives what they can do to help project management mature? |  |  | A. | Less than 30 minutes |  |  | B. | Take risks upon approval by senior management |  | 25 | 0 |  | 2 | 3 | 4 | 5
| D. | 25 - 50 percent |  |  | F. | Nondedicated teams with empowerment |  |  | B. | Negotiating with managers for the best people available |  |  | A. | Less than 5 |  |  | A. | None! Our executives know everything |  |  | B. | 30 - 60 minutes |  |  | C. | Take risks upon approval by project sponsors |  | 26 | 0 |  | 2 | 1 | 2 | 3 | 5
| E. | 50 -75 percent | [6 empty] | C. | Negotiating for deliverables rather than people |  |  | B. | 6 - 10 |  |  | B. | Less than 25 percent |  |  | C. | 60 - 90 minutes |  |  | D. | Avoid risks |  | 27 | 0 |  | 0 | 1 | 3 | 5 | 5 |  |  |  | Your Score | Benchmark
| F. | 75 - 100 percent |  | 10. |  | With regard to morals and ethics, my company believes that: |  |  | D. | Using senior management to help get the appropriate people |  |  | C. | 11 - 20 |  |  | C. | 25 - 50 percent |  |  | D. | 90 minutes - 2 hours | [5 empty] | 28 | 0 |  | 0 | 1 | 3 | 4 | 5 |  |  |  | 0 | 169
[5 empty] | A. | The customer is always right |  |  | E. | Taking whatever he or she gets, no questions asked |  |  | D. | 21 - 30 |  |  | D. | 50 - 75 percent |  |  | E. | Greater than 2 hours |  | 42. |  | Consider the following statement: Our project mangers have a sincere interest in |  | 29 | 0 |  | 2 | 4 | 5 | 1 | 0
4. |  | On what percent of your projects do you try to compress product/deliverable |  |  | B. | Decisions should be made in the following sequence: best interest of the | [6 empty] | E. | More than 30 |  |  | E. | More than 75 percent | [7 empty] | what happens to each team member after the project is scheduled to be |  | 30 | 0 |  | 0 | 3 | 4 | 5 | 0
|  | schedules, by performing work in parallel rather than in series? |  |  |  | customer first, then the company, then the employees |  | 17. |  | Our middle/lower managers: | [9 empty] | 35. |  | Our customers mandate that we manage our projects: |  |  |  | completed. |  | 31 | 0 |  | 5 | 2 | 3 | 1 | 0
| A. | 0 percent |  |  | C. | Decisions should be made in the following sequence: best interest of the |  |  | A. | Accept total accountability for the work in their area |  | 23. |  | With regard to the previous answer, what percentage of the courses are more |  | 29. |  | In my company, employees are promoted to management because: |  |  | A. | Informally |  |  | A. | Strongly Agree |  | 32 | 0 |  | 3 | 5 | 4 | 2 | 1
| B. | 5 - 10 percent |  |  |  | company first, customer second, and the employees last |  |  | B. | Ask the project manager to accept total accountability |  |  |  | behavioral than quantitative? |  |  | A. | They are technical experts |  |  | B. | Formally, but without customer meddling |  |  | B. | Agree |  | 33 | 0 |  | 2 | 3 | 4 | 5 | 0
| C. | 10 - 25 percent |  |  | D. | We have no such written policy or set of standards |  |  | C. | Try to share accountability with the project manager |  |  | A. | 10 - 25 percent |  |  | B. | They demonstrate the administrative skills of a professional manager |  |  | C. | Formally, but with customer meddling |  |  | C. | Not sure |  | 34 | 0 |  | 4 | 5 | 3 | 1 | 0
| D. | 25 - 50 percent | [6 empty] | D. | Hold the assigned employees accountable |  |  | B. | 25 - 60 percent |  |  | C. | They know how to make sound business decisions |  |  | D. | It is our choice as long as the deliverables are met |  |  | D. | Disagree |  | 35 | 0 |  | 3 | 4 | 3 | 5
| E. | 50 -75 percent |  | 11. |  | My company conducts internal training courses on: |  |  | E. | We don't know the meaning of the word "accountability": it is not part of our |  |  | C. | 50 - 60 percent |  |  | D. | They are at the top of their pay scale | [6 empty] | E. | Strongly disagree |  | 36 | 0 |  | 1 | 2 | 4 | 5 | 0
| F. | 75 - 100 percent |  |  | A. | Morality and ethics within the company |  |  |  | vocabulary |  |  | D. | 60 - 75 percent |  |  | E. | We have no place else to put them |  | 36 |  | My company believes that employees with poor performance | [5 empty] | 37 | 0 |  | 3 | 1 | 5 | 2 | 0
[5 empty] | B. | Morality and ethics in dealing with customers | [6 empty] | E. | Greater than 75 percent | [6 empty] | A. | Should never be assigned to teams | [5 empty] | 38 | 0 |  | 3 | 5 | 5 | 5 | 4
5. |  | My company's risk management process is based upon: |  |  | C. | Good business practices |  | 18. |  | In the culture within our company, the person most likely to be held accountable | [5 empty] | 30. |  | A report must be written and presented to the customer. Neglecting the cost to |  |  | B. | Once assigned to a team, are the responsibility of the project manager for | [5 empty] | 39 | 0 |  | 2 | 2 | 2 | 5 | 3
| A. | We do not use risk management |  |  | D. | All of the above |  |  |  | for the ultimate technical integrity of the final deliverable is/are: |  | 24. |  | My company believes that: |  |  |  | accumulate the information, the approximate cost per page for a typical report is: |  |  |  | supervision | [5 empty] | 40 | 0 |  | 3 | 3 | 5 | 1
| B. | Financial risks only |  |  | E. | None of the above |  |  | A. | The assigned employee |  |  | A. | Project management is a part-time job |  |  | A. | I have no idea |  |  | C. | Once assigned to a team, are the responsibility of the functional manager for | [5 empty] | 41 | 0 |  | 5 | 3 | 4 | 1
| C. | Technical risks only |  |  | F. | At least two of the first three |  |  | B. | The project manager |  |  | B. | Project management is a profession |  |  | B. | $100 - $200 per page |  |  |  | supervision | [5 empty] | 42 | 0 |  | 5 | 4 | 2 | 1 | 1
| D. | Scheduling risks only | [6 empty] | C. | The middle/lower manager |  |  | C. | Project management is a profession and we should become certified as project |  |  | C. | $200 - $500 per page |  |  | D. | Can be effective if assigned to the right team
| E. | A combination of financial, technical, and scheduling risks based on the project |  | 12. |  | With regard to scope creep or scope change, our culture: |  |  | D. | The project sponsor |  |  |  | management professionals, but at our own expense |  |  | D. | Greater than $500 per page |  |  | E. | Should be promoted into management | [6 empty] | Categories |  |  | Totals
[5 empty] | A. | Discourages changes after project initiation |  |  | E. | The whole team |  |  | D. | Project management is a profession and our company pays for us to become |  |  | E. | Free; exempt employees in our company prepare the reports at home or on | [10 empty] | Integrated Processes |  |  | 0
6. |  | The risk management methodology in my company is: |  |  | B. | Allows changes up to a certain point in the project's life cycle using a formal | [7 empty] | certified as project management professionals |  |  |  | their own time |  | 37. |  | Employees who are assigned to a project team (either full-time or part-time) have | [6 empty] | Culture |  |  | 0
| A. | Nonexistent |  |  |  | change control process | [6 empty] | E. | We do not have project managers in our company | [7 empty] | a performance evaluation conducted by: | [6 empty] | Management Support |  |  | 0
| B. | More informal than formal |  |  | C. | Allows changes anywhere in the project's life cycle using a formal change | [14 empty] | A. | Their functional manager only | [6 empty] | Training & Education |  |  | 0
| C. | Based upon a structured methodology supported by policies and procedures |  |  |  | control process | [14 empty] | B. | The project manager only | [6 empty] | Project Management |  |  | 0
| D. | Based upon a structured methodology supported by policies, procedures |  |  | D. | Allows changes but without any formal process | [14 empty] | C. | Both the project and functional manager | [6 empty] | Behavioral Excellence |  |  | 0
|  | and standardized forms to be completed | [18 empty] | E. | Both the project and functional manager, together with a review by project sponsor | [7 empty] | Overall Totals |  | 0

## Benchmarking
LEVEL | The following 25 questions explore how mature you believe your organization to be in regard to Level 4 - Benchmarking. | [43 empty] | SCORING | Transpose your scores for each question below. (If you are taking the computer version of this assessment,
FOUR | Beside each question you will enter the number that corresponds to your opinion based on the following key | [44 empty] | the scores should appear below.)
|  |  | Your | Strongly | Disagree | Slightly | No | Slightly | Agree | Strongly |  |  |  | Your | Strongly | Disagree | Slightly | No | Slightly | Agree | Strongly |  |  |  | Your | Strongly | Disagree | Slightly | No | Slightly | Agree | Strongly |  |  |  | Your | Strongly | Disagree | Slightly | No | Slightly | Agree | Strongly
|  |  | Opinion | Disagree |  | Disagree | Opinion | Agree |  | Agree |  |  |  | Opinion | Disagree |  | Disagree | Opinion | Agree |  | Agree |  |  |  | Opinion | Disagree |  | Disagree | Opinion | Agree |  | Agree |  |  |  | Opinion | Disagree |  | Disagree | Opinion | Agree |  | Agree
Question |  |  | Enter | -3 | -2 | -1 | 0 | 1 | 2 | 3 |  | Question |  | Enter | -3 | -2 | -1 | 0 | 1 | 2 | 3 |  | Question |  | Enter | -3 | -2 | -1 | 0 | 1 | 2 | 3 |  | Question |  | Enter | -3 | -2 | -1 | 0 | 1 | 2 | 3
[46 empty] | Quantitative |  | Qualitative |  |  |  |  | EXPLANATION OF POINTS FOR LEVEL 4
1. |  | Our benchmarking studies have found | [9 empty] | 8 | Our benchmarking efforts are looking at | [9 empty] | 15. | Our benchmarking efforts are looking at | [9 empty] | 22. | Our benchmarking are looking at | [10 empty] | Benchmarking |  | Benchmarking | [8 empty] | Your Score | Benchmark
|  | companies with tighter cost control | [10 empty] | nonsimilar industries (i.e., industries in | [10 empty] | software enhancements through new | [10 empty] | ways of integrating existing processes | [18 empty] | Quantitative benchmarking investigates improvements to the methodology and processes. |  | Quantitative | 0 | 25
|  | processes. | [8 empty] | 0 |  | different business areas). | [8 empty] | 0 |  | purchases. | [8 empty] | 0 |  | into our singular methodology. | [8 empty] | 0 |  | 1 | 0 | 6 | 0 | Quantitative benchmarking total |  | 0 |  | Scores |  | Qualitative | 0 | 12
[46 empty] | 2 | 0 | 7 | 0 | Qualitative benchmarking total |  | 0 |  | Greater than 25 | Your organization is committed to quantitative benchmarking | Combined | 0 | 37
2. |  | Our benchmarking studies have found | [9 empty] | 9. | Our benchmarking efforts are looking at | [9 empty] | 16. | Our benchmarking efforts are looking at | [9 empty] | 23. | Our benchmarking efforts are looking at | [10 empty] | 3 | 0 | 8 | 0 |  | Combined total | 0 |  | Between 11 and 24 | Some benchmarking may be taking place within your organization.
|  | companies with better impact analysis | [10 empty] | nonsimilar industries to seek out new | [10 empty] | the way other companies attract new | [10 empty] | ways other companies have integrated | [10 empty] | 4 | 0 | 9 | 0 |  |  |  |  | Less than 10 | There is a lack of commitment or that the organization does not
|  | during scope change control. | [8 empty] | 0 |  | ideas and new applications for project | [10 empty] | internal users to their methodology for | [10 empty] | new methodologies and processes into | [10 empty] | 5 | 0 | 14 | 0 | [5 empty] | understand how to benchmark or against whom to benchmark.
[13 empty] | management. | [8 empty] | 0 |  | project management. | [8 empty] | 0 |  | their singular methodology. | [8 empty] | 0 |  | 10 | 0 | 15 | 0
3. |  | Our benchmarking studies have found | [43 empty] | 11 | 0 | 16 | 0
|  | that companies are performing risk | [9 empty] | 10. | Our benchmarking efforts are looking at | [9 empty] | 17. | Our benchmarking efforts are focusing | [9 empty] | 24. | Our benchmarking efforts are looking at | [10 empty] | 12 | 0 | 22 | 0 |  |  |  |  | Qualitative benchmarking looks more at applications benchmarking and how the culture executes the methodology.
|  | management by analyzing the detailed | [10 empty] | other companies concurrent engineering | [10 empty] | on how other companies perform | [10 empty] | the way other companies handle or | [10 empty] | 13 | 0 | 23 | 0 |  |  |  |  | Scores
|  | level of the work breakdown structure (WBS). | [8 empty] | 0 |  | activities to see how they perform resource | [10 empty] | technical risk management. | [8 empty] | 0 |  | discourage the development of parallel | [10 empty] | 17 | 0 | 24 | 0 |  |  |  |  | Greater than 12 | Your organization is excelling at qualitative benchmarking
[13 empty] | scheduling and tracking. | [8 empty] | 0 | [12 empty] | methodologies. | [8 empty] | 0 |  | 18 | 0 | [6 empty] | Between 6 and 11 | A marginally acceptable effort is being made at qualitative benchmarking.
4. |  | Our benchmarking studies are | [20 empty] | 18. | Our benchmarking efforts are focusing | [21 empty] | 19 | 0 | [6 empty] | Less than 5 | There is not much of an emphasis on the "soft side" of benchmarking.
|  | investigating supplier involvement | [9 empty] | 11. | Our benchmarking efforts have found | [10 empty] | on how other companies obtain better | [9 empty] | 25. | Our bench marking efforts are seeking | [10 empty] | 20 | 0
|  | in project management activities. | [8 empty] | 0 |  | other companies that are performing resource | [10 empty] | efficiency and effectiveness of their project | [10 empty] | out other companies' use of corporate | [10 empty] | 21 | 0
[13 empty] | constraint analysis. | [8 empty] | 0 |  | management technology. | [8 empty] | 0 |  | resource models. | [8 empty] | 0 |  | 25 | 0 | [6 empty] | Combined Scores
5. |  | Our benchmark studies are investigating | [51 empty] | 37 or greater | Your organization is performing benchmarking well. The right information is being considered and
|  | customer involvement in project | [9 empty] | 12. | Our benchmarking efforts are looking at | [9 empty] | 19. | Our benchmarking efforts focus on how | [30 empty] | the right companies are being targeted. The balance between quantitative and qualitative benchmarking
|  | management activities. | [8 empty] | 0 |  | the way other companies manage their customers | [10 empty] | to obtain a lower cost of quality. | [8 empty] | 0 | [21 empty] | is good.
[13 empty] | during scope change management process. | [8 empty] | 0
6. |  | Our benchmarking studies are | [20 empty] | 20. | Our benchmarking efforts are looking at
|  | investigating how to obtain increased | [9 empty] | 13. | Our benchmarking efforts are looking at | [10 empty] | the way other companies are performing
|  | loyalty/usage of project management | [10 empty] | the way other companies involve their customers | [10 empty] | risk management during concurrent
|  | methodology. | [8 empty] | 0 |  | during risk management activities. | [8 empty] | 0 |  | engineering activities. | [8 empty] | 0
7. |  | Our benchmarking efforts are looking at | [9 empty] | 14. | Our benchmarking efforts are looking at | [9 empty] | 21. | Our benchmarking efforts are looking at
|  | industries in the same business area as | [10 empty] | software enhancements through internal | [10 empty] | the way other companies use enhancement
|  | our company. | [8 empty] | 0 |  | upgrades. | [8 empty] | 0 |  | projects as part of scope change management. | [8 empty] | 0

## Continuous Improvement
LEVEL | The following 16 questions explore how mature you believe your organization to be in regard to Level 5 - Continuous Improvement. | [21 empty] | SCORING | Transpose your scores for each question below. (If you are taking the computer version of this assessment,
FIVE | Beside each question you will enter the number that corresponds to your opinion based on the following key | [22 empty] | the scores should appear below.)
|  |  | Your | Strongly | Disagree | Slightly | No | Slightly | Agree | Strongly |  |  |  | Your | Strongly | Disagree | Slightly | No | Slightly | Agree | Strongly
|  |  | Opinion | Disagree |  | Disagree | Opinion | Agree |  | Agree |  |  |  | Opinion | Disagree |  | Disagree | Opinion | Agree |  | Agree
Question |  |  | Enter | -3 | -2 | -1 | 0 | 1 | 2 | 3 |  | Question |  | Enter | -3 | -2 | -1 | 0 | 1 | 2 | 3
LEVEL 5 Maturity
1. |  | The improvements to our methodology have | [9 empty] | 10. | Our culture is a cooperative culture to the | [10 empty] | Continuous Improvement
|  | pushed us closer to our customers. | [8 empty] | 0 |  | point where informal rather than formal | [12 empty] | SCORES
[13 empty] | project management can be used, and | [10 empty] | 1 | 0
2. |  | We have made software enhamcements to | [10 empty] | changes have been made to the informal | [10 empty] | 2 | 0 | Scores 20 or more are indicative of an organization committed
|  | our methodology. | [8 empty] | 0 |  | project management system. | [8 empty] | 0 |  | 3 | 0 | to benchmarking and conitnuous improvement.
[24 empty] | 4 | 0
3. |  | We have made improvements that allowed us | [9 empty] | 11. | Changes in power and authority have | [10 empty] | 5 | 0 | Scores between 10-19 are indicative that some forms of continuous
|  | to speed up the integration of activities. | [8 empty] | 0 |  | resulted in a looser methodology (I.e., | [10 empty] | 6 | 0 | improvement are taking place, but the changes may be occurring slowly.
[13 empty] | guidelines rather than policies and procedures). | [8 empty] | 0 |  | 7 | 0
4. |  | We have purchased software that allowed us | [21 empty] | 8 | 0 | Scores less than 9 imply strong resistance to change or simply a lack of
|  | to eliminate some of our reports and documentation. | [8 empty] | 0 | 12. | Overtime requirements mandated change in our | [10 empty] | 9 | 0 | support for continuous improvement.
[13 empty] | forms and procedures. | [8 empty] | 0 |  | 10 | 0
5. |  | Changes in our training requirements | [21 empty] | 11 | 0
|  | have resulted in changes to our methodology. | [8 empty] | 0 | 13. | We have changed the way we communicate | [10 empty] | 12 | 0
[13 empty] | with our customers. | [8 empty] | 0 |  | 13 | 0
6. |  | Changes in our working conditions (eg., facilities, | [8 empty] | 0 | [12 empty] | 14 | 0
|  | environment) have allowed us to to streamline | [9 empty] | 14. | Because our projects' needs have changed, | [10 empty] | 15 | 0 |  | Your Score | Minimal Acceptable | Benchmark
|  | our methodology (eg., paperwork reduction). | [8 empty] | 0 |  | so have the capabilities of our resources. | [8 empty] | 0 |  | 16 | 0 |  | 0 | 10 | 20
7. |  | We have made changes ot the methodology | [9 empty] | 15. | (If your organization has restructured) | [9 empty] | Total Score |  | 0
|  | in order to get corporate-wide acceptance. | [8 empty] | 0 |  | Our restructuring caused changes in the
[13 empty] | signoff requirements in the methdology. | [8 empty] | 0
8. |  | Changes in organizational behavior have
|  | resulted in changes to the methodology. | [8 empty] | 0 | 16. | Growth of the company's business base
[13 empty] | has caused enhancements to our methodology. | [8 empty] | 0
9. |  | Management support has improved to the
point where we need fewer gates and
|  | checkpoints in our methodology. | [8 empty] | 0

## Summary of Results
| Your Score | Benchmark
Scope | 0 | 30
Time | 0 | 30
Cost | 0 | 30 |  | Your Score | Benchmark
Human Resources | 0 | 30 | Maturity | 0 | 6
Procurement | 0 | 30 | Growth | 0 | 6 |  |  |  | Your Score | Benchmark
Quality | 0 | 30 | Middle/Lower Management | 0 | 6 | Your Score | Benchmark | Quantitative | 0 | 25
Risk | 0 | 30 | Executive | 0 | 6 | 0 | 169 | Qualitative | 0 | 12
Communications | 0 | 30 | Embryonic | 0 | 6 |  |  | Combined | 0 | 37 | Your Score | Minimal Acceptable | Benchmark
[11 empty] | 0 | 10 | 20