## Tips
1. When you sit down to take exam at a computer testing center, you’ll be given scratch paper. You’ll also have 15 minutes to go through a tutorial that shows you how use the exam system. Before you finish the tutorial, take a minute and write down all of the formulas. Write down the earned value formulas and the formula to calculate the lines of communication on the scratch paper. That will make any calculation question easy. 2. Books / reference material * PMBOK_4th_Edition.pdf * http://www.pmroadtrip.com/readonlinev4.html -- very good examples, helps understanding concepts from PMBOK * Head First PMP 2nd Edition (2009).pdf * Kim Heldman.PMP.5th.Edition.Jun.2009.pdf -- Excellent sample PMP tests * Rita 6 Edition PMP Exam PREP.pdf -- MUST read (twice or more) 3. The PMP exam is a 4-hour multiple choice exam. In these 4 hours, you are going to have to answer 200 questions. Each question is either scenario based or knowledge based and has 4 possible answers - A, B, C or D. You can only select one answer. Out of these 200 questions, 25 are considered "pretest questions". These pretest questions do not affect your score. The PMI uses them as an effective and legitimate way for testing the questions. In other words: new questions for the exam are first tried out in this way, to see how well they work. The pretest questions are randomly placed throughout the exam. So you start out with 200 questions minus the 25 pretest questions which leaves 175 questions. Out of these, you must answer 106 correctly , that is 61%. 4. For Practice exam online, try the free: * Head First PMP online exam simulator: http://www.headfirstlabs.com/PMP/free_exam/ * Free exam: http://www.oliverlehmann.com/contents/free-downloads/175_PMP_Sample_Questions.pdf 5. Exam Question distribution: Project Initiation 11% Project Planning 23% Project Execution 27% Project Monitoring and Control 21% Project Closure 9% Code of conduct 9%

## Intro
Enterpise Environmental Factors: People: The skills and organizational culture where you work. Risk Tolerance: Some companies are highly tolerant of risk and some are really risk averse. Market: The way your company is performing in the market can affect the way you manage your project. Databases: Where your company stores its data can make a big difference in the decisions you make on your project. Standards: Some companies depend on government standards to run their business and when they change, it can have a big impact Organisational culture, infrastructure, PMIS (an automated tool, a config mgmt system...) | Portfolio: A portfolio is a group of projects or programs that are linked together by a business goal. Program: A program is a group of projects that are closely linked, to the point where managing them together provides some benefit. Project: A project is any work that produces a specific result and is temporary. Projects always have a beginning and an end. But they are never ongoing. Operations: are ongoing. If you’re building cars on an assembly line, that’s a process. If you’re designing and building a prototype of a specific car model, that’s a project. A project may or may not be part of a program, but a program will always have projects. Portfolios are organized around business goals and Programs are organized around a shared benefit in managing them together.
Deal with project constraints: Sometimes there will be constraints on the project that you’ll need to deal with. You might start a project and be told that it can’t cost more than $200,000. Or it absolutely MUST be done by the trade show in May. Or you can only do it if you can get one specific programmer to do the work. Or there’s a good chance that a competitor will beat you to it if you don’t plan it well. It’s constraints like that that make the job more challenging, but it’s all in day’s work for a project manager. | Stakeholder: Anyone who will be affected by the outcome of your project is a stakeholder. - sponsor who’s paying for the project - the team who’s building it - people in management who gave the project the green light are all good examples. Constraints: Cost, Time, Scope, Quality, Risk, and Resources Qs. A project coordinator is having trouble securing programmers for her project. Every time she asks her boss to give a resource to the project he says that they are too busy to help out with her project. Which type of organization is she working in? Ans: Since the project manager has to ask permission from the functional manager and can’t overrule him, she’s working in a functional organization. Qs. A project manager is having trouble securing programmers for her project. Every time she asks the programming manager for resources for her project, he says they’re all assigned to other work. So she is constantly having to go over his head to overrule him. Which type of organization is she working for? Ans: The Project Manager in this scenario can overrule the functional manager, so she’s working in a Strong Matrix organization. If it were a projectized organization, she wouldn’t have to get permission from the functional manager at all because she’d be the person with authority to assign resources to projects.
In a FUNCTIONAL Organization, the teams working on the project don’t report directly to the PM. Instead, the teams are in departments, and the project manager needs to “borrow” them for the project. Project team members always report to a functional manager. In PROJECTIZED Organization, the team reports to the project manager, who has a lot more authority. -- Teams are organized around projects. When a project is done, the team is released, and the team members move to another project. -- The project manager makes all of the decisions about a project’s budget, schedule, quality, and resources. -- The PM is responsible for the success or failure of their project. WEAK MATRIX: -- PMs have some authority but they aren’t in charge of the resources on a project. -- Major decisions still need to be made with the functional manager’s cooperation or approval. BALANCED MATRIX: Folks who work in a balanced matrix organization report to a PM AND a functional manager equally. STRONG MATRIX: Project managers have more authority than functional managers, but the team still reports to both managers. Exam Tip: If a question on the exam doesn’t state an organization type, assume it’s referring to a matrix organization. That means the PM is responsible for making budgets, assigning tasks to resources, and resolving conflicts.
-- Costs and staffing levels are lowest early in the life cycle, peak while the project work is underway, and then drop off as the project nears completion. -- Risk is highest early in the project since uncertainty is high about the project’s deliverables, resource needs, and work required. and all this uncertainty means that a project is most likely to fail early in its life cycle. -- Stakeholder influence in the project and its deliverables is highest early in the life cycle but diminishes as the project proceeds because the cost of incorporating changes increases the further the project is into its life cycle. So one way of controlling unexpected project cost is to engage stakeholders early to prevent unnecessary and costly changes later in the project. Payback Period: The payback period tells us how long it will take to recoup the expense of the project, so a shorter payback period is better. It’s often used in conjunction with other sophisticated formulas, but at its simplest, the payback period is calculated using the project costs plus any ongoing costs as a result of the project compared to any savings or increase in profits the project’s product will provide. For example, a project to replace an outmoded process is expected to cost $80,000 and require $10,000 a year to maintain. But it’s expected to result in a $50,000 annual savings. The payback period for this project will be two years. When calculating a payback period, keep in mind how long the project will take. In the example below, if the project requires one year to be completed, the payback period would be three years instead of two. Opportunity Cost: Opportunity cost is the monetary value that is forgone when one action is chosen over another. For us, it simply reflects what money is “lost” by choosing one project over another, and it’s the entire value of the opportunity not chosen. For example, if project A was valued at $50,000 and project B was valued at $80,000: •Choosing project A results in a lost opportunity cost of $80,000 (the entire value of project B) •Choosing project B results in a lost opportunity cost of $50,000 (the entire value of project A) | Benefit/Cost Ratio Formulas: Benefit/cost formulas are used by nearly every organization to assist in making project selection decisions. Below is an overview of common formulas. Return on Investment (ROI): ROI is attractive for its simplicity, but it doesn’t reflect the time value of money or profitability. A larger ROI is the better choice. ROI = (Benefit – Cost)/Cost Example: The ROI of a project that will cost $100,000 but result in a $250,000 benefit or increase in profits is 1.5. ROI=(250,000-100,000)/100,000 ROI=150,000/100,000 ROI=1.5 Future Value (FV): We all know that $1 today will not have the same purchasing power in the future, so the future value formula accounts for this time value of money. It uses the interest rate and the number of periods to calculate what the future value of money will be. A higher future value is preferred. Using future value, if the interest rate is 5 percent, $1 today will be worth $1.05 next year. FV = Current Value x (1 + I)^n where I is the interest rate and n is the number of periods. Example: The future value of $100,000 in two years at an average interest rate of 5% is $110,250. FV = 100,000 x (1 + .05)^2 FV=100,000 x (1.05)^2 FV=100,000 x 1.1025 FV=110,250 Present Value (PV): If a project will return $1 next year, what is that dollar worth in today’s value? The present value formula is the inverse of the future value formula, and it converts future money to reflect what its present value is by using the interest rate. PV = Future Value / (1 + I)^n where I is the interest rate and n is the number of periods. Example: The present value of $125,000 earned five years from now at an average interest rate of 7% is worth only $89,123.38 today. PV=125,000 / (1 + .07)^5 PV=125,000 / (1.07)^5 PV=125,000 / 1.40255 PV=89,123.38

## PrjMgtFramework
Project Mgt Framework
Definition of Project: A project: - is a teporary endeavour with a beginning and an end. - creates a unique product, service or result. Operational Work: is ongoing work and repetitive Program: is a group of related Projects. Portfolio: is a group of programs to achieve a specific strategic business goal. Objectives: -project objectives are contained in the project charter -projects are considered complete when objectives are met. Management by Objectives (MBO): -establish unambiguous and realistic objectives -periodically observe if objectuves are being met -implement corrective actions Constraints: Cost, Time, Scope, Quality, Resources, Risk, Customer satisfaction | Why do projects end? -when they meet their objectives -an also end prematurely when it becomes clear that the objectives can’t be met -need for the project no longer exists. --Project scope: work, and only the work required to produce the project’s deliverables. --Product scope: describes the characteristics and functionality of the product, service, or result. --Costs and staffing levels are LOWEST early in the life cycle, peak while the project work is underway, and then drop off as the project nears completion. --Risk is highest early in the project since uncertainty is high about the project’s deliverables, resource needs, and work required. --Stakeholder influence in the project and its deliverables is highest early in the life cycle but diminishes as the project proceeds because the cost of incorporating changes increases the further the project is into its life cycle. --Programs are collections of individual projects that support a central objective --Portfolios are organized around business goals and Programs are organized around a shared benefit in managing them together. --PMO: may help provide resources, terminate projects, help gather lessons learned, be part of Change Cntrl Board,...etc --Knowledge, performance, and personal skills are the three areas that project managers focus on to get better at their jobs.
Organisational Structure: Functional: org is grouped by areas of specialization within different functional areas. Authority is with functional managers. Projectized: entire company is organised by projects. The PM has control of projects. Perssonal are assinged and report to a PM. Team members only complete the project work and when the project is over, they do not have a department to go back to. Matrix: Team member reports to two bosses, the PM and the Functional Mgr. Share responsibility and authority between the two. As compared to functional org, there would be improved Proj Mgr control over the resources and better horizontal & vertical dissemination of information. In STRONG Matrix - power rests with Project Mgr. Project managers have more authority than functional managers, but the team still reports to both managers. In BALANCED Matrix - Project managers share authority with the functional managers. In WEAK Matrix - power rests with Functional Mgr and power of Project Mgr is comparable to that of a coordinator or expediter. PMs have some authority but they aren’t in charge of the resources on a project. A project expediter is somebody who keeps track of status but has no decision-making authority on a project at all. just keeps everybody informed of projects progress. A project coordinator is someone who does pretty much the same thing, but does get to make some of the minor decisions on the project without having to run them by the functional manager. Coordinators usually report to somebody who is pretty high up in the organization, while expediters are more like assistants to the functional manager. ------------- You’re likely to find project expediters in functional organizations. ------------- Project coordinators and expediters don’t exist in a projectized organization. When you’re taking the PMP exam, if you see a question that mentions a PM, then you should assume that the question is asking about a matrix organization if it doesn’t say up front which kind of organization is being described. Functional organizations are usually painted in a negative light because they tend to give less authority to project managers. If a question on the EXAM doesn’t state an organization type, assume it’s referring to a Matrix organization. That means the PM is responsible for making budgets, assigning tasks to resources, and resolving conflicts. Product Life Cycle: CONCEPTION, GROWTH, MATURITY, DECLINE, WITHDRAWAL. A Product can spawn across many projects over its life. Project Life Cycle: Feasibility, Planning, Design, Coding, testing, installation, conversion, turnover to operations.

## Proff Resp
PMI Code of Ethics and Professional Conduct
Ethics and professional responsibility questions make up 9% of the exam. That’s good news because these questions are really easy if you understand the ideas behind the PMP Code of Professional Conduct.
Bribes aren’t always cash. They can be anything ranging from free trips to tickets to a ball game. Any time you’re offered anything to change your opinion or the way you work, you must decline the offer and disclose it to your company.
Fly business class? Even if it seems like no harm will be done if you don’t follow the policy, and even if you will be able to get away with it, you should not do it. And that goes double for laws—under no circumstances are you ever allowed to break a law, no matter how much good it “seems” to do you or your project.
New software When it comes to copyright, it’s never OK to use anything without permission. Books, articles, music, software... you always need to ask before using it. For example, if you want to use some copyrighted music in a company presentation, you should write to the copyright owner and ask for permission.
Shortcuts You might see a question or two that asks if you really need to follow all of the processes. Or you might be asked by your boss to keep certain facts about your project hidden from stakeholders or sponsors. You have a responsibility to make sure your projects are run properly, and to never withhold information from people who need it.
Being responsible to the community is even more important than running a successful project. But it’s more than being environmentally aware—you should also respect the cultures of everyone else in your community, and the community where your project work will be done.
PMI Code of Ethics and Professional Conduct
The PMI Code of Ethics and Professional Conduct outlines four areas of responsibility: 1- Responsibility -- ownership of decisions and actions 2- Respect -- treatment of people and resources 3- Fairness -- objective and impartial decision 4- Honesty -- truth-based actions
Responsibility: Responsibility is the act of making decisions that are for the good of the organization rather than ourselves, admitting our mistakes, being responsible for the decisions we make and the consequences that result, along with other actions. -- Ensuring Integrity: As a project manager, one of your professional responsibilities is to ensure integrity of the project management process, the product, and your own personal conduct. Correctly applying the project management processes you’ve learned will ensure the integrity of the product. -- Accepting Assignments: You should not knowingly accept assignments that are beyond your capabilities or experience. -- Laws and Regulations Compliance: This might seem obvious, but as a professional, you’re required to follow all applicable laws and rules and regulations that apply to your industry, organization, or project. This includes PMI organizational rules and policies as well. -- Confidential Information: -- Company Data: -- Intellectual Property:
Respect: Respect involves several areas as well, including the way we conduct ourselves, the way we treat others, listening to other viewpoints, conducting ourselves in a professional manner, and so on. -- Professional Demeanor: * Part of acting professionally involves controlling yourself and your reactions in questionable situations. As a professional, your concern for the project and the organization should take precedence over your concern for your own feelings. Therefore, lashing out in return would be unprofessional. Maintain your professional demeanor, and don’t succumb to shouting matches or ego competitions with others. -- Reporting Ethics Violations: As a PMP, one of the responsibilities that falls into this category is your responsibility to report violations of the PMP code of conduct. When you know a violation has occurred and you’ve verified the facts, notify PMI. Part of this process—and a requirement of the code of conduct—is that you’ll verify that an ethics violation has occurred (in other words, don’t report bogus or unsubstantiated reports) and will assist PMI in the investigation by supplying information, confirming facts and dates, and so on. This includes anything listed as violations in the PMI Code of Ethics and Professional Conduct, such as conflicts of interest, untruthful advertising, and false reporting of PMP experience and credentials, appearances of impropriety, and so on. -- Cultural Awareness: “When in Rome, do as the Romans do”? -- Culture Shock: Working in a foreign country can bring about an experience called culture shock.One of the ways you can avoid culture shock is to read about the country you’re going to work in before getting there. -- Diversity Training: Sometimes you might find yourself working with teams of people from different countries or cultures. Some team members might be from one country and some from another. The best way to ensure that cultural or ethical differences do not hinder your project is to provide training for all team members. Team-building activities are ways to build mutual trust and respect and bond team members with differing backgrounds. -- Respecting Your Neighbors: -- Perceiving Experiences:
Fairness: Fairness includes avoiding favoritism and discrimination against others, avoiding and reporting conflict of interest situations, and maintaining impartiality in our decision making process. -- Conflict of Interest: A conflict of interest is when you put your personal interests above the interests of the project or when you use your influence to cause others to make decisions in your favor without regard for the project outcome. In other words, your personal interests take precedence over your professional obligations, and you make decisions that allow you to personally benefit regardless of the outcome of the project. * Associations and Affiliations: For example, perhaps your brother-in-law owns his own construction company and you are the project manager who has just published an RFP. Your brother-in-law bids on the project and ends up winning the bid. * Vendor Gifts: Don’t accept gifts that might be construed as a conflict of interest. If your organization does not have a policy regarding vendor gifts, set limits for yourself depending on the situation, the history of gift acceptance by the organization in the past, and the complexity of the project. It’s always better to decline a gift you’re unsure about than to accept it and later lose your credibility, your reputation, or your PMP status because of bad judgment. * Stakeholder Influence:
Honesty: Honesty can include a lot of topics: reporting the truth regarding project status, being honest about your own experience, not deceiving others, not making false statements, and so on. -- Personal Gain: Honesty involves not only information regarding your own background and experience, but information regarding the project circumstances as well. -- Truthful Reporting: As a project manager, you are responsible for truthfully reporting all information in your possession to stakeholders, customers, the project sponsor, and the public when required. Always be up front regarding the project’s progress. -- Role Delineation Study: In addition to the areas covered in the PMI Code of Ethics and Professional Conduct, you should be aware of four other focus areas that PMI discusses in its role delineation study. This study was published in PMI’s publication Project Management Professional (PMP®) Examination Specification. The four focus areas are as follows: * Ensure Personal Integrity and Professionalism * Contribute to the Project Management Knowledge Base * Enhance Personal Professional Competence * Promote Interaction Among Team Members & Other Stakeholders
Applying Professional Knowledge: Professional knowledge involves the knowledge of project management practices as well as specific industry or technical knowledge required to complete an assignment. As a PMP, you should apply project management knowledge to all your projects. Take the opportunity to educate others by keeping them up-to-date on project management practices, training your team members to use the correct techniques, informing stakeholders of the correct processes, and then sticking to those processes throughout the course of the project. One way to apply professional knowledge is to become and remain knowledgeable in project management best practices techniques. -- Project Management Knowledge:

## Integration
INTEGRATION
Sl# | Inputs | Tools & Techniques | Outputs
| Understanding How Projects Come About: 1. Needs and Demands: Market demand, Strategic opportunity/business need, Customer request, Technological advance, Legal requirement, Social need…etc 2. Feasibility Studies: One is to determine whether the project is a viable project. A second reason is to determine the probability of the project succeeding. 3. Selecting and Prioritizing Projects: Using Project Selection Methods: There are generally two categories of selection methods: mathematical models (also known as calculation methods) and benefit measurement methods (also known as decision models). * Mathematical models is that they use linear, dynamic, integer, nonlinear, and/or multi-objective programming in the form of algorithms—or in other words, a specific set of steps to solve a particular problem. Mathematical models are also known as Constrained optimization methods * Benefit Measurement Methods: employ various forms of analysis and comparative approaches to make project decisions. These methods include comparative approaches such as cost-benefit analysis, scoring models, and benefit contribution methods that include various cash flow techniques and economic models. -- Scoring Model or Weighted Scoring Model: -- PAYBACK Period: The payback period is the length of time it takes the company to recoup the initial costs of producing the product, service, or result of the project. -- DISCOUNTED CASH FLOWS: FV = PV (1+r)n, , discounted cash flow technique compares the value of the future cash flows of the project to today’s dollars. In order to calculate discounted cash flows, you need to know the value of the investment in today’s terms, or the PV. PV is calculated as follows: PV = FV / (1 + i)n . NET PRESENT VALUE - NPV: When you get a positive value for NPV, it means that the project will earn a return at least equal to or greater than the cost of capital. INTERNAL RATE OF RETURN - IRR: is the discount rate when the present value of the cash inflows EQUALS the original investment. When choosing between projects or when choosing alternative methods of doing the project, projects with higher IRR values are generally considered better than projects with low IRR values. |  |  | Apply the PV formula to the projects you’re considering, and then compare the discounted cash flows of all the projects against each other to make a selection. Here is an example comparison of two projects using this technique: Project A is expected to make $100,000 in two years. Project B is expected to make $120,000 in three years. If the cost of capital is 12 percent, which project should you choose? Using the PV formula used previously, calculate each project’s worth: The PV of Project A = $79,719. The PV of Project B = $85,414. Project B is the project that will return the highest investment to the company and should be chosen over Project A. Exam Spotlight For the exam, you need to know three facts concerning IRR: 1. IRR is the discount rate when NPV equals zero. 2. IRR assumes that cash inflows are reinvested at the IRR value. 3. You should choose projects with the highest IRR value.
1 | Develop Project Charter: The process of developing a document that formally authorize a project or a phase and documenting initial requirements that satisfy the stakeholder's needs and expectations. The sponsor of a project is responsible for creating the project charter. The sponsor of a project pays for the project. The initiator's (sponsor) signature on the Charter authorizes the project. The approved Project Charter formally initiates the project. The PM manages the project. ** Remember for the EXAM that the charter is authorized by someone EXTERNAL to the project. SOW: The essential elements of the SOW are 1. WHAT is to be done (Product Scope Description), 2. the business REASON for doing it (Business Need), and 3. HOW the project supports the organization's strategy (Strategic Plan). And it is a written description of the project's product, service, or result. PMI calls a SOW for external organizations 'a contract statement of work'. For Internal Projects, the Project Initiator or Sponsor provides. For External Projects, the Customer provides as part of a bid document. Project Selection Methods: 1- Benefit Measurement Methods (Comparative approach): a. Economic Models, b. Scoring Models, c. Comparative Approach, d. Benefit Contribution, and e. Murder Board 2- Constrained Optimization Methods (Mathematical): a. Linear programming, b. Non-Linear programming, c. Dynamic, d. Integer, and e. Multi-objective algorithms 3. Additional Methods: 1. Benefit Cost Ratio (BCR), 2. Economic Value Add (EVA) - If a project does not make more moeny than those opportunity costs, it has not truly added economic value to the organization, 3. Internal Rate of Return (IRR) - Bigger is better, 4. Opportunity Cost - 'What is the cost of the other opportunities we missed by investing our money in this project?'. The Smaller the opportunity cost, the better. 4. Payback Period - a Shorter payback period is better than a longer one., 5. Present Value (PV) and Net Present Value (NPV): Bigger PV or NPV makes a project more attractive., 6. Return on Investment (ROI) - Bigger is better., and 7. Retun on Invested Capital (ROIC) = Net Income (after tax) from Project / Total Capital Invested in the Project. |  |  | Project Charter contains: -Project Description: This is a high-level description of the goals of your project. It’s usually a few sentences that describe the project’s main purpose. -Project Requirements (SOW):Anything you know that the customer,stakeholder, or sponsor expects to getout of the project should go here. Describes the product your project has to make. -Assigned Project Manager and Authority Level: Who the project manager is and what he has to do -Summary Milestone Schedule: (very high‑level schedule) A list of dates that your project needs to meet -Business Case:This section lists the reasons why it makes sense for your business to do this project. -The major stakeholders and their influences and project interest. -The measurable success criteria for the project and who’ll sign off and measure those success points when the project is completed. -PC is signed by the performing organization's Senior Management. Project Selection Methods: 1. Present value PV = Future Value FV / ( 1 + r )n 2. Net Present value NPV = total benifits - costs over the period....generally if NPV is positive, then investment is good. The project with greatest NPV is selected. Question: You have 2 projects to select from. Project A will take 3 years to complete and has NPV of $45,000. Project B will take 6 years to complete and has NPV of $85,000. Which one would you prefer? Answer: Project B, the time period is not relevant as would have been taken care while calculating NPV. 3. Internal Rate of Return IRR: The project with greatest IRR is selected. 4. Payback Period: refers to number of time periods it takes to recover your investments in the project before you start accumulating profit. The project with lowest payback period is selected. 5. Benefit cost ratio: A benefit cost ratio greater than 1 means benefits are greater than costs. A benefit cost ratio less than 1 means costs are greater than benefits. A benefit cost ratio equal to 1 means costs and benefits are same. Question: if the BC ratio of Proj A is 2.3 and the BC ratio of Proj B is 1.7, which proj would you select? Answer: A, the proj with higher benefit cost ratio is selected. 6.Opportunity Cost: this refers to the opportunity given up by selecting one project over another. Question: You have 2 projects to select from. Project A has NPV of $45,000 and Project B has NPV of $85,000. What is the opportunity cost of selecting project B? Answer: $45,000 Exam Q: What type of project selection method is linear programming: => Constrained Optimization Methods Depreciation: ------1-----Straight Line depreciation -------2----Accelerated Depreciation ---------------2.a-------Double declining balance ---------------2.b-------Sum of the Years Digit
INITIATING | Contract | 1. Expert Judgment | 1. Project Charter (PC)
| Business Case: - A Business Case document says why it’s worth it to spend money on the project. - It includes a narrative and benefit/cost information. | a. Project Charter is created based on some need, and it should explain that need. | e. PC should include a high-level milestone view of the project schedule.
| Project Statement of Work (SOW): A statement of work is a written description of the project's deliverable. SOW should contain: business need, scope, and how the proejct fits into the strategic plan. When the project is internal, this document is usually written by either the project sponsor. When the project is external to the organization, the buyer typically writes the SOW. | b. PC is signed by the performing organization's Senior Management. | f. PC is a high-level document that does not include project details; the specifics of project activities
| Enterprise Environmental Factors: Organizational culture, structure, and processes etc. | c. PC names the PM and gives PM authority to manage. | will be developed later.
| Organizational Process Assets: (for referring to lessons learned from past) | d. PC should include the high-level proj requirements, high-level Project Description, high-level Risks. | g. PC includes a summary-level prelim project budget. h. Show organizational, environmental and external CONSTRAINTS and ASSUMPTIONS.
2 | Develop Project Management Plan: The process of documenting the actions necessary to define, prepare, integrate, and coordinate all subsidiary plans. The Project Plan is "a formal, approved document that defines HOW the project is executed, monitored and controlled, and closed. It may be summary or detailed and may be composed of one or more subsidiary management plans and other planning documents". It would be approved by * The Project Manager, * The Project Sponsor, * The Functional Manager who are providing resources for the project. (for the exam we will do much better to think of the Project Management Plan as always being DETAILED). |  |  | The project management plan is a single document, but it’s broken into a bunch of pieces called subsidiary plans. There’s one subsidiary plan for each of the other knowledge areas: scope management, time management, cost management, quality management, human resource management, communications management, risk management, and procurement management. Proj Mgmt Plan contains scope, cost, schedule baselines. Scope baseline is Proj scope stmt + WBS + WBS Dictionary -- Together these baselines are called Performance Measurement Baseline. Exam: if the exam asks what to do when a project deviates significantly from established baselines, the correct answer is likely the one about reviewing the projects risk mgmt process. Deviations from baselines are often due to incomplete identification of risks and risk management. * You may get a question on the exam that asks what to do when you encounter a change. * You always begin dealing with change by consulting the project management plan. * The work authorization system is a part of your company’s Enterprise Environmental Factors, and it’s generally part of any change control system. * The project management plan includes baselines: snapshots of the scope, schedule, and budget that you can use to keep track of them as they change.
PLANNING | 1. Project Charter | 1. Expert Judgment | 1. Project Management Plan
| 2. Outputs from Planning Processes |  | (The SCOPE mgmt plan, the SCHEDULE mgmt plan, the COST mgmt plan, the CHANGE mgmt plan, and the CONFIGURATION mgmt plan are created right here.) Project Sponsor APPROVES the Proj Mgmt Plan. Configuration Mgmt System: is part of the PMIS. It contains organisations standard config mgmt tools, processes and procedures.
3. Enterprise Environmental Factors
4. Organizational Process Assets
3 | Direct and Manage Project Execution: The Direct and Manage Execution Process is where you and your team actually do the project work to produce the Deliverables. The process of perfoming the work defined in the project management plan to achieve the project's objectives. It occurs any time; we are following the project management plan to create project deliverables. Most of the project resources and costs are expended in this process. * Direct and Manage Execution process has a bunch of inputs and outputs—but most of them have to do with implementing changes, repairs, and corrective action |  |  | The three components of the Direct and Manage Project Execution process: 1. Use the plan to create deliverables 2. Repair defects in deliverables 3. As the project plan changes, make sure those changes are reflected in the deliverables Proj Mgmt tools used to ensure common understanding on a project: scope mgmt plan, WBS, WBS Dictionary,
EXECUTING | 1. Project Management Plan | 1. Expert Judgment | 1. Deliverables
| 2. Approved Change Requests | 2. Project Management Information System - PMIS | 2. Work Performance Information Your job is to direct the work, but you need to do more than deliver the results. You also need to keep track of how well your team performed—and that’s what the work performance information output is about
| 3. Enterprise Environmental Factors | (It can include both manual and automated systems | 3. Change Requests
| 4. Organizational Process Assets | used together, integrate, and disseminate the outputs of | 4. Project Management Plan Updates
|  | the Develop Project Management Plan Process) | 5. Project Document Updates
4 | Monitor and Control Project Work: The process of tracking, reviewing, and regulating the progress to meet the performance objectives defined in the project management plan. Any necessary changes in the work or the plan are identified and made in this process. # Mid-Project Evaluations are conducted while project work is still in progress. The main purpose of such evaluations is to determine if objectives are still relevant and if these objectives are being met. Lessons Learned should also be documented at this time instead of waiting for the project to be completed. A third party or people outside the team should be used to conduct mid-project evaluations. -----------------------------------------------------Monitoring and Controling means measuring against the project mgmt plan.-------------------------------------------- Change Requests: 1.Corrective Actions: Documented direction for executing the project work to bring expected future performance of the project work in line with the project management plan. 2.Preventive Actions: A documented direction to perform an activity that can reduce the probability of negative consequences associated with project risks. 3.Defect Repair: The formally documented identification of defect in the project componenet with a recommendation to either repair the defect or completely replace the component. 4.Updates: Changes to formally controlled documentation, plans, etc., to reflect modified or additional ideas or content. # Corrective and Preventive Actions do not normally effect the Project Baselines, only the performance against the baselines. # Any information (Schedule/Milestones/Cost/Quality/Etc) related to the deliverables being produced here could be considered Work Performance Information. |  |  | ** The Monitor and Control Project Work process is where you find the changes that you may want to make. Exam: if the exam asks what you should do if a work activity on project takes longer than estimated, then answer is to take corrective actions to make up for the delay. The documented scope, schedule, and cost baselines are in the Project Management Plan are called the Performance Measurement Baseline. Exam: situational Q for exam, for example: a functional manager wants to make a change to the project, what is the first thing a PM should do? 1. evaluate the impact - considering all the project constraints 2. create options - are created based on crashing, fast tracking, reestimating..etc 3. get change request approved internally 4. get customer buy-in (if required) Exam: ####### Detailed Process of Making Changes: 1. Prevent the root cause for changes 2. Identify change 3. Look at impact of the change 4. Create a change request 5. Perform Inetegrated Change Control a. evaluate the impact - considering all the project constraints b. create options - are created based on crashing, fast tracking, reestimating..etc c. get change request approved internally d. get customer buy-in (if required) 6. Adjust the Proj Mgmt Plan, proj doc, baseline 7. Communicate change to stakeholders 8. Manage Project to the revised Proj mgmt Plan.
M & C | 1. Project Management Plan | 1. Expert Judgment | 1. Change Requests
| 2. Performance Reports |  | 2. Project Management Plan Updates
| 3. Enterprise Environmental Factors |  | 3. Project Document Updates
4. Organizational Process Assets
5 | Perform Integrated Change Control: The process of reviewing all change requests, approving changes, and managing changes to 1. the deliverables, 2. organizational process assets, 3. project documents, and 4. the project management plan. It brings together (integrates) all of the other Monitoring and Controlling Processes. And it evaluate the IMPACT of a change across the entire project. Changes may be requested by any stakeholder involved with the project. # Perform Integrated Change Control is primarily focused on MANAGING CHANGE to the project's SCOPE, while Monitor and Control Project Work is primarily focused on MANAGING THE WAY that SCOPE is EXECUTED. # Approved Change Requests will be implemented by the Direct and Manage Project Execution process. # CCB is responsible for reviewing changes and change requests and its level of authority should be spelled out in the Project Management Plan. |  |  | The Perform Integrated Change Control process is where you decide whether or not to make them. But you’re not the one actually making that decision – a big part of Perform Integrated Change Control is that you need to get your changes approved by the Change Control Board. After Integrated Change Control, we go back to the Direct & Manage Project Execution process to put the approved changes in place. If the Integrated Change Control process says it’s OK to go ahead, you make the change. The important thing to remember is that the change requests come from Monitor and Control Project Work, but are actually made during Direct and Manage Execution. Q: Once a change is approved, what do I do with it? A: You change your project management plan to incorporate the change. This can mean that you create a new baseline with the new project management plan. Be careful about questions on Change, Sometime evaluations are done, so the NEXT best thing to do is to look for options. Sometimes evaluation AND looking for options are done, then the NEXT best thing to do is to meet the sponsor or CCB and get the change approved.
M & C | 1. Project Management Plan | 1. Expert Judgment | 1. Change Request Status Updates
| 2. Work Performance Information | 2. Change Control Meetings | 2. Project Management Plan Updates
| 3. Change Requests |  | 3. Project Document Updates
4. Enterprise Environmental Factors
5. Organizational Process Assets
6 | Close Project or Phase: The process of finalizing all activities across all of the Project Management Process Groups to formally complete the project or phase. It is all about shutting the project down properly. This includes creating the necessary documentation and archives, capturing the lessons learned, ensuring that the contract is properly closed, and updating all organizational process assets. # The Transition implies that the product has been accepted and is ready for this handover. |  |  | Exam: Remember for exam that "You always close out a project, no matter the circumstances under which it stops, is terminated or is completed " ------Closing Activities: 1. Confirm work is done to requirements 2. Complete procurement closure 3. Gain formal acceptance of the product 4. Complete final performance reporting 5. Index and archive records 6. Update lessons learned knowledge base 7. Hand-off completed product 8. Release resources
CLOSING | 1. Project Management Plan | 1. Expert Judgment | 1. Final Product, Service, or Result Transition
| 2. Accepted Deliverables |  | 2. Organizational Process Assets Updates
3. Organizational Process Assets
# Project Charter's key aspects are: * Purpose and project objectives, * Project sponsor or authority, * Project description and requirements, * Success Criteria, * Acceptance Criteria, * Identified Risks, * Initial WBS, Preliminary Milestones and Summary Budget, and * Project Manager Assignment (with responsibility and authority level)
# Change Control System: It is also a collection of formal documented procedures that define HOW project change requests are submitted, validated, recorded, approved or rejected, communicated, and worked within the project. In many areas the Change Control System is a subset of the Configuration Management System.
# Configuration control is focused on the specification of both the deliverables and the processes while change control is focused on identifying, documenting and controlling changes to the project and the product baselines.
Exam Q. Which of the following can be found in the Project Charter? A. Business Case Document Some answers will clearly be wrong. The Business Case Document is one of the tools and techniques from Develop Project Charter. B. Expert Judgment Some answers are a little misleading! This is part of the Develop Project Charter process—but it’s from the tools and techniques, not a part of the Project Charter itself. C. Authorization for the project manager Here’s the right answer! The project manager’s authorization is included in the project charter. D. Project Management Information System You haven’t seen this one yet—it’s part of Enterprise Environmental Factors, an input to the Develop Project Charter Process, but not in the charter itself.

## Scope
SCOPE
Sl# | Inputs | Tools & Techniques | Outputs
7 | Collect Requirements: The process of defining and documenting stakeholders' needs to meet the project objectives. In this process, you find out all of the stakeholder’s needs and write them down so that you know what to build and your requirements can be measured and tracked. # TT1: Interviews: Project Manager or Business Analyst will do the Interviews with Subject matter expert and it is One-to-one meeting # TT2: Focus Groups: are another way to get a group of people to discuss their needs with you. The key to this tool lies in picking the subject matter experts and stakeholders to participate in the focus group. # TT3: Facilitated Workshops: Cross-functional stakeholders come together in a facilitated workshop to discuss and define requirements that affect more than one department. In facilitated workshops, misunderstandings and issues can get reconciled all at once because all of the stakeholders are working together to define the requirements. Exam Spotlight The primary difference between focus groups and facilitated workshops are that focus groups are gatherings of prequalified subject matter experts and stakeholders and facilitated workshops consist of cross-functional stakeholders who can define cross-functional requirements. # TT4: Group Creativity Techniques: 1. Brainstorming 2. Nominal Group Technique: where brainstormed ideas are voted upon and sorted by priority, 3. Delphi Technique, 4. Idea and Mind Mapping, and 5. Affinity Diagram: large numbers of ideas to be sorted into groups # TT5: Group Decision making techniques: • Unanimity: means everyone agrees on the decision • Majority: support from more than 50% of the members of the group, • Plurality: the largest block in a group decides even if a majority is not achieved, • Dictatorship: one individual makes the decision for the group. # TT8: Types of Prototypes: 1.Proof-of-Principle Prototype, 2.Form Study Prototype, 3.Visual Prototype, and 4.Functional/Working Prototype. Modern Prototyping (Computerized) # Categories of Requirements: Project: 1. Business Requirements, 2. Project Mgmt Requirements, 3. Delivery Requirements, and 4. Political Requirements. Product: 1. Technical Requirements, 2. Security Requirements, 3. Performance Requirements, 4. Cost Requirements, and 5. Quality Requirements. Product scope means the features and functions of the product or service that you and your team are building. Project scope is all of the work that needs to be done to make the product. |  |  | Product scope: means the features and functions of the product or service that you and your team are building. Project scope: is all of the work that needs to be done to make the product. Five Scope Management processes: Planning Process Groups - Collect requirements - Define scope - Create WBS Monitoring & Control Process Groups - Verify Scope - Control Scope Exam Spotlight: The project scope management plan is a planning tool that documents how the project team will go about defining project scope, how the work breakdown structure will be developed, how changes to scope will be controlled, and how the work of the project will be verified and accepted. Scope management plan is a subsidiary of the project management plan. | - Approved Project Scope Statement, its associated WBS, WBS Dictionary are the scope baseline for the Project. - Completion of Project Scope is measured against the Project Management Plan. - Completion of Product scope is measured against Product Requirements. - Q: How do I know when I’m done collecting requirements? A: Your requirements need to be measurable to be complete. So it’s not enough to write down that you want good performance in your product. You need to be able to tell people what measurement counts as good performance for you. You know your requirements are complete when you’ve got a way to verify each of them once they’re built.
PLANNING | 1. Project Charter | 1. Interviews | 1. Requirements Documentation | Requirments Document: contains :::: - business/proj objectives, - Functional/Non Functional reqs, - quality reqs, - acceptance criteria, - training reqs, - assumptions/constraints, - impact to other organisational areas..etc Requirements Management Plan:contains::::: - how req activities will be planned, tracked & reported., - config mgmt activities, - req priortization process, traceability structure Requirements Traceability Matrix:::: This document shows where the requirements come from, where they get implemented, and how they get verified. It’s a great way to take a quick high-level look at all your requirements and make sure they’re mapped to specific test cases.
| 2. Stakeholder Register | 2. Focus Groups | 2. Requirements Management Plan (HOWs)
|  | 3. Facilitated Workshops | 3. Requirements Traceability Matrix
4. Group Creativity Techniques
5. Group Decision Making Techniques
6. Questionnaires and Surveys
7. Observations ('Job Shadowing' by Observer)
|  | 8. Prototypes (providing a working model) | Exam Spotlight: the requirements traceability matrix helps assure that business value is realized when the project is complete because each requirement is linked to a business and project objective.
8 | Define Scope: The process of developing a detailed description of the Project and Product. It turns all requirements into a more detailed project scope statement. Project Scope statement includes: 1. Product scope description and Project goals, 2. Product acceptance criteria, 3. Project Deliverables, 4. Project inclusions and exclusions, 5. Project constraints and assumptions, and 6. Identified risks related to the scope. TT2: Product Analysis includes * Product Breakdown, * Systems Analysis, * Requirements Analysis, * Systems Engineering, * Value Engineering, and * Value Analysis. PMI advocates Project Objectives that follow the SMART guideline. S - Specific; M - Measurable; A - Assignable; R - Realistic; T - Timely. |  |  | The project scope statement tells what work you are—and are not—going to do to do in the project.
PLANNING | 1. Project charter | 1. Product analysis: When you use product analysis to define the scope of the work to be done, you’re figuring out what deliverables the team needs to work on in order to build your scope statement. So product analysis is concerned with how the work will be done, not what’s in it. | 1. Project Scope Statement | The scope statement tells you what you have to do. Project Scope Statement includes: * Project Objectives - need to be measurable * Product Scope Description * Product Acceptance Criteria * Project Deliverables: The deliverables includes EVERYTHING the * project creates including project management stuff. * Project Exclusions * Project Constraints: are known limitations - such as limit on resources, budget, schedule & scope * Project Assumptions: are things you think are TRUE.
| 2. Requirements Documentation | 2. Alternatives Identification-: Think f other ways that you could do the work. Exploring different ways to do the work will help you find the one that is most efficient for the project | 2. Project Document Updates: Includes: - stakeholder register - requirements traceability matrix - requirements documentation
| 3. Organizational Process Assets | 3. Facilitated Workshops::When you do Faciliated Workshops with your stakeholders, figure out what they need, and write it all down. An important part of stakeholder analysis is doing your best to set quantifiable goals.
4. Expert Judgment
9 | Create WBS: The process of subdividing project deliverables and project work into smaller, more manageable components. After creation; it becomes a HUB OF INFORMATION for the project. It is a primary tool for verifying and controlling the project's scope. Every level in WBS is the detailed explanation of the level above it. WBS is a graphical, hierachical chart, logically organized from top to bottom. # Code of account is used to name the WBS (Unique Identification), # Planning packages (Set of work) are between Control Accounts and Work Packages. # WBS isn’t time based, # WBS does form the Scope Baseline, # WBS is a communication tool, # Created by the entire Project Team WBS Dictionaly might include 1. the number of the node, 2. the name of the node, 3. the written requirements for the node, 4. to whom it is assigned, 5. time (Date Assigned and Date Due), 6. cost, and 7. accounting information. # Management Control Points (Control Account): Where the integration of scope, schedule, and cost take place and where performance is measured. Advantages: 1. EV Calculation take place, 2. It is the building block of Performance Measurement, and 3. The sum of the control accounts will add up to the total project value (Rule of thumb is 300 Hours). Control Account may include one or more Work Packages, each Work Package represents only one Control Account. Sometimes, particularly when working on large projects that consist of several subprojects, some of the subprojects might not be scheduled until a future date. Obviously, it makes sense to develop the WBS in detail at that future date when the deliverables and subprojects are better known and more details are available. This technique is called rolling wave planning. |  |  | The WBS doesn’t show the order of the work packages or any dependencies between them. Its only goal is to show the work involved in creating the product. The two most common ways of visualizing the work are by deliverable or by phase. The work package is the LOWEST level on a WBS; Decompose deliverables into work packages::::is subdivision of project deliverables into smaller components until the work and deliverables are defined to the work package level.
PLANNING | 1. Project Scope Statement | 1. Decomposition | 1. WBS | Code of Account Identifier: This account identifier is important—it’s how you hook your WBS into your company’s accounting system. That way you can make sure all of the work is paid for. Scope Baseline: As the project goes on, you will want to compare how you are doing to what you planned for. So, the scope baseline is there to compare against. It’s made up of the scope statement, the WBS, and the WBS Dictionary.
| 2. Requirements Documentation |  | 2. WBS Dictionary The WBS Dictionary contains the details of every Work Package. It should include the following: -Code of accounts identifier - Description of the work of the component - Organization responsible for completing the component -Schedule milestone, duration -Schedule activities associated with the schedule milestones -Resources Assigned -Cost estimates -Quality requirements -Criteria for acceptance - Technical references - Contract information
| 3. Organizational Process Assets(The forms and templates here will be really useful) | Exam Spotlight: The WBS doesn’t show the order of the work packages or any dependencies between them. | 3. Scope Baseline (Proj Scope Stmt + WBS + WBS Dict): Approved changes are changes to the scope management plan also, so it’s important that you re-baseline your project when they are approved. That way, you’ll always be comparing your performance to the most updated plan.
4. Project Document Updates
10 | Verify Scope: The process of formalizing acceptance of the completed project deliverables. Formal process to verify and obtain stakeholder acceptance of the completed project scope and deliverables. Usually performed after Perform Quality Control. # Verify Scope happens at the end of each phase and the project and upon delivery of Product/Service/Result. # Verify Scope is concerned with completeness and acceptance, and Perform Quality Control is concerned with correctness. # If the project is cancelled/terminated before completion, Verify Scope is performed to show where the Project was in relation to the Scope when it ended. # Verify Scope is all about comparing the Deliverables with the documented Scope to ensure that everything was completed. # Verify Scope is typically performed by the PM, the Sponsor, the Customer, and the Functional Managers, and the result is a formal, written acceptance by the appropriate stakeholders. # If we don't receive a final sign off from our customer; we have to escalate the issue to our Management. # Characteristics of Verify Scope: 1. Signoff, Review, Inspection, 2. Documenting completed deliverables, and 3. Ensuring that the deliverables conform to the requirements. |  |  | Scope verification is primarily concerned with ACCEPTANCE of deliverables. - Quality control is done before scope verification. Bad change: * Scope Creep: This happens when you think you know the impact of a change so you go ahead, but it turns out that that change leads to another one, and since you are already making the first change, you go with the next. Then another change comes up, and another, and another, until it’s hard to tell what the scope of the project is. * Gold Plating: Sometimes people think of a really great improvement to the product and go ahead and make it without even checking the impact.
M & C | 1. Project Management Plan | 1. Inspection | 1. Accepted deliverables | Accepted deliverables are formally signed off by the customer. Formal acceptance received from the customer acknowledging formal stakeholder acceptance of project deliverables is sent to Close Project Phase.
| 2. Requirements Documentation | (It involves a point-by-point review of the Scope and the associated Deliverable). Examine the deliverables, Measure it, Inspect it, and Weigh it. | 2. Change Requests
| 3. Requirements Traceability Matrix |  | 3. Project Document Updates
4. Validated Deliverables: These are validated deliverables, which means they’ve been through Perform Quality Control.
11 | Control Scope: The process of monitoring the status of the project and product scope and managing changes to the scope baseline. Scope Creep will be eliminated. Integrated Change Control spans: * Control Scope * Control Schedule * Control Cost * Quality Control * Monitor and Control Risk * Administer Procurements # Customer's interests should always be weighed heavily and disputes should be resolved in favor of the customer. |  |  | The goal of Control Scope is updating the scope, plan, baseline, and WBS info.
M & C | 1. Project Management Plan | 1. Variance analysis | 1. Work Performance Measurements | Exam Spotlight: Arrange all of the activities you do to control scope in the right order.: 1. You figure out that you have to make a change 2. Create a change request 3. Get approval to make the change 4. Compare the change against the baseline 5. Go back and plan for the new work 6. Update the baseline 7. Store the updated baseline in the configuration management system 8. Now the team can change the way they do the work
| 2. Work Performance Information | VA can be used to measure differences btwn what was defined in the Scope Baseline & what was created. It is useful in this process as a way to investigate and understand the root causes behind these differences. | 2. Change Requests
| 3. Requirements Documentation |  | 3. Project Management Plan Updates
| 4. Requirements Traceability Matrix |  | 4. Project Document Updates
| 5. Organizational Process Assets |  | 5. Organizational Process Assets Updates
# SCOPE MANAGEMENT is a presentation of logical processes to understand requirements, define, break down, and control the scope of the project, and verify that the project was completed correctly. The Project Manager should always be in control of scope through rigid management of the requirements, details, and processes, and scope changes should be handled in a structured, procedural, and controlled manner. Scope may refer to 1. Product Scope (Features and Functions), and 2. Project Scope (Work need to be completed).
# A Baseline (whether for Scope, Schedule, Cost, or Quality) is the Original Plan + All Approved Changes.
# Uncontrolled changes are often referred to as project scope creep. Scope Creep Results from * Poor initial requirements definition, * Failure to involve users in early stages, * A missing Scope Baseline, * Poor Change Control, * Projects take long therefore requirements also change, * Weak Management, and * Failure to manage user expectations.
# Work Performance Information: Information and data, on the status of the project schedule activities being performed to accomplish the project work, collected as part of the direct and manage project execution processes. # Task: Work not necessarily listed in the WBS and is the lowest level of effort on the project.
# Work Performance Measurements: Results from measurements when comparing PLANNED Vs ACTUAL Technical Performance.
# If a variance is a Beneficial Variance: * Keep that variance, * Issue a change request to update the Scope Baseline to do the changes in characteristics.

## Time
TIME
Sl# | Inputs | Tools & Techniques | Outputs
The processes in Time Management are: •Define Activities: Decomposing the work packages into activities. First you come up with a list of all of the activities that will need to be completed. •Sequence Activities: Determining the order the activities need performed in. Next, you figure out which activities need to come before others and put them in the right order. The main output here is a network diagram, a picture of how activities are related. •Estimate Activity Resources: Finding out the quantities and types of resources needed for the activities. Estimate the resources you’ll need to do the job, and create a list of them... •Estimate Activity Durations: Determining how long the activities will take. ...and then estimate the time it will take to do each activity. •Develop Schedule: Creating the project schedule. Then you build a schedule from all of the estimates, and the resource and activity information you’ve created. •Control Schedule: Monitoring the schedule and influencing the factors that can lead to schedule changes. Finally, you monitor and control changes to the schedule to make sure that it is kept up to date.
12 | Define Activities: The process of identifying the specific actions to be performed to produce the project deliverables. The first step in time management is figuring out how the project work breaks down into activities—and that’s what the Define Activities process is for. |  |  | Defining activities is an iterative process performed together by the project manager and the project team member by further decomposing the WBS work packages. Since the activity list and WBS can be looked upon as companion documents, each activity should have a unique identifier that correlates it to the WBS work package.
PLANNING | 1. Scope Baseline (Approved Proj Scope Stmt + WBS + WBS Dict) | 1. Decomposition | 1. Activity List It’s all the activities that must be accomplished to deliver the work packages | Decomposition: An adequate level of activity decomposition is generally reached when the activities: •Are assignable to one person •Can have a level of effort determined for them •Can have their resource needs estimated •Can have their expected costs reasonably established •Can have their progress determined and tracked. Rolling Wave Planning: Work to be completed in near future is planned in detail and future work is planned at HIGHER level of the WBS.
| 2. Enterprise Environmental Factors | 2. Rolling Wave Planning When you plan this way, you decompose only the activities that you need to plan for because they’re coming up soon first. You leave everything else planned at the milestone level until it gets closer to the time when you’ll do it | 2. Activity Attributes - Activity ID, WBS ID, Activity Name, Activity description, predecessor activities, successor activities, logical relationships, leads and lags, resource requirements, imposed dates, assumtions & constraints,…
| 3. Organizational Process Assets | 3. Templates | 3. Milestone list
4. Expert Judgment
13 | Sequence Activities: Properly sequencing activities involves determining the dependencies and relationships between activities and applying leads and lags Activity dependencies: Mandatory, Discretionary & External Activity relationships: There are four types of activity precedence relationships: Finish-to-Start (FS): The successor activity can begin only after the predecessor activity is completed (Activity B can't start until Activity A is completed). This is the most common type of relationship. For example, a house's concrete foundation can't be poured until the excavation activity is fully completed. Finish-to-Finish (FF): The completion of the successor activity depends upon the completion of the predecessor activity (Activity B can't finish until Activity A is finished). This relationship is necessary when both activities need to finish at the same time (or very close) to each other, but there's not any relationship between the activity start dates. For example, you must finish Testing before you finish Documentation. Start-to-Start (SS): The successor activity can't start until the predecessor activity starts (Activity B can't start until Activity A has started). This relationship is needed when the starting dates of the activities are dependent upon each other, but the ending dates are not. For example, you must start Designing and wait for two weeks lag in order to have enough of the design completed to start coding. Start-to-Finish (SF): The completion of the successor activity depends upon the predecessor activity starting (Activity B can't complete until Activity A has started). For example, in a project in which equipment is being replaced, before the old equipment can be fully decommissioned (Activity B), the initial testing of the new equipment should have been successfully started (Activity A). The testing doesn't need to be fully completed but just far enough along that the team can be assured the new equipment is functioning before the old equipment is dismantled. There are two types of Network Diagrams: - Arrow Diagramming Method (ADM) - Precedence Diagramming Method (PDM) The Arrow Diagramming Method (ADM) creates diagrams known as activity-on-arrow (AOA). This is because ADM diagrams use activities shown on arrows and connected by nodes, usually shown as circles. ADM’s drawback is that it can only show finish-to-start (FS) relationships. In order to show relationships between tasks on different node branches, ADM diagrams use dummy activities. The Precedence Diagramming Method (PDM) creates diagrams known as activity-on-node (AON). It uses nodes, usually shown as squares, to hold the activities which are connected by arrows to show the relationships. The PDM diagram is the one most commonly used.
PLANNING | 1. Activity List | 1. PDM (Precedence Diagramming Method) | 1. Project Schedule Network Diagrams: - Graphically show the relationships, sequences, and durations of all activities from the start to the end of the project. | Lead time is overlap between tasks that have a dependency. For example, if a task can start when its predecessor is half-finished, you can specify a finish-to-start dependency with a lead time of 50 percent for its successor task.You enter lead time as a negative value. Lag time is a delay between tasks that have a dependency. For example, if you need a two-day delay between the finish of one task and the start of another, you can establish a finish-to-start dependency and specify a two-day lag time. You enter lag time as a positive value. ● Lead time causes the successor task to begin before its predecessor task concludes...FS-2 would schedule the successor task to start before the predecessor task finish. ● Lag time causes the successor task to begin some time after its predecessor task concludes...for example, FS+1 would delay the start of the successor by 1 day.
| 2. Activity Attributes | 2. Dependency Determination: -Mandatory Predecessors (hard logic) -Discretionary (logical or Preferred order to the activities) -External: External dependencies can also lead to scheduling problems when no hard date is available | 2. Project Document Updates:
3. Milestone List
| 4. Project Scope Statement: Knowning the full scope of the project helps to be sure that we have got all of the activities needed to do the work. | 3. Applying Leads and Lags
| 5. Organizational Process Assets | 4. Schedule Network Templates
14 | Estimating Activity Resource: The process of estimating the type and quantities of material, people, equipment, or supplies required to perform each activity. Before you can assign resources to your project, you need to know which ones you’re authorized to use on your project. That’s an input, and it’s called Resource Calendars. # Resource Calendars specify WHEN and HOW LONG identified project resource will be available during the project. |  |  | Rough order of magnitude estimate: These are usually top-down estimates made by expert judgment. The variance range for this type of estimate is expected to be -25% to +75% of the final actual figure. During early initiating or planning phases, this may be the only estimate available. Budget estimate: These have less variance than rough order of magnitude, but they are still broad estimates. The variance range for this type of estimate is expected to be -10% to 25% of the final actual figure. Budget estimates should be used once planning processes are underway, and previous rough order of magnitude estimates should be re-estimated. Definitive estimate: This type is the most accurate estimate. The variance range for this type of estimate is expected to be -5% to 10%. Budget estimates of this type should be expected once substantial planning has occurred or project execution has been underway
PLANNING | 1. Activity list | 1. Alternatives Analysis: Identifying resource needs will require evaluation of different resource types, financial comparisons between staffing or outsourcing, renting versus leasing, and building versus buying. | 1. Activity Resource Requirements
| 2. Activity Attributes | 2. Bottom-up Estimating | 2. Resource Breakdown Structure
| 3. Resource Calendars | 3. Published Estimating Data | 3. Project Document Updates
| 4. Enterprise Environmental Factors | 4. Project Management Software
| 5. Organizational Process Assets | 5. Expert Judgment
15 | Estimating Activity Duration: The process of approximating the number of work periods needed to complete individual activities with estimted resources. # Analogous (top down): is when you look at activities from previous similar activities. The degree of similarity affects accuracy. This technique should be used early in the estimating cycle when there is not much detail known about the activity. It uses Historical information and expert judgement. It is less costly, less time consuming than others, and less accurate. It can be applied to a total project or to segments of a project and may be used in conjunction with other estimating methods. # Parametric/Quantitately-Based Estimating: It uses a statistical relationsip between HISTORICAL DATA and OTHER VARIABLES (Ex: Square footage in construction) to calculate an estimate for activity parameters, such as cost, budget, and duration. It can be applied to a total project or to segments of a project and may be used in conjunction with other estimating methods. Cost = Qty in units X Unit Rate. # Three-Point Estimate or Triangular Distribution: Come up with three points, Optimistic, Pessimistic, and Most Likely (Realistic) = (P+R+O)/3 # PERT (Program Evaluation and Review Technique)/Beta/Weighted Three-Point Estimate = (P+4R+O)/6 # Standard Deviation σ = (P-O)/6 Effort: The number of labour units required to complete a schedule activity or WBS component. Usually expressed as staff hours, staff days, or staff weeks. (Requirements for effort estimation: The Expert Judgement, Task Complexity, Sill Level, and Expectations). Duration: The total number of work periods (not including holidays and non-working periods) required to complete a schedule activity or WBS component. Usually expressed as workdays or workweeks. (Requirements for Duration estimation: Resource Availability and Resource Capability). Elapsed Time: Waiting periods. |  |  | Reserve analysis Reserve analysis looks at various factors in the project, such as risks and overall uncertainty, and sets aside separate contingency reserves, time reserves, or buffers that can be drawn from if activities exceed their duration. Buffers can also achieve more accurate estimates by moving the padding out of the activity and into a separate bucket where it can be better managed. Whether this reserve time is added to the schedule as a whole, to individual activities, or to crucial points within the schedule depends upon the project manager and his or her scheduling approach. You may have guessed from the name that the Activity DURATIONS Estimates are always duration estimates, not effort estimates, so they show you calendar time and not just person-hours. Heuristic (like a rule of thumb)
PLANNING | 1. Activity List | 1. Analogous Estimating: is when you look at activities from previous projects that were similar to this one and look at how long it took to do similar work before. | 1. Activity Duration Estimates | Three-Point Estimates: are when you come up with three numbers: a realistic estimate (R) that’s most likely to occur, an optimistic (O) one that represents the best-case scenario, and a pessimistic (P) one that represents the worst-case scenario. The final estimate is the average. = (P + R + O)/2 PERT:is the most common form of three-point estimation. Since the pessimistic and optimistic estimates are less likely to happen than the the normal estimate, the normal estimate is weighted (by multiplying it by 4) and added to the optimistic and pessimistic estimates, and then the whole thing is divided by 6 to give an expectued duration. The formula looks like this: (Optimistic Duration + (4* Most likely Duration) + Pessimistic Duration) / 6 = Expected duration Expected Activity Duration EAD = ( O + 4R + P) / 6 The formula for Standard Deviation SD we’re most likely to encounter on the PMP examination is: SD = ( P - O) / 6 Activity Variance AV = [ (P - O) / 6 ]2 * Parkinson's Law states that work expands to fill the time available. This means that if we estimated an activity will take two weeks, it'll end up taking two weeks even if it could have been finished it in one. Test may ask you to provide range for an individual activity estimate: you calculate the range using EAD +/- SD Start range = EAD - SD End range = EAD + SD For finding SD for entire proj, add-up Acitivity Vairance for all the individual activities and do square root of AV. In order to find SD of a series of items, remember the rule, you cannot add SDs; you must first convert the SD into vairances, add the variances and then take the SQUARE ROOT of the total and convert back into SD.
| 2. Activity Attributes | 2. Parametric Estimating: means plugging data about your project into a formula, spreadsheet, database, or computer program that comes up with an estimate. | (It doesn't include LAGS. It may include some indication of the range of possible results.)
| 3. Activity Resource Requirements | 3. Three-point Estimates
| 4. Resource Calendars | 4. Reserve Analysis : looks at various factors in the project, such as risks and overall uncertainty, and sets aside separate contingency reserves, time reserves, or buffers that can be drawn from if activities exceed their duration. | 2. Project Document Updates
5. Project Scope Statement
6. Enterprise Environmental Factors
| 7. Organizational Process Assets | 5. Expert Judgment | Q: Difference between a duration estimate and an effort estimate? A: Duration is the amount of time that an activity takes, while effort is the total number of person-hours that are expended. If it takes two people six hours to carve the ice sculpture for the centerpiece of a wedding, the duration is six hours. But since 2 people worked on it for the whole time, it took 12 person-hours of effort to create!
16 | Develop Schedule: The process of analyzing activity sequences, durations, resource requirements, and schedule constraints to create the project schedule. It determines the planned start and finish dates for project activities and milestones. # Critical Path Method: It calculates the theoretical Early Start and Finish Dates, and Late Start and Finish Dates, for all activities without regard for any resource limitations, by performing a Forward and Backward pass analysis through the schedule network. Critical paths have either ZERO or NEGATIVE Total Float. Float = Late Start - Early Start OR Late Finish - Early Finish # Critical Chain Method: The resource-constrained critical path is known as the Critical Chain. The longest sequence of resource-leveled tasks is the critical chain. It tries to adjust for problems in estimating and managing tasks that result from 1. poor multi-tasking, 2. estimates with too much contingency for uncertainty, 3. work that expands to fill the available time, 4. waiting until the latest possible time to start and 5. lack of prioritization. Critical Chain Method focuses on managing remaining buffer durations against the remaining durations of task chains. In CCM; buffers are two types: 1. Project Buffer (Protects the target finish date from slippage along the Critical Chain), and 2. Feed Buffer (Protects the Critical Chain from slippage along the Feeding Chains). # Float/Slak/Total Float: amount of time an activity can slip before it causes delay in project. * Float for activities on CP is 0. CP- next longest path= float. # LEAD: Task can be started before completion of the predecessor (Ex: Start writing the Training Material before completion of the Testing). # LAG: Finish to Finish - The successor cannot be started before finishing the predecessor (Ex: Pouring Concrete). # Schedule Compression: includes Fast-tracking and crashing. # Crashing adds more resources, usually personnel, in order to decrease an activity's duration. Crashing almost always increases cost. Over Time is considered as Crashing. Cheapest Task has to be crashed first. # Heuristics: Rules for which no formula exists. Usually derived through trial and error. # Free Float: how much time an activity can be delayed without affecting the early start date of subsequent dependent activities. # Resource Leveling: can be used when shared or critical required resources are only available at certain times, are only available in limited quantities, or to keep resource usage at a constant level. It can often cause the original critical path to change. Exam: #Can there be more than ONE critical path? Yes, can have many critical paths.# Would you leave the project with Negative float? No; you would compress the schedule. |  |  | To find the FLOAT or SLACK for an activity, figure out how much it can slip before it makes the project late. The float for any activity on the critical path is ZERO! Calculating float Calculating float requires either a completed node with some combination of early start, early finish, late start, and late finish supplied, or we have to utilize the network diagram. There are three kinds of float: free float, total float, and project float. Project Float: Project float is easy. It's only applicable when there's a duration constraint on the entire project. Using our continuing example, we know that the critical path (longest duration) is 17 periods. If the project had a constraint of 20 periods, then the project float would be three periods. Free Float: Free float is how long an activity's duration can increase without impacting the start of any successor activities. Free float requires that we know the early start of activities because it’s calculated by taking the early start of the successor activity minus the early start plus the duration of its predecessor activity. Free float = ES (of successor) - ( ES of predecessior + DURATION of predecessor ) Total float or total slack is how much leeway an activity has before an extension to its duration delays the end date of the project. By looking at the sample diagram, we can see that the total project duration is 17 days. Since the combined duration of Activity A and Activity C is 15 days, Activity A has a total float of two days as does Activity C because either or both can slide a total of two days without lengthening the duration of the project. Total float = (LF - EF) of that activity OR (LS-ES) of that activity ## EXAM: Don’t forget that when two paths intersect, you have to decide which ES or LF value to take for the calculation in the next node. For the forward pass, use the LARGER value; for the backward pass, use the SMALLER one.
PLANNING | 1. Activity List | 1. Critical Path Method CPM: Exam Spotlight: CPM manages the total float of schedule network paths, whereas critical chain manages buffer activity durations. | 1. Project Schedule (Formats 1. Milestone Charts, 2. Bar Charts, and 3. Project Schedule Network Diagrams) Network Diagram: to show interdependencies beween activities Milestone charts: to report to senior management. Bar charts: to track progress, to report to the team. | Critical Path: It’s the string of activities that, if you add up all of the durations, is longer than any other path through the network. It usually starts with the first activity in the network and usually ends with the last one. The reason that the critical path is, well, critical, is that every single activity on the path must finish on time in order for the project to come in on time. A delay in any one of the critical path activities will cause the entire project to be delayed. There are FOUR types of CONSTRAINTS: Start No Earlier Than (SNET or SNE): The activity can't start until a predetermined date. Start No Later Than (SNLT or SNL): The activity must be started before but not later than a predetermined date. Finish No Earlier Than (FNET or FNE): The activity must be finished after a predetermined date. Finish No Later Than (FNLT or FNL): The activity must be finished before a predetermined date A good rule of thumb is that sequential activities can sometimes be fast-tracked by up to 33%. In other words, if you're fast-tracking, you can start the second of two sequential activities when the first activity is 66% complete. There is risk involved. However, this seems to be a level of fast-tracking risk that is normally acceptable. Critical chain method is a schedule network analysis technique that will modify the project schedule by accounting for limited or restricted resources. After the project schedule network diagram is constructed using duration estimates, dependencies, and constraints, resource availability is entered into the scheduling tool. The modified schedule is calculated and you’ll find that it often changes the critical path. The new critical path showing the resource restrictions is called the critical chain. A few steps are involved in the critical chain process: - Construct the schedule network diagram using activity duration estimates - Define dependencies - Define constraints - Calculate critical path - Enter resource availability into the schedule - Recalculate for the critical chain
| 2. Activity Attributes | 2. Critical Chain Method:
| 3. Activity Resource Requirements | 3. Resource Leveling: If 12 programmers are needed in week 3 but only eight are available, if activity A were most critical then 4 programmers would be assigned to it so that its duration and sequencing remains intact. How the remaining pool of 4 programmers would be allocated depends on the importance of the remaining two activities, how much float they have, and what resource requirements the successor activities need. Exam Spotlight: Resource leveling can cause the original critical path to change. | 2. Schedule Baseline: The project schedule will undergo some manner of approval or sign-off. Once approved, the schedule baseline comes into existence
| 4. Activity Duration Estimates | 4. What-if Scenario Analysis:Monte Carlo analysis is a computer-driven simulation technique that applies different variables to the schedule, and the results can identify high-risk and vulnerable areas within the schedule. | 3. Schedule Data: At a minimum, the schedule data includes the milestones, activities, activity attributes, assumptions, and constraints. Milestone chart - for reporting to senior mgmt/customer Bar chart - for tracking progress, to report to the team
| 5. Project Schedule Network Diagrams | 5. Applying Leads and Lags
| 6. Resource Calendars | 6. Schedule Compression: -Fast tracking: involved doing critical path activities in parallel. -Crashing: resources could be added to critical path, always results in increased costs.
| 7. Project Scope Statement | 7. Scheduling Tool
| 8. Enterprise Environmental Factors | 8. Schedule Network Analysis: is the various techniques used to analyze and apply scenarios to the schedule. Schedule network analysis includes the critical path method, critical chain method, resource leveling and smoothing, what-if analysis, and schedule compression, as well as any other analysis methods employed by the project manager.
| 9. Organizational Process Assets |  | 4. Project Document Updates
17 | Control Schedule: The process of monitoring the status of the project to update project progress and managing changes to the schedule baseline. # Schedule Baseline is updated, whenever the Customer requests a significant change and when original estimates were wrong.
M & C | 1. Project Management Plan | 1. Performance Reviews | 1. Work Performance Measurements (SV & SPI values)
| 2. Project Schedule | 2. Variance Analysis (SV/SPI) | 2. Change Requests
| 3. Work Performance Information: Work performance information is any data that can be considered related to the work which produces the project deliverables. Examples are schedule and progress status information, budget and cost status, quality status, estimates to complete, resource utilization information, and lessons learned | 3. Resource Leveling | 3. Project Management Plan Updates
| 4. Organizational Process Assets | 4. What-if Scenario Analysis | 4. Project Document Updates
|  | 5. Adjusting Leads and Lags | 5. Organizational Process Assets Updates
6. Schedule Compression
7. Scheduling Tool
8. Project Management Software
# HAMMOCK Activity: For control and mangement communication, the broader, more comprehensive summary activity.
# Path Convergence: The merging or joining parallel schedule network paths into the same node in a project schedule network diagram. Path convergence is characterized by a schedule activity with more than one predecessor activity. # Path Divergence: Extending or generating parallel schedule network paths from the same node in a project shedule network diagram. Path devergence is characterized by a schedule activity with more than one successor activity.
30.25
64
2.25
4.6959
10.0596
[5 empty] | 3.87 | 7.74
[5 empty] | -3.87 | -7.74

## Cost
COST
| •Estimate Costs: Develop estimated costs for each scheduled activity. •Determine Budget: Aggregate activity costs into an approved project budget. •Control Costs: Monitor, manage, and control costs. |  | cost management plan includes: •what types of indirect costs, if any, will be posted against the project •units of currency to be used •precision level/acceptable rounding for costs •currency conversion issues •acceptable thresholds for cost variances •the general ledger or control accounts for expenses and costs •the performance measurement formulas that will be used •at what points in the project performance measurements will be made
Sl# | Inputs | Tools & Techniques | Outputs
18 | Estimate Costs: The process of developing an approximation of the monetary resources needed to complete project activities. It is performed after Define Scope, Create WBS, Define Activities, Estimate Activity Resources, and Estimate Activity Durations. Estimations must be done based on a WBS to improve accuracy. # Cost of quality: Cost that is incurred to achieve required quality # Stranded/Sunk Costs: costs incured that cannot be reversed irrespective to future events # Value Engineering/ Analysis: finding less costly way to do the same work. E.g. outsourcing # Marginal analysis: Spend time on improvement if it improves revenues or productivity. # Order of Magnitude Estimate: Rough Order of Magnitude (ROM): -50% to +50% (at Initiation) as the project moves, estimates should become more accurate, Conceptual Est: -30% to + 50%, Preliminary Est: -20% to +30%, Definitive Est: -15% to +20%, Control Est: -10% to +15% (for Activities with relatively few unknowns). |  |  | Types of costs: Direct cost: include dedicated labor, material, supplies, equipment, licenses, fees, training, travel, or professional service fees Indirect cost:Example, if a color printer is shared by several project teams, it’s difficult to definitively determine what percentage of costs each should share. Variable cost: fluctuate and can't be predicted with absolute certainty. For example, travel or transportation costs that can change depending upon the cost of fuel or certain commodities and types of raw materials. Fixed cost: are static throughout the project or have only a small likelihood of fluctuation. Fixed costs are usually for items such as rents, leases, licenses, salaries, and fixed fees Factors affecting costs: -Risks:During early phases, the greatest risk to budget accuracy is usually that the scope, activity, and constraints aren’t fully known -Total Cost of Ownership/Life-Cycle: -Cost of Quality: Cost that is incurred to achieve required quality -Marketplace Conditions: Accuracy of Estimates: Rough order of magnitude estimate ROM: this type of estimate is made during initiating process. Typical range is +/-50 percent from actual. Budget estimate: this type of estimate is made during Planning phase. Typical range is -10 to +25 percent from actual. Definitive estimate: Later during the project estimates will become more refined, some PMs use the range of -5 to +10 or -/+10.
PLANNING | 1. Scope Baseline | 1. Expert Judgment | 1. Activity Cost Estimates
| 2. Project Schedule | 2. Analogous Estimating (Gross Value Estmting apprch) Top-down estimates are the least accurate. -Gives Project Manager an idea of the level of Management's expectations. | 2. Basis of Estimates: is the supporting detail that provides supplementary information about the activity estimates, such as any assumptions made, constraints, how the estimate was derived, the confidence level in the estimate, and any risk factors that were considered.
| 3. Human Resource Plan: to know labor rates | 3. Parametric Estimating (Uses Statistical relationship) | 3. Project Document Updates
| 4. Risk Register | 4. Bottom-up Estimating
| 5. Enterprise Environmental Factors | 5. Three-Point Estimates
| 6. Organizational Process Assets | 6. Reserve Analysis: Reserve analysis evaluates risks by making financial allowances for them in the project’s funding requirements. - Budget reserve - Contingency reserves (for known risks) - Mgmt reserves (for unknown risks)
7. Cost of Quality
8. Vendor Bid Analysis
9. Project Management Estimating Software
19 | Determine Budget (Cost Performance Baseline): The process of aggregating the estimated costs of individual activities or work packages to establish an authorized cost baseline. Budget, is time-phased (WHAT costs will be incurred and WHEN they will be incurred). The Cost Baseline describes a detailed budget that shows costs and timelines for each work package or activity. It is performed after Define Activities, Estimate Activity Resources, Estimate Activity Durations, Develop Schedule and Estimate Costs. # Larger projects may be divided into multiple Cost Baselines. The entire estimated cost of the budget, including any contingency or management reserves, is the project funding requirements. Project funding requirements = Project Budjet (Project Base Cost+Risk response cost[planned]) + Reserve (contigency reserve[known unknowns] + Mgmt reserve[unknowns]) Cost Aggregation: 1.Activity Estimates ->2.Work Package Estimates ->3. Control Account Estimates ->4. Project Estimates ->5.Contingency Reserves ->6.Cost Baseline ->7.Mgmt Reserves ->8. Cost Budget. |  |  | At a broad level, the budgetary classifications are generally: •Reserves•Labor/Personnel•Professional, Contracted, or Outside Services•Supplies, Materials•Equipment, Hardware, and Software •Training, Travel•Licenses, fees•Indirect Costs You will get questions on the EXAM asking you to select between projects using Net Present Value (NPV) or Benefit Cost Ratio(BCR). Always choose the project with the BIGGEST NPV or BCR. A Management Reserve is money set aside to cover unplanned, unexpected costs. Your project’s funding requirements need to cover both the budget in the Cost Performance Baseline and the management reserve.
PLANNING | 1. Activity Cost Estimates | 1. Cost Aggregation | 1. Cost Performance Baseline (S - curve) Time phased funding requirements - the performing organization needs to know when the project will need money.
| 2. Basis of Estimates | 2. Reserve Analysis
| 3. Scope Baseline | 3. Expert Judgment
| 4. Project Schedule | 4. Historical Relationships | 2. Project Funding Requirements (Dotted Steps)
| 5. Resource Calendars | 5. Funding Limit Reconciliation | (Expenditures, Liabilities, and Reserves)
| 6. Contracts |  | 3. Project Document Updates
7. Organizational Process Assets
20 | Control Costs: The process of monitoring the status of the project to update the project budget and managing changes to the cost baseline. -Cumulative CPI: The rate at which the project performance is meeting cost expectations from the beginning up to a point in time. Also used to forecast project’s cost at completion. CPIC (CPI Cumulative)= EVC (EV Cumulative)/ ACC (AC Cumulative) = Which calculates the project's performance up to a point in time. -To-Complete Performance Index (TCPI): performance needed in order to achieve earned value targets (either financial or schedule). Two forms, TCPIC and TCPIS. # TCPI (Based on BAC) = Work Remaining i.e, (BAC-EV) / Remaining Funds i.e., (BAC-AC) (lower than 1 is good) # TCPI (Based on EAC) = Work Remaining i.e, (BAC-EV) / Remaining Funds i.e., (EAC-AC) (lower than 1 is good) # TCPI calculation is based on a specified management goal. If the cumulative CPI falls below the baseline plan, all future work of the project will beed to immediately be performed in the range of the TCPI (BAC) to stay within the authorized BAC. Once management acknowledges that the BAC is no longer attainable, the PM will prepare a new EAC for the work, and one approved the project will work to the new EAC value and it supersedes the BAC. # The EVM method works well in conjunction with manual forecasts of the required EAC costs. The most common EAC forecasting approach is a MANUAL, BOTTOM-UP SUMMATION by the PM and Project Team. # Project Manager monitor EV, both incrementally to determine CURRENT STATUS and cumulatively to determine long-term PERFORMANCE TRENDS. |  |  | For formulas, refer attached Word Doc on Earned Value
M & C | 1. Project Management Plan | 1. Earned Value Management (Variances and Trends) | 1. Work Performance Measurements
| 2. Project Funding Requirements | 2. Forecasting (EAC and ETC) | 2. Budget Forecasts
| 3. Work Performance Information | 3. To-complete Performance Index (TCPI) | 3. Change Requests
| 4. Organizational Process Assets | 4. Performance Reviews | 4. Project Management Plan Updates
|  | 5. Variance Analysis | 5. Organizational Process Assets Update
|  | 6. Project Management Software | 6. Project Document Updates
# Project Cost Baseline = Project Estimates + (Cost) Contingency Reserves; # Project Cost Budget = Project Cost Baseline + Management Reserves
# PV: Planned Value / Budgeted Cost of Work Scheduled (BCWS) = BAC X Planned % Completed
# EV: Earned Value / Budgeted Cost of Work Performed (BCWP) = BAC X Actual % Completed
# AC: Actual Cost / Actual Cost of Work Performed (ACWP) = SUM of the Costs for a given period of time.
# Life Cycle Costing includes Acquisition, Operation, Maintenance, and Disposal Costs.
# The Cost Management Processes and their associated tools and techniques are usually selected during the project life cycle definition, and are documented in the Cost Management Plan (which has been produced by Develop Project Mgmt Plan Process). For example, the Cost Mgmt Plan can establish the following: 1. Level of Accurary (Rounding of the data), 2. Units of Measurement (Staff Hours, Staff Days, Weeks, or Lump Sum), 3. Organizational Procedures Links (The WBS component used for the Project Cost Accounting is called the Control Account (CA). Each Control Account is assigned a unique code or account number that links directly to the performing organization's Accounting System), 4. Contol Thresholds (Thresholds are typically expressed as percentage deviations from the baseline plan), 5. Rules of Performance Measurement (EVM rules of performance measurement are set), 5. Reporting Formats (Formats and frequency of various cost reports are defined), and 6. Process Descriptions (description of each of the three cost mgmt processes are documented).
# The Scope Statement provides the Product Description, Acceptance Criteria, Key Deliverables, Project Boundaries, Assumptions, and Constraints about the Project.
# Project Cost Control includes: 1) Influencing the factors that create changes to the authorized cost baseline, 2) Ensuring that all change requests are acted on in a timely manner, 3) Managing the actual changes when and as they occur, 4) Ensuring that cost expenditures do not exceed the authorized funding, by period and in total for the project, 5) Monitoring cost performance to isolate and understand variances from the approved cost baseline, 6) Monitoring work performance against funds expended, 7) Preventing unapproved changes from being influded in the reported cost or resource usage, 8) Informing appropriate stakeholders of all approved changes and associated cost, and 9) Acting to bring expected cost overruns within acceptable limits.
There are a few numbers that will appear on the test as definitions. You won’t need to calculate these, but you should know what each term means. Benefit cost ratio (BCR): This is the amount of money a project is going to make versus how much it will cost to build it. Generally, if the benefit is higher than the cost, the project is a good investment. Net present value (NPV): This is the actual value at a given time of the project minus all of the costs associated with it. This includes the time it takes to build it and labor as well as materials. People calculate this number to see if it’s worth doing a project. Opportunity cost: When an organization has to choose between two projects, they are always giving up the money they would have made on the one they don’t do. That’s called opportunity cost. It’s the money you don’t get because you chose not to do a project. Example -- If a project will make your company $150,000, then the opportunity cost of selecting another project instead is $150,000 because that’s how much your company’s missing out on by not doing the project. Internal rate of return: This is the amount of money the project will return to the company that is funding it. It’s how much money a project is making the company. It’s usually expressed as a percentage of the funding that has been allocated to it. Depreciation: This is the rate at which your project loses value over time. So, if you are building a project that will only be marketable at a high price for a short period of time, the product loses value as time goes on. Lifecycle costing: Before you get started on a project, it’s really useful to figure out how much you expect it to cost—not just to develop, but to support the product once it’s in place and being used by the customer.
BAC
AC
AC%
Planned%
PV (planned % X BAC)
EV (AC% X BAC)
Sch
| SV=EV - PV | 0
| SPI = EV / PV | #DIV/0!
Cost
| CV=EV - AC | 0
| CPI=EV / AC | #DIV/0! | 400000
| EAC = BAC / CPI | #DIV/0!
| ETC = EAC - AC | #DIV/0!
| VAR = BAC - EAC | #DIV/0!
| TCPI[BAC] = (BAC-EV)/(BAC-AC) | #DIV/0!
| TCPI[EAC] = (BAC-EV)/(EAC-AC) | #DIV/0!
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Quality
QUALITY
Sl# | Inputs | Tools & Techniques | Outputs
21 | Plan Quality: The process of identifying quality requirements and/or standards for the project and product, and documenting how the project will demonstrate compliance. Decisions made about quality can have a significant impact on other decisions such as scope, time, cost, and risk. Most Project Management Practitioners view SCOPE and QUALITY as INSEPARABLE. # If Quality Policy doesn't exist, the Project Team should write one for this project. "Determine WHAT the quality standards for the project will be and document HOW the project will be measured for compliance". QUALITY: is defined as degree to which your project fulfills requirements. Customer satisfaction, Fitness for use, Conformance to requirements # Cost benefit: Looking at how much your quality activities will cost. # Benchmarking: means using the results of quality planning on other projects to set goals for your own. # Design of experiments: is the list of all the kinds of tests you are going to run on your product. # Attribute Sampling :is binary, it either conforms to quality or it doesn’t (YES or NO). # Variable Sampling: Measures how well something conforms to quality (RANGES). # Special Causes: considered unusual and preventable by process improvement. # Common Causes are generally acceptable. # Tolerances deal with the limits your project has set for product acceptance. # Control Limits are set at three standard deviations above and below the mean. As long as your results fall within the control limits, your process is considered to be in control. ## Toleranes focus on whether the product is acceptable, while Control Limits focus on whether the process itself is acceptable. # Control Charts: The upper and lower control limits are set at THREE STANDARD DEVIATIONS ABOVE and BELOW MEAN. # Rule of Seven: If seven or more consecutive data points fall on one side of the mean, they should be investigated. This is true even if the seven data points are within control limits. |  |  | Quality metrics: defines how Q will be measured. Quality metrics can include any type of applicable measurements, including defect rates, bug rates, failure rates, up-time, reliability, and coverage area. Cost of Good Quality (cost of conformance) •Prevention Costs •Quality management activities, such as training and process documentation, and checklist development. •Appraisal Costs •Quality assurance activities, like appraisals and audits •Quality control activities, like testing and inspections. Cost of Poor Quality (cost of nonconformance) •Internal Failure Costs •Failures found by the project team, including the costs related to rejects, rework, delays, shortages, scrap, and other inefficiencies. •External Failure Costs •Failures found by the customer, including costs related to warranties, returns, lost sales, and lost good will Cost-benefit analysis: determine the appropriate trade-off between quality and the cost to achieve that level of quality. The goal of meeting the quality requirements is to reduce costs through less rework and higher productivity, but there are costs associated with meeting the quality requirements, and what we want to find is the agreeable level between quality requirements and the costs associated with meeting those requirements. Marginal analysis: As we strive for improving products and processes, we don't want to exceed a point beyond (unnecessary quality) which the costs of the improvements aren't offset by the anticipated increase in revenue (sales or profits). Just In Time (JIT): To reduce expensive cost of holding inventory, many companies decrease inventory close to zero. A company using JIT must have high quality practices. Benchmarking compares similar processes between different organizations, helping to generate ideas for improvement and to provide a measurement basis by helping the organization determine what the "standard" is. Force field analysis: aids in visualizing the pro and con forces involved in an issue or situation. The premise behind this technique is that a situation is held in equilibrium by two sets of opposing forces. Driving forces are those striving for change, and restraining forces are those desiring the status quo. A situation can change only when the strength of the driving forces exceeds the restraining forces. By concentrating on the core factors giving strength to the restraining forces, the desired change can proceed. Design of experiments: Design of experiments is a statistical method that can help make processes and products more efficient by mathematically simulating changes all at once to the variables affecting the process. Gold Plating: is often the teams impression of what is valued by the customer, and the customer might not agree. Remember that QUALITY MUST BE PLANNED IN, NOT INSPECTED IN. Quality means that something does what you needed it to do. Grade describes how much people value it. Increase in Quality can result in increased productivity, cost effectiveness and decreased cost risk. Specification Limits: while control limits represent the performing organisations standards for quality, the specification limits represents the customers expectations or contractual requirements. To meet customers specification limits, the performing orgs control limits must be stricter than those of the customer. Therefore, on the exam, assume that specification limits are outside the upper and lower control limits.
PLANNING | 1. Stakeholder Register | 1. Cost-Benefit Analysis:is looking at how much your quality activities will cost versus how much you will gain from doing them. | 1. Quality Management Plan: The Quality Management Plan is the main tool for preventing defects on your project. It includes: -quality standards that apply to the project -who will be involved in managing Quality -the meetings to be held for addressing quality -the reports that will address quality -what metrics will be used to measure quality -what parts of the project will be measured and when.
| 2. Scope Baseline (approved project scope statement, WBS, and WBS dictionary) | 2. Cost of Quality: Quality involves costs, and the cost of quality quantifies this cost. The cost of quality has two main components –the cost of conforming to quality requirements and the cost of not conforming to quality requirements. The cost of conformance should be lower than costs of non-conformance.
| 3. Cost Performance Baseline | 3. Control Charts: is a type of run chart that is used to determine whether a process is in control or out of control. A run chart is a line graph that displays measurements taken over time, and with the addition of upper and lower control limits, the chart shows at what points in time measurements exceeded thresholds. | 2. Quality Metrics (Defines how Q will be measured) are the specific quality goals the project must meet and how the quality control processes will confirm compliance. It can include any type of applicable measurement, including defect rates, bug rates, failure rates, etc.
| 4. Schedule Baseline: is the approved project schedule. It has the start and finish dates for all project activities, which impact quality requirements | 4. Flowcharting: means coming up with a graphical depiction of the the process you’re doing so that you can anticipate where quality activities might help you prevent defects | 3. Quality Checklists ("to-do" lists that ensure that everything is performed and in the correct order.)
| 5. Risk Register | 4. Benchmarking | 4. Process Improvement Plan
| 6. Organizational Process Assets | 5. Design of Experiments (DOE) | 5. Project Document Updates
| 7. Enterprise environmental factors | 6. Statistical Sampling
8. Proprietary Quality Management Methodologies
9. Additional Quality Planning Tools
22 | Perform Quality Assurance: The process of auditing the quality requirements and the results from quality control measurements to ensure appropriate quality standards and operational definitions are used. "Use the measurements to see if the quality standards will be MET; VALIDATE the standards". Perform Quality Assurance is for determining "Are we using the Standards" and "Can we improve the Standards" # Imp Point: Perform Quality Assurance is primarily concerned with overall PROCESS IMPROVEMENT. It is NOT about inspecting the product for quality or measuring defects. Instead, Performance Quality Assurance is focused on steadily improving the activities and processes undertaken to achieve quality. # Proactive steps taken by PM and the mgmt team to insure the quality standards are being help and monitored. |  |  | Thus quality assurance is focused on the processes and not the quality of the deliverables. This is important for us to remember: quality assurance is concerned with quality processes while quality control is concerned with quality deliverables.
EXECUTING | 1. Project Management Plan (Q M Pl & Process Imp Pl) | 1. Quality Audits (Key Tool): Ensure that the project is complying with its own quality policy. | 1. Change Requests (for Procedural Changes)
| 2. Quality Metrics (Defines how Q will be measured) | 2. Process Analysis: involves techniques which examine the project's processes, looking for any non-value added activities (inefficiencies). Process analysis techniques implement the continuous improvement plan | 2. Project Management Plan Updates
| 3. Quality Control Measurements | 3. Plan Quality and Perform Quality Control Tools | 3. Project Document Updates
| 4. Work Performance Information: Work performance information is any data that can be considered related to the work which produces the project deliverables. Examples are schedule and progress status information, budget and cost status, quality status, estimates to complete, resource utilization information, and lessons learned. | and Techniques | 4. Organizational Process Assets Updates
23 | Perform Quality Control: The process of monitoring and recording results of executing the quality activities to assess performance and recommend necessary changes. This process uses the tool of INSPECTION to make sure the results of the work are what they are supposed to be. Perform Quality Control is the process where each deliverable is INSPECTED, MEASURED, and TESTED. This process makes sure that everything produced meets quality standards. "Perform the MEASUREMENTS and COMPARE to specific quality standards; IDENTIFY ways of eliminating the problem in the future". # Cause and Effect Diagram (Ishikawa/Fishbone): Used to show how different factors relate together and might be tied to potential problems. It imporves quality by identifying quality problems and trying to UNCOVER THE UNDERLYING CAUSE. # Flow Chart: Shows HOW PROCESSES INTERRELATE. # Histogram (Column Chart): It shows HOW OFTEN something occurs, or its FREQUENCY (no Ranking). # Pareto Charts (80-20 rule): This is a Histogram showing defects RANKED from GREATEST to LEAST. This rule states that 80% of the problems come from 20% of the causes. It is used to help determine the FEW ROOT CAUSES behind the MAJORITY OF THE PROBLEMS on a project. # Run Chart: tell about TRENDS in the project. Shows the HISTORY and PATTERN. # Scatter Diagram: It is powerful tool for SPOTTING TRENDS in Data. Scatter Diagrams are made using two variables (a dependent variable and an independent variable). # Statistical Sampling: It is a powerful tool where a RANDOM sample is selected instead of measuring the entire population. |  |  | Perform Quality Control makes sure that the project's deliverables comply with the quality requirements and prevents non-compliance issues from recurring. Quality control terminology: -- Prevention: Prevention activities involve looking at processes for factors that can potentially lead to defects, and when defects are detected, determining the root causes so that those factors can be mitigated. -- Inspection activities are the testing, measurement, review, and examination of the deliverable to determine whether it's in compliance with the quality requirements. -- Accuracy and precision: Accuracy describes how close a measurement is to its true value while precision describes how repeatable the measure is and how many significant digits it’s measured in. -- Tolerances are the acceptable variations in limits, such as a fluorescent light bulb should burn between 4000 and 5000 continuous hours. They define the maximum variations from a nominal value that are acceptable because they will have a negligible effect on the quality level. -- Special and common causes: A special cause is an unusual event outside of the process that leads to a measurable change in the process. Though unusual, special causes are considered preventable. For example, a backup generator failed to start up during a power failure. The failure of the backup generator can be prevented in the future through regular mechanical maintenance and operational tests. A common cause is a normal event within the process that leads to a measurable change in the process. Common causes result in rare, but tolerable variations. Even if it were possible to remove all possible common causes from a process, the effort to do so would usually be cost prohibitive. Common causes are thus generally considered as non-preventable and accepted as part of the process. For example, let’s imagine that about one screw out of every 50,000 from a supplier is misthreaded. When a manufacturing process encounters one of these misthreaded screws, it causes a jam in the machine which must be manually removed. The jam would result in a measurable change in the process (seen as decrease in production), but since it would be cost prohibitive to have all screws individually inspected before they were used in the manufacturing process this is considered an unpreventable cause. -- Control limits: are the upper and lower limits set for a process, usually at three standard deviations from the mean, and determine whether a process is in control or out of control -- Statistical sampling is a broad term that involves choosing random, representative samples for testing rather than testing each individual deliverable. -- Standard deviation and Sigma values: Standard deviation is used to measure how data is organized. For the PMP examination, we should know the basic standard deviation formula, the concept of standard deviation and what it's used for, and the four sigma values for normally distributed data. Standard deviation formula is the result of the optimistic estimate subtracted from the pessimistic, divided by six: = (Pessimistic Estimate - Optimistic Estimate) / 6 1 sigma -- 68.25% 2 sigma -- 95.46% 3 sigma -- 99.73% 6 sigma -- 99.99% --Scatter charts help you look at the relationship between two different kinds of data. Exam Spotlight Don’t confuse inspection with prevention; they’re two different tools. Inspection keeps errors in the product from reaching the customer. Prevention keeps errors from occurring in the process.
MONITORING & CONTROLLING | 1. Project Management Plan (Q M Plan) | 1. Cause and Effect Diagram (Ishikawa/Fishbone) | 1. Quality Control Measurements: are all of the results of your inspections: the numbers of defects you’ve found, numbers of tests that passed or failed—stuff like that
| 2. Quality Metrics | 2. Control Charts | 2. Validated Changes
| 3. Quality Checklists | 3. Flowcharting: Flowcharts help you get a handle on how processes work by showing all of the decision points graphically. | 3. Validated Deliverables
| 4. Deliverables | 4. Histogram | 4. Change Requests
| 5. Approved Change Requests | 5. Pareto Chart: Pareto charts go together with the 80/20 rule. It says that 80 percent of the problems you’ll encounter in your project are caused by 20 percent of the root causes you can find. Pareto charts plot out the frequency of defects and sort them in descending order. -helps focus attention on most critical issues -priortize potential causes of the problem -separate the critical few from the uncritical many | 5. Project Management Plan Updates
| 6. Work Performance Measurements | 6. Run Chart: Run charts are used to show variations in the process over time or to show trends (such as improvements or lack of improvements) in the process. In a run chart, you are looking for trends in the data over time. | 6. Project Document Updates
| 7. Organizational Process Assets | 7. Scatter Diagram: Scatter charts help you look at the relationship between two different kinds of data. | 7. Organizational Process Assets Updates
8. Statistical Sampling
9. Inspection
|  | 10. Approved Change Requests Review | Exam Spotlight The most important fact you should know about the Verify Scope process is that Verify Scope formalizes the acceptance of the project scope and is primarily concerned with the acceptance of work results. Don’t confuse this process with the Perform Quality Control process. You can remember the difference between Verify Scope and Perform Quality Control this way: -- Perform Quality Control = checking for correct work results and assuring that the quality requirements are met -- Verify Scope = accepting work results
# Plan Quality, Perform Quality Assurane, and Perform Quality Control map closely to the Plan-Do-Check-Act cycle as described by W. Edwards Deming (He also developed 14 activities for implementing quality). # Philip Crosby, similar to Deming, he too developed 14 Steps to improving quality. # Joseph Juran: Fitness-for-use, Juran Trilogy (Quality of Design, Quality of Conformance, and Quality Characteristics), Juran Trilogy approach Plan-Improve-Control. # Dr. Genichi Taguchi developed the concept of 'Loss Function'.
# Investment in Quality is usually born by the Organization (not by the project). # Plan-Do-Check-Act has been defined by SHEWHARD and modified by DEMING in ASQ Handbook.
# Quality is "the degree to which a set of inherent characteristics fulfill requirements."
# Total Quality Management (TQM): Everyone in the company is responsible for quality and is able to make a difference in the ultimate quality of the product. TQM shifts the primary quality focus away from the product that is produced and looks instead at the underlying process of how it was produced.
# Continuous Improvement Process (CIP)/KAIZEN: A philosophy that stresses constant process improvement, in the form of small changes in products or services.
# Just-In-Time (JIT): A manufacturing method that brings inventory down to Zero (or near Zero) levels. It forces a focus on quality, since there is no excess inventory on hand to waste. # • 1σ = 68.25% • 2σ = 95.46% • 3σ = 99.73% • 6σ = 99.99966% # ISO 9000: Ensures Companies document what they do and do what they document. It may be an important component of Performance Quality Assurance, since it ensures that an organization follows their processes. # Mutually Exclusive: one choice excludes the other. # CMMI: Defines the essential elements of effective processes.
# Statistical Independence: When the outcomes of two processes are not linked together or dependent upon each other, they are statistically independent.
# Six Sigma: Six sigma quality strives to make the overwhelming majority of the bell curve fall within customer quality limits. Six sigma is a quality management philosophy that sets very high standards for quality, and that one sigman quality is the lowest quality level, allowing 317,500 defects per 1,000,000 outputs, three sigma quality is higher, allowing 2,700 defects per 1,000,000, and six sigma is the highest of these, allowing only 3.4 defects per 1,000,000. Pharmaceutical Industry, the Airline Industry, and Power Utilities typically strive for higher levels of quality than six sigma would specify in some areas of their operations.

## HR
HUMAN RESOURCE
Sl# | Inputs | Tools & Techniques | Outputs
•Group: A small group of people with complementary skills and abilities who are committed to a leader's goal and approach and are willing to be held accountable by the leader. •Team: A small group of people with complementary skills and abilities who are committed to a common goal and approach for which they hold each other accountable. ------------------------------Interpersonal power bases: ------------------------------ Legitimate (Formal): Also known as formal or normative power, this type of power comes from one's position, title, or hierarchy. In a matrixed organization, the project manager doesn’t have legitimate power, because the team doesn’t directly report to the project manager. Expert: This type of power comes from one's knowledge, expertise, skills, talents, or experience. Reward: This type of power comes from one's ability to bestow desired rewards to others. Coercive: This type of power comes from one's ability to apply negative influences, such as punishments, on others. Referent: This type of power comes from one's charisma, personality, or hero/heroine status. Reward and expert are the interpersonal powers favored by PMI FORMAL, REWARD, PENALTY are powers derived from project managers position in the company. ------------------------------Leadership styles:------------------------------------ #Authoritarian: The leader is in total control, relying only on his or her judgment, arbitrarily making decisions, and generally sharing information only on a need-to-know basis. #Democratic: The leader seeks input and involvement from the group as part of the decision-making process and openly shares information with the group. #Laissez-faire: The leader turns nearly all control over to the group and is generally absent. The leader is likely to share information only when directly asked for it. ------------------------------Leadership theories:------------------------------ Theory X/Theory Y: --Theory X, managers believe that employees show little ambition and will avoid responsibility unless they are constantly monitored, and that they care very little about their work product and are motivated to do it well only through strong controls, coercion, and the threat of punitive measures. A manager subscribing to this viewpoint is likely to rely on an authoritarian leadership style. --Theory Y, managers believe that employees are generally ambitious and self-motivated if given the chance, and that they feel a sense of pride in their work and are motivated by the feeling of a job well done. A manager subscribing to this viewpoint is most likely to rely on a democratic and in some cases a laissez-faire leadership style. --Theory Z, managers believe that employees are motivated by stability, longevity, and involvement in the decision-making process. Things such as life-career balance, collective decision making, and long-term employment are characteristics of a Theory Z organization. A manager subscribing to this viewpoint is likely to rely on a democratic leadership style. ------------------------------Management & Leadership styles:------------------------------------ Directing: telling others what to do. Facilitating: coordinating the input from others Coaching: in this managers helps others achieve their goals Supporting: involves providing assistance along the way Autocratic: in this manager has power to do whatever he wants. The manager may coach or delegate, but everyone is doing what manager wants them to do. Consultative: The manager obtains other opinions and acts as servant for the team. Consultative-Autocratic: manager solicits inputs from team members, but retains decision making authority for him. Consensus: involves problem solving in group, making decisions based on group agreement Delegating: in this manager establishes goals and then gives team sufficient authority to complete the work. Bureaucratic: this style focuses on following procedures exactly. Charismatic: these managers energize and encourages team in performing project work. Democratic or Participative: involves encouraging team participation in decision making process. Laissez-faire: this manager is not directly involved in the work of the team, but manages and consults as necessary. this style is appropriate with a highly skilled team. ------------------------------Roles & Responsibilities:------------------------------------ Role of Project Sponsor: -is one who provides financial resources for the project. -Approves the final project plan -protects the project from outside influences and changes. -Resolves conflicts that extends beyond project managers control -Provides formal acceptance of the deliverables.
24 | Develop Human Resource Plan: The process of identifying and documenting Project Roles, Responsibilities, and Required Skills, Reporting Relationships, and creating a Staff Management Plan. The HR Plan documents project Roles and Responsibilities, Porject Organization Charts, and the Staffing Management Plan including the Timetable for Staff Acquisition and Release. It may also include Identification of Training Needs, Team-Building Strategies, Plans for Recognition and Rewards Programs, Compliance Considerations, Safety Issues, and the Impact of the Staffing Management Plan on the Organization. TT1: Three Primary Formats are 1. Hierachical, 2. Matrix (RAM - Responsibility Asssignment Matrix, which displays work packages in the rows and roles in the columns - Popular Type is RACI chart - R-Responsible; A-Accountable; C-Consult; I-Inform. It is important when team consists of Internal and External Resources), and 3. Text (Job/Position Descriptions and Role-Responsibility-Authority Forms - This tool is prticularly useful in Recruiting). TT2: For understanding Organizations and Teams behavior. TT3: Networking is the process of communicating with others within your "Network" of contacts - By networking within the organization, PM can understand the political and Organizational Forces that will influence the project. HR Networking activities include Proactive Correspondance, Luncheon Meetings, Informal Conversations including Meeting and Events, Trade Conferences, and Symposia. It can be a useful technique at the beginning of a project. O1: Resource Histogram - shows the resource usage for a given period of time. It illustrates the number of hours a person, department, or entire project team will be needed each week or month over the course of the project. |  |  | Human resource management plan: --Staff acquisition procedures: staffing management plan describes how and through what methods the people needed for the project will be acquired, which may include both personnel internal to the performing organization and external to it, such as consultants. --Resource timetables, calendars, histograms: human resource plan includes information on when resources will be needed and in what durations, shown through calendars, timetables, and histograms. #Resource calendars show when roles or personnel will be needed by the project, including expected working hours, holidays, shifts, or other important information the project staff will need to know. It is also applicable to non-human resources. As part of procurement activities, those resources are added to the calendar, showing expected arrival dates, general availability, hours of access, and quantities available. #Resource histograms that show the work units by time period that a role, person, or department will provide to the project. --Training: The human resource management plan includes the formal plan for project team member training. Only the training required by the project team is addressed by the plan. We shouldn’t confuse it with whatever training plan might be required for stakeholders in the use of the project’s deliverables. For example, if the customer will require training sessions on how to use a software application created by the project, that training (and whatever activities it may require) are treated as a project deliverable. --Compliance and safety: The human resource management plan also describes any measures that will be taken to ensure that any safety, governmental, regulatory, organizational, or contractual obligations are followed that are applicable to human resource requirements. --Team performance assessments:The human resource management plan will include any team performance goals, and how the overall performance of the project team will be measured and evaluated. --Project performance appraisals: The human resource management plan will include the procedures, methods, and guidelines for the performance appraisal of individual project team members. --Recognition and rewards: The human resource management plan details the approaches that will be taken for promoting and reinforcing desired behavior, including the costs associated with any recognition or reward program --Staff release criteria: The staffing management plan describes how team members will be released from the project. Team members are released from the project when their work is completed or when other unexpected reasons occurs. # Staffing Mgmt Plan include: 1.Staff acquisitions, 2.Resource calendars/histogram, 3.Staff release plan, 4.Training needs, 5.Recognition & Rewards, 6.Compliance, and 7.Safety. There are lots of ways to record and communicate roles and responsibilities, including RAM, organisation breakdown structures, resource breakdown structures, position descriptions.
PLANNING | 1. Activity Resource Requirement: The activity resource requirements document describes the resource needs at the activity level. It focuses on the resource types and quantities needed, and it helps determine the competencies that will be needed for the project. | 1. Organization Charts and Position Descriptions: These documents describe the project roles, hierarchy, reporting relationships, and responsibilities. They include project organization charts, position descriptions, role-responsibility-authority forms, RAM’s, and RACI’s. | 1. Human Resource Plan - It has three componenets a. Roles and Responsibilities: outlines every unique project role and includes each role’s authority, skills needed, and responsibilities A RAM (Responsibility Assignment Matrix) shows by activity what role is responsible, and as people are assigned to roles their names are added to the table. A RACI (pronounced ray-cee) is a type of RAM that derives its name from the responsibility designation that's given to each role/activity combination: R=Responsible: The role is primarily responsible for performing the work required of that activity. A=Accountable: The role is held accountable for the activity's output, deliverable, or artifact. C=Consult: The role is in an advisory position for the activity. I=Inform: The role will be kept in the loop as the activity is underway. b. Organization Charts c. The Staffing Management Plan: describe how the project will be staffed, and how the project team will be trained, evaluated, compensated, rewarded, and released from the project.
| 2. Enterprise Environmental Factors: company culture or existing systems that project will have to deal with. | 2. Organizational Theory: These are sociological, behavioral, and psychological theories that describe how individuals, teams, groups, and other organizational units behave.
| 3. Organizational Process Assets | 3. Networking: Networking involves the formal and informal interaction between others in the enterprise, profession, or industry. Networking includes conferences, electronic communities, luncheons, trade groups, and seminars.
25 | Acquire Project Team: process results in personnel being assigned to the roles needed in order for the project work to be performed. TT1: Pre-Assignment: Occasionally specific resources will be Pre-Assigned to fill a role. This may occur before the Human Resource Plan has been created and even before the project formally begins. TT2: Negotiation: It is an important skill for PM to cultivate. TT3: Aquisition: It refers to looking outside the organization for resources when they cannot be provided by your organization. TT4: Virtual teams are when all team members don’t work in the same location. |  |  | You should read the the phrase "Acquire Project Team" as "Acquire FINAL project team": Acquire Project Team invloves: 1. knowing which resources are pre-assigned and confirming their availability. 2. Negotiating for the best possible resources. 3. Hiring new employees 4. Hiring through contracting 5. Managing the risk of resources becoming unavailable. Halo Effect: You are a great programmer. Therefore we will make you a project manager and expect you to be great at that as well.
EXECUTING | 1. Project Management Plan | 1. Pre-Assignment | 1. Project Staff Assignments : is a listing of whom is fulfilling what project roles
| 2. Enterprise Environmental Factors | 2. Negotiation (Key Technique of this process) | 2. Resource Calendars
| 3. Organizational Process Assets | 3. Acquisition | 3. Project Management Plan Updates
4. Virtual Teams
26 | Develop Project Team: The process of improving the competencies, team interaction, and the overall team environment to enhance project performance. "Project Management Skills, Leadership Styles, Power, Team Building and the Motivation of people are all concepts that fall into this process." Five kinds of powers: Reward power, Expert power, Referent power, Punishment power (Coercive), and legitimate power (Formal power) - Reward and Expert as the most effective forms of power and Punishment/Coercive as the least effective. Recognition and Reward (Theories of Motivation) - Win-win rewards as the best choices for team building. • Maslow’s hierarchy of needs - Maslow presented a hierarchy of deficiency needs that must be met in order for a person to reach his or her pinnacle. In most cases, each lower need must be met before the next level of satisfaction can be achieved, and previously satisfied needs are no longer motivating factors for the person. LOWER needs: 1. Physiological Needs: Food, water, air, shelter 2. Security/Safety: Stability (political, environmental, financial), personal safety, health 3. Acceptance/Social: Friendship, community, family, intimacy. HIGHER Needs 4. Esteem: Respect from others, respect of others, self-respect 5. Self-Actualization: is when a person reaches a need for constant personal growth and improvement. To reach and continue self-actualization, Maslow found that two additional factors had to be present: •Cognitive stimulation: Intellectual stimulation, access to knowledge •Aesthetic stimulation: Access to imagery, beauty, and art Characteristics of self-actualizing people: • Don't deny or avoid facts • Effective perception of reality • Spontaneous in ideas and actions • Creative • Problem-solving • Social interest in other people • Objective • Trusting • Acceptance of others • Independent with a need for solitude • Herzberg’s Motivation-Hygiene Theory: Hygiene factors (Company Policy, Supervision, Good relationship with boss, working conditions, Paycheck, Personal life, Status, Security, and Relationship with co-workers) does not make someone satisfied, but their absence will make someone unsatisfied. Hygiene factors do not motivate by themselves. Motivation factors (Achievement, Recognition, Work, Responsibility, Advancement, and Growth) will motivate, but they will not work without the Hygiene factors in place. So to really motivate team members, we need to eliminate job dissatisfaction factors while also providing motivating factors, such as recognition and giving team members activities that are challenging and stimulating. • Victor Vroom’s Expectancy Theory: If workers believe their efforts are going to be successful and rewarded, they will tend to be highly motivated and productive. He suggested that employees are really motivated by goals only when three beliefs are present: •Valence: The person wants to achieve the goal. •Expectancy: The person believes it's possible to attain the goal. •Instrumentality: Instrumentality is a judgment the person makes about whether he or she believes that the reward will be given • David McLelland’s Achievement Theory(Theory of three needs): this Theory says that people need achievement, power, and affiliation to be motivated. -- Achievement is when someone performs well and is recognized for it. -- Power means he or she has a lot of control or influence in the company. -- And someone feels a strong sense of Affiliation from being a part of a working team and having good relationships with coworkers. • Douglas McGregor’s Theory X and Theory Y: Theory X - Team members are Selfish, Unmotivated, Dislike work (constant supervision is required - 'authoritarian management' style). Theory Y - Naturally motivated to do good work (manager trusts team members - 'participative management' style). • Dr. William Ouchi’s Theory of – “Z Theory”: Productivity can be increased by how well the workers and management get along and trust each other. Japanese style of management • Contingency Theory (Fred E. Fiedler): In stressful times, a task-oriented leader will be more effective, while in relatively calm times a relationship-oriented leader will function more effectively. • Hersey and Blanchard's Life Cycle Theory: Leadership style must change with the maturity of individual employees. The PM's style should move from Directing, to Coaching, to Supporting, Then to Delegating as the project moves through its life cycle. |  |  | Team formation stages: -#-Forming: Characteristics: Group members may be shy or uncomfortable among each other, and everyone is usually on his or her best behavior. From each individual's standpoint, they've been brought together by management and not because they share any common goals. Members are usually hesitant to speak openly of ideas or opinions. Leadership: The leader needs to set clear, broad expectations for the group without specifically telling the group how to get there. The leader should facilitate group interaction and development of trust, such as through project planning activities, and by establishing GROUND RULES, goals, milestones, approaches, and objectives. The leader needs to stay closely involved and set an example of expected and acceptable behavior. -#-Storming: Characteristics: Conflict is common as group members begin to express ideas and opinions but do not yet fully trust each other's motives. Conflict may cause some group members to withdraw while it may make others hostile and vocal. Some members may be apprehensive, anxious, or nervous about the group being able to meet its goals, and work progress is slow. Leadership: This is the most difficult time for the team, so the leader needs to stay involved and facilitate healthy conflict resolution when needed. It's very important for the leader to set an example of trust, tolerance, patience, and to remain realistically upbeat. If ground rules aren't followed and the team doesn't correct the situation on its own, the leader should return the group back to a discussion on its ground rules. -#-Norming: Characteristics: The group begins to develop trust and grows comfortable with each other. The first signs of community and interdependence are shown. Collaboration, rather than individual efforts, begins to show. Motivation and productivity increase and a sense of common spirit appears. Leadership: The leader needs to stay involved, but he or she should continue efforts to let the team begin holding itself accountable and making its own decisions. The leader should move predominantly into a facilitator role. There are two things the leader needs to watch for: •Cliques: While not always unhealthy, subgroups within the team can disrupt the whole team if they develop too much autonomy, power, or influence. •Groupthink: Groups may slip into such a comfortable and trusting state that the members begin to think alike and stop questioning each other. This can lead to poor decisions or missed opportunities, which is a very dangerous state for the group. The leader may have to find healthy ways to de-normalize the team, such as by introducing new team members into the mix. -#-Performing: Characteristics: The team is performing at its highest and most productive levels, and it does so naturally and instinctively. Members have a strong sense of reliance on each other and trust. Ideas and opinions are openly shared, and as a result innovation and creativity in the team's approaches and solutions are evident. Leadership: The team is self-directing, self-managing, and holding itself accountable. The leader can focus on facilitation when needed, and rewarding and recognizing the team to maintain its motivation -#-Adjourning: Characteristics: It’s when the team has accomplished its goals and is disbanding. Some have also proposed a "transforming" stage in which the team identifies new goals to tackle and thereby transforms its goals and purpose. Leadership: For the project management team, this stage will occur during phase project closure. The leader needs to ensure team-formation lessons learned are documented and that recognition to the team is given. Because the team has developed personal bonds, opportunities for socializing during the project closure should be provided.
EXECUTING | 1. Project Staff Assignments (will have list | 1. Training | 1. Team Performance Assessments Team performance assessments measure the effectiveness of the overall team. These are really a measurement of how well the project management team is implementing the applicable components of the human resource plan.
| of all team members) | 2. Team-building Activities
| 2. Resource Calendars | 3. Ground Rules: Ground rules are the behavioral expectations the team has for its members. Ground rules are established and enforced by the team itself.
| 3. Project Management Plan | 4. Co-location (or War Room)
5. Recognition and Rewards
|  | 6. Interpersonal Skills (Soft Skills) | 2. Enterprise Environmental Factors Upd
27 | Manage Project Team: The process of tracking team member performance, providing feedback, resolving issues, and managing changes to enhance the project performance. Methods of Conflict Mgmt: • Problem solving (Confronting): It’s a Win-Win situation (Highly favoured way) • Compromising: Lose-Lose method • Withdrawal: Lose-Leave method (PMI does not favour this method) • Smoothing: Lose-Yield method (Doesn't produce a solution) • Forcing: Win-Lose method (Worst way). Leadership styles: • Autocratic/Authoritarian/Directing: Strong style. The PM seeks little or no information from the team, and is the sole decision maker. • Bureaucratic/Persuading/Consultative Autocratic: Input is received from selected team members, but the PM is still the sole decision maker. • Democratic/Participative/Consensus: Consults team for open discussion and information gathering; uses help from team to come up with a decision. • Lassiez-faire/Delegating/Free Reign/Shareholder: (Poor Leadership Style) Little or no information exchange takes place within the project group. Team has ultimate authority on final decision, hands-off attitude. • Transactional: Transactional leadership is really just a way of managing (mangement by exception) rather than a true leadership style as the focus on the short-term tasks. • Transformational: A person with this leadership style is a true leader who inspires his or her team constantly with a shared vision of the future. |  |  | Conflict management: The project manager, project management team, and the project team all need to be aware of and skilled in conflict resolution techniques. In the project environment, conflict can come from seven main sources, of which the first three account for 50%: 1. Schedules 2. Priorities 3. Manpower/human resource availability 4. Technical opinions 5. Procedural or project administration 6. Costs 7. Personalities Conflict resolution: There are five broad categories for resolving conflict: 1. Problem-solving: also known as confronting, is the preferred approach because it's the one most likely to result in a WIN-WIN solution for all parties. Problem solving is a logical approach to finding the cause as well as the best solution. It lets everyone discuss contributing factors and what the pros and cons are for each solution. Problem solving is best used when there is sufficient time to approach the problem and the group members have a certain level of trust with each other. Problem solving is also good at fostering team development because it involves everyone in exploring the issue. 2. Compromise is when all parties perform some give-and-take to reach a middle settlement. Unfortunately, this results in a LOSE-LOSE solution because no one is truly happy with the solution. Problem solving is the best approach, but compromise may be necessary when time is scarce or there's a deadlock that can't be logically resolved. 3. Forcing is using one's power to dictate his or her will on the group. Forcing results in a WIN-LOSE situation, and this is generally the worst approach. It's harmful to team morale because the team is always on the losing position. However, forcing may be necessary in critical situations when the stakes are extremely high and there is no time for identifying alternatives. When forcing is needed, its ill effects on the team can be tempered by sharing the rationale with them. 4. Smoothing is downplaying the issue or focusing only on the positive. It's really hiding from the problem, and it doesn't address the problem or even acknowledge that the problem exists. Smoothing can be used to buy time or when one party believes the stakes are low and giving a "win" on this issue may be used to create an obligation later. Smoothing can often be seen when one party gives in by saying something like “Well, it’s not important anyway, so you choose.” 5. Withdrawal is avoidance or hiding from the problem, so it's not even a conflict resolution technique. Withdrawal may be an option as a temporary measure when there's a need for cooling off or there are likely to be other alternatives that will present themselves if given enough time. 6. Collaborating means working with other people to make sure that their viewpoints and perspectives are taken into acount. It’s a great way to get a real commitment from everyone.
EXECUTING | 1. Project Management Plan | 1. Observation and Conversation: The project management team needs to stay closely involved in the day-to-day activities of the team in order to monitor progress and get first-hand impressions from the team members. | 1. Change Requests Staffing changes, for whatever reasons, are treated as change requests. Team performance issues can also result in the need for corrective or preventative actions.
| 2. Project Staff Assignments: Project staff assignments are the people assigned to develop the project’s deliverables. It’s needed for this process to know who is on the project team and who is responsible for what items. | 2. Project Performance Appraisals: are formalized feedback about the individual's team members contributions to the project. The purpose of appraisals is twofold: first, the team member needs recognized for what he or she is doing well; secondly, they need honest and direct feedback on where improvements can be made. | 2. Project Management Plan Updates
| 3. Team Performance Assessments: Team performance assessments measure the effectiveness of the overall team. | 3. Conflict Management | 3. Organizational Process Assets Updates
| 4. Performance Reports: These provide performance reporting on activities, accomplishments, and issues | 4. Issue Log: The issue log tracks all problems that can keep the project from its goals | 4. Enterprise Environmental Factors Updates
| 5. Organizational Process Assets | 5. Interpersonal Skills
# Generally, only one person is assigned Accountability for a work package, but more than one person may be responsible for performing the work on a work package.
# Training Expenses should be paid for by the Performing Organization or the Functional Manager and not by the Customer or the Project.
# Ground Rules: Formal or informal rules that define the boundaries of behavior on the project. It is important that ground rules be defined and communicated to the team members. # Five Stages of Team Development are: 1. Forming, 2. Storming, 3. Norming, 4. Performing, and 5. Adjourning
# Constructive Team Roles: Initiators, Information Seekers, Information Givers, Encouragers, Clarifiers, Harmonizers, Summarizers, and Gate Keepers.
# Distructive Team Roles: Aggressors, Blockers, Withdrawers, Recognition Seekers, Topic Jumpers, Dominators, and Devil's Advocates.
# The greatest project conflict occurs between Project Managers and Functional Managers. Most conflict on a project is the result of disagreement over Schedule, Priorities, and Resource. # Deligation is completely opposit to Micromanagement (it is completely opposite to Deligation)
# PM's Style of Leadership over Project Timeline: i. Directing Leader, ii. Coaching Leader, iii. Facilitating Leader, and iv. Supporting Leader
# PMI views the process of managing conflict within the project team as initially being the responsibility of the project team members.
# Staffing Mgmt Plan include: 1.Staff acquisitions, 2.Resource calendars/histogram, 3.Staff release plan, 4.Training needs, 5.Recognition & Rewards, 6.Compliance, and 7.Safety.

## Communication
COMMUNICATIONS
Sl# | Inputs | Tools & Techniques | Outputs
28 | Identify Stakeholders: Identify all people or organizations impacted by the project and document their interests, involvement and impact on project success. Stakeholder Analysis Steps: 1. Identify Stakeholders 2. Analyze & Classify Stakeholders 3. Develop Strategy. Stakeholders Classification Models: 1. Power/Interest Grid (Authority/Concern) 2. Power/Influence Grid (Authority/Involvement) 3. Influence/Impact Grid (Influence/Ability to effect Planning & Execution) 4. Salience Model - describing classes of stakeholders based on their Power, Urgency and Legitimacy. Categories: 1. Champions - Positive Attitude, 2. Neutral - No influence expected, 3. Challenger - Questions the project, 4. Decision Makers - Manage Challengers, Support Champions. Strategies: For Individuals - A. Assessment Matrix, B. Strategy Matrix. For Groups - A. Commmunication Strategy Matrix. |  |  | Proj charter: information about internal / external parties affected by proj, like sponsor(s), customers, team members, groups & departments participating in project, other people /orgs affected by the proj. Stakeholder Analysis: is process of gathering / analysing quantitative/qualitative information to determine whose interest should be taken care through out the project. Step1: identify all potential stakeholders and relavent information, such as their roles, departments, interests, knowledge levels, and influence levels. Key stakeholders are easy to identify....identifying others is done my interviewing the key stakeholders and expanding the list until all the stakeholders are identfied. Step2: priortize the key stakeholders; indentify potential impact or support each stakeholder could generate and classify them so as to define an approach strategy. Stakeholders Classification Model: Grids are a tool to plot a stakeholder’s position along two axes that each represents a separate key factor. The two axes split the grid into four quadrants, and where the plotted point falls gives us an indication of what level of participation the stakeholder needs and how much effort the project manager will want to expend on meeting the stakeholder’s expectations. - In the upper-right quadrant are stakeholders who need actively engaged in the project - In the upper-left quadrant are stakeholders who need occasional engagement with the project and project manager - The project manager needs to keep an open and regular dialogue with the stakeholders in the lower-right quadrant. - those in the lower-left quadrant need to receive occasional follow-up and information about the project, but the project manager doesn’t want to overwhelm them with communication - Power / Interest grids: grouping based on their level of authority (power) & their level of concern (interest) regarding project outcomes - Power / Influence grids: grouping based on their level of authority (power) & their active involvement (influence) in the project. - Influence / impact grids: grouping based on their active involvement (influence) and their ability to effect changes in project planning or execution Salience model: describes classes of stakeholders based on : - power (This is a subjective determination of how much influence the stakeholder has to impose his or her will. For example, a chief executive in the company usually has a very high level of power even if he or she isn’t directly involved in the project.) - urgency (This is an assessment of how quickly the stakeholder will expect his or her will to be acted upon.) - legitimacy (This is a gauge of how much vested interest the stakeholder has, giving the stakeholder a legitimate stake in the project. For example, a marketing manager probably has no legitimacy in a project for the accounting department.) Step3: Know the influence each stakeholder holds; assess how key stakeholders are likely to react or respond in various situations, in order to plan how to influence them to enhance their support and mitigate potential negative impact.
INITIATING | 1. Project Charter | 1. Stakeholder Analysis investigates the interests, expectations, and influences of the project’s stakeholders To perform stakeholder analysis, we'll need to: 1. Make sure we’ve identified every person, group, or entity affected by the project 2. Assess each stakeholder's interests in the project 3.Know the influence each stakeholder holds 4.Develop proactive strategies for dealing with stakeholders 5.Develop proactive strategies for dealing with stakeholders | 1. Stakeholder Register is the list of all people positively or negatively affected by the project
| 2. Procurement Documents |  | 2. Stakeholder Management Strategy Stakeholder analysis uses a variety of techniques to qualitatively and quantitatively identify the interest, expectations, influences, and needs of stakeholders. (Stakeholder Analysis Matrix) •How will positive stakeholders be kept satisfied? •How could we reduce or eliminate the opposition from negative stakeholders? •How can we mitigate the risks negative stakeholders may generate? •What's the role of others (outside the project) in managing stakeholders? •What types of communications, forums, and face-to-face opportunities will work best for the various types of information and issues that will need addressed?
| 3. Enterprise Environmental Factors | 2. Expert Judgment
| 4. Organizational Process Assets | In face-to-face communication, - words make up only seven percent of the message - while paralingual elements convey 38% and - nonverbal elements convey 55%.
29 | Plan Communications: Determining the project stakeholder information needs and defining a communication approach. * Plan Communication is tighly linked with Enterprise Environmental Factors (Org Structure). TT1: Total No of Comm Channels or Paths = n(n-1)/2 --- Comm Channels: # Upward Comm to Management # Lateral Comm to Peers, other Functional Groups and Customers # Downward Comm to Subordinates. TT2: Factors that can effect - 1. Urgency of the need for information 2. Availability of Technology 3. Expected Project Staffing 4. Duration of the Project 5. Project Environment. TT3: It consists of the following components - a Sender, a Receiver, Encode, Decode, a Medium (through which messages are send and received), Noice and Message & Feedback Message. TT4: 1. Interactive Comm - A. Formal Verbal (Presentations and Speeches), B. Informal Verbal (Meetings, Conversations, Humor, and Inquiries) 2. Push Comm - A. Formal Written (Proj. Plans, Charter, Comm over Long Distances, Complex Problems, Legal Docs and Long or Tech situations for a wide and varied audience), B. Informal Written (Status Updates, Information Updates and Day-to-day Comm., Email) 3. Pull Comm - for very large volumes of information, or for very large audiences (Internet Sites, E-learining and Knowledge Repositories. And are more likely to use Formal Written Methods) |  |  | Plan communications process determines who needs what info, when they will need it, how it will be given to them, and by whom. Communications planning should cover both the formal and informal communication needs. Formal needs include progress meetings, status reports, performance reports, issue disposition, and other customer, stakeholder, management, or team communication items that are expected. Informal communications are those generally considered as social interactions or impromptu meetings --ad-hoc conferences, lunches, or hallway conversations. Communication Requirement Analysis: This analysis looks not only at what is generally required for all projects, but what communication needs are specific to the project being undertaken and its environment. -- Another important factor to consider is the interest level of the stakeholders in different types of project communication. Much depends upon the project, but as an example stakeholders in the accounting department will have different information needs than will stakeholders in the manufacturing department. -- Other project-level factors to consider is how often specific information needs to be updated (e.g., daily, weekly, monthly), the risk level of the project, and whether the project team is co-located, disbursed across multiple locations, or is operating wholly or partially as a virtual team -- PM should also consider the number of potential communication channels as an indicator of the complexity of the project. Total number of communication channels is: n ( n - 1) / 2 , where n is number of stakeholders. It's the SENDER'S responsibility to make the message clear, complete, and understood while it's the RECEIVER's responsibility to make sure the message is received in its entirety and understood. Communication methods: -- Interactive communication: involves just two or many people, one person provides information; others receive it and then respond to the information. Interactive communication involves meetings, instant chats, electronic social messaging, telephone calls, forums, and conferences. -- Push communication: this method involves one-way stream of information, the sender provides the information to the people who need it but does not expect feedback on the information. Examples are status reports, company memo..etc -- Pull communication: in this the project manager places the information on a central location, the recipients are then responsible for retrieving or 'pulling' the information from that location. Pull communications involve web sites, intranet repositories, podcasts, recorded webcasts, project libraries, and e-learning materials
PLANNING | 1. Stakeholder Register | 1. Communication Requirement Analysis: means figuring out what kind of communication your stakeholders need from the project so that they can make good decisions. | 1. Communications Management Plan: • stakeholder communication requirements • information to be communicated, format, language… • reason for distribution of that info • time frame & frequency of distribution • person responsible for communication • person/groups who will receive communication • methods/technologies to convey communication • escalation process • glossary of common terminology • flowchart of info flow in project • communication constraints
| 2. Stakeholder Management Strategy | 2. Communication Technology: Methods used to transfer information…converstaions, meetings, written docs.
| 3. Enterprise Environmental Factors | 3. Communication Models: demonstrate how the various people associated with your project send and receive their information. Sender: The person encoding and transmitting the message. Receiver: The person receiving the message. Encode: The formulation of the message by the sender. Message: The output of the encoding process. Medium: The transport mechanism for the message chosen by the sender, such as telephone, e-mail, speech, or printed document. Decode: The translation of the message by the receiver. Noise: This is anything that disrupts the flow or understanding of the message. Noise can be auditory disruptions, like static or background noise. Factors like receivers education, experience, language, and culture effect the way receiver decodes the message. Communication model calls these types of factors as 'noise'
| 4. Organizational Process Assets | 4. Communication Methods: interactive , push, pull | 2. Project Document Updates
30 | Distribute Information: Execution of Comm Management Plan, as well as responding to unexpected requestss for information. It is the process of making relevant information available to project stakeholders as planned. It is performed according to Comm Management Plan, it is where the Bulk of Project Communication takes place. TT1: Individual and Group Meetings, Video and Audio Conferences, Computer Chats, and other remote comm methods. TT2: 1. Hard-copy document distribution, 2. Electronic Comm and Conferencing tools (Email, Fax, Voice Mail, Telehpne, Video and web Conferencing, Websites and Web Publishing), 3. Electronic Tools for Project Management (Scheduling & Proj Mgmt SW, Meeting and Virtual Office Support SW, Portals, and Collaborative Work Management Tools). |  |  | There are only four communication types; formal written, informal written, formal verbal, and informal verbal. For the test, you need to be able to tell which is which. Be careful about when you use different kinds of communication. Any time you need to get a message to a client or sponsor, you use formal communication. Meetings are always informal verbal, even if the meeting is to say something really important. And any project document—like a project management plan, a requirements specification, or especially a contract—is always formal written. There are a important aspects to effective communication: Nonverbal communication means your gestures, facial expressions, and physical appearance while you are communicating your message. Paralingual communication is the tone and pitch of your voice when you’re talking to people. If you sound anxious or upset, that will have an impact on the way people take the news you are giving. Feedback is when you respond to communication. The best way to be sure people know you are listening to them is to give lots of feedback. Some ways of giving feedback are summarizing their main points back to them, letting them know that you agree with them, or asking questions for clarification *Anytime you are communicating with the customer about the scope of your project, it’s a good idea to use formal written communication.
Executing | 1. Project Management Plan | 1. Communication Methods: • Informal Written: Emails, memos. • Formal Written: Contract, legal notices, project documents. • Informal Verbal: Meetings, discussions, phone calls. • Formal Verbal: Speeches, mass communication, presentations. | 1. Organizational Process Assets Updates
| 2. Performance Reports | 2. Information Distribution Tools
3. Organizational Process Assets
31 | Manage Stakeholder Expectations: It is the process of communicating and working with stakeholders to meet their needs and addressing issues as they occur. It works to identify and resolve stakeholder concerns in a proactive and timely manner. It will be performed throughout the project. The Project Manger is responsible for stakeholder expectations management. Mgmt: 1. Actively managing the expectations, 2. Addressing concerns, 3. Clarifying and Resolving Issues. |  |  | Interpersonal Skills: Building trust, resolving conflicts, active listening, overcoming resistance to change::::This is where you use your “soft skills” to keep everybody on track and working toward the same goal. Management Skills: Presentations skills, negotiation skills, writing and public speaking skills.
EXECUTING | 1. Stakeholder Register | 1. Communications Methods: -- This is where you decide how you’ll keep people in the loop using Push, Interactive and Pull methods. | 1. Change Requests
| 2. Stakeholder Management Strategy | (Face-to-face is the best) | 2. Project Management Plan Updates
| 3. Project Management Plan | 2. Interpersonal Skills: | 3. Project Document Updates
| 4. Issue Log (Action Item Log) (Each Issues should be assigned to one Owner) | 3. Management Skills | 4. Organizational Process Assets Upd
5. Change Log
6. Organizational Process Assets
32 | Report Performance: It involves collecting and disseminating Project Information, Communicating Progress, Utilization of Resources and Forecasting Future Progress and Status. It reports to the stakeholders how the project is progressing against the plan. Important note in Report Performance is that Performance Reports are actively pushed to stakeholders rather than waiting for them to pull them down. TT2: Forecasting Methods: 1. Time Series Methods - use historical data as the base (EV, Moving Average, Extrapolation, Linear Prediction, Trend Estimation, and Growth Curve), 2. Causal/Econometric Methods - use Assumptions (Regression analysis using Linear Regression or Non-linear Regression, Autoregressive Moving Average (ARMA), ARIMA, and Econometrics, 3. Judgmental Methods - incorporate intuitive judgements, opinions, and probability estimates (Composite forecasts, Surveys, Delphi method, Scenario building, Technology forecasting, and Forecast by analogy), 4. Other Methods (Simulation, Probabilistic forecasting, and Ensemble forecasting) |  |  | The Report Performance process can sometimes be confused with the Distribute Information process, but there are some key differences: Distribute Information is concerned with general project information, such as meeting minutes, issues, and correspondence. Report Performance focuses on performance reporting against baselines, such as scope, schedule, cost, or quality. Report Performance uses time, cost, and related work performance information. Work Performance Information tells you the status of each deliverable in the project, what the team’s accomplished, and all of the information you need to know in order to figure out how your project’s going. Whenever you hear back from a team member about how the job is going, that’s work performance information.
M & C | 1. Project Management Plan (Performance Measurement Baseline - It includes Cost, Schedule, Scope, Quality and Other Baselines) | 1. Variance Analysis - Backward Looking Tool (It is an after-the-fact); Looking at performance data to see how it varies from the baseline | 1. Performance reports: (It shows how the project is progressing against the various baselines (Scope, Time, Cost and Quality).
| 2. Work Performance Information (Deliverables Status, Schedule Progress, and Costs Incurred) | 2. Forecasting Methods - Forward Looking Tool (EAC, ETC) ; Using Earned Value and other Forecasting methods to find out whether we’re on budget and on schedule. | Common Formats - Bar Charts, S-curves, Histograms, and Tables. Variance, EV, Forecasting.
| 3. Work Performance Measurements Planned vs actual [ (CV, SV, CPI, CPIc, SPI) ] | 3. Communication Methods (PM generally uses a PUSH Comm Technique); Deciding on Push, Pull, or Interactive methods of communicating | 2. Change Requests: happen when you do Report Performance. What do you do if you find out that your forecasts have your project coming in too late or over budget? You put the change request in as soon as possible. And if you need the project to change course, you’ll need to recommend corrective actions to the team.
| 4. Budget Forecasts | 4. Reporting Systems (Standard Tool for PM to Capture, | 3. Organizational Process Assets Updates: especially your lessons learned.
| 5. Organizational Process Assets | Store and Distribute Information); A system to keep track of how much time and money people spend doing work
# According to Kerzner - "90% of the Project Manager's time is spent communicating".
# Project Manager should be in control of Project Communication Management Plan.
# Communication on Schedule slippage, Cost overrun, and Other major Project Statuses should be FORMAL and in WRITING.
# Lessons Learned focus on Variance from the Plan and what would be done differently in the future in order to avoid these.

## Risk
RISK
Sl# | Inputs | Tools & Techniques | Outputs
33 | Plan Risk Management: The process of DEFINING HOW to conduct risk management activities for a project. In Plan Risk Management, the remaining FIVE risk management processes are PLANNED (creating a road map for them) and HOW they will be conducted is documented. Here focus will be on "HOW RISKS WILL BE APPROACHED ON THE PROJECT". # Risk Management Plan defines WHAT LEVEL of risk will be considered tolerable for the project, HOW risk will be managed, WHO will be responsible for risk activities, the AMOUNTS OF TIME and COST tht will be allotted to risk activities, and HOW risk findings will be COMMUNICATED. # Risk Breakdown Structure (RBS): It is not breaking down the actial risks, instead, we are breaking down the CATEGORIES of risks that we will evaluate. |  |  | There are four basic ways to handle a risk: Avoid: The best thing that you can do with a risk is avoid it—if you can prevent it from happening, it definitely won’t hurt your project Mitigate: If you can’t avoid the risk, you can mitigate it. This means taking some sort of action that will cause it to do as little damage to your project as possible. Transfer: One effective way to deal with a risk is to pay someone else to accept it for you. The most common way to do this is to buy insurance. Accept: When you can’t avoid, mitigate, or transfer a risk, then you have to accept it. But even when you accept a risk, at least you’ve looked at the alternatives and you know what will happen if it occurs. == ====== ======= ==== ==== ==== ===== ================ ==== ====== ===== ===== == ===== The amount of tolerance a person or organization has for risks is referred to as its risk utility, which is a measure of how much negative impact the organization or person is willing to accept in trade for a potential positive benefit. Risk tolerant/risk seeking: These people have a willingness to accept risks even when the benefit doesn’t seem worth the negative impact Risk averse: These people have a tendency to avoid risks even when the reward outweighs the potential negative impact Risk neutral: These people generally have a logical, balanced approach that is weighted against the pros and cons of the risk. RBS: you come up with major risk categories, and then decompose them into more detailed ones Exam Spotlight: For the exam, don’t forget that you define probability and impact values during the Plan Risk Management process.
PLANNING | 1. Project Scope Statement | 1. Planning Meetings and Analysis | 1. Risk Management Plan (It includes the following:
| 2. Schedule Management Plan for risk planning, it defines how risk management activities will be scheduled. | held with project team members, stakeholders, functional managers, and others who might have involvement in the risk management process | a) Methodology: Describes the approaches, tools, and techniques that’ll govern how project risk management will occur b) Roles and Responsibilities: •Risk roles as required for the project (risk manager, risk management team) •Responsibilities for subsequent risk management processes (risk identification, qualitative and quantitative analysis, risk response planning, and risk monitoring) c) Budgeting: •Activities needed for risk management (and incorporated into the project schedule) •Resources and costs allocated to risk management and risk activities as later defined and incorporated into project cost baseline •Frequency of risk management activities, such as risk reassessments and risk audits d) Timing: defines when and how often risk mgmt processes will be performed throughout the project life cycle. e) Risk Categories: are general classifications that individual risks will be assigned to, and these categories are established as part of the risk management plan...RBS risk breakdown structure to list the categories and sub-categories of risks a typical project. f) Definitions of risk probability and impact: Probability and impact scales - A relative scale (or ordinal scale) is the most simple and uses indicators such as low, medium, and high. - A linear scale (or cardinal scale) is numeric, and is commonly used to express the probability of the risk, so a rating of 1 would imply a very low probability while a rating of 9 would indicate a very high probability. - A non-linear scale is also numeric, but the intervals between the designations aren't equal (e.g., 1, 2, 4, 8, 16). g) Probability and impact matrix h) Revised stakeholders' tolerances i) Reporting formats j) Tracking |  |  |  |  | -325
| 3. Cost Management Plan For planning of risks, the cost management plan defines how the financial costs of risk management activities will be budgeted for. | [6 empty] | -30000
| 4. Communications Management Plan For risk planning, it defines how data on risk will be communicated | [6 empty] | -30325
5. Enterprise Environmental Factors: One of the key elements of the enterprise environmental factors to consider as in input in this process is the risk tolerance levels of the organization and the stakeholders
| 6. Organizational Process Assets | * The project manager is responsible for ensuring that risk management is properly carried out. * The risk manager establishes the overall project risk management methodology and for monitoring and controlling risks. * Each individual risk has a risk owner, who’s responsible for managing that risk, and one or more risk action owners, who’ll carry out risk response activities. Risk management planning involves: •Defining what risk management activities will occur. •Establishing the allotted time and cost for risk management activities. •Assigning risk management responsibilities. •Deciding how risk probability and impact will be measured. •Deciding on acceptable risk thresholds and tolerances.
34 | Identify Risk: The process of determining WHICH risks may affect the project and documenting their characteristics. # TT1: Documentation reviews is when you look at OPA and any documents to squeeze any possible risk out of them. # TT2: Most common Techniques are 1. Brainstorming, 2. Delphi Technique, 3. Expert Interviews, and 4. Root Cause Identification. # TT4: Assumptions analysis is when we look as project assumptions. # TT5: Diagramming Techniques: Ishikawa/Cause-and-effect/Fishbone Diagram, Influence Diagram, and System or Process Flow Charts. # TT6: SWOT: It is a tool to measure each RISK's SWOT. Each risk is plotted, and the quadrant where the Weekness (usually Internal) and Threats (usually External) are HIGHEST, and the quadrant where Strenghts (again, usually Internal) and Opportunities (usually External) are HIGHEST will present the HIGHEST RISK on the project. |  |  | Watchlist: Low priority risks should be regularly monitored so make sure they are not occurring and that their probability, impact, or priority hasn't changed. Prioritized risks: Qualitative analysis results in which risks are the highest priority and should receive detailed risk management efforts. Urgent risks: Risk processes may uncover risks that are already underway or which are imminent. Urgent risks need immediate planning and action. Trends and common factors: Risk categories, root causes, and impacts may expose trends that can make for more efficient risk response planning or risk monitoring. Probabilities: Risk scores can be aggregated and analyzed at the objective, deliverable, or project level to predict how likely it is that the project will reach its objectives. An overall risk level for the project can also be tabulated. Enterprise Environmental Factors: Be certain to check for industry information (commercial databases, checklists, benchmarking studies, and so on) or academic research that might exist for your application areas regarding risk information. Cause-and-effect diagrams show the relationship between the effects of problems and their causes. This diagram depicts every potential cause and subcause of a problem and the effect that each proposed solution will have on the problem. This diagram is also called a fishbone diagram or Ishikawa diagram. Influence diagramming: Simply put, they visually depict risks (or decisions), uncertainties or impacts, and how they influence each other. Example: The weather is a variable that could impact delivery time, and delivery time is a variable that can impact when revenues will occur.
PLANNING | 1. Risk Management Plan | 1. Assumptions Analysis: reviews the reliability of each assumption, what consequences will occur if the assumption turns out to be inaccurate, and what risk factors are generated by the assumption | 1. RISK REGISTER: Risk: The name, description, and a unique identifier for the risk. Risk Owner: The risk owner is the person in charge of monitoring and controlling the risk. Risk category: The categorization from the risk management plan that the risk falls within. Root cause: The core factor(s) leading to the risk. Potential response: Responses to risks are planned in Risk Response Planning, but potential responses may become obvious during risk identification and should be captured in the risk register. Impact: The risk register contains the specific details about what will be effected should the risk occur. Probability: The probability of the risk expressed as a percentage or on a scale as defined by the risk management plan. Symptoms/Warning Signs: Any specific conditions likely to trigger the risk or symptoms that the risk is about to occur should be identified. This will help during risk monitoring. Risk Score: The probability and impact score for the risk. This is obtained from a formula (usually probability x impact) defined in the risk management plan and generated from the probability and impact matrix. Risk Ranking/Priority: This is the prioritization or relative ranking for the risk that allows efforts to be spent more effectively on the higher priority risks. Risk Response: The strategies and activities that will be taken to encourage and exploit a positive risk, or address a negative risk. Risk Response Responsibilities: The risk action owners are people who have risk response actions to take. Secondary Risks: Risk responses can often raise new risks. Risk Response Budget: This is the budgeted cost to implement approved risk responses. Risk Response Schedule: The scheduled activities necessary to put the risk response into action. Contingency Plan: These are the actions that will take place should the risk response fail. The contingency plan also establishes under what criteria it's to be enacted. Fallback Plan: The fallback plan is a backup to the contingency plan should it fail.
| 2. Scope Baseline: The project scope statement, work breakdown structure, and WBS dictionary are the best places to begin looking for risks since these documents thoroughly explain the project work and identify constraints and assumptions. | 2. Checklist Analysis (it uses RBS): Checklists can be developed based on the risk categories (used in the risk breakdown structure) or from similar projects
| 7. Activity Cost Estimates: the Activity Cost Estimates review may result in projections indicating the estimates is either sufficient or insufficient to complete the activity. | 3. SWOT Analysis: Strengths: Positive attributes or elements within the performing organization that will help the project reach the objective. Weaknesses: Negative attributes or elements within the performing organization that can inhibit the project from reaching the objective. Opportunities: Positive attributes or elements outside the performing organization that will help the project reach the objective. Threats: Negative attributes or elements outside the performing organization that can inhibit the project from reaching the objective.
| 6. Activity Duration Estimates | 4. Diagramming Techniques
| 3. Schedule Management Plan | 5. Information Gathering Techniques: Brainstorming, interviewing, surveys (such as Delphi), root cause analysis, Nominal Group Technique
| 4. Cost Management Plan | 4. Documentation Reviews: A documentation review looks for incomplete, missing, or out-of-date documents, which implies a lack of integrative project management. Document reviews might also uncover assumptions and constraints that were not explicitly identified in the project scope statement.
| 5. Quality Management Plan | 7. Expert Judgement
8. Stakeholder Register
9. Project Documents
10. Enterprise Environmental Factors
11. Organizational Process Assets
35 | Perform Qualitative Risk Analysis: it prioritizes risks based on their probability of occurring and their potential impact to the project objectives. Prioritization is needed because risk identification uncovers a large number of risks having at least some potential to influence project objectives. However, many of those risks will be of such a low priority or have such a small impact that it isn't cost effective to address them, so qualitative analysis allows the project team to focus on the most important risks. |  |  | Perform Qualitative Risk Analysis follows risk identification, and it prioritizes risks based on their likelihood of occurring and their potential impact to the project objectives. Prioritization is needed because risk identification uncovers a large number of risks having at least some potential to influence project objectives. However, many of those risks will be of such a low priority or have such a small impact that it isn't cost effective to address them, so qualitative analysis allows the project team to focus on the most important risks Risk register provides the list of identified risks to be evaluated. Risk management plan provides the details on how probability and impact will be assessed and what risk scoring formula and ranking criteria will be used. Risks are prioritized and ranked based on their overall risk rating score, but risks can also be prioritized by their expected monetary value, impact, or any combination of other methods Risk probability and impact assessment: This assessment investigates each identified risks to expose the probability and impact to all the project objectives. This data is used to prioritize or rank risks. Probability and impact matrix: The probability and impact matrix uses an established rating criteria and scoring formula for assigning a score to identified risks based on their probability and impact. Risk data quality assessment: Before qualitative analysis is performed, the risk data gathered should be reviewed for accuracy, reliability, and integrity. Otherwise, the analysis will be based on flawed data. Risk categorization: To help in prioritization or ranking, risks can be categorized in any useful method, such as by deliverable, phase, objective, or technology. Risk urgency assessment: Qualitative analysis may uncover risks that are imminent. These may need fast-tracked into subsequent risk processes for immediate attention. Expert judgment: Qualitative analysis requires subject matter experts and expert judgment is needed to interpret, evaluate, and present the qualitative data uncovered.
PLANNING | 1. Risk Register | 1. Risk Probability and Impact Assessment: Probability is usually estimated as a percentage while impact is estimated as a cost, time, or quality measure. Both estimates are usually quite subjective, and given in ranges. For instance, impact might be given only as "between $25,000 and $50,000" or "between 7 days and 14 days." | 1.Risk Register Updates Updates include: 1. Relative ranking or priority list of project risks, 2. Risks grouped by categories, 3. Causes of risk or project areas requiring particular attention, 4. List of risks requiring response in the near-term, 5. List of risks for additional analysis and response, 6. Watchlists of low-priority risks, and 7. Trends in qualitative risk analysis results). Qualitative risk analysis can also be used to: 1. determine whether the project should be selected, continued or terminated. Exam Spotlight: The PMBOK® Guide notes that the probability and impact matrix values are usually set by the organization and are part of the organizational process assets.
| 2. Risk Management Plan | 2. Probability and Impact Matrix Probability rating: Very Low (=10%), Low (=30%), Medium (=60%), High (=80%), Very High (=95%) impact scale: Very Low (1), Low (2), Medium (3), High (4), Very High (5) Scoring formula: probability rating X impact rating
| 3. Project Scope Statement | 3. Risk Data Quality Assessment: reviews the quality, reliability, accuracy, and integrity of the risk data collected
| 4. Organizational Process Assets | 4. Risk Urgency Assessment: As risks are reviewed, it may be obvious that some risks are more likely to occur in the near term (or are already occurring), making these risks a top priority and requiring them to be fast-tracked to other risk processes for immediate planning and action.
5. Risk Categorization: Grouping and sorting risks in different manners can help to prioritize them..Ways that risks can be grouped include by risk owner, deliverable, phase, or technology.
6. Expert Judgment
36 | Perform Quantitative Risk Analysis: The process of NUMERICALLY ANALYZING the effect of identified risks on overall project objectives. It relies on the prioritized list of risks from the Perform Qualitative Risk Analysis process. It delves further into identified risks by assigning COST or other impact measurements to them. COST and SCHEDULE are easily quantified, and this process is concerned with quantifying the risks. SCOPE generally fits better into the Qualitative Risk Analysis. # TT1: 1. Interviewing, 2. Probability Distribution (Beta Distribution, Triangular Distribution). Uniform Distribution can be used if there is no obvious value (early concept stage of design). Probability Distributions are very useful for analyzing risks. # TT2: 1. Sensitivity Analysis (Tornado Diagram shows HOW SENSITIVE each analyzed area of the project is to risk. It ranks the bars from GREATEST to LEAST on the project so that the chart takes on a Tornado-like shape). 2. Expected Monetary Value Analysis (EMV): The EMV of OPPORTUNITIES will generally be expressed as POSITIVE VALUES, while those of THREATS will be NEGATIVE. EMV requires a Risk-Neutral assumption, neither risk averse, nor risk seeking. A common type is "Decision Tree Analysis". 3. Modeling and Simulation: Monte Carlo Analysis throws large numbers of scenarios at the schedule to see the impact of certain risk events. |  |  | Expected monetary value (EMV) analysis: is the cost or benefit of an uncertain event. It's calculated by multiplying the monetary impact by probability. EMV is what one could expect over time if the condition is repeated over and over. For an example, let's assume that there is a carnival game in which there are three shells but only one has a ping-pong ball under it. The game costs $1 to play and the winner will receive $2 if he correctly picks the shell with the ball hidden under it. There are two outcomes based on the one-in-three chance of choosing the correct shell: either the player loses 66.66% of the time or he wins two dollars 33.33% of the time. The EVM for this game is: EMV = (66.66% x $0) + (33.33% x $2) EMV = $0 + $0.67 EMV=$0.67 EMV incorporates any initial cost for the decision as a negative value (such as cost of goods or services), which in our example is the price of the game: Net EMV = (-$1) + $0.67 Net EMV = (-$0.33) A negative EMV is a risk cost and a positive EVM is a benefit, so in this example the odds are not in the player's favor over the long term even if he wins $2 one out of every three tries. But if the game pays out $5 instead, the odds turn to his favor and he'll win an average of $0.67 each time he plays. EMV = (66.66% x $0) + (33.33% x $5) EMV=$0 + $1.67 EMV = $1.67 Net EMV = (-$1) + 1.67 Net EMV = $0.67 Another use of EMV is in establishing the contingency reserve by aggregating the EMV for each known risk. | 230000 | 0.6
PLANNING | 1. Risk Register: The risk register is a comprehensive list of all threats and opportunities the project faces. It also contains supplementary data about each risk, including its impact, probability, risk response, budget, risk owner, and contingency and fallback plans. | 1. Data Gathering and Representation Techniques: -- Interviewing -- Probability distribution -- Expert judgment | 1. Risk Register Updates (Updates include 1. Probabilistic analysis of the project, 2. Probability of achieving cost and time objectives, 3. Prioritized list of quantified risks, and 4. Trends in quantitative risk analysis results) |  | 150000 | 0.4
| 2. Risk Management Plan | 2. Quantitative Risk Analysis and Modeling Techniques: - Sensitivity analysis - looks individually at each project objective and measures how uncertainty could impact that objective. This makes it possible to identify what risks have the greatest potential impact, and can show how uncertainty can impact project objectives. For example, if labor cost could fluctuate between -20% and +20%, sensitivity analysis applies this cost range throughout affected project components and then displays which components are most susceptible to this risk. sensitivity analysis are usually shown as a tornado diagram or a spider diagram - Expected monetary value (EMV) analysis - Decision tree analysis | For exam, simply know the following, Monte Carlo analysis: 1. evaluates overall risk in the proj 2. provides probability of completing a proj on any specific day or for any specific cost. 3. Takes into account path convergence on Network Diagram. 4. Results in probability distribution. --- For the EXAM, remember that interviewing is a tool and technique of the Perform Quantitative Risk Analysis process. Although you can use this technique in the Identify Risks process, remember that it’s part of the data gathering and representation technique and not a named tool and technique itself. --- Normal and lognormal distributions use mean and standard deviations to quantify risk, which also require gathering the optimistic, most likely, and pessimistic estimates. --- For the EXAM, remember that simulation techniques are used to predict schedule or cost risks. |  |  |  | 78000
| 3. Cost Management Plan | 3. Expert Judgment
4. Schedule Management Plan
5. Organizational Process Assets
37 | Plan Risk Responses: in this we’ll decide on the ACTIONS needed to reduce the threat of negative risks or enhance the opportunities for positive risks as well as developing contingency plans. This process occurs after identified risks have been prioritized, and it will generally focus only on the highest priority risks. Risk actions are of 3 types: 1- Risk response:- The risk response determines the strategy for influencing the probability and impact of the risk before it occurs. For negative risks, its aim is to eliminate the risk or reduce its impact should it occur. For positive risks, the response tries to increase the probability or impact of the risk. 2-Contingent response/contingent plan:- it establishes what activities will take place should a specific event or situation occur. A contingency plan aims to influence the impact of a risk that is occurring. The risk response occurs BEFORE the risk and tries to alter the probability and/or impact while the contingency plan only occurs AFTER the trigger (usually the risk event) and focuses only on changing the impact. 3-Fallback plan:- The fallback plan kicks in if the contingency plan fails. It can be looked at as a contingency plan for the contingency plan. The fallback plan spells out steps will be taken to recover if the contingency plan fails -- Residual risk is a leftover risk. After you’ve implemented a risk response strategy—say mitigation, for example—some minor risk might still remain. The contingency reserve is set up to handle situations like this. Residual risks are those that remain and whose probability and impact are such that they're acceptable to the performing organization's level of risk tolerance. They can also be those risks in which there are no reasonable responses for. -- Secondary risks are risks that come about as a result of implementing a risk response. The example where you transferred risk by hiring a driver to take you to your destination but the person became ill along the way is an example of a secondary risk. The driver’s illness delayed your arrival time, which is a risk directly caused by hiring the driver or implementing a risk response. When planning for risk, identify and plan responses for secondary risks. # TT1: Avoid - Undesirable Risks, Transfer/Deflect - to another party (Contractual Agreements and Insurance), Mitigate - to make it less, Accept (Negative/Positive) - best strategy may not be to Avoid, Transfer, Mitigate, Share, or Enhance it. Instead, the best strategy may be simply to Accept it and continue with the project. If the cost or impact of the other strategies is too greater, acceptance is the best strategy. # TT2: Exploit - trying to remove any uncertainty, Share - improve their chances of the positive risk occurring by working with another party, Enhance - first we have to understand the underlying cause(s) of the risk. By influencing the underlying risk triggers, you can increase the likelihood of the risk occurring. 1. Risk Register Updates: Resedual Risks, Secondary Risks, Contingency Plan, Risk Response Owners, Fallback Plans, Reserves/Contingency, and Risk Triggers. |  |  | RISK response strategies: -- Threats:- Avoid, Mitigate, Transfer -- Opportunities:- Exploit, Enhance, Share -- Either (Threats OR Opportunities): Accept, Contingent Responses for NEGATIVE risks (threats): #Avoid: Avoidance activities aim to completely eliminate a risk’s probability or impact to zero. Avoidance can take several forms, such as restructuring the project activities, scope, schedule, or cost to eradicate the root causes leading to the risk. #Mitigate: If the risk cannot be avoided, actions might be taken to reduce the risk's probability or its impact if it does occur. Mitigation usually involves making alternate choices that can be less than ideal. #Transfer: Transference assigns all or part of risk to a third party through outsourcing, contracts, insurance, warranties, guarantees, or performance clauses. Responses for POSITIVE risks (opportunities): Exploit: Exploiting a positive risk is about ensuring everything is in place to increase the probability of the occurrence of the risk. Here is an example of exploiting a risk. Suppose, some members of your team have determined a new technique to develop a product and by using this technique, the project duration can be reduced by 20%. To exploit this, you can ensure the technique is used in the project and other team members are trained on the new technique. Share: Sometimes it’s harder to take advantage of an opportunity on your own. Then you might call in another company to share in it with you. Enhance: Enhancing a risk involves identifying the root cause of a positive risk so that you can influence the root cause to increase the likelihood of the positive risk. For example, in order for you to get a business deal, your workforce needs to have substantial PeopleSoft skills. You can enhance the positive risk (opportunity) by training your workforce on PeopleSoft or hiring PeopleSoft specialists. Hence, the probability of you getting the deal is increased. Accept: Just like accepting a negative risk, sometimes an opportunity just falls in your lap. The best thing to do in that case is to just accept it! ##Note: Accepting is a strategy that is applicable to both Negative and Positive Risks. It is important for you to remember this for the PMP exam.
PLANNING | 1. Risk Register | 1. Strategies for Negative Risks or Threats | 1. Risk Register Updates
| 2. Risk Management Plan | 2. Strategies for Positive Risks or Opportunities | 2. Risk-related Contract Decisions
| No O.P.A & E.E.F | 3. Contingent Response Strategies | 3. Project Management Plan Updates
| Exam: Tricky question, when in the risk mgmt process are responses documented? Answer is in both Identify risk and Plan risk responses. | 4. Expert Judgment | 4. Project Document Updates
38 | Monitor and Control Risks: The process of IMPLEMENTING risk response plans, TRACKING identified risks, MONITORING residual risks, IDENTIFYING new risks, and EVALUATING risk process effectiveness throughout the project. #TT5: Focuses on functionality, looking at HOW the project has met its goals for delivering the scope over time. 1. Risk Register Updates: Outcomes of Risk Audits and Reassements, Identification of New Risks, Closing Risks that no longer applicable, Details what happened when Risks occurred, and Lessons Learned. |  |  | Management Reserve, which is money set aside to handle any unknown costs that come up on the project. That’s a different kind of reserve than the one for controlling risks. The kind of reserve used for risks is called a Contingency Reserve, because its use is contingent on a risk actually materializing. Project managers sometimes talk about both kinds of reserves together, because they both have to show up on the same budget. When they do, you’ll sometimes hear talk of “known unknowns” and “unknown unknowns.” The management reserve is for unknown-unknowns—things that you haven’t planned for but could impact your project. The contingency reserve is for known - unknowns, or risks that you know about and explicitly planned for and put in your risk register. Proj Budget=> Proj Base cost + Risk response cost (planned) Proj Funding Requirements => Reserve =>Contingency (known unknowns) + Mgmt Reserve (unknown)
M & C | 1. Risk Register | 1. Risk Audits: review the overall risk management policies, procedures, and processes | 1. Risk Register Updates
| 2. Project Management Plan | 2. Risk Reassessment: You should have some regularly scheduled reassessment meetings to go over all of the information you have to date and see if your risk register still holds true. In a reassessment, your main goal is to find any new risks that have come up. | 2. Change Requests
| 3. Performance Reports | 3. Reserve Analysis: Just like you keep running tabs on your budget, you should always know how much money you have set aside for risk response. As you spend it, you should be sure to subtract it so you know if you have enough to cover all of your remaining risks. | 3. Project Management Plan Updates
| 4. Work Performance Information | 4. Status Meetings (Team Meetings): | 4. Project Document Updates
| No O.P.A & E.E.F | 5. Technical Performance Measurement: Comparing the performance of your project with its planned performance. So if you expected to hit a specific milestone, you could check performance information on your product at that time to see if it measured up to the plan. If not, that might indicate that there are risks you didn’t plan for. | 5. Organizational Process Assets Updates
6. Variance and Trend Analysis: Comparing the actual project performance to the plan is a great way to tell if a risk might be happening. If you find that you’re significantly over budget or behind schedule, a risk could have cropped up that you didn’t take into account.

## Procurement
PROCUREMENT
Sl# | Inputs | Tools & Techniques | Outputs
39 | Plan Procurements: Here’s where you take a close look at your needs, to be sure that you really need to create a contract. You figure out what kinds of contracts make sense for your project, and you try to define all of the parts of your project that will be contracted out. * Document Make/Buy decisions and define the purchasing approach. * Buyers Risk (from Highest to Lowest) - CPFF - T&M - CPIF - FPIF - FFP * Commonly used & Preferred Type - FFP * Direct Cost or Out-of-Pocket Cost * RFI - Request for Information * IFB - Invitation for Bid * RFB/P - Request for Bid/Proposal * RFQ - Request for Quotation (Proc Docs) * IFB or RFB/P used for 1. Single Price, 2.High $ Value, 3. Standardized * RFQ used for 1. Per Item/Hour Price, 2. Lower $ Value, 3. May be used to develop info in RFP The procurement documents are what you’ll use to find potential sellers who want your business. The source selectrion criteria are what you’ll use to figure out which sellers you want to use. ---The Time & Materials (T&M) contract is the riskiest one for the BUYER, because if the project costs are much higher than the original estimates, the buyer has to swallow them, while the seller keeps getting paid for the time worked. --- A FIXED price contract is the riskiest sort of contract for the SELLER. That’s because there’s one price for the whole contract, no matter what happens. So if it turns out that there’s a lot more work than expected, or the price of parts or materials goes up, then the seller has to eat the costs. |  |  | CONTRACT types: contract is what creates the buyer-seller relationship -- FIXED Price: A fixed price contract is for a product, service, or result at a specified flat price. This type of contract is an option only if the extent of the work, time involved, and material needs can be accurately described and costs reasonably estimated. Fixed pricing arrangements can be combined with other types of contracts to even out the risks for both the buyer and seller: #Fixed price with incentives (FPI): This arrangement includes additional financial incentives that are tied to the seller achieving specific objectives. Incentives can be based on schedule, performance, quality, or any other measures. #Fixed price with economic price adjustments (FPEPA): This contract has specific conditions or scheduled periods during which the fixed price baseline may be adjusted based on market conditions. #Fixed price, level of effort (FPLOE): A level of effort contract is still a fixed price, but it includes a requirement that the seller expend at least a specific amount of effort. For example, in a research and development project, the buyer agrees to a $50,000 flat price and the seller agrees that its contractors will devote 1,000 hours of effort. #Fixed price with prospective price redetermination (FPPPR): This arrangement is a “staged” fixed price contract where the fixed price for each stage is negotiated, possibly based on past performance. -- COST reimbursable: In a cost-reimbursable contract the buyer pays the actual incurred costs plus a margin to the seller. Cost-reimbursable contracts are appropriate when there's a high level of uncertainty in what will be required to provide the contracted product, service, or result. The BUYER is the one who bears the risk of cost overruns, and cost-reimbursable contracts also involve more administration from both buyer and seller since there has to be some method of submitting, validating, and auditing of actual costs. Some common approaches the buyer can use to keep the project timeline and expenses from getting out of control: #Cost-reimbursable with ceiling: In this arrangement, costs are reimbursed up to a maximum, agreed-upon level. This helps reduce the buyer’s risk of cost overruns. #Cost-savings sharing: In this contact, a budget is established for actual costs, and the buyer shares a portion of the unused budget with the seller at the conclusion of the project. This serves as an incentive for the seller to keep costs low. #Cost plus fixed fee (CPFF): In this arrangement, the seller’s profit is a flat fee, which serves as a motivator for the seller to keep the duration as short as possible. Since the seller earns the same amount of money if it takes three months or nine months, it makes fiscal sense to earn its profit in as short a time as possible so that the seller can move on to another job. #Cost plus incentive fee (CPIF): In this contract, the seller's margin is tied specifically to its achievement of agreed-upon objectives -- TIME and MATERIALS: In a time and material contract, the buyer is responsible for labor costs at an agreed-upon rate plus any ancillary costs the seller may incur. The buyer bears a high risk of schedule overruns resulting in extra labor costs. Incentives and caps can be incorporated into a T&M contract to reduce this risk. -- UNILATERAL: this is a special class of contract in which the seller doesn't have to explicitly accept the offer in order for a contract to be established. This is a unilateral contract, and the best example is a purchase order (PO). When the buyer submits a purchase order to the seller, it has established an offer to buy goods or services from the seller. By simply fulfilling the purchase order, the seller has accepted the offer and a contract exists even though the seller did not formally acknowledge the buyer's offer (purchase order). -- UNIT price: A unit price contract is generally for products, materials, or other tangible goods that are bought in quantities at a fixed rate for a pre-determined quantity of goods --TEAMING agreements: EXAM: you are trying to decide whether to lease or buy. the daily lease cost is $120D. To purchase the item the investment cost is $1000, and daily cost is $20D. How long will it take for the lease cost to be same as the purchase cost? $120D = $1000 + $20D $120D - $20D = $1000 $100D = $1000 D= $1000/$100 = 10, this indicates that the costs are same after 10 days. if planning to use the item for less than 10days then lease wld be better and if it is to be used for more than 10 days, then it wld be better to purchase.
PLANNING | 1. Requirements Documentation | 1. Make-or-Buy Analysis:it is better to make if: -work involves proprietary info -you want to retain control -you have an idle workforce/plan etc. | 1. Procurement Management Plan: Defines how the overall procurement needs of the project will be planned, executed, managed, monitored, and closed
| 2. Teaming Agreements |  | 2. Procurement Statement of Work (SOW): Provides the potential sellers the deliverables, materials, specifications, milestones, requirements, acceptance criteria, and any other characteristics
3. Scope Baseline
| 4. Project Schedule: to determine when procurement wld be required. | 2. Contract Types: Three broad categories: -Fixed Price (FP) -T&M -Cost Reimbursible(CR)
5. Activity Cost Estimates
| 6. Cost Performance Baseline (Budget) |  | 3. Procurement Documents: Proposed contract is inclued in Proc Doc. Contains collection of written materials that provides the potential sellers all the information they need to develop and submit a bid or proposal: example: RFP, IFB,RFQ
7. Activity Resource Requirements
| 8. Risk Register |  | 4. Make-or-Buy Decisions
| 9. Risk-Related Contract Decisions |  | 5. Source Selection Criteria: are what you’ll use to figure out which sellers you want to use. Before the bid or proposals are solicited, the selection and evaluation methods that'll be used for choosing the seller should be established
10.Enterprise Environmental Factors: market place conditions etc.
| 11. Organizational Process Assets: list of pre-qualified sellers, lessons learned etc | 3. Expert Judgement | 6. Change Requests
Procurement management plan includes: •How make-or-buy analysis and decisions are to be made.•What qualified seller lists will be used or how qualified seller lists will be created.•The types of contracts allowed.•The explicit procurement roles and responsibilities and levels of authority those roles have within the project.•The procurement documents to be used, such as any standardized forms, and the formats for statements of work.•The procedures for bid and proposal solicitation.•When and how independent estimates will be gathered.•Identified constraints and assumptions related to procurement processes.•How sellers will be managed, performance monitored, and what reporting and frequency will be required.•What insurance or performance bonds will be required and under what situations.•Milestones that need established in contracts.•What the procedures are for seller payments, vouchers, and reimbursements.•How appropriate coordination between procurement processes and other project management processes (scope, time, cost, quality) will be ensured.•The frequency, responsibility, and guidelines for procurement audits. Well defined Procurement Doc will help in: - easier comparison of sellers responses -more accurate pricing -more complete responses -decrease in number of changes to the project.
40 | Conduct Procurements: -- process distributes procurement documents (before u send proc doc to prospective sellers, u need to know who those sellers are - Advts, Internet Search.. -- collects responses -- evaluates the bids or proposals -- lastly establishes a contract with the selected seller |  |  | Point of total assumption (PTA): is the point at which the seller assumes the costs. Only applicable to FPIF contracts. The PTA is when the seller becomes responsible for all costs. The formula uses the ceiling and target prices and the buyer's cost sharing portion. The ceiling price is the most pessimistic cost based on reasonable factors. Anything above the ceiling price is considered to be due to lack of oversight by the seller. PTA = Target Cost + [ (Ceiling Price - Target Price) / Buyer's Percentage Share of Cost ] For example, a contractor has agreed to build a storage depot at a ceiling price of $100,000. The targeted price is $90,000, and the buyer and seller agree that the target cost is $80,000, and that the seller will be responsible for 25% of costs that run over the target. This structure will make the buyer responsible for 100% of the costs up to $80,000, and 75% of costs between $80,000 and $100,000. Target Price: $90,000 PTA = $80,000 + ($100,000 - $90,000) / 75% Target Cost: $80,000 PTA = $80,000 + $10,000/.75 Ceiling Price: $100,000 PTA = $80,000 + $13,333.33 Share Ratio: Buyer = 75%; Seller = 25% PTA = $93,333.33 PTA = Target Cost + [ (Ceiling Price - Target Price) / Buyer's Percentage Share of Cost ] Target Price = Target Cost + Target Fee Actual fee (AF) = TF + {(TC - AC) x SSR} Final price = AC + AF Cost savings = Target cost- Actual cost Seller's share(IF) in cost savings = % x Cost savings Cost of the contract = Actual Cost + Seller's minimum fee + seller's share(IF) in cost savings Price: is the amount seller charges the buyer. Profit (fee): this is planned into the price the seller provides to buyer. Ceiling Price: is the highest price buyer will pay to seller. TC TF TP = TC + TF AC AF = ((TC - AC) x S%) + TF AP = AC + AF Cost savings = TC - AC Cost of contract = AC + Sellers min fee + ( S% x Cost savings) PTA = ((CP - TP) / B%) + TC
EXECUTING | 1. Project Management Plan (Pr M Pl) | 1. Advertising | 1. Selected Sellers
| 2. Project Documents | 2. Internet Search | 2. Procurement Contract Award
| 4. Procurement Documents | 3. Bidder Conference (Vendor/Pre-bid/Contractor) | 3. Resource Calendars
| 3. Teaming Agreements (Master Services Agreement): in this there is a contract in place between the seller & buyer for a type of service as needed. When specific work is needed , the buyer & seller work to create scope of work and then initiate a project under existing terms of MSA. | 4. Proposal Evaluation Techniques | 4. Change Requests
| 5. Make-or-Buy Decisions | 5. Independent Estimates (buyer may compare sellers proposal with an estimate created in-house or with outside assistance) | 5. Project Management Plan Updates
| 6. Source Selection Criteria | 6. Procurement Negotiations: Objectives of Negotiation: -obtain a fair & reasonable price -develop a good relationship with seller Main Items to negotiate: -scope, -schedule, -price | 6. Project Document Updates
7. Qualified Sellers' List
8. Seller Proposal
| 9. Organizational Process Assets | 7. Expert Judgement
41 | Administer Procurements: The process of managing procurement relationships between buyer and seller, monitoring contract performance, and making changes and corrections as needed. * Manage the relationships, monitor performance and make changes as necessary. * The buyer and seller review the contract and the work results to ensure that the results match the contra contract. * Manages any early terminations of the contract work (for Cause, Convenience or Default) in accordance with the Termination Clause in Contract. |  |  | FP-when there is well defined specs and requirements…seller is at risk. T&M-in which level of EFFORT cannot be defined at the time the cotract is awarded. Cost re-imbursible-when the exact scope of WORK is uncertain and therefore cost cannot be estimated accurately enogh to use FP. Incentives-are used to bring the sellers objective in line with the buyer's. PO-when you are buying standard commodities. From BUYERS perspective Priorities least to most important: Cost Plus Fixed Fee - CPFF: Cost, Time, Performance Cost Plus Incentive Fee-CPIF: Time, Performance, Cost -for incentive fee, Cost is most important criteria Cost Plus Award Fee-CPAF: Cost, Time, Performance T&M: Performance, Time, Cost FPIF: Time, Performance, Cost -for incentive fee, Cost is most important criteria FP: Cost, Time, Performance Termination: --- The buyer may terminate a contract for cause if the seller breaches the contract. --- The buyer can also terminate a contract before the work is complete because they no longer want the work done (termination for convinience). In this case the seller is paid for the work completed and work in progress.
M & C | 1. Project Management Plan | 1. Inspections and Audits | 1. Procurement Documentation
| 2. Procurement Documents | 2. Procurement Performance Reviews | 2. Change Requests
| 3. Contract | 3. Performance Reporting | 3. Project Management Plan Updates
| 4. Approved Change Requests | 4. Contract Change Control System | 4. Organizational Process Assets Updates
| 5. Performance Reports | 5. Payment System: The payment system is how your company pays its sellers.
| 6. Work Performance Information | 6. Claims Administration: Claims are usually addressed through the contract change control system.
7. Records Management System There are a lot of records produced by a typical contract: invoices, receipts, communications, memos, emails, instructions, clarifications, etc. You’ll need to put a system in place to manage them.
42 | Close Procurements: The process of completing each project procurement. * Finalize and Close each purchasing contract. * When the contract is Completed or Terminated for any reason, this process is performed. |  |  | Procurements are closed when: -- When contract is closed -- When contract is terminated before the work is completed. Procurement closure needs to happen before Project Closure. All procurements MUST be CLOSED before the project is closed. --- Procurement Closure is done only at the completion of each closure. Administrative Closure (close project or phase process): Procurement closure: ------------------Procurement closure involves: # Product verfication, # Negotiated settlements, # Financial closure, # Procurement Audits,
CLOSING | 1. Project Management Plan | 1. Procurement Audits (Review of Procurement Processes - for capturing Lessons Learned) | 1. Closed Procurements
| 2. Procurement Documentation | 2. Negotiated Settlements | 2. Organizational Process Assets Updates
3. Records Management System
# FFP - Risk is entirely shifted to the SELLER. It is very popular 'When the Scope of work is throughly defined & completely known'.
# FPIF - Point of Total Assumption (PTA) is a point in the contract where a subcontractor assumes responsibility for all additional costs. PTA = Target Cost + ((Ceiling Price - Target Price + Fixed Fee (if it is there)) / Buyer's % share of cost overrun)
# FP-EPA - Fxied Price with Economic Price Adjustment. It is popular where Fluctuations in Exchange Rates and Interest Rates. Economic Stipulation may be based on the Interest Rates, the Consumer Price Index, Cost of Living Adjustments, Currency Exchange Rates or other Indices.
# T&M - The Buyer bears the most risk of Cost overruns. It is used when the SCOPE of work is not completely defined.
CEILING PRICE (CP)
|  | TARGET COST (TC) | 9000000
|  | TARGET FEE (TF) | 850000
|  | TARGET PRICE = TC + TF | 9850000
|  | ACTUAL COST (AC) | 8000000
|  | ACTUAL FEE (AF) = ((TC - AC) X S%) + TF | 1150000 | FINAL FEES
|  | ACTUAL PRICE = AC + AF | 9150000 | FINAL PRICE
COST SAVINGS = TC - AC
COST OF CONTRACT= AC + SELLERS MIN FEE + (S% X COST SAVINGS)
|  | PTA=((CP - TP) / B% ) + TC | -7416666.6667
|  | S% IS SELLERS PERCENT | 0.3
|  | B% IS BUYERS PERCENT | 0.6

## ImpPoints-1
IMPORTANT POINTS - 1
Sl# | Point to remember
1 | EEF & OPA must be taken into account for every process, even if they are not explicitly listed as inputs in the process specification.
2 | Project Management Team Activities: 1. Analyze and understand the scope. That includes the project and product requirements, criteria, assumptions, constraints, and other influences related to a project, and how each will be managed or addressed within the project. 2. Understand how to take the idetified information and then transform it into a project management plan using a structured approach. 3. Perform activities to produce project deliverables. and 4. Measure and monitor all aspects of the project's progress and take appropriate action to meet project objectives.
3 | Often the Scope, Schedule, and Cost Baselines will be combined into a Performance Measurement Baseline that is used as an overall Project Baseline against which integrated performance can be measured. The Performance Measurement Baseline is used for Earned Value Measurements.
4 | # Activities necessary for Administrative Closure of the Project or Phase, including step-by-step methodologies that address: 1. Actions and activities necessary to satisfy completion or exit criteria for the phase or project; 2. Actions and activities necessary to transfer the project's products, services, or results to the next phase or to production and/or operations; and 3. Activities needed to collect project or phase records, audit project success of failure, gather lessorns learned and archive project information for future use by the organization.
5 | # Configuration Management System (CMS): A CMS with Integrated Change Control provides a standardized, effective, and efficient way to centrally manage approved changes and baselines within a project. CM is a systematic procedure that refers to change management. CM protects both the customer and the project staff. * CMS is a collection of formal documented procedures used to apply direction and control compliance of products and componenets with project requirements. * Is a subsystem of the PMIS. * Includes the processes that define how project deliverables and documents are controlled, changed, and approved. * In many areas includes the Change Control System. Configuration Management Activities: 1. Configuration Identification, 2. Configuration Status Accounting, and 3. Configuration Verification and Audit.
6 | # Fait accompli: An accomplished fact; an action which is completed before those affected by it are in a position to query or reverse it. The literal translation into English of this French phrase is a fact realized or accomplished - what might these days be called a done deal.
7 | # WBS: WBS a deliverable-oriented hierarchical decomposition of the work to be executed by the project team. The WBS is finalized by establishing Control Accounts for the work packagess and a unique identifier from a code of accounts. The WBS represents all product and project wori, including the project management work (This is sometimes called the 100% rule). # The WBS can be structured as an outline, an organizational chart, a fishbone diagram, or other method. # Different deliverables can have different levels of decomposition. # Excessive decomposition can lead to non-productive management effort, inefficient use of resources, and decreased efficiency in performing the work. # Decomposition may not be possible for a deliverable or subproject that will be accomplished far into the future.
8 | # Work Performance Information: Focus on WHAT has been done (provideds information on the Status of a Deliverables).
9 | # Performance Reports: Focus on HOW it was done. (Focus on Cost, Time, and Quality performance). Here Actual Results are compared against the Baselines to show how the project is performing against the Plan.
10 | # Project Cost Baseline = Project Estimates + (Cost) Contingency Reserves; # Project Cost Budget = Project Cost Baseline + Management Reserves
11 | # Residual Risks comprise of 1. Risk that remain after applying risk response strategies, and 2. Risks that we simply ACCEPT - if it happens, it happens, we have a plan to deal with it.
12 | # Contingency Plans deal with the outcome of Residual Risks on project. # Contingency Resivers cover the outcome of Residual Risk, and account for the "Known Unknowns".
13 | # Fallback Plans are employed for Residual Risks when the Contingency Plans fail. # Secondary Risks are new risks that emerge as a result of Risk Response Plan.
14 | # Watchlist: All non-critical/non-top/low rating risks are put on the Watchlist and monitored(Watched) regularly. It is created at Perform Qualitative Risk Analysis Process. # Management Reservers account for the "Unknown Unknowns".
15 | # Utility Theory: An appropriate method for describing Risk Tolerance. * Risk Averse: Where there is more money at stake, the Risk Averter's satisfaction diminishes; he or she prefers a more certain outcome and demands a premium to accept projects of high risk. * Risk Neutral: Tolerance for risk remains the same as the money at sake increases. * Risk Seeker: The higher the stakes, the better; as risk increases, the risk seeker's satisfaction increases; he or she is even willing to pay a penalty to take on projects of high risks.
16 | # Force Majeure Risks, such as Earthquakes, Floods, Acts of Terrorism, Etc., should be covered under Disaster Recovery Procedures instead of Risk Management.
17 | # Monte Carlo Analysis would show you is WHERE SCHEDULE RISK EXISITS (Points of Schedule Risk). It is a Computer-based Analysis & useful for revealing Schedule Risks
18 | In accordance with the Planning process group, the order of processes are: develop project management plan, collect requirements, define scope, create WBS, define activities, sequence activities, estimate activity resources, estimate activity durations, develop schedule, estimate costs, determine budget, plan quality, develop HR plan, plan communications, plan risk management, identify risks, perform qualitative risk analysis, perform quantitative risk analysis, plan risk responses, and plan procurements.
19 | What is the meaning of a concept called the "Journey to Abilene"? Committee decisions can have the paradox outcome, that a jointly made or approved decision is not desired by any individual group member.
20 | What is a constructive change? A direction by the buyer or an action taken by the seller that the other party considers an undocumented change to the contract.
21 | Liquidated damages (LDs) are contractually agreed payments in order to… ...cover the customer's costs caused by late completion or failure to meet specifications by the contractor.
22
23
24

## ImpPoints-2
IMPORTANT POINTS - 2
Sl# | Introduction to Project Management
1 | A project is a temporary endeavor to create a unique product or service. Operations are ongoing activities.
2 | Progressive elaboration is the process of taking a project concept through to the project plan. As the planning and research activities continue, the more detailed and focused the concept becomes. Progressive elaboration happens throughout the project. It is the process of elements within the project becoming more and more exact as additional information and details become available.
3 | Milestones are not completed by the project manager, but by the project team. In addition, milestones are the results of activities, not activities themselves.
4 | Project closure is also known as the project postmortem.
5 | The project scope defines the required work, and only the required work, to complete the project.
6 | Scope verification is the proof that the project manager has completed the project.
7 | Whenever you have access to historical information, this is your best source of input.
8 | Quality policy is the organization-wide rules and requirements for quality.
9 | The project manager should use approved rewards and incentives to move the project team towards completion.
10 | An information retrieval system is paramount for a project with so much documentation. Technically, all projects should have an information retrieval system.
11 | The contract between the organization and the vendor supercedes all other work-related documents.
12 | Programs are a collection of projects with a common cause.
13 | Project Portfolio Management is the process of choosing and prioritizing projects within an organization. An excellent project idea can still be denied if there are not enough resources to complete the project work.
14 | Businesses exist to make money.
15 | Customers, internal or external, are the most important stakeholders in a project.
16 | Getting collective action from a group of people who may have quite different interests is 'Politics'.
17 | Generally, a difference in requirements resolved in favor of the customer. However, it is the project manager's responsibility to inform the customer of other options.
18 | The project management office can be established to offer services ranging from basic support to total management of all projects. Choice D covers the diverse opinions of management, and will meet all their needs.
19 | You might remember a similar question with a different answer. Operations and maintenance activities are not part of projects. The work to collect data, meet with operations and maintenance to explain the project, and other such activities should be included in the project.
20 | Management by objectives tries to focus all activities on meeting the company's objectives. If the project's objectives are not in line with the company's objectives, the project may be impacted or cancelled.
21 | The project coordinator reports to a higher-level manager and has authority to make some decisions. The project expediter has no authority to make decisions.
22 | The key word here is "cross-disciplinary." Cross-disciplinary means that the project covers more than one department or technical area of expertise. In such a case, a matrix organization is needed with representatives from each department or discipline.
23 | Effective project management requires a life cycle approach to running the project.
24 | The PMO determines whether a project supports the organization's strategic plan and can authorize exceptions to projects not linked to the strategic plan.
25 | The work of completing the product scope is accomplished during the executing process group.
26 | It is a responsibility of the project management office to prioritize the company's projects. When prioritization is clear, it is easier to allocate resources among projects.
27 | Notice that this question asks about product verification, not scope verification. The Verify Scope process occurs during project monitoring and controlling, and product verification is done during project closing.
28 | Deliverables are determined in part by the customer, but not the sponsor.
29 | The best answer is stakeholders, as their input is critical for collecting all the lessons learned on each project. The term "stakeholders" includes all the other groups
30 | The project manager or the project management team determines how best to accomplish the project.
31 | The organization has a direct influence on the project. A participative approach will probably not be as effective in a hierarchical organization.
32 | During the monitoring and controlling process group, project performance is measured, and needed changes are identified and approved.
33 | The project charter gives authorization to begin a project or project phase. The project charter is approved in the initiating process group.
34
35
Sl# | Examining the Project Management Framework
1 | The project life cycle is comprised of phases.
2 | The completion of a project phase may also be known as a kill point or stage gate. Kill points are typically at the end of a project phase. A kill point does not mean the project is killed, just that the potential for termination exists.
3 | Managing has to do with consistently producing key results that are expected by stakeholders.
4 | Email is not a Formal Communication.
5 | Arbitration is a form of negotiation. Technically, it is a form of assisted negotiation.
6 | To influence an organization (in order to get things done), a project manager must understand the explicit and implied organizational structures within an organization.
7 | Rumors and gossip can sabotage a project. This is an example of cultural achievability.
8 | Exit criterion are activities or evidence that allow a project to move forward. Stakeholder expectations are universal to the entire project, not just to one project phase.
9 | Projects typically have low costs and low demand for resources early in their life cycle. As the project moves closer to completion, the likelihood of risk diminishes
10 | Projects with much risk and reward are most likely to be accepted within an entrepreneurial organization.
11
12
Sl# | Examining the Project Management Processes
1 | A process is a series of actions bringing about a result. Recall that processes exist in projects and in project phases.
2 | Product-orientated processes are unique to the product the project is creating.
3 | Rolling wave planning is a description of the planning process in most large projects. It requires the project manager and the project team to revisit the planning process to address the next phase, implementation, or piece of the project.
4 | By involving the stakeholders at different aspects of the project, their requirements are more likely to be met. Specifically, scope verification ensures that the stakeholders are seeing that phase deliverables, project progress, quality, and expectations are being met.
5 | Organizational planning is the facilitating planning process which defines roles and responsibilities-and the reporting structure within the project.
6 | On a project with 45 key stakeholders, the project manager must work to manage stakeholder expectations. Given the impact of the project and the identified controversy, the project manager will need to proceed with caution to ensure the project deliverables meet the required expectations of the stakeholders.
7 | Projects fail at the beginning, not the end. A poor requirements document, inadequate needs assessments, unfulfilled planning, and more early processes can contribute to project failure.
8
9
Sl# | Project INTEGRATION Management
1 | Projects are selected based on business needs first.
2 | Change requests do not always require more money. Approved changes may require more funds, but not always. The change request may be denied, so no additional funds are needed for the project.
3 | A formal, documented change request is the best course of action for a change request stemming from a law or regulation. Integrated Change Control requires detail for implementing the change. Without evidence of the need for the change, there is no reason to implement it.
4 | The project sponsor can help the project manager and the stakeholders resolve issues during project integration management.
5 | If management has assigned the project constraint of a fixed budget, the project manager and the project team must determine how the project can operate within the constraint.
6 | Project plans communicate to the project team, the project sponsor, and stakeholders. Q: The primary purpose of your project plan is: A: To provide accurate communication for the project team, project sponsor, and stakeholders.
7 | A project baseline serves as a control tool. Project plan execution and work results are measured against the project baselines.
8 | Gantt charts are excellent tools to measure and predict the project progress, but are not needed during the project plan development process.
9 | A PMIS can assist the project manager the most during project execution. It does not replace the role of the project manager, but only serves as an assistant. It helps the project manager plan, schedule, monitor, and report findings.
10 | The project plan serves as a guide to all future project decisions.
11 | A configuration management is the documentation of the project product, its attributes and changes to the product.
12 | Integrated Change Control is a system to document changes, their impact, response to changes, and performance deficits.
13 | The project plan is the formal document used to manage and control project execution.
14 | General management skills, status review meetings, and Work Authorization Systems are the best tools described here that serve as part of the project plan execution.
15 | EVM, earned value management, is used throughout the project processes. It is a planning and control tool used to measure performance.
16 | A project manager must manage a project. If all activities are delegated, chaos ensues and team members will spend more time jockeying for position than completing activities.
17 | Configuration management involves making sure that everyone is working off the same documents and version.
18 | The schedule baseline is there for you to determine how the project is progressing. Follow your change management process, and continue to track against your baseline.
19 | Effective project integration usually requires an emphasis on: Effective Communications at key interface points.
20 | With everything going well on the project, the only choice that makes sense is to review the management plans for the project.
21 | The change control system must also include procedures to handle changes that may be approved without prior review, for example, as the result of emergencies.
22 | Only with formal acceptance can the project manager be sure the project work is really complete.
23 | All Technical Work is completed (means you are in Closing Process Group) on the project - the remaining thing is 'Completing Lessons Learned'.
24 | Because net present value is the value in today's dollars of different cash flows, the project with the highest NPV is the best one. The number of years is included in the NPV calculation.
25 | Integration can be done during Planning and Executing, but it is most important when you reach key interface points in the project. You must orchestrate the coming together of the results.
26 | The sponsor issues the project charter and so he or she should help the project manager control changes to the charter. The primary responsibility lies with the sponsor.
27 | Constrained optimization uses mathematical models. Linear programming is a mathematical model.
28 | Most often, projects outsourced outside of the country encounter communication and time zone barriers. The procurement process should have assured the project manager that the sellers were skilled.
29 | Directing (choice A) occurs while the project management plan is being created. During project executing, the project manager should be focused on integrating the work of others into a cohesive whole. This is more important than just coordinating (choice C) or leading (choice D).
30 | Whenever a large number of changes occur on a project, it is wise to confirm that the business case, as stated in the project charter, is still valid.
31 | Present Value (PV): We convert a future cash flow into a value today. This allows us to DIRECTLY compare two future cash flows.
32 | The larger the BCR, SPI and CPI the better. A project with high priority normally holds more senior commitment.
33 | Integrated change control requires coordinating changes across knowledge areas. For example, a proposed schedule change will often affect cost, quality, risk, and resources.
34 | Remember, the internal rate of return is similar to the interest rate you get from the bank. The higher the rate is, the better the return.
35 | Meeting the baseline is one indicator of project success.
36 | Recollections (of information) are less reliable than other documented results.
37 | Change Control Procedure might address how to handle changes, but does not reflect approved changes. Changes made via the change control system will be documented in some part of the project management plan and/or project documents.
38 | Remember, project length is incorporated when computing NPV. You would choose the project that provides the most value, in this case the project with the highest NPV.
39 | You want to capture data at the end of each phase of a project. If you wait until the end, you may forget important information.
40 | A work authorization system is used to coordinate when and in what order the work is performed so that work and people may properly interface with other work and other people.
41 | Q: When should the Project Baselines be changed? A: For all Approved Changes. Sometimes, certain classifications of changes get automatic approval on a project and do not need a change control board's approval. For example, in an emergency, changes should be made by the project manager without the change control board. Changes can be made to the baselines, but only when they are officially approved.
42 | The biggest problem is retaining team members until closure of the project. People start looking for their next project and leave before administrative closure is complete.
43 | It is the sponsor's role to determine objectives. These objectives are described in the project charter.
44 | The project charter is issued by the sponsor. The project manager may have a role in its creation.
45 | Once the change has been made by the Project Manager, you need to update the documents affected by the change; the project management plan and/or project documents.
46 | A project without a charter is a project without support.
47 | A poor communications management plan is not likely to cause the volume of changes in this instance.
48 | It is the project manager's responsibility to manage the project scope completion within budget and reserves.
49 | The project manager loses credibility and performance by using overtime.
50 | Before anyone can be notified, the change must be finished. That means looking for time, cost, quality, risk, resources, and customer satisfaction impacts.
51 | A single high-level executive can end an entire project if he or she is not satisfied with the results, even if that person has, by choice, been only tangentially involved in the project. It is critical to ensure that all of the final decision makers have been identified early in a project in order to ensure that their concerns are addressed.
52 | Before you can do anything else, you have to know what YOU are going to do. Developing the management strategy will provide the framework for all the rest of the choices presented and the other activities that need to be done.
53 | The change management process should be formal so changes don't "just happen." You manage them. You want them documented for historical purposes so there is an audit trail indicating why you made the changes.
54 | A project is complete when all work, including all project management work, is complete and the product of the project, not just deliverables, accepted. The lessons learned are project management deliverables.
55 | A change management plan includes the processes and procedures that allow smooth evaluation and tracking of changes.
56 | Only a work authorization system helps with integrating work packages into a whole. A work authorization system helps ensure that work is done at the right time and in the right sequence.
57 | Primary Responsibility of the Project Manager is 'Interact with others in a Professional Manner while completing the project'.
58 | The change control system should already have methods of making changes described.
59 | Half the project is done and half the cost has been expended. The answer is simple. Or is it? In fact, you do not know what was planned, so you cannot answer this question.
60 | All types of closure must make sure that the actual product of the project meets the requirements for the product.
61 | The Project Manager should offer your assistance without doing the work of the other Project Manager.
62 | Documents that serve as historical records for future projects' are collected throughout the project, but are only archived during the Close Project or Phase process.
63 | Outputs of the Close Project or Phase process include archives, lessons learned, and project closure. However, some project resources (people, computers, telephones) must be used to perform these closing activities. Once completed, the project can release its resources.
64 | A project manager should be looking at where changes are coming from and doing whatever is necessary to limit the negative effects of change on the project. He needs to find the root cause, so future changes may be avoided.
65 | One of the ways to check if a change should be approved is to determine whether the work falls within the project charter. If not, it should be rejected, assigned to a more appropriate project or addressed as a project of its own.
66 | A work authorization system (choice A) helps tell the team when work should begin on work packages. A change control system (choice B) helps track, approve or reject, and control changes. A project management information system (PMIS - choice D) helps the project manager know how the project is going. Only a configuration management system (choice C) addresses controlling documents.
67 | The project manager is an integrator. This is a question about your role as an integrator and communicator.
68 | All the project documentation goes into the archives. Therefore, it must be completed. The archive is the last thing to create before releasing the team.
69
Sl# | Project SCOPE Management
1 | Most change requests are a result of Value-added change. Value added change centers on adding some element that was not available to the project scope to reduce costs at scope creation.
2 | The project team member did not follow the change management plan's method of incorporating changes into the scope.
3 | The responsibility to ensure that the project work is authorized, contracted, and funded rests with the project manager.
4 | Scope statements must at least include the quantifiable criteria of cost, schedule, and quality metrics. The scope statement serves as a point of reference for all future project decisions.
5 | The stakeholders determine the project requirements and decide whether the project was a success.
6 | After the customer's input, the performing organization's project team is responsible for scope baseline preparation. The scope baseline includes the WBS, WBS dictionary, and project scope statement.
7 | Team buy-in is a direct result of the WBS creation process.
8 | The heuristic (rule of thumb) we use in project decomposition is 80 hours. It doesn't matter how experienced the team members are. You need this level of reporting to manage the project effectively.
9 | The project manager must facilitate a fair and equitable solution, but the customer is the first of equals.
10 | Decomposing: The important words here are "project work packages". This indicates that a WBS has already been created. If ithe question said "project deliverables," the answer would have been 'Creating a WBS'.
11 | The numbering system allows you to quickly identify the level in the work breakdown structure where the specific element is found. It also helps to locate the element in the WBS directory.
12 | A change request is the most effective way of handling the disconnect between what users actually want and what management thinks they want.
13 | A team member should have flexibility at the work package level to make some changes as long as they are within the overall scope of the WBS dictionary.
14 | Informal changes to project scope and plan are probably the chief cause of schedule slippage, cost overruns and project team member frustration. Effective scope control is critical to the success of a project.
15 | The project manager should validate with the customer that the change will add value, and then follow the change process.
16 | Much of the work on the project is dictated by the project scope statement. Any imprecision in such a key document will lead to differing interpretations.
17 | The scope management plan describes how requested scope changes will be managed.
18 | The level of uncertainty in scope increases based on the scale of effort required to identify all the scope. For larger projects it is more difficult to "catch" everything.
19 | Work not in the WBS is outside the scope of the project.
20 | Scope verification focuses on customer acceptance of a deliverable while product verification is focused on making sure all the work is completed satisfactorily.
21 | The Verify Scope process is done at the end of each phase of the project. If it is not done, you risk delivering something in the next phase that is not acceptable to the customer.
22 | You need to first understand the change before you can evaluate it. In this instance, verbal communication is not likely to provide enough information to evaluate. Once you understand the change, you can work with the team to determine the impact and options.
23 | A submittal that does not meet the requirements should not be accepted.
24 | Customers do not generally approve the project scope (what you are going to do to complete their requirements); instead, they approve the product scope (their requirements)
25 | Fait accompli - Commonly used to describe an action which is completed before those affected by it are in a position to query or reverse it.
26
Sl# | Project TIME Management
1 | GERT, Graphical Evaluation and Review Technique, allows for conditional advancement. GERT allows for branching and loopbacks.
2 | Subnets are often included in network templates to summarize common activities in a project.
3 | Soft logic allows the project manager to make decisions based on conditions outside of the project, best practices, or guidelines.
4 | Commercial duration estimating databases are valid resources to confirm or base time estimates upon.
5 | Parkinson's Law states that work will expand to fulfill the time allotted to it.
6 | Rather than bloat activities, projects should use contingency reserve. Contingency reserve is a portion of the project schedule allotted for time overruns on activities.
7 | A Gantt chart is a bar chart that represents the duration of activities against a calendar. The length of the bars represent the length of activities while the order of the bars represent the order of activities in the project.
8 | Milestone Schedule can also be called as Master Schedule.
9 | The arrow diagramming method does not support finish-to-finish of relationships.
10 | Project planning (choice A) would use both types of charts. Team members (choice B) need to see details and so they need a bar chart rather than a milestone chart. Risk analysis (choice D) COULD make use of both charts. A milestone chart is used instead of a bar chart for any situation where you want to report in a less detailed way (choice C). Bar charts can scare people with their complexity and often show too much detail to be worthwhile on a management level. Milestone charts are more effective for reporting to management.
11 | The critical path does not change if the scope is the same. A more aggressive deadline simply means the project is two weeks behind.
12 | The wider the range between the optimistic and pessimistic estimates in a three-point estimate, the more uncertainty the estimator has.
13 | In addition to the Project Management Plan, the project team must create "Management plans document how the team will manage on a more detailed level. Examples of management plans include project scope, schedule, cost, quality, and risk management plans".
14 | A Discretionary Dependancy in one that base on: Experience (Based on lessons we learned from past projects or from our past experience, we prefer to do activities in a certain order).
15 | Assuming the project manager is meeting the project objectives and constraints, sponsor approval of a detailed schedule (choice A) is not as critical as that of functional managers. The customer (choice D) does not need to approve the detailed project schedule, just the end date and any milestones they might impose. The team (choice B) would at least have provided their estimates. Getting functional managers to approve will also, indirectly get team members' approval. Remember that the book PMP® Exam Prep says to assume a matrix organization. If functional managers knew what each of their people were doing, the timeframe, and when their activities were on the critical path, resource problems would not be as frequent. Approval of the schedule by functional managers provides the most benefits.
16 | The question is really asking, "What is done after Estimate Activity Durations?" Schedule compression occurs before finalizing the schedule.
17 | Many people forget to make use of the tools of project management planning while the project work is ongoing. Do not make that mistake. A network diagram does help you track flow, but it should be the flow of the work, not information (choice A). The network diagram has nothing to do with cost (choice C) or reward systems (choice D). The network diagram helps you know when work on the project should be done and in what order.
18 | Think of what you would do in the real world. Many project managers just ask for more resources or more time (choices B and C),. Asking for an extension of time is generally the best thing to do only when scope is added to the project. Adding resources will add cost. Choice D should be the last choice. Compressing the schedule lets you get more done with the resources and time that you already have on the project. It is almost always the first thing to do when there is a delay generated from within the project.
19 | You must change the critical path inorder to shorten the project duration. In this case, both activity C and activity H are on the critical path. If you have a choice, all things being equal, choose the earlier option. Therefore, activity C is the best answer.
20 | Standard deviation is a range that an estimate can vary +/- from the mean. The project needs to be done in 40 days, and the schedule calls for 38 days, so the project float is 2 days. With a standard deviation of two days, the project will take 38 +/- 2 days, or 36 to 40 days. Therefore, project float could be 0 to 4 days. Standard Deviation tells you how unsure the estimate is.
21 | Leveling resources generally extends the schedule. Resource leveling refers to keeping the number of resources the same and letting time and cost be flexible.
22 | Corrective action is anything done to bring expected future schedule performance in line with the project management plan. Such action should always be an output.
23 | A milestone shows the completion of a series of activities or work packages. Therefore it takes no time of its own.
24 | Parametric estimating does not make use of estimates from the team.
25 | Project network diagrams are schematic displays of the logical relationships among activities.
26 | You do not necessarily need to change the schedule, unless, of course, the delay is more than the activity's float.
27 | The only certain impact of a scope change is a schedule change to shorten or lengthen subsequent activities.
28 | There is no reason to think the project is going well or poorly based solely on float.
29 | "Project management" software is not designed to do a good job of creating a WBS. It cannot create a complete project management plan, nor can it manage a complete project. It is designed to create and control schedules.
30 | More interdependencies on a project increase the need for communication.
31 | GERT is the only diagramming technique that allows loops.
32 | A heuristic is a rule of thumb. Examples are cost per line of code, cost per square foot of floor space, etc.
33 | The primary purpose of a network diagram is to show logical relationships.
34 | A Monte Carlo analysis provides the ability to compute the probability of completing a project on a specific day.
35 | When the project is completed early, the project manager should report that the project came in ahead of time and explain WHY. This is a success! If there was proper project planning, this should occur because an expected risk did not materialize.
36
Sl# | Project COST Management
1 | The learning curve allows the cost to decrease as a result of decreased installation time as workers complete more of the installation procedure. As the project team completes more and more units, the time to complete a hotel room should take less and less time.
2 | Value analysis/engineering is a systematic approach to find less costly ways to complete the same work.
3 | The cost management plan controls how cost variances will be managed.
4 | Funding limit reconciliation most likely will affect the project schedule, since work will need to be moved to when funds will be available.
5 | A Definitive Estimate: The most expensive to create (A great deal of work is needed to fine tune a project so that you can get a definitive estimate).
6 | The Project Budget and Baseline will not be finalized and accepted until the planning processes are completed.
7 | A Cost Management Plan contains a description of: The WBS level at which Earned Value will be calculated.
8 | The variable and direct costs are most affected by the size and scope of the project. Indirect costs are usually computed as a percentage of direct costs.
9 | Value analysis is a way of finding the least expensive way to do the work.
10 | The life cycle cost will provide the picture of the total cost of the project. It includes project costs and operations and maintenance costs.
11 | Training Costs: You are training the team on skills required for the project. The cost is directly related to the project and thus a direct cost.
12 | Fringe benefits are included in overhead and are part of indirect costs.
13 | A full-time team member who completes her work sooner than planned could be forced to wait for the start of her next activity. Since she is full time, she would have to be paid for time not working.
14
Sl# | Project QUALITY Management
1 | The project team (the individuals completing the project work) is responsible for the quality of the project deliverables.
2 | Internal failure cost is attributed to failure that results in rework. It is an example of the cost of nonconformance to quality.
3 | QC requires an inspection of the work results. While quality is planned into a project, inspections ensure it exists. QA is typically a management process.
4 | ISO 9000 is not a quality management system, but a system to ensure an organization follows its own quality procedures.
5 | Kaizen technologies are small changes to processes and products on a steady, continuous basis to save costs and improve quality.
6 | Quality, in regard to the project scope, is about completing the work as promised.
7 | Q: Optimal quality is reached at what point? A: When revenue from improvement equals the incremental costs to achieve the quality. E: Marginal analysis provides that optimal quality is reached when the cost of the improvements equals the incremental costs to achieve the quality.
8 | Design of experiments uses experiments and 'what-if' scenarios to determine what variables are affecting quality.
9 | Checklists are simple but effective quality management tools that the project manager can use to ensure the project team is completing the required work.
10 | Quality attributes are the measurements that determine if the product is acceptable. They are based on the characteristics of the product for which they were designed.
11 | Perform Quality Assurance involves determining whether standards are being followed. This would be the least effective, since it does not address the specific problem described in the question.
12 | The only choice listed that makes sense and is an official input to Perform Quality Assurance is choice C. This question is similar to others in this program but not exactly the same. You may also see this occur on your exam. Carefully read the questions!
13 | Data points outside the control limits indicate the process is out of control, and production should be stopped until a solution is found.
14 | nspections may be conducted at any level including the project team, and at any time throughout the product development. They are used to prevent defects from being delivered to the customer.
15 | Developing specifications should come from a technical expert. The only choice listed that meets that description is engineering. Not every question on the exam will require that a project manager do the work.
16 | Benchmarking is the common term for a performance measurement standard.
17 | Trend analysis examines project results over time to evaluate performance.
18 | The Perform Quality Assurance process is the process in which we do quality audits to make sure we are using the correct processes.
19 | Quality management should be performed regularly and in parallel with other planning processes throughout the project.
20 | A good project manager will find the root cause and deal with that, even if it means attempting to improve the company's policies and processes. This is continuous improvement. Because there are several activities affected by the policy, it would serve the project better to get to the root cause of the problem and solve it.
21 | DOE: Proper design allows you to find those factors that have the most impact on quality. It allows the project manager to focus attention on the factors that are most important.
22 | Even though it is occurring during the execution of the project, determining what standards to use is part of quality planning. We sometimes need to fall back into planning during other parts of a project. In planning, we determine what quality standards are applicable to the project and how to implement and control them.
23 | Standard deviation is the measurement of a range around the mean.
24 | The control limits are more constraining than the specification limits. Control limits are how you measure your process quality. Specification limits are how the customer measures quality.
25 | The fishbone diagram is a tool that we use to help stimulate thinking (brainstorming), to create an atmosphere conducive to open sharing of thoughts, and to gather our thoughts in a cohesive way. It can be used during analysis to determine the cause of defects.
26 | This can be a tricky question, in that most project managers dismiss the need to focus on quality. Quality, cost, and schedule should be considered of equal importance unless specific project objectives make any one of them most important. Quality, cost, schedule, scope, risk, and other factors may be prioritized differently on each project.
27 | Although quality planning usually occurs during project planning, sometimes we need to go back to planning from other processes to make a decision.
28 | As you increase quality, there will be associated benefits for the project. Some of these benefits are increased productivity, increased cost effectiveness, decreased cost risk, and improved morale.
29 | A data point that requires you to determine the cause of the problem calls for a special cause.
30 | The control limits are set based on the company's quality standard and indicate the acceptable range.
31 | Discovering non-value activities is part of process analysis: implementing the process improvement plan. Many people choose to perform a quality audit (choice C). However, performing a quality audit relates to determining whether you are using the right processes and whether those processes are effective, rather than improving processes.
32 | The group is using organizational process assets to improve their project. Although the incident just occurred, it was on another project. They are in the Plan Quality process.
33 | You can use the WBS (choice C) in many ways to control quality.
34 | Inconsistency and nonpredictability are indications that the process is out of control.
35 | Having an allowable defect rate is an example of the cost of non-quality. Any system or process that will accept defects adds cost to the product or service.
36
Sl# | Project HR Management
1 | When projects are similar in nature, the project manager can use the roles and responsibilities definitions of the historical project to guide the current project.
2 | When project managers, or managers in general, are referred to as different terms, a job description is needed so the project manager can successfully complete the required obligations.
3 | The halo effect is the assumption that because the person is good at a technology they’d also be good at managing a project dealing with said technology.
4 | Q: Susan is the project manager for the PMG Project. She makes all decisions on the project team regardless of the project team objections. This is an example of which of the following management styles? A: Susan is an autocratic decision maker.
5 | When Harold always has to win an argument and team members begin to give into Harold’s demands simply to avoid the argument rather than to find an accurate solution, this is a yield-lose situation.
6 | The Expectancy Theory describes how people will work based on what they expect because of the work they do. If people are rewarded because of the work they complete, and they like the reward (payment), they will continue to work.
7 | Forcing happens when the project manager makes a decision based on factors not relevant to the problem. Just because a team member has more seniority does not mean this individual is correct.
8 | A reward and recognition system involves formal management action to promote desired behavior of individuals.
9 | Remember that confronting means problem solving and problem solving is the best way to resolve conflict ? but not here. The question asks "what conflict resolution technique would you IMMEDIATELY use with the team members." Tempers are too hot and you have the sponsor to deal with. The best immediate choice here is avoidance.
10 | There is always the option to simply postpone dealing with the issue until later. This is withdrawing.
11 | Notice that this question talks about what the team member should do? It is important for the project manager to understand the team member's role and possibly even instruct team members on how to work on projects and what is expected of them. Choices A, B, and C have one thing in common. They involve the team member asking the project manager to do something. In reality, it may very well be the team member who will come up with a solution (such as decreasing the scope of the activity, fast tracking, or specific suggestions about changes to predecessor activities). Therefore, choice D is the best choice. But ask yourself how you run your projects. Which is better, your way or this way? Lastly, please note that recommended corrective or preventive actions can come from the team or stakeholders in addition to the project manager.
12 | Keep in mind that the staffing management plan is created as part of Develop Human Resource Plan and updated as part of Acquire Project Team.
13 | A project manager can rarely tell or direct that project resources be assigned. Most frequently on projects, the functional manager owns the resources.
14 | Staffing Management Plan: WHEN and HOW resource will be ADDED and TAKEN OFF the team.
15 | A project charter is created during project initiating. A project manager is assigned during project initiating, not after it.
16 | A histogram is a bar chart where each bar represents the percent of time the resource is working. Each bar shows one unit of time (e.g., a week, a month, etc.). It does not show usage for each activity or area of expertise. The histogram is a set of bars that depict when a resource is being used, and to what level.
17 | A corner office is a "perk" whereas health benefits are a fringe benefit.
18 | Training: The project manager must ensure that the necessary skills are developed as part of the project.
19 | The tools and techniques of the Manage Project Team process are observation and conversation (watch the team and report on team members' performance), project performance appraisals (do a 360-degree feedback session), conflict management (use appropriate conflict resolution techniques) and issue log.
20 | Smoothing will emphasize that everyone agreed on a plan and that the team should have confidence in that plan.
21 | The role of each stakeholder is determined by: The Project Manager and The Stakeholder.
22 | Top four sources of conflict: schedules, project priorities, resources, and technical opinions
23 | Project performance appraisals deal with how each team member is performing work, rather than how well the team is working together.
24 | Mentoring: is the work that a project manager may be frequently called on to perform.
25 | Resource leveling refers to maintaining the same number of resources on the project for each time period. Leveling has nothing to do with assigning activities or managing meetings.
26 | After a team member completes project work, it is the project manager's job to provide input to the team member's manager regarding performance appraisals.
27 | Performance issues are senior and functional management's responsibility - usually the manager who supervises the resource.
28 | Functional management is responsible for addressing individual performance problems.
29 | Projects often need their own reward systems to affect performance. Project managers should create such a system for each project.
30 | Generally, the best forms of power are reward or expert. The project manager has not had time to become a recognized expert in the company (choice D) and reward is not included as a choice here. This leaves formal power (choice A) as the only logical answer.
31 | Halo Effect: It refers to the tendency of "Move people into Project Management because they are good in their technical field". (Just because a person is good in his technical field does not mean he will also be a good project manager).
32 | Technical issues of the project are managed by the team members' managers (Functional Managers).
33 | A project organizational chart shows resources and their responsibilities.
34 | A reward needs to be specific to the activities at hand to maximize the effect. Although the existing company reward system (choice A) may work, one created specifically for the project will address project-specific objectives and motivators.
35 | The final steps of problem solving include: implement a decision, review it, and confirm that the decision solved the problem.
36
Sl# | Project COMMUNICATIONS Management
1 | Communications Management Plan details the requirements and expectations for communicating information among the project stakeholders.
2 | A communication matrix is an excellent tool to identify the stakeholders and their requirements for communication.
3 | The figure is called a communications bull’s eye and is used to trigger communication needs to management when EVM results fall within the identified ranges.
4 | Paralingual is a term used to describe the pitch and tone of one’s voice.
5 | An exception report is typically completed when variances exceed a given limit.
6 | Administrative closure should take place at the completion of each phase. Administrative closure is the process of generating, gathering, and disseminating project information.
7 | Project meetings should have a set time limit.
8 | Conflict is not a filter of communication—it is a communication hindrance.
9 | Mutual respect and cooperation is the environment needed for fair and balanced negotiations. Collaborating is the ideal method when negotiating. The goal of negotiations is to work together for the good of the project.
10 | When information is sent, it is considered to be transmitted.
11 | The transfer of knowledge is evidence that communication has occurred.
12 | Report Perfromance is a monitoring and controlling process, and is also done during closure to report the performance of the project in the final report.
13 | Expectations are unspoken requirements and are often more critical to a project's stakeholders than the stated ones. Unless these expectations are identified and recorded, there is likely to be a high level of dissatisfaction with the project.
14 | The work breakdown structure (WBS) allows communication vertically and horizontally within the organization as well as outside the project.
15 | A user of the project's product is always a stakeholder, while the others may or may not be.
16 | Working with people from different cultures, with different cultural values and beliefs necessitates an understanding both basic definitions and the areas of cultural impact. As project managers, we need to have good communication skills and a willingness to adapt to other cultures.
17 | Gathering Information is a part of Communication Plan: With proper planning, you will be able to communicate effectively and accurately. In this case you are not gathering the correct information needed to report to the client.
18 | Understanding the receiver's perspective allows you to direct the communication to meet his needs.
19 | Project Manager wants to more extensively involve the Stakeholders on the project: Have the Stakeholders periodically review the list of Project Requirements.
20 | The overriding measurement of what information to accumulate and communicate on a project is whether that information contributes to the success of the project. The required information would take time away from the project and not provide added value.
21 | Aid to solve complex problems, written communication is the best: Written communication allows your words to be documented, and they will go to everyone in the same form. When there are complex problems, you want everyone to receive the same thing.
22 | Nonverbal communication carries 55 percent of the message you send. With this much at stake, nonverbal communication is of major importance.
23 | The bar chart is the tool that shows the schedule at a detailed enough level for discussion with the team.
24 | To ensure clear, concise communications, the project manager must manage communications by deciding what form of communication is best.
25 | Because of the differences in culture and the distance between team members, formal written communication is needed.
26 | Progress Reports generally show problems after they have occurred.
27 | Stakeholders can be identified throughout the project management process groups.
28 | Lateral Communication - Information exchange between the project manager and his/her peers: functional managers, staff personnel, contractors, other project managers, etc. Involves negotiating resources, schedules, and budgets; coordinating activities between groups, as well as developing plans for future operating periods.
Sl# | Project RISK Management
1 | An error value of seven percent represents the threshold the project is allowed to operate under. Should the number of errors increase beyond seven percent, the current plastic will be substituted. Q: A project manager and the project team are actively monitoring the pressure gauge on a piece of equipment. Sarah, the engineer, recommends a series of steps to be implemented should the pressure rise above 80 percent. The 80-percent mark represents what? A: The threshold - The 80-percent mark is a threshold.
2 | The utility function describes a person's willingness to tolerate risk.
3 | When the scope has been changed, the project manager should require risk planning to analyze the additions for risks to the project success.
4 | Monte Carlo simulations can reveal multiple scenarios and examine the risks and probability of impact.
5 | # Force Majeure Risks, such as Earthquakes, Floods, Acts of Terrorism, Etc., should be covered under Disaster Recovery Procedures instead of Risk Management.
6 | # Monte Carlo Analysis would show you is WHERE SCHEDULE RISK EXISITS (Points of Schedule Risk). It is a Computer-based Analysis & useful for revealing Schedule Risks
7 | Notice how many choices are half right? Monte Carlo could help you know that an estimate for an activity needs to change, but not what the activity estimate should be (choice B). Monte Carlo is a simulation (choice C) but it simulates time, not order of activities. Monte Carlo can be used to prove things to management (choice D) but its main focus deals with time, not staff. Risk can be assessed using Monte Carlo analysis (choice A). By considering the inputs to the PERT estimates and the network diagram, you can obtain a better overview of the overall project risk.
8 | # Workaround is what you do if the RISK OCCURS, but it does NOT REDUCE THE RISK.
9 | A decision tree allows you to make an informed decision today based on probability and impact analysis. You can decide based on the expected monetary value of each of your options.
10 | The range of estimates with the smallest range is the least risky.
11 | A risk rating matrix is developed by a department or a company to provide a standard method for evaluating risks. This improves the quality of the rating for all projects. A risk rating matrix is created during the Perform Qualitative Risk Analysis process.
12 | If you cannot determine an exact cost impact of the event, use qualitative estimates such as Low, Medium, High, etc.
13 | Prioritized risk ratingsare an input to the Plan Risk Responses process.
14 | First, you should evaluate the impact of the change. Next, determine options. Then go to management and the customer.
15 | The Risk Owner should be looking for triggers and implementing the risk response strategy.
16 | # Expected monetary value (EMV) is computed by EMV = Probability x Impact. We need to compute both positive and negative values and then add them. 0.6 x $100,000 = $60,000. 0.4 x ($100,000) = ($40,000). Expected Monetary Value = $60,000 - $40,000 = $20,000 profit. # The expected monetary value takes into account the probability and the impact. The calculation is: (0.05 x 21) + (0.5 x 56) - (0.3 x 28) The last part is subtracted because it represents an opportunity and should be balanced against the threat.
17 | The risk response owner is assigned to carry out responses and must keep the project manager informed of any changes.
18 | # Force majeure is a powerful and unexpected event, such as a hurricane or other disaster.
Sl# | Project PROCUREMENT Management
1 | A fair contract shares a reasonable amount of risk between the buyer and the seller.
2 | A bonus to complete the work by August 30 is an incentive.
3 | Privity is a confidential agreement between the buyer and seller.
4 | An SOW can be a contract if both parties agree to the SOW and sign the document as a contract.
5 | A single source seller means there is only one seller the company wants to do business with.
6 | An IFB is typically a request for a sealed document that lists the seller’s firm price to complete the detailed work.
7 | Procurement documents detail the requirements for the work to ensure complete proposals from sellers.
8 | For immediate work, a letter contract may suffice. The intent of the letter contract is to allow the vendor to get to work immediately to solve the project problem.
9 | A unilateral form of a contract is simply a purchase order.
10 | We decompose the Project using a WBS.
11 | The product description defines the details and requirements for acceptance of the project. This information also serves as a valuable input to the process of determining what needs to be procured. The product description defines what the end result of the project will be. When dealing with vendors to procure a portion of the project, the work to be procured must support the requirements of the project’s customer.
12 | Contracts are legal documents and, therefore, generally require more sign-offs.
13 | In a fixed price contract, the seller has the cost risk and therefore wants to completely understand the contract statement of work before bidding.
14 | Look again at the question. Ask yourself "How many computers does the contract say?" Did you read it as twenty (25)? This is an example of a conflict in the contract. The intent of the contract can be determined by remembering that words are more binding than numbers. Therefore, you should return the five extra computers.
15 | You need to encourage the client to realize that they have a problem and to finalize their requirements.
16 | As the project manager, you know what the project risks are. You need to make sure that provisions are included in the contract to address these risks.
17 | The requirement to provide PMP certified project managers is a screening system. A system to minimize personal prejudice is a weighting system.
18 | This is an example of privity. Because Companies A and C have no legal relationship, Company A cannot direct Company C. The smart thing to do is for the project manager of Company A to call the project manager from Company B, and have him communicate the directive from Company A.
19 | The project manager should attend the bidder conference.
20 | Procurement is a very formal process. Changes need to be fully documented and signed by both parties.
21 | Remember that PMI's definition of an audit is different. According to PMI, audits are used to improve the processes.
22 | Changes in resources used would generally not be part of a fixed price contract.
23 | If the seller completes the work specified in the procurement statement of work, the contract is considered complete. That does not mean the same thing as the procurement being closed. The Close Procurements process must still occur. However, in this situation, the contract work is completed. Tricky!
24 | Contract that limits fees for large projects with limited scope definition is cost plus fixed fee.
25 | There are certain basic things that should go into all contracts; an arbitration (or dispute resolution) clause is one of them. Imagine a situation where you have a dispute, but no plan already agreed to in the contract!
26 | If the contract is terminated, the project needs to enter closure. You need those results for historical purposes.
27 | It is not common for alternatives to be discussed at the bidder conference. They may be included in bids or proposals and discussed later.
28 | A customer's meeting minutes have no impact on disputes that arise; therefore, they are not required.
29 | A seller cannot issue a change order (although he could request one). Generally, only the buyer can terminate a contract.
30 | Terms and conditions should be the result of a risk analysis. This means the project manager has been assigned and has completed the risk management process before the contract is drafted. Contracts are risk mitigation tools!
31 | T & M Contract: Profit is factored into the hourly rate. Therefore, profit is increased for each hour worked. If many hours are used, profit can be higher than a fixed bid contract.
32 | The team members should not be requesting deliverables from the seller. However, since they did, you must pay for them and review the procedures with the team.
33 | Special provisions take precedence over general provisions.
34 | Any time that a seller does not perform according to the contract, the project manager must take action. The preferred choice might be to contact the seller and ask what is going on, but that choice is not available here. Therefore, the best choice is to let him know he is in default (choice C).
35 | The only way to change the cost plus fixed fee contract is to negotiate a change to the contract, normally in the form of change orders. Change orders should include an additional fee if additional work is added to the contract.
36 | Sellers are generally required under contract to keep working unless told otherwise.
37 | A procurement statement of work may be revised and refined as it moves through procurement.
38 | Did you notice that the question described change requests, not changes from other sources? Each of these change requests should be weighed to determine the benefits and the impact on the project. The criteria should be laid out in the procurement and change management plans. The best answer is to approve changes that benefit the project (choice C). For example, a change might cause a cost increase or schedule change, but still result in an overall benefit to the quality of the project.
39 | This is a large effort. No procurement statement of work can be developed, and expertise cannot be found internally. CPIF would be an incentive to the vendor to perform on or ahead of schedule.
40 | The contract change control system includes a method for controlling cost on the procurement.
41 | This situation is outside ofyour authority to control. You should therefore bring enough information to management that they can make a determination as to what to do.
42 | Workers Strike: The situation described is probably a force majeure. The appropriate response to a force majeure is to extend the contract.
43 | If it is not in the contract (which includes the specifications), a change order is needed to acquire it.
44 | Procrastination or a lack of planning on the part of the project manager does not create an emergency situation for the procurement manager.
45 | The project manager must be involved to protect the relationship between the company and the seller.
46 | The key to answering this question is to understand that this is a severe situation with many problems-so many problems that it is clear the contract is not serving either party. When a contract no longer serves the needs it was intended to serve, it can be renegotiated if the appropriate parties agree to this.
47 | When the seller has more expertise than the buyer, the procurement statement of work should describe performance or function rather than a complete list of work. In any case, the procurement statement of work should be as detailed as possible.
48 | Bidder conferences are held to provide all bidders a clear and common understanding of the work required.
49 | When you must begin work immediately without a procurement statement of work, the most appropriate choice is time and material.
50 | Seller has the patent for an item: If the seller goes bankrupt, you will no longer have a source for that material. You must deal with this risk.
51 | The buyer has the right to terminate the contract for cause or if the seller breaches the contract by not performing accordingly. Therefore, the procurement would enter the Close Procurements process. Any disputed payments or terms would be handled according to the dispute resolution procedures in the contract.
52 | The independent estimate is most concerned with cost, comparing cost estimates with in-house estimates, or with outside assistance.
53 | The most important issue is the level of detail in the procurement statement of work. If you have a design contract statement of work, a fixed bid contract is possible. Without this level of detail, the risk is high for the seller and thus the price is higher.
54 | Recognize that the procurement manager has power regarding the contract, while the project manager needs to look out for the specific needs of the project. This will cause conflict when the project's needs change and the procurement manager doesn't want to make changes.
55 | his question is asking for the output of the procurement process as a whole, not an output of the pieces within the process. The procurement process should lead toward formal acceptance (not the Contract) of the product of the project, making choice C the best choice. Be careful to properly read questions on the exam!
56 | A procurement audit includes what went right and wrong for the purposes of creating historical records and improving future performance.
57 | Here we are tying together the concepts of standard deviation and contracts. Using the concept of standard deviation, we find that the cost of this project will vary, at one standard deviation, from $1.8M to $2.2M. Since this is not insignificant, there would appear to be some ambiguity with the project definition. As we are not totally sure of the scope, we would not pick a fixed price option (choice A or C). Of the two CR options, you need to select the better of the two. Cost plus percentage of costs (choice D) is probably the worst type of contract to use, as there is no incentive for the seller to control costs. This leaves only choice B, a cost plus fixed fee contract.
58 | A letter of intent is not binding in a court of law, it does make the seller feel more comfortable about expending funds before a contract is signed.
59 | The time and material contract is the easiest to negotiate and allows for rapid turnaround. If you didn't have the time constraint, you would select a fixed price contract
60 | Generally in procurement situations, a change control board might review and approve or reject a change, but only the procurement manager has the authority to sign a change.
61 | Quality is defined as conformance to requirements. If inspection work is not performed as required in the contract, the project's quality standards are not being met.
62 | One factor in determining the contract type to use is the level of detail in the scope. In this case, we have little detail. A fixed price contract (choice C) is not the best due to the high risk to the seller and probable high cost bid. Therefore, a cost plus fixed fee gives the buyer the freedom to determine what they want while the contract is in process with no contract changes. The risk rests with the buyer.
63 | Due to the lack of detailed scope, you should not select a fixed price contract (choice A). Because the buyer wants to be in full control, the time and material contract (choice B) is the best option.
64 | In a procurement situation, generally only the procurement manager has the authority to sign changes. Sometimes the project manager has certain expanded authority to sign in the event of an emergency. However, an increase in cost is generally not considered an emergency.
65 | Once signed, a contract is binding. Generally, the inability to perform, get financing, or one party's belief that the contract is null and void does not change the fact that the contract is binding. If, however, both sides agree to terminate the contract, the contract can move into the Close Procurement process. Once closure is completed, the project is considered completed.
66 | Incentives are meant to bring the objectives of the seller in line with those of the buyer. That way both are progressing toward the same objective.
67 | In a Fixed Price Contract, the fee or profit is : Unknown (To the seller, it is known, but this question is from the buyer's perspective. You do not know what profit the seller included in the contract).
68 | The form of the deliverables for a specific portion of the project should have been reviewed and clarified during the Plan Procurements process.
69 | You always need to follow the change control process. You cannot arbitrarily decide to refuse to pay claims. Reserves should be used for identified risks and not used arbitrarily.
70 | The first thing that should come to mind is whether this is an ethical situation and whether it violates any company rules or laws. If it does not violate any of these, it would be best to check qualifications.
71
72
Sl# | PROFESSIONAL AND SOCIAL RESPONSIBILITY
1 | Professional and social responsibility requires the investigation of any instance where the legitimate interests of the customer may be compromised. If such a compromise is found, action must be taken.
2 | Diversity can enhance a project if planned and coordinated throughout the project.
3 | Whenever you are uncertain of whether a payment is a bribe, you should discuss the situation with legal counsel.
4 | You should offer your assistance to another Project Manager without doing the work.
5 | When the project is completed early, the project manager should report that the project came in ahead of time and explain WHY. This is a success! If there was proper project planning, this should occur because an expected risk did not materialize.
6 | The project manager is neither empowered nor competent to determine the legality of company procedures. NOTE: There is an important distinction between practices and procedures. All unethical practices should be reported. For example, a project manager must report an act of fraud. Fraud is not a company procedure (normally). However, a project manager is not in a position to determine whether company procedures comply with existing law.
7 | The project manager's responsibility is to provide truthful project information. He or she should thereafter discuss the impacts of their actions with the team members. If that does not work, the next step is to report it to their functional managers.
8 | Cultures are thought of as: Integrated wholes.
9 | Effective verbal communication: The Project Manager should always be as EXPLICIT, DIRECT, and UNAMBIGUOUS as possible given the cultural conditions.
10 | Performance Domains include: Planning, Executing, Controlling, and Professional Responsibility.
11 | The Code of Ethics and Professional Conduct advocates transparency in decision making, but it is not necessary for the Project Manager to take responsibility for all decisions.
12 | PMI does not condone deceit or competition without considering the needs of the organization.
13 | As the Project Manager, you have an obligation to report any unethical behavior. You may need to strategize with your sponsor before confronting anyone.
14 | In a Japanese cultural context, Project Managers would do best to focus on personal contact and relationship building before getting down to business.
15

## ImpPoints-3
IMPORTANT POINTS - 3
Sl# | Point to remember
1 | A project life cycle is a collection of generally sequential and sometimes overlapping project phases whose name and number are determined by the management and control needs of the organization or organizations involved in the project, the nature of the project itself, and its area of application.
2 | Parametric estimating uses a statistical relationship between historical data and other variables.
3 | Triggers. Indications that a risk has occurred or is about to occur. Triggers may be discovered in the risk identification process and watched in the risk monitoring and control process. Triggers are sometimes called risk symptoms or warning signs.
4 | Influence diagrams. These are graphical representations of situations showing causal influences, time ordering of events, and other relationships among variables and outcomes.
5 | When closing the project, the project manager will review all prior information from the previous phase closures to ensure that all project work is complete and that the project has met its objectives.
6 | Significant differences in cost estimates can be an indication that the procurement statement of work was deficient, ambiguous, and/or that the prospective sellers either misunderstood or failed to respond fully to the procurement statement of work.
7 | Since all other factors are kept at baseline values and only one element (i.e. currency rate) is changed, we are using Sensitivity Analysis. This can be shown using a Tornado diagram.
8 | Portfolio refers to a collection of projects or programs and other work (i.e. operations) that are grouped together to facilitiate effective management of that work to meet strategic business objectives.
9 | Teaming agreement:... The effort of the buyer and the seller in this process is to collectively prepare a procurement statement of work that will satisfy the requirements of the project. The parties will then negotiate a final contract for award.
10 | To evaluate the team`s effectiveness, we may include indicators such as: - Improvements in skills that allow individuals to perform assignments more effectively - Improvements in competencies that help the team to perform better as a team - Reduced staff turnover rate - Increased team cohesiveness whereby team members share information and experiences and help each other to improve the overall project performance To evaluate the team`s effectiveness, we do not consider the project delivery parameters like scope, time or cost.
11 | Milestone is a significant point or event in the project. Since milestones only indicate when a particular task is going to be started or completed, they will not have any duration, i.e., the duration for milestone is zero.
12 | During the project life cycle, the project team and key stakeholders identify lessons learned concerning all aspects of the project. The lessons learned are compiled, documented, and distributed so that they become part of the historical database. However, most of the organizations prefer post-implementation meetings and case studies to document lessons learned.
13 | In some cultures where offering gifts is a custom, rejecting or returning the gifts may be considered rude and inappropriate behavior. Appreciation of cultural differences is the way to win the trust of people from divergent cultures.
14 | Payback Period: 1. Number of years required for an organization to recapture an initial investment. 2. Discount rate is not taken into account in calculations of Payback Period, and 3. Project Selection Criterion: Select project with low Payback Period.
15 | In the project management context, integration includes characteristics of unification, consolidation, articulation, and integrative actions that are crucial to project completion, successfully managing stakeholder expectations, and meeting requirements.
16 | The areas to be considered in the process improvement plan include process boundaries, process configuration, process metrics, and targets for improved performance.
17 | In Estimate Activity Durations process, which of the following is not an assumption? A: Examples of assumptions include, but are not limited to, existing conditions, availability of information, and length of the reporting periods.
18 | The duration of the project should be calculated after drawing a network diagram and determining the critical path. The duration of the project is the length of the critical path and not the sum of the duration of all the tasks in the project.
19 | Since the change request pertains to a government regulation and the project is being managed as part of a contract, it is mandatory to implement the change. The first step towards that is to activate the change control mechanism.
20 | (Quality) Affinity diagrams are used to visually identify logical groupings based on natural relationships.
21 | (Quality) Force Field Analysis: Which are diagrams of the FORCE FOR and AGAINST CHANGE.
22 | A work authorization system is a collection of formal documented procedures that specifies how project work is authorized to ensure that work is done by the identified organization at the right time and in the proper sequence. Depending on the size of the project, the design of a work authorization system would vary. For example, on many smaller projects, verbal authorizations will be adequate.
23 | Organizational theory provides information regarding the way in which people, teams, and organizational units behave. Effective use of this information can shorten the amount of time, cost, and effort needed to create the human resource planning outputs and improve the likelihood that the planning will be effective.
24 | Identify stakeholders is the process of identifying all people or organizations impacted by the project, and documenting relevant information regarding their interests, involvement, and impact on project success... It is critical for the project success to identify the stakeholders early in the project, and to analyze their levels of interest, expectations, importance and influence. Identify Stakeholders is done as part of Initiating Process Group.
25 | The major difference between single source contracts and sole source contracts— though both are non-competitive forms of procurements— is that in single source contracts, contract is awarded to a seller because he is the organization’s preferred seller, where as in sole source contracts, contract is awarded to a seller because there are no other sellers for the organization’s required procurement item. Sole source contracts help organizations save time.
26 | There are multiple classification models(for stakeholders) available including, but not limited to: Power/interest grid, grouping the stakeholders based on their level of authority (power) and their level or concern (interest) regarding the project outcomes; Power/influence grid, grouping the stakeholders based on their level of authority (power) and their active involvement (influence) in the project; Influence/impact grid, grouping the stakeholders based on their active involvement (influence) in the project and their ability to effect changes to the project`s planning or execution (impact); and Salience model, describing classes of stakeholders based on their power (ability to impose their will), urgency (need for immediate attention), and legitimacy (their involvement is appropriate).
27 | A project life cycle is a collection of generally sequential and sometimes overlapping project phases whose name and number are determined by the management and control needs of the organization or organizations involved in the project, the nature of the project itself, and its area of application. Project can be broken into several phases, which can be done by using a life cycle approach.
28 | Schedule variance analysis along with review of progress reports, results of performance measures and modifications to the project schedule can result in change requests to the schedule baseline and/or to other components of project plan.
29 | The ability to influence cost is greatest at the early stages of the project, making early scope definition critical.
30 | Since this is a "minor flaw," but rectification of that flaw would take a long time, it is better to discuss with the sponsor and customer and get their inputs.
31 | ‘Prevention costs’ are costs incurred by an organization to create high quality products in order to avoid failures. They include cost of training, cost of documenting processes, cost of equipment, etc
32 | SMART Goals: The performance goals should be SMART - Specific, Measurable, Achievable/Attainable, Relevant and Time-specific.
33 | Preventive action: A documented direction to perform an activity that can reduce the probability of negative consequences associated with project risks.
34 | Trend analysis is performed using run charts and involves mathematical techniques to forecast future outcomes based on historical results. Trend analysis is often used to monitor technical performance, i.e., how many errors or defects have been identified, and how many remain uncorrected and cost and schedule performance, i.e., how many activities per period were completed with significant variances.
35 | Variance analysis is used to determine the cause and degree of variance relative to the schedule baseline and decide whether corrective or preventive action is required.
36 | Sequence Activities is the process of identifying and documenting the relationships among the project activities. Schedule network templates are the tools used in this process. (Scheduling tool) is used for Develop Schedule; (Decomposition) is used for Define Activities; (Schedule compression) is used for Develop Schedule
37 | Precision and accuracy are not equivalent. Precision means the values of repeated measurements are clustered and have little scatter. Accuracy means that the measured value is very close to the true value. Precise measurements are not necessarily accurate. A very accurate measurement is not necessarily precise.
38 | Inspections are sometimes called reviews, product reviews, audits, or walkthroughs. Stage gates are also referred to as phase-end reviews or kill points. They are different from Inspection.
39 | Some of the configuration management activities included in the integrated change control process are... configuration identification, configuration status accounting, and configuration verification and audit.
40 | Weight is the only variable here. All the other options refer to units of currency (Dollor, Pound) and measurement (Meters).
41 | Enterprise environmental factors may enhance or constrain project management options and may have a positive or negative influence on the outcome.
42 | Requests for change can be direct or indirect, externally or internally initiated, and can be optional or legally/contractually mandated. Request for change is always a formal process.
43 | Cancellation of the contract has to be done by both the seller and the buyer (i.e., the buyer cannot unilaterally cancel the contract).
44 | Definitive: - 5% to +10% accuracy Budgetary: -15% to +25% accuracy Order of magnitude: - 50% to +50% accuracy
45 | Project Management System: The aggregation of the processes, tools, techniques, methodologies, resources, and procedures to manage a project.
46 | Any time the customer requests for a change, you should: 1. Understand what kind of change is requested and talk with team members to assess the implication of the change. 2. Open up a change control if there is a formal change control mechanism. 3. Communicate the change to the management, and inform the customer about the impact of the change (e.g. increase in sizing, schedule, etc.). 4. Implement the change if it is accepted.
47 | The most preferred conflict resolution techniques adopted by project managers (in descending order of preference) are as follows: 1. Confrontation 2. Compromise 3. Smoothing 4. Forcing 5. Withdrawal
48 | Terms such as bid, tender, or quotation are generally used when the seller selection decision will be based on price (as when buying commercial or standard items), while a term such as proposal is generally used when other considerations such as technical capability or technical approach are paramount.
49 | A milestone list identifies all milestones and indicates whether the milestone is mandatory, such as those specified by contract, or optional, such as those based upon historical information.
50 | Due to varying organizational structures, many organizations treat contract administration as an administrative function separate from the project organization.
51 | People exhibit greatest resistance to change.
52

## ImpPoints-4
IMPORTANT POINTS - 4
Sl# | Point to remember
1 | Programs may often include 'Operations'.
2 | Sponsor - Project Champion.
3 | SMEs - Subject Matter Experts.
4 | Change Control System is a part of OPA (Organizational Process Assets).
5 | Outputs of all 42 Processes will be stored in PMIS.
6 | M & C Project Work: Activities - Measuring, Collecting, Inspecting, Questioning, and Assessing.
7 | M & C Processes' inputs are either PLAN or ACTUAL.
8 | All 10 M & C Processes have Change Requests as an output.
9 | Perform Integrated Change Control acts as 'Clearinghouse'.
10 | Project Management Software is a 'Means' not the 'End'.
11 | High Standard Deviation is High Risk.
12 | CPM - FLOAT usage; CCM - Buffer usage.
13 | PMI's 100% Rule - Complete SCOPE should be available in WBS.
14 | WBS: Graphical/Hierachical/Numerical
15 | Control Accounts - Performance Check Points/Management Check Points.
16 | Requirements Categories: 1. Product Requirements (Technical Specifications); 2. Project Requirements (Operational Specifications)
17 | Control Charts also called 'Shrewhart Charts'.
18 | Project Murder Board, which is defined as a panel of people who try to shoot down a new project idea. The other answers are also project selection methods, but they don’t explain why there is a panel of people that asks all of these questions.
19 | Observation and Conversation. This is also known as MBWA or Management By Walking Around.
20 | The conflict is of a technical nature, so the best way the project manager could solve the problem is by using his or her technical expertise.
21 | Forcing does do away with the conflict - but only temporarily. It is when the manager says that it is his project and you will do things his way. Period, end of discussion. The root of the problem is not addressed by this approach, thus the solution is only temporary.
22 | In Matrix Organization, the project manager is responsible for Manage Project Team.
23 | The standard deviation measures how diverse the population is. It does this by averaging all of the data points to find the mean, then calculating the average of how far each individual point is from that mean. For a very diverse population, you will have a high standard deviation. For a highly similar population, your standard deviation will be low.
24 | Job shadowing is also known as Observation, Quality Function Deployment is a facilitated workshop, and combined with surveys, these are all tools of the Collect Requirements process.
25 | Cause & Effect/Ishikawa/Fishbone Diagram or 5 WHY Technique.
26 | Quality Benefits must outweigh the Cost.
27 | LOW Standard Deviation means LOW Fluctuation; HIGH Standard Deviation means HIGH variation.
28 | Average Response Time should be less than TWO Hours.
29 | Perform Quality Control: - Inspecting; - Measuring; - Testing; - Charting; - Analyzing.
30 | Attribute Sampling is 'Binary' (Yes/No); Variable Sampling is Degree of Conformity.
31 | Inspection: Keeping errors out of the hands of the customer; Prevention: Keeping errors out of the process.
32 | Work Performance Measurements reveal actual results: * Condition of Deliverables; * Status of Schedule; * Status of Budget; * Performance Reports; * Technical Specifications. And it is a subset of WPI.
33 | The BIG Four: 1. Ishikawa; 2. Deming; 3. Juran; and 4. Crosby.
34 | The definition of the work authorization system is the system used to ensure that resources are formally being released to perform work at the right time and in the right sequence. In this case, a meeting with the resources’ functional manager would qualify as being a system.
35 | Leads and lags are APPLIED as part of the Develop Schedule process, but then they are ADJUSTED in the process of Control Schedule.
36 | In Verify Scope, the PM, sponsor, and customer inspect the product and verify that it meets the defined scope. ALL stakeholders are not involved in this process. Why not? There are too many stakeholders to seek acceptance from all; some stakeholders may be opposed to the project and never accept it! Don't confuse stakeholders with key stakeholders.
37 | The stakeholder register is used as an input in the following five processes: Collect Requirements (Scope), Plan Communications (Communications), Plan Quality (Quality), and Identify Risks (Risk). 'B' is the correct answer. This is an IMPORTANT input!
38 | A successful project manager will learn the art of delegation - what to delegate to others and what to not delegate. So, let's look at this list. 'A' - routine activities can be delegated - sure. The team will have regular responsibilities (routine tasks) that they are accountable for. 'B' - technical specs should be developed by the persons that have the expertise. That is probably not the PM. 'C' - picking the team-building activity for the next meeting - no problem. These first 3 can be delegated to the team. 'D,' however, should not be. The project manager is responsible for evaluations of team members. The PM should be providing feedback to the functional manager on the performance of staff. So, 'D' should not be delegated.
39 | You want to simulate the risk event (the server crashes and must be rebuilt) and determine the impact it has on the project. Think of this tool of Perform Quantitative Risk Analysis as you would a military drill or emergency drill. The team is thrown into a simulated, precarious situation and learns how to best respond. 'A' and 'C' are both tools of Perform Quantitative Risk Analysis but are not the correct choices here.
40 | Sensitivity analysis is the tool used when you want to evaluate how one change will affect the overall project. It works by keeping the other variables stable (that is, held at a baseline) and analyzing the impact of a change. Like sensitivity analysis, 'A' and 'B' are both tools of Perform Quantitative Risk Analysis; however, they are not a good match for the scenario provided. 'C' is a made-up term.
41 | This is a very realistic situation for most PMs. You should remember that face-to-face communication is always best and that team development should start early in the project - as soon as you have team members. This makes 'A' the best answer. 'C' includes incorrect information. Virtual teams are a tool of Acquire Project Team, not of Develop Project Team. 'B' is not the right answer because the policy doesn't state that no travel is allowed. Travelling to meet team members, as well as other stakeholders, is a realistic expense and not an extravagance.
42 | The Close Project or Phase process should be performed at the end of each phase or at the end of the project. It should also be observed early in the project to understand closure criteria from the very beginning of project planning. It is the process where the project is formally accepted and the project records are created. It is important to understand that Close Project or Phase may happen several times throughout the project.
43 | Team Building is Very Difficult in MATRIX, Very Easy in FUNCTIONAL, and next Esiest in PROJECTIZED.
44 | Risk SCORE will help guide Risk RESPONES.
45 | Zero Schedule Varience (SV) means the taks is completed.
46 | The more channels of communication on a project, the more difficult it is to control communications.
47 | The To-Complete-Performance-Index (TCPI) is: The cost performance index (CPI) required in the remainder of a project to meet financial goals.
48 | PMI prefers collaboration when it comes to resolving issues or conflicts. Some of the other answers are very tempting, but for the exam, focus on collaboration or either problem-solving confrontation as the best methods!
49 | It is the role of senior management to resolve organizational conflicts and to prioritize projects.
50 | Throughout the life of a project, a project manager should generally move through four phases of leadership: Directing, coaching, facilitating, and supporting.
51 | The Budget at Completion (BAC) and Planned Value (PV) can both be calculated before work begins.
52 | Configuration management is: A procedure to identify and document the functional and physical characteristics of an item or system.
53 | As part of integrated change control, the project manager will need to know when change has occurred, manage the changes, and influence the factors that cause change, but the project manager should not take on the attitude of denying change whenever possible. Some change is inevitable, and all change requests should be evaluated and not automatically rejected.
54 | The PMBOK Guide emphasizes the use of the configuration management system as it relates to managing and controlling change requests, specifically in the process of Perform Integrated Change Control.
55 | Prioritizing the changes is the job of the project manager.
56 | The S curve is the cost performance baseline. The cost performance baseline is used to track cost performance based on the original plan plus approved changes.
57 | An activity's late finish date is the latest an activity can finish without delaying the project. If it exceeds the late finish date, the critical path will change, ultimately resulting in the finish date slipping. Choice 'A' is close to the definition of free float.
58 | The contract change control system is defined in the contract, which is created as an output of the Conduct Procurements process, which is an executing process.
59 | The issue log is a tool used in Manage Project Team in the Human Resource Management knowledge area.
60 | There is a difference between present value and net present value. Present value tells the expected future benefits of the project in today's dollars. Net present value is very similar, but it also includes (or nets out) the expected future costs in today's dollars.
61 | Procurement performance reviews are a tool of Administer Procurements where the buyer arranges a meeting with the seller to review the seller's performance against the plan. This question presents a near-textbook case of this.
62 | If two events have no bearing on each other, they are statistically independent. Mutually Exclusive is when two events cannot both happen at the same time.
63 | A document management system is a configuration management tool, useful in the project management information system. Configuration information in particular will assist with the tool of Variance Analysis in the process of Control Scope.
64 | Resolving contract disputes is performed in Administer Procurements. However, when closing the contract, as in this case, the tool of Negotiated Settlements is used to settle any open claims, even if Alternate Dispute Resolution forms are invoked.
65 | The To Complete Performance Index is defined as the spending efficiency that is needed for the remainder of a project in order to meet a financial target or goal. If the goal is to complete the project on budget and the CPI is 90%, then the TCPI will need to be greater than 100% to compensate for the previous overruns. However, if the goal is amended to be the forecasted completion (EAC - which is derived from the CPI), then the current CPI will achieve the goal. Therefore, the TCPI equals the CPI for a target of EAC.
66 | Both the buyer and the seller perform Administer Procurements to ensure that all of the legal terms of the contract are being met by both parties.
67 | Until the scope has been defined and documented in the approved Scope Statement, WBS, and WBS Dictionary, which make up the scope baseline, it is not stable enough to be put under control.
68 | The tool being described is alternatives identification, used in the process of Define Scope. SMEs can help the project team brainstorm about the various creative ways that the project requirements might be accomplished.
69 | There is a difference between the product scope and the project scope. The scope of the project may be much larger than the scope of the product! The features and attributes that characterize a project deliverable or result describe which of the following? The product scope.
70 | Which of the following is the best description of a configuration management system? It provides a standard, efficient method to manage approved changes to baselines in a project.
71 | The definition of the work authorization system is the system used to ensure that resources are formally being released to perform work at the right time and in the right sequence. In this case, a meeting with the resources’ functional manager would qualify as being a system.
72 | TCPI: The completion of the remaining work at an actual cost not to exceed the remaining funds.
73 | Claims against the contracted parties should be filed as a result of a dispute, and resolving such claims is done in the process of Administer Procurements.
74 | The key phrase in this question is the sponsor's statement about achieving the budget goal. This should lead you to think of the To-Complete-Performance-Index. This index is the spending efficiency that you must maintain to achieve the stated goal, in this case, finishing the project on budget. TCPI=Remaining Work divided by Remaining Funds. Remaining Work is BAC-EV while Remaining Funds (with BAC as the goal) is BAC-AC. You are given AC and CV. EV=CV+AC so EV=$815K. Since you are 50% complete with the project, then BAC is twice the EV, or $1630K. Dividing remaining work ($815K) by Remaining Funds ($910K) gives you 89.6% which shows that Answer B at 90% is the best answer.
75 | In the Communications process of Identify Stakeholders, the PM leads the team to identify the project's stakeholders and the needs of the stakeholders. Stakeholder analysis is a tool of the Identify Stakeholders process.
76 | Soft skills such as interpersonal and management skills are important in relating to individuals, building trust, and delivering a clear message.
77 | Meetings are classified as informal verbal - even when the subject matter is important!
78 | Estimate Activity Resources outputs (primarily the activity resource estimates and the resource breakdown structure) are ideally created by the person doing the work. You would not necessarily need someone external to the project to review them.
79

## Ini & Clo
INTEGRATION
Sl# | Inputs | Tools & Techniques | Outputs
1 | Develop Project Charter:
INITIATING | 1. Project Statement of Work (SOW) | 1. Expert Judgment | 1. Project Charter (PC)
| 2. Business Case (is the document that justifies why the project should be accomplished) | a. Project Charter is created based on some need, and it should explain that need. | e. PC should include a high-level milestone view of the project schedule.
| 3. Contract | b. PC is signed by the performing organization's Senior Management. | f. PC is a high-level document that does not include project details; the specifics of project activities
| 4. Enterprise Environmental Factors | c. PC names the PM and gives PM authority to manage. | will be developed later.
| 5. Organizational Process Assets | d. PC should include the high-level proj requirements, high-level Project Description, high-level Risks. | g. PC includes a summary-level prelim project budget. h. Show organizational, environmental and external CONSTRAINTS and ASSUMPTIONS.
COMMUNICATIONS
28 | Identify Stakeholders:
INITIATING | 1. Project Charter | 1. Stakeholder Analysis | 1. Stakeholder Register
| 2. Procurement Documents | (Participation Analysis) | 2. Stakeholder Management Strategy
| 3. Enterprise Environmental Factors | 2. Expert Judgment | (Stakeholder Analysis Matrix)
4. Organizational Process Assets
INTEGRATION
6 | Close Project or Phase:
CLOSING | 1. Project Management Plan | 1. Expert Judgment | 1. Final Product, Service, or Result Transition
| 2. Accepted Deliverables |  | 2. Organizational Process Assets Updates
3. Organizational Process Assets
PROCUREMENT
42 | Close Procurements: The process of completing each project procurement. * Finalize and Close each purchasing contract. * When the contract is Completed or Terminated for any reason, this process is performed.
CLOSING | 1. Project Management Plan | 1. Procurement Audits (Review of Procurement Processes - for capturing Lessons Learned) | 1. Closed Procurements
| 2. Procurement Documentation | 2. Negotiated Settlements | 2. Organizational Process Assets Updates
3. Records Management System

## Exe
INTEGRATION
Sl# | Inputs | Tools & Techniques | Outputs
Direct and Manage Project Execution:
EXECUTING | 1. Project Management Plan | 1. Expert Judgment | 1. Deliverables
| 2. Approved Change Requests | 2. Project Management Information System - PMIS | 2. Work Performance Information (WPI)
| 3. Enterprise Environmental Factors |  | 3. Change Requests
| 4. Organizational Process Assets |  | 4. Project Management Plan Updates
5. Project Document Updates
SCOPE
TIME
COST
QUALITY
Perform Quality Assurance:
EXECUTING | 1. Project Management Plan (Q M Pl & Process Imp Pl) | 1. Quality Audits (Key Tool) | 1. Change Requests (for Procedural Changes)
| 2. Quality Metrics (Defines how Q will be measured) | 2. Process Analysis | 2. Project Management Plan Updates
| 3. Quality Control Measurements | 3. Plan Quality and Perform Quality Control Tools | 3. Project Document Updates
| 4. Work Performance Information | and Techniques | 4. Organizational Process Assets Updates
HUMAN RESOURCE
Acquire Project Team:
EXECUTING | 1. Project Management Plan | 1. Pre-Assignment | 1. Project Staff Assignments
| 2. Enterprise Environmental Factors | 2. Negotiation (Key Technique of this process) | 2. Resource Calendars
| 3. Organizational Process Assets | 3. Acquisition | 3. Project Management Plan Updates
4. Virtual Teams
Develop Project Team:
EXECUTING | 1. Project Staff Assignments (will have list | 1. Training | 1. Team Performance Assessments
| of all team members) | 2. Team-building Activities | 2. Enterprise Environmental Factors Upd
| 2. Resource Calendars | 3. Ground Rules
| 3. Project Management Plan | 4. Co-location
5. Recognition and Rewards
6. Interpersonal Skills (Soft Skills)
Manage Project Team:
EXECUTING | 1. Project Management Plan | 1. Observation and Conversation | 1. Change Requests
| 2. Project Staff Assignments | 2. Project Performance Appraisals | 2. Project Management Plan Updates
| 3. Team Performance Assessments | 3. Conflict Management | 3. Organizational Process Assets Updates
| 4. Performance Reports | 4. Issue Log | 4. Enterprise Environmental Factors Updates
| 5. Organizational Process Assets | 5. Interpersonal Skills
COMMUNICATIONS
Distribute Information:
Executing | 1. Project Management Plan | 1. Communication Methods | 1. Organizational Process Assets Updates
| 2. Performance Reports | 2. Information Distribution Tools
3. Organizational Process Assets
Manage Stakeholder Expectations:
EXECUTING | 1. Stakeholder Register | 1. Communications Methods | 1. Change Requests
| 2. Stakeholder Management Strategy | (Face-to-face is the best) | 2. Project Management Plan Updates
| 3. Project Management Plan | 2. Interpersonal Skills | 3. Project Document Updates
| 4. Issue Log (Action Item Log) (Each Issues should be assigned to one Owner) | 3. Management Skills | 4. Organizational Process Assets Upd
5. Change Log
6. Organizational Process Assets
RISK
PROCUREMENT
Conduct Procurements:
EXECUTING | 1. Project Management Plan (Pr M Pl) | 1. Advertising | 1. Selected Sellers
| 2. Project Documents | 2. Internet Search | 2. Procurement Contract Award
| 4. Procurement Documents | 3. Bidder Conference | 3. Resource Calendars
| 3. Teaming Agreements | 4. Proposal Evaluation Techniques | 4. Change Requests
| 5. Make-or-Buy Decisions | 5. Independent Estimates ('Should-Cost' Estimate) | 5. Project Management Plan Updates
| 6. Source Selection Criteria | 6. Procurement Negotiations | 6. Project Document Updates
| 7. Qualified Sellers' List | 7. Expert Judgement
8. Seller Proposal
9. Organizational Process Assets

## M&C
INTEGRATION
Sl# | Inputs | Tools & Techniques | Outputs
4 | Monitor and Control Project Work:
M & C | 1. Project Management Plan | 1. Expert Judgment | 1. Change Requests
| 2. Performance Reports |  | 2. Project Management Plan Updates
| 3. Enterprise Environmental Factors |  | 3. Project Document Updates
4. Organizational Process Assets
5 | Perform Integrated Change Control:
M & C | 1. Project Management Plan | 1. Expert Judgment | 1. Change Request Status Updates
| 2. Work Performance Information | 2. Change Control Meetings | 2. Project Management Plan Updates
| 3. Change Requests |  | 3. Project Document Updates
4. Enterprise Environmental Factors
5. Organizational Process Assets
SCOPE
10 | Verify Scope:
M & C | 1. Project Management Plan | 1. Inspection | 1. Accepted deliverables
| 2. Requirements Documentation | (It involves a point-by-point review of the Scope and the associated Deliverable). Examine the deliverables, Measure it, Inspect it, and Weigh it. | 2. Change Requests
| 3. Requirements Traceability Matrix |  | 3. Project Document Updates
4. Validated Deliverables
11 | Control Scope:
M & C | 1. Project Management Plan | 1. Variance analysis | 1. Work Performance Measurements
| 2. Work Performance Information | VA can be used to measure differences btwn what was defined in the Scope Baseline & what was created. It is useful in this process as a way to investigate and understand the root causes behind these differences. | 2. Change Requests
| 3. Requirements Documentation |  | 3. Project Management Plan Updates
| 4. Requirements Traceability Matrix |  | 4. Project Document Updates
| 5. Organizational Process Assets |  | 5. Organizational Process Assets Updates
TIME
17 | Control Schedule:
M & C | 1. Project Management Plan | 1. Performance Reviews | 1. Work Performance Measurements (SV & SPI values)
| 2. Project Schedule | 2. Variance Analysis (SV/SPI) | 2. Change Requests
| 3. Work Performance Information | 3. Resource Leveling | 3. Project Management Plan Updates
| 4. Organizational Process Assets | 4. What-if Scenario Analysis | 4. Project Document Updates
|  | 5. Adjusting Leads and Lags | 5. Organizational Process Assets Updates
6. Schedule Compression
7. Scheduling Tool
8. Project Management Software
COST
20 | Control Costs:
M & C | 1. Project Management Plan | 1. Earned Value Management (Variances and Trends) | 1. Work Performance Measurements
| 2. Project Funding Requirements | 2. Forecasting (EAC and ETC) | 2. Budget Forecasts
| 3. Work Performance Information | 3. To-complete Performance Index (TCPI) | 3. Change Requests
| 4. Organizational Process Assets | 4. Performance Reviews | 4. Project Management Plan Updates
|  | 5. Variance Analysis | 5. Organizational Process Assets Upd
|  | 6. Project Management Software | 6. Project Document Updates
QUALITY
23 | Perform Quality Control:
MONITORING & CONTROLLING | 1. Project Management Plan (Q M Plan) | 1. Cause and Effect Diagram (Ishikawa/Fishbone) | 1. Quality Control Measurements
| 2. Quality Metrics | 2. Control Charts | 2. Validated Changes
| 3. Quality Checklists | 3. Flowcharting | 3. Validate Deliverables
| 4. Deliverables | 4. Histogram | 4. Change Requests
| 5. Approved Change Requests | 5. Pareto Chart | 5. Project Management Plan Updates
| 6. Work Performance Measurements | 6. Run Chart | 6. Project Document Updates
| 7. Organizational Process Assets | 7. Scatter Diagram | 7. Organizational Process Assets Updates
8. Statistical Sampling
9. Inspection
10. Approved Change Requests Review
HUMAN RESOURCE
COMMUNICATIONS
32 | Report Performance:
M & C | 1. Project Management Plan (Performance Measurement Baseline - It includes Cost, Schedule, Scope, Tech, and Other Baselines) | 1. Variance Analysis - Backward Looking Tool (It is an after-the-fact) | 1. Performance reports (It shows how the project is progressing against the various baselines (Scope, Time, Cost and Quality).
| 2. Work Performance Information (Deliverables Status, Schedule Progress, and Costs Incurred) | 2. Forecasting Methods - Forward Looking Tool (EAC, ETC) | Common Formats - Bar Charts, S-curves, Histograms, and Tables. Variance, EV, Forecasting.
| 3. Work Performance Measurements (CV, SV, CPI, CPIc, SPI) | 3. Communication Methods (PM generally uses a PUSH Comm Technique) | 2. Change Requests
| 4. Budget Forecasts | 4. Reporting Systems (Standard Tool for PM to Capture, | 3. Organizational Process Assets Updates
| 5. Organizational Process Assets | Store and Distribute Information)
RISK
38 | Monitor and Control Risks:
M & C | 1. Risk Register | 1. Risk Audits | 1. Risk Register Updates
| 2. Project Management Plan | 2. Reserve Analysis | 2. Change Requests
| 3. Performance Reports | 3. Risk Reassessment | 3. Project Management Plan Updates
| 4. Work Performance Information | 4. Status Meetings | 4. Project Document Updates
| No O.P.A & E.E.F | 5. Technical Performance Measurement | 5. Organizational Process Assets Updates
6. Variance and Trend Analysis
PROCUREMENT
41 | Administer Procurements:
M & C | 1. Project Management Plan | 1. Inspections and Audits | 1. Procurement Documentation
| 2. Procurement Documents | 2. Procurement Performance Reviews | 2. Change Requests
| 3. Contract | 3. Performance Reporting | 3. Project Management Plan Updates
| 4. Approved Change Requests | 4. Contract Change Control System | 4. Organizational Process Assets Updates
| 5. Performance Reports | 5. Payment System
| 6. Work Performance Information | 6. Claims Administration
7. Records Management System