## Dashboard
Dashboard
Project: | Project Title Here
Project #: | Project Number Here
Project Manager: | Project Manager Name Here
Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here
Last Update: | Date of Last Update
Accounting Code: | PLCF0011
Note on B2: Enter project information in white cells and it will populate the information in all templates.
New Defects in Models for Last 4 Weeks

## BTTCA Complexity Tool
Business Transition & Technology Complexity Assessment (BTTCA) Model
| Project: | Project Title Here |  | Project #: |  |  |  | Project Number Here
| Project Manager: | Project Manager Name Here |  | Sponsor: |  |  |  | Sponsor Name Here
| Project Artifacts: | Location of Project Documents Here |  | Last Update: |  |  |  | Date of Last Update
| Accounting Code: | PLCF0011
Business Transition Complexity Criteria Table
|  |  | NA | 1 | 2 | 3 | 4 | 5 |  | Comments/Details
| Categories | Low Complexity | [6 empty] | High Complexity
| Sponsor | One | [6 empty] | None/Many
| Objectives | Clear | [6 empty] | Vague
| Goals | Clearly Defined | [6 empty] | Not Clearly Defined
| Business Processes | Clearly Defined | [6 empty] | Not Clearly Defined
| Business Rules | Few - Known | [6 empty] | Many - Unknown
| Business Location | One | [6 empty] | Many
| Federal/State Mandate | Few Business Changes | [6 empty] | Many Business Changes
| Other Key Drivers (Audit Findings, Sanctions, Lawsuits) | Simple | [6 empty] | Complex
| Stakeholder Impact | Low | [6 empty] | High
| Duration of Effort | 3 Months or less | [6 empty] | More than 3 years
| Contract Need | None | [6 empty] | Significant/Complex
| Conflicting Projects | None | [6 empty] | Many
| Cross Departmental Involvement | None | [6 empty] | Many
| Critical Business Processes Affected | One | [6 empty] | Many
| Level of Training Effort Required | Informal | [6 empty] | Formal/Classroom
| Number of Internal Users | 20 or Less | [6 empty] | More than 2000
| Number of External Users | 20 or Less | [6 empty] | More than 2000
| Delivery Schedule | Compressed | [6 empty] | Flexible
| Funding Source | Non-Constrained | [6 empty] | Grant /Time Constrained
| Human Resources Staffing Impact | Low | [6 empty] | High
|  | Business Complexity Trend: |  | 0 | 0 | 0 | 0 | 0
Technical Complexity Criteria Table
|  |  | NA | 1 | 2 | 3 | 4 | 5 |  | Comments/Details
| Categories | Low Complexity | [6 empty] | High Complexity
| Technology/Platform | DHS Standard | [6 empty] | New Technology
| Development Locations | One | [6 empty] | Many
| System Platform | One | [6 empty] | Many
| Amount of Integration | Simple | [6 empty] | Complex
| Number of Users | Less than 20 | [6 empty] | Greater than 2000
| System Availability | 8-5, M-F | [6 empty] | 24-Hrs, 7 Days
| Internal Technical Resources | Experienced | [6 empty] | Inexperienced
| External Maintenance Technical Experience | Experienced | [6 empty] | Inexperienced
| Fed/State Mandate | Few Changes | [6 empty] | Many Changes
| Conflicting Projects | None | [6 empty] | Many
| Rough Estimate | Under $75,000 | [6 empty] | Over $1,000,000
| Contract Need | None | [6 empty] | Significant/Complex
| Multiple IT Group Involvement | No Other | [6 empty] | More than 5 Other
| Security/Roles | Low (Less than 3) | [6 empty] | High (More than 6)
| Co-Location of Technical Team | Local | [6 empty] | Outside Oregon
| Data Conversion | One system | [6 empty] | Multiple Systems
| Hosting | Internal | [6 empty] | External
|  | Technical Complexity Trend: |  | 0 | 0 | 0 | 0 | 0
Business Transition Criteria Table
|  |  | NA | 1 | 2 | 3 | 4 | 5 |  | Comments/Details
| Categories | Low Complexity | [6 empty] | High Complexity
| Cross Departmental Involvement | One | [6 empty] | Many
| Critical Business Processes Affected | One | [6 empty] | Many
| Level of Training Effort Required | Informal | [6 empty] | Formal/Classroom
| Business Processes | Defined/Familiar | [6 empty] | Undefined/Unfamiliar
| Business Rules | Defined/Established | [6 empty] | Undefined/Non-Existent
| Business Location | One | [6 empty] | Many
| Number of Users Impacted | 50 or Less | [6 empty] | More than 50
| End User Impact | Low | [6 empty] | High
| Duration of Effort | 3 Months or Less | [6 empty] | More than 3 Months
| Technical Complexity Criteria | Low |  | 1 |  |  |  |  | High
|  | Business Complexity Trend: |  | 1 | 0 | 0 | 0 | 0
For Business Transition Criteria determinations assume that the Technical Complexity Level will always be scored as a 1.
| Rough Order of Magnitude (ROM) | BTTCA |  |  | Business Transition Trend |  |  |  | Combined Totals
|  | #,# |  |  | #,#
| Combined Trend Here: | 3,3 |  |  | 1,1
| Cost Estimate | $$$ |  | $$$ |  |  |  |  | $$$
| Low | 234475.56 |  | 7534.944 |  |  |  |  | 242010.504
| High | 703426.68 |  | 22604.832 |  |  |  |  | 726031.512
| Duration Estimate | mths. |  | mths. |  |  |  |  | mths.
| Low | 5 |  |  | 1 |  |  |  | 5
| High | 15 |  |  | 3 |  |  |  | 15
| FTE Estimate | # of FTE |  | # of FTE |  |  |  |  | # of FTE
| Low | 3 |  |  | 1 |  |  |  | 3
| High | 9 |  |  | 3 |  |  |  | 9
Do Not Change Any Data Values
Trend | Rating | Ave Rate Factor | Cost Factor | Dur Factor | Mth Hr Factor | FTE Factor | Cost - Low | Cost - High | Dur - Low | Dur - High | FTE - Low | FTE - High
1,1 | LL | 38 | 0.648 | 2 | 153 | 2 | 7534.944 | 22604.832 | 1 | 3 | 1 | 3
1,2 | LM | 38 | 0.756 | 4 | 153 | 3 | 26372.304 | 79116.912 | 2 | 6 | 1.5 | 4.5
1,3 | LH | 38 | 0.864 | 6 | 153 | 4 | 60279.552 | 180838.656 | 3 | 9 | 2 | 6
1,4 | ML | 38 | 1.08 | 6 | 153 | 4 | 75349.44 | 226048.32 | 3 | 9 | 2 | 6
1,5 | MM | 43 | 1.188 | 10 | 153 | 6 | 234475.56 | 703426.68 | 5 | 15 | 3 | 9
2,1 | LM | 38 | 0.756 | 4 | 153 | 3 | 26372.304 | 79116.912 | 2 | 6 | 1.5 | 4.5
2,2 | LH | 38 | 0.864 | 6 | 153 | 4 | 60279.552 | 180838.656 | 3 | 9 | 2 | 6
2,3 | ML | 38 | 1.08 | 6 | 153 | 4 | 75349.44 | 226048.32 | 3 | 9 | 2 | 6
2,4 | MM | 43 | 1.188 | 10 | 153 | 6 | 234475.56 | 703426.68 | 5 | 15 | 3 | 9
2,5 | MH | 43 | 1.296 | 12 | 153 | 8 | 409266.432 | 1227799.296 | 6 | 18 | 4 | 12
3,1 | LH | 38 | 0.864 | 6 | 153 | 4 | 60279.552 | 180838.656 | 3 | 9 | 2 | 6
3,2 | ML | 38 | 1.08 | 6 | 153 | 4 | 75349.44 | 226048.32 | 3 | 9 | 2 | 6
3,3 | MM | 43 | 1.188 | 10 | 153 | 6 | 234475.56 | 703426.68 | 5 | 15 | 3 | 9
3,4 | MH | 43 | 1.296 | 12 | 153 | 8 | 409266.432 | 1227799.296 | 6 | 18 | 4 | 12
3,5 | HL | 49 | 1.458 | 12 | 153 | 8 | 524670.048 | 1574010.144 | 6 | 18 | 4 | 12
4,1 | ML | 38 | 1.08 | 6 | 153 | 4 | 75349.44 | 226048.32 | 3 | 9 | 2 | 6
4,2 | MM | 43 | 1.188 | 10 | 153 | 6 | 234475.56 | 703426.68 | 5 | 15 | 3 | 9
4,3 | MH | 43 | 1.296 | 12 | 153 | 8 | 409266.432 | 1227799.296 | 6 | 18 | 4 | 12
4,4 | HL | 49 | 1.458 | 12 | 153 | 8 | 524670.048 | 1574010.144 | 6 | 18 | 4 | 12
4,5 | HM | 54 | 1.62 | 16 | 153 | 10 | 1070755.2 | 3212265.6 | 8 | 24 | 5 | 15
5,1 | MM | 43 | 1.188 | 10 | 153 | 6 | 234475.56 | 703426.68 | 5 | 15 | 3 | 9
5,2 | MH | 43 | 1.296 | 12 | 153 | 8 | 409266.432 | 1227799.296 | 6 | 18 | 4 | 12
5,3 | HL | 49 | 1.458 | 12 | 153 | 8 | 524670.048 | 1574010.144 | 6 | 18 | 4 | 12
5,4 | HM | 54 | 1.62 | 16 | 153 | 10 | 1070755.2 | 3212265.6 | 8 | 24 | 5 | 15
5,5 | HH | 59 | 1.728 | 16 | 153 | 12 | 1497470.976 | 4492412.928 | 8 | 24 | 6 | 18
Ave Rate Factor =average rate of internal IT, contracted and business staff | [5 empty] | Mth Hr Factor=average available full-time hours per month - based on
Cost Factor=factor of cost not associated with labor | [6 empty] | 260 non weekend days, 10 holidays, 10 vacation, 10 other
Dur Factor=average duration for level of complexity | [5 empty] | FTE Factor=average FTE for level of complexity
BTTCA Model
The Business Transition and Technical Complexity Assessment (BTTCA) is used to assist in the development of a clear understanding of the proposed project costs, duration, and full-time equivalencies (FTEs) with limited detailed information. The BTTCA is performed in the Pre-Initiating process and will be used as an input in the development of the Business Case and the Project Charter for the proposed project. It may also be used periodically throughout the project.
Scoring Business Transition and Technical Complexity
The following matrices are completed by reviewing each criteria and providing a rating from a “1” (low) to “5” (high). Criteria that do not apply will be rated as “NA” (not applicable).
Note that the absolute accuracy of each score is not necessary; the final result will be based on a scoring mode. Completion of this assessment by a multidisciplinary group will yield a more accurate score and provide a higher degree of confidence. Each member will individually rate the criteria. Afterwards, the group will discuss the scores that are different and agree on a final rating.
Determining a Trend
The final ratings determine a business transition complexity and technical complexity trend which guides the amount of project management and business transition planning and controls. This trend is used to estimate a Rough Order of Magnitude (ROM) of project costs, duration, and FTE’s of the project.
Once the complexity criteria have been scored it is necessary to calculate the business transition complexity and technical complexity mode. The mode is not an average, but rather the value that occurs most frequently in a set of data. Thus the column that has been checked the most determines the trend. For example, three “4s,” two “5s,” two “2s” and three “NAs” on the business matrix would indicate a business complexity trend of “4”. NA criteria are excluded from the overall score.
To obtain a trend where there is an evenly distributed set of scores, use the scores from the criteria that more heavily impacts or proposes the greatest amount of risk to this particular project.
ROM Estimate Steps:
1. The business and technical complexity score is automatically entered into the spreadsheet from the Complexity Tool. The order entry does not matter, "2,3 or 3,2"
2. If the range estimate results for cost, duration, full-time equivalents (FTE) are reasonable skip to step 5.
3. Review the following assumptions for the mathematical model:
· The business and technical complexity score include the primary factors influencing the cost of the project or phase.
· Complexities of a project progressively increase the cost, duration, and FTE estimates.
· Cost estimates include all resources (staff, procurements)
· The number of FTEs is an average per month and does not account for high and low work effort periods. The number represents the full-time effort required. For example 1 FTE can be accomplished by two people working half time.
· FTE numbers represent all work estimated whether it is intended to be performed by OIS, contracted or business staff.
4. Apply expert judgement and decide if assumptions and estimates apply. Revise assumptions and revise estimates.
Business Transition Management
As projects continue to be implemented and completed within the organization, a greater understanding is being developed that changes to the Business need to be accounted for, managed and implemented along with the project to ensure greater success of the project and greater levels of acceptance for the changes that the project brings to the organization.
Business Transition Management is a process that utilizes the disciplines of Business Change Management (BCM) and Business Process Engineering (BPE) (including Lean Six Sigma) in support of Project Management to achieve a required business outcome.
BCM is the process, tools and techniques to manage the people-side of business change to achieve the required business outcome, and to realize that business change effectively within the social infrastructure of the workplace.
BPE is the process, tools and techniques to manage the process-side of business change to achieve the required business outcome.
Determining the Business Transition Management Complexity Trend
Once the Business Transition criteria have been scored it is necessary to calculate the Business Transition complexity mode. This is not an average. The column that has been checked the most determines the trend. For example, three “4s”, two “5s”, two “2s” and three “NAs” on the business matrix would indicate a business complexity trend of “4”. NA criteria are excluded from the overall score.

## Complexity Assessment
Business Transition & Technology Complexity Assessment (BTTCA) Model
|  | Project: | Project Title Here |  |  |  | Project #: |  |  | Project Number Here
|  | Project Manager: | Project Manager Name Here |  |  |  | Sponsor: |  |  | Sponsor Name Here
|  | Project Artifacts: | Location of Project Documents Here |  |  |  | Last Update: |  |  | Date of Last Update
|  | Accounting Code: | PLCF0011
Business Complexity
Instructions: On a scale of .5 - low to 4-high (0 = N/A), rate each applicable attribute and compute the Business Complexity by dividing the total by the number of items rated above zero. [Notes: Business and technical complexity will be computed automatically in this worksheet, using the ratings you enter. Move your pointer over each attribute cell, marked with a red triangle, to see a definition of the attribute.]
|  | Low Complexity |  |  | Business Attribute |  |  | High Complexity |  |  | Rating
|  | 0 1 |  |  | 2 |  |  | 3
|  | Static |  |  | Business rules |  |  | Changing
|  | Static |  |  | Current Business Systems |  |  | Changing
|  | Known and Followed |  |  | Decision Making Process |  |  | Not Known
|  | Low |  |  | Financial Risk to Organization |  |  | High
|  | Local |  |  | Geography |  |  | Company Wide
|  | Clear and Stable |  |  | High Level Requirements |  |  | Vague
|  | Few & Routine |  |  | Interaction with Other Departments and Entities |  |  | Many and New
|  | None |  |  | Impact to Business Process |  |  | High
|  | Few & Straight Forward |  |  | Issues |  |  | Multiple & Contentious
|  | High |  |  | Level of Authority |  |  | Low
|  | Clear |  |  | Objectives |  |  | Vague
|  | Established |  |  | Policies |  |  | Non-existent
|  | Minimal |  |  | Politics |  |  | High
|  | Familiar |  |  | Target Users |  |  | Unfamiliar
|  | Experienced |  |  | Project Manager's Experience |  |  | Inexperienced
|  | Experienced |  |  | Team |  |  | Inexperienced
|  | Loose |  |  | Time Scale |  |  | Tight
|  | Low |  |  | Visibility |  |  | High
[9 empty] | Total: |  | 0
[9 empty] | Complexity: |  | 0
Technical Complexity
Instructions: On a scale of 0-low to 4-high, rate each applicable attribute and compute the Technical Complexity by dividing the total by the number of items rated above zero. Use the definitions in the student notebook for clarity.
|  | Low Complexity |  |  | Technical Attribute |  |  | High Complexity |  |  | Rating
|  | 0 1 |  |  | 2 |  |  | 3
|  | Local |  |  | Communications |  |  | Company wide
|  | Established |  |  | Delivery Mechanism |  |  | New
|  | Local |  |  | Geography |  |  | Company wide
|  | Proven |  |  | Hardware |  |  | New
|  | Stand-alone |  |  | Level Of Integration |  |  | Tightly Integrated
|  | Proven/Stable |  |  | Networks (L/W) |  |  | New
|  | In place |  |  | New Technology Architecture |  |  | Not in place
|  | 9-5, Mon-Fri |  |  | Operations |  |  | 24-hour, 7-day
|  | Expert |  |  | PM Technical Experience |  |  | Novice
|  | Established and in use |  |  | Scope Management Process |  |  | None
|  | Light |  |  | Security |  |  | Tight
|  | Proven |  |  | Software |  |  | New
|  | Established and In Use |  |  | Standards And Methods |  |  | None
|  | Experienced |  |  | Team |  |  | Inexperienced
|  | High |  |  | Tolerance To Fault |  |  | Low
|  | Low |  |  | Transaction Volume |  |  | High
[9 empty] | Total: |  | 0 | 0
[9 empty] | Complexity: |  | 0
[11 empty] | 0 | 0
Complexity Diagram
Instructions: Plot your project in the appropriate complexity zone. [Note: Your project will be plotted automatically in this worksheet, using the values computed in the previous tables.]
|  |  | Scores | Business Complexity |  |  | 0
|  |  |  | Technical Complexity |  |  | 0
Suggested Project Manager Skill Set Guidelines
| Complexity |  |  |  | Duration |  |  | Budget |  |  |  | Resources |  | Complexity |  | Duration |  | Budget |  | Resources |  | Score | Level | Guidelines
|  | Zone 1 |  |  |  | < 6 months |  |  | <$500K |  |  |  | < 5 | TRUE | 25 | TRUE | 20 | TRUE | 20 | TRUE | 20 | 33 - 40 | Novice | Experience: Minimum 1 year working as a key team member on an IT project. Technical experience commensurate with the proposed technology.
|  | Zone II, Medium Zone III, Medium |  |  |  | < 1 year |  |  | <$1M |  |  |  | <10 | FALSE | 50 | FALSE | 40 | FALSE | 40 | FALSE | 40 |  |  | Professional Knowledge: Understands the CA-PMM and department’s methodology.
|  | Zone II, High Zone III, High |  |  |  | >1 year; < 3 years |  |  | >$1M; <$5M |  |  |  | 11 – 20 | FALSE | 75 | FALSE | 60 | FALSE | 60 | FALSE | 60 | 41 - 50 | 1 | Experience: Minimum 3 years working as a key team member on an IT project or as a Project Manager on other small IT projects. Technical experience commensurate with the proposed technology.
|  | Zone IV |  |  |  | >3 years; <10 years |  |  | >$5M; <$100M |  |  |  | 21 – 40 | FALSE | 100 | FALSE | 80 | FALSE | 80 | FALSE | 80 |  |  | Professional Knowledge: Understands the CA-PMM and department’s methodology.
[6 empty] | >10 years |  |  | >$100M |  |  |  | 40+ |  |  | FALSE | 100 | FALSE | 100 | FALSE | 100 | 51 - 75 | 2 | Experience: 3 – 5 years as a key team member on a medium or large IT project or as a Project Manager on small or medium IT project. Technical experience commensurate with the proposed technology.
| 25 | 35% |  |  | 20 | 15% |  | 20 | 35% |  |  | 20 | 15%
21.75
| PM Level: |  |  |  | Novice | Experience: Minimum 1 year working as a key team member on an IT project. Technical experience commensurate with the proposed technology. | [17 empty] | Professional Knowledge: Strong working knowledge of the CA-PMM, department’s methodology, Software Development Life Cycle. Familiar with CA Budgeting, Procurement and Contracting processes.
[6 empty] | Professional Knowledge: Understands the CA-PMM and department’s methodology. | [15 empty] | 76 - 90 | 3 | Experience: 3-5 years working as Project Manager on medium or other large IT projects. Technical experience commensurate with the proposed technology.
For Oversight Purposes: | [23 empty] | Professional Knowledge: Strong working knowledge of the CA-PMM, department’s methodology, Software Development Life Cycle. Familiar with CA Budgeting, Procurement and Contracting processes.
Zone I = Low Criticality/Risk
Zones II and III = Medium Criticality/Risk | [5 empty] | Assess the complexity of the project periodically: every two - three months and/or at the conclusion of each phase | [15 empty] | 91+ | 4 | Experience: 5+ years working as Project Manager or Project Director on large IT projects . Technical experience commensurate with the proposed technology.
Zone IV = High Criticality/Risk | [23 empty] | Professional Knowledge: Strong working knowledge of the CA-PMM; CA Budgeting, Procurement and Contracting processes; department’s methodology; and Software Development Life Cycle.
Note on G16: The degree to which business rules governing the industry either are in place and constant, or are growing and changing with the demands of the organization.
Note on G17: The number and complexity of current business systems the project must interact with (e.g. approval processes, purchasing systems, etc.)
Note on G18: A description of the authorities and individuals involved in making the decisions required by the project.
Note on G19: The size of the money that is at stake for the Organization.
Note on G20: The areas in which the project must be managed and implemented.
Note on G21: The clarity and completeness of the functional requirements for the project.
Note on G22: The degree to which the team must interact with and rely on other departments to complete the work involved in the project.
Note on G23: The degree to which existing business processes will be impacted by the project.
Note on G24: The number and type of unanswered questions or differences of opinion that exist about the project.
Note on G25: The authority that the project team has to make decisions regarding the project.
Note on G26: The extent to which the end goal of the project is specific, measurable, achievable, relevant to overall strategy, and time-bound.
Note on G27: Organizational rules or regulations that may impact the project.
Note on G28: The degree of competition between competing interest groups or individuals for power and/or leadership.
Note on G29: The individuals who are intended to use the product of the project.
Note on G31: The average level of experience possessed by the team in the business functions required by the project.
Note on G32: The tightness of the development schedule for the project.
Note on G33: The degree that the outcome of the project is visible to DOE, upper management, stakeholders, and the general organization.
Note on G45: The area(s) to which communications to the project will be needed.
Note on G46: The method by which the products of the project will be delivered to the client.
Note on G47: The area(s) where the project will be implemented.
Note on G48: Machinery and equipment: CPU, disks, tapes, modem, cables, printers, monitors, etc.
Note on G49: The degree to which the project combines the activities of multiple applications or systems.
Note on G50: LAN: A communications network that serves users within a confined geographical area. It is made up of servers, workstations, a network operating system and a communications link. WAN: A communications network that serves a wide geographical area such as a state or a country. A WAN requires the network facilities of common carriers.
Note on G51: The design of a computer system setting the standard for all devices that connect to it and all the software that runs on it.
Note on G52: The hours that the product (or the project) will be in use.
Note on G53: The level of project specific technical knowledge and experience possessed by the project manager.
Note on G54: The process by which change to scope is evaluated and then either dropped or integrated into the project.
Note on G55: The degree to which the project needs protection from theft, copying, or corruption.
Note on G56: Instructions for the computer: system software is made up of control programs, and application software is any program that processes data.
Note on G57: The specifications and practices for either software or hardware that are widely in use that will guide us through the development of the project.
Note on G58: The technical experience level of the team.
Note on G59: The degree to which defects can be tolerated.
Note on G60: Number of requests, activities, orders, etc.
Note on L36: Summation of business complexity rankings.
Note on L37: The average of score of the items rated above zero.
Note on L64: Summation of technical complexity rankings.
Note on L65: The average of score of the items rated above zero.
III
Low Complexity
High
Complexity
Medium
Complexity
(Technical)
Medium
Complexity
(Business)
Clear Entries
Print Worksheet
Top of the Page
Technical Complexity
Complexity Diagram
Complexity Diagram
Business Complexity
Technical Complexity
Suggested PM Skill Set Guidelines
Project Manager Qualifications
Project Manager Qualifications
Technical Complexity
Complexity Diagram
Business Complexity
Business Complexity
Spell Check

## Minicharter
Project Minicharter
Project: | Project Title Here | Project #: | Project Number Here
Project Manager: | Project Manager Name Here | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
Background
Business need and business benefits
Objectives
Scope | In Scope | Out of Scope
Deliverables | Deliverable | Due Date
Flexibility matrix | Scope
Schedule
Cost
Key considerations | Assumptions & Constraints | Risks
|  | Category | Risk Description
Success criteria | 1 -
2 -
3 -
4 -
5 -
Signatures
Sponsor
Signature
Printed name
Date
Project Manager
Signature
Printed name
Date
Note on B20: Note A for assumptions, C for constraints
Note on C17: Options are: Most flexible Moderately flexible Least flexible
Note on C18: Options are: Most flexible Moderately flexible Least flexible
Note on C19: Options are: Most flexible Moderately flexible Least flexible
Note on C21: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Project Structure and Schedule
This section covers the factors not covered in the other three sections including:
* Project Schedule* - This would be done at the level of major milestones/project events (i.e., Sponsor/System Owner approval, workplan development, major deliverables, reassessment points, system development life cycle phases, etc.)
* Project Management Tools - could include such items as software, status reports, and status meetings
* Oversight
• Description of the administrative control processes and bodies (i.e., Executive Committee, OCIO Review, Independent Verification and Validation, etc.)
• Description of product approval process
• Description of change control process
• Description of issue escalation/resolution process.
*Special Note: For displaying dates associated with the project schedule, the following guidelines should be observed:
* Dates shown for schedule components should be documented with assumptions
* Mandated dates should be noted as such (document impact if these dates are not met)
* Optionally, only provide dates for milestones/project events through the next reassessment period. (Note when the dates for non-scheduled milestones will be determined.)
Minincharter
Example of Guidelines for the Development of a Project Mini-Charter
The Project Charter will be one of your first key documents in your project binder. If you don't have a project binder, where do you store project-specific information? Keep the charter there.
Preparing the charter with your customer allows you to ask specific questions of your customer about their requirements, the scope of the project and the commitment of customer resources. This is a time of learning, building trust and opening communication channels.
The process you go through with your customer to develop the project charter is as important as the product.
The scope description is probably the most important and the most difficult to develop. Work at it. Documenting what is out of scope is as important as what is in scope at this time. As requirements are converted to diagrams later on you will learn more but this is the time to state the scope as clearly as possible in English. Be polite but be persistent and get it down in black and white now.
Document the constraints. When the customer mentions some vaguely related project, get them to elaborate - there may be a dependency lurking there!
Charters can be very short yet still have value. The time you invest in the charter should be commensurate with the size and complexity of the project. Invest a little more in the charter the first time you work with a customer.
Review the Guidelines for the Development of a Project Charter before you meet with your customer.
PURPOSE
Developing the charter with your customer allows you to communicate openly about the customer's requirements, expectations and commitment and document your understanding. You are partners at this point and your success depends on the trust you build at this stage. There's plenty of time to become opponents later.
LEVEL OF DETAIL
Large projects justify a significant effort in developing comprehensive charters. Multi-day off site meetings with customer process owners is appropriate for developing these charters. Mini-projects (less than one staff month) deserve a phone call to the customer to confirm requirements and priority, convey expected start and completion dates, and confirm user acceptance procedures. This phone call should be followed with something in writing (e-mail qualifies) so the customer also has a record of your understanding.
RECOMMENDED FORMATS FOR THREE LEVELS OF PROJECT CHARTERS
THE PROJECT CHARTER FOR A MINI PROJECT
Confirm the customer's requirements as stated in their request and the priority of the request. Inform them of the expected start and completion dates and any tasks which they must perform. Discuss contingencies which could affect the plan. Summarize your discussions in a note so that you and the customer have something in writing.
Sample Follow-up Note
To: Customer
From: Project Manager
Subject: XYZ Business Case
Per our conversation this afternoon, we will assign staff to work on this DPSR starting Monday. The requirements stated on the DPSR have not changed except the related system changes described will not occur at this time. Therefore, this project will add the operator's initials to the note that is generated when an address is changed. We expect to complete unit and system test by May 15. Your staff will need to complete acceptance testing by COB the 16th if we are to release this in time for the next production run on Friday the 17th.
If this enhancement is not accepted on this schedule, we will run the manual process we have been using for the past three months again on the 17th and correct our problems to get this into production the following week. Thus your acceptance testers would have to sign off by COB on the 23rd in this case. As I mentioned, if the 3086 project plan is approved tomorrow, I could lose my staff who would do this work. I'll let you know by Friday if we have to re-schedule this DPSR.
THE PROJECT CHARTER FOR A MEDIUM SIZED PROJECT
The charter for the medium sized project is more formal that the mini charter but not as detailed as the large project charter. You may use the structure of the large charter and simply provide less detail. It should include:
• Project Title
• Start and Estimated End Date
• Definition (what, when, where - identify the customer, objectives, requirements)
• Expected Results (completion criteria)
• Resources (people and their roles, funding)
• Schedule (milestones and dates)
THE PROJECT CHARTER FOR A LARGE PROJECT
The Project Charter typically consists of a cover page and four primary sections. The cover page identifies the project name, Executive Sponsor(s), and dates of Project Charter approval. The primary sections are the
• Project Identification and Scope
• Authority and Resource Need Definition
• Project Methodology, Roles, and Responsibilities, and
• Project Structure and Schedule.
Project Identification
This section is used primarily to define the scope of the project being undertaken, why it is being undertaken, and for whom the project is being developed. Information that should be contained in this section includes:
• Project name/title
• Who the project is being developed for (i.e., the customer)
• Background/Introduction/Purpose
• Policy considerations
• Problem(s) being addressed
• Opportunities being explored
• Mandates to be complied with
• The business systems/functions being addressed
• The automated systems being affected
• Scope Statement (potentially defined in terms of what the project is and what it is not)
• End-task objectives (i.e., products, benefits, etc. - defines when the project is complete)
• Expected results
• Constraints imposed
• Identification and discussion of any risks associated with the project (see Risk Assessment tab for detailed questions on strategic, financial, project management, technology, change management and operational risks)
Authority and Resource Need Definition
This section defines the resources needed for the project to be successful and how these resources will be managed.
• Resource Needs
• Project-assigned staff (program/support/technical) \ (full/part-time)
• Specific-task staff resources (program/support/technical)
• Vendor Need
• Space
• Equipment (hardware and software)
• Training requirements for team and non-team members
• Other
• Funding sources
• Authority
• Description of reporting relationships of team members including Project Manager
• Funding spending allocation/approval authority
• Any special accounting or reporting requirements
• Product approval signoff authority
Project Methodology/Roles/Responsibilities
This section is used to describe the process by which the project will be conducted and how all the project participants fit into that process.
• Describes methods/tasks to be performed
• Defines project team roles related to the methods/tasks described
• Defines how the results of projects will be measured to determine if the project met its objectives

## Stoplight
Stoplight Report
Project: | Project Title Here |  |  |  |  | Project #: | Project Number Here
Project Manager: | Project Manager Name Here |  |  |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  |  |  |  | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
Deliverables
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Schedule
Scope
Cost
Risk
Issues
Planned completion
Est. Completion
Management Alert
ID | Situation Requiring Management Attention |  |  |  | Action Plan |  |  |  | Owner
Accomplishments During Reporting Period
ID | Description of Accomplishment |  |  | Planned Completion | Date Completed | Owner |  | Comments
Deliverables | Title/Description |  |  |  |  | Title/Description
1 |  |  |  |  | 6
2 |  |  |  |  | 7
3 |  |  |  |  | 8
4 |  |  |  |  | 9
5 |  |  |  |  | 10
Note on A28: In Row 7 there are 10 deliverables listed. This section allows you to explain each deliverable.
Note on B8: Options are: Green: On schedule/on budget Yellow: Somewhat behind schedule/somewhat over budget Red: Behind schedule/over budget
How to Read a Project Stoplight Report
A project stoplight report is a simple, visual way to show the status of projects. Green shows the project is good, yellow shows it is in danger, and red shows it as in trouble. Unfortunately, that doesn't help much beyond giving a summary. Managers often ask for these reports as a simple way to understand the status of portfolios of projects, and focus on the red and yellow areas.
Project leaders, though, understand that a yellow or red indicator could be taken as showing weakness in their own project leadership skills. In this case, the project leader is inclined to show a troubled project as green and hope they can fix any problems before they are noticed. There is also a dynamic that red and yellow projects require more work from the project manager to explain what is going wrong and to do extra tasks to fix the problems. When the project is already in trouble, this extra work is the last thing the project leader needs. This is another reason to shade projects toward green.
Instead of this, managers could set the meaning of green, yellow and red differently, such that they get more value from the stoplight report.
I suggest that Green can mean, "The project is going well, we don't need help from management."
Yellow can mean, "We are starting to worry about some aspects of the project and want some advice from management about how do proceed." For yellow projects, the project leader should give options to the management team for a decision rather than just present the problems.
Then Red can mean, "This project is in trouble and needs action from management to fix it." In most cases, red projects should have been escalated to management as soon as they turned red, so if they are still red at the project review, that should mean that the project leader has yet to receive the support they needed from the managers on the project. Red becomes a reminder to the management team that the project needs their help.
With a better use of the project stoplight report, management reviews can become a useful working session rather than a tedious meeting of blame passing.

## Budget
Budget
Project: | Project Title Here | Project #: | Project Number Here
Project Manager: | Project Manager Name Here | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
Budget Status
Approved Budget | Planned Expenditures to Date | Actual Expenditures to Date | Variance
50000 | 12000 | 9500 | 2500
| Planned Remaining Budget | Actual Remaining Budget | Variance
| 38000 | 40500 | -2500
Additional $ needed
Budget Details
Internal Expenses
Salaries | Hourly Rate | # Hours | Total Cost
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Other Internal Expenses |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total Internal Expenses |  |  |  | 0
External Expenses
Consulting Costs |  |  | Total Cost
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Capital Expenditures |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total External Expenses |  |  |  | 0
Total Budget |  |  |  | 0
Budget Guidelines
The Budget sheet allows you to track original budget, expenditures to date, and any cost variance. This section can be substituted with other Excel budget planning and tracking financial sheets.

## CBA
Cost/Benefit Analysis
Project: | Project Title Here |  |  | Project #: | Project Number Here
Project Manager: | Project Manager Name Here |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  |  | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
Project Development and Maintenance Costs
Description | FY2010 | FY2011 | FY2012 | FY2013 | FY2014 | Total
Cost of Project Development
Salaries
Other internal expenses
Consulting costs
Capital expenditures
Total Project Costs | 0 | 0 | 0 | 0 | 0 | 0
Cost of Support
Operational Costs
Nonrecurring Costs
Recurring Costs
Total ongoing Support Costs | 0 | 0 | 0 | 0 | 0 | 0
Benefits/Savings
Current Process | FY2010 | FY2011 | FY2012 | FY2013 | FY2014 | Total
Total Annual Price
New Process
Total Annual Price
Annual savings | 0 | 0 | 0 | 0 | 0 | 0
Cumulative savings | 0 | 0 | 0 | 0 | 0 | 0
Cumulative costs | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Total Net Savings | 0 | 0 | 0 | 0 | 0 | 0
Future Value
Present Value | Interest Rate |  | # Periods |  | Future Value
0
Present Value
Future Value | Interest Rate |  | # Periods |  | Present Value
0 |  |  |  |  | 0
Net Present Value
Period | Cash Flow |  |  |  | Present Value
1
2
3
4
5
Totals | 0 |  |  |  | 0
Project Development Cost |  |  |  |  | 0
Net Present Value (NPV) |  |  |  |  | 0
Note on B32: How much is the money worth today?
Note on B36: This is how much money you expect the project to be worth.
Note on C40: FV for the period's return. Note: Change the PV # Periods to match the Period here.
Note on E32: How many years will the project last?
Note on E36: How many years will it take until the company starts seeing this profit?
Note on G32: This is how much money you expect the project to be worth.
Note on G36: This is how much the money you project making will be worth in today's market.
Note on G40: This is how much the money you project making would be worth in today's market.
Cost/Benefit Analysis
Evaluating Quantitatively Whether to Follow a Course of Action?
You may have been intensely creative in generating solutions to a problem, and rigorous in your selection of the best one available. However, this solution may still not be worth implementing, as you may invest a lot of time and money in solving a problem that is not worthy of this effort.
Cost Benefit Analysis or CBA is a relatively* simple and widely used technique for deciding whether to make a change. As its name suggests, you simply add up the value of the benefits of a course of action, and subtract the costs associated with it.
Costs are either one-off, or may be ongoing. Benefits are most often received over time. We build this effect of time into our analysis by calculating a payback period. This is the time it takes for the benefits of a change to repay its costs. Many companies look for payback on projects over a specified period of time e.g. three years.
How to Use the Tool:
In its simple form, cost-benefit analysis is carried out using only financial costs and financial benefits. For example, a simple cost benefit ratio for a road scheme would measure the cost of building the road, and subtract this from the economic benefit of improving transport links. It would not measure either the cost of environmental damage or the benefit of quicker and easier travel to work.
A more sophisticated approach to building a cost benefit models is to try to put a financial value on intangible costs and benefits. This can be highly subjective - is, for example, a historic water meadow worth $25,000, or is it worth $500,000 because if it’s environmental importance? What is the value of stress-free travel to work in the morning?
These are all questions that people have to answer, and answers that people have to defend.
The version of the cost benefit approach we explain here is necessarily simple. Where large sums of money are involved (for example, in financial market transactions), project evaluation can become an extremely complex and sophisticated art.
Example:
A sales director is deciding whether to implement a new computer-based contact management and sales processing system. His department has only a few computers, and his salespeople are not computer literate. He is aware that computerized sales forces are able to contact more customers and give a higher quality of reliability and service to those customers. They are more able to meet commitments, and can work more efficiently with fulfillment and delivery staff.
His financial cost/benefit analysis is shown below:
Costs:
New computer equipment:
• 10 network-ready PCs with supporting software @ $2,450 each
• 1 server @ $3,500
• 3 printers @ $1,200 each
• Cabling & Installation @ $4,600
• Sales Support Software @ $15,000
Training costs:
• Computer introduction - 8 people @ $400 each
• Keyboard skills - 8 people @ $400 each
• Sales Support System - 12 people @ $700 each
Other costs:
• Lost time: 40 man days @ $200 / day
• Lost sales through disruption: estimate: $20,000
• Lost sales through inefficiency during first months: estimate: $20,000
Total cost: $114,000
Benefits:
• Tripling of mail shot capacity: estimate: $40,000 / year
• Ability to sustain telesales campaigns: estimate: $20,000 / year
• Improved efficiency and reliability of follow-up: estimate: $50,000 / year
• Improved customer service and retention: estimate: $30,000 / year
• Improved accuracy of customer information: estimate: $10,000 / year
• More ability to manage sales effort: $30,000 / year
Total Benefit: $180,000/year
Payback time: $114,000 / $180,000 = 0.63 of a year = approx. 8 months

## Defects Log
Daily Defects Log
Project: |  | Project Title Here |  | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here |  | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here |  | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
No. | Date Identified | Defect ID | Summary | Defect Type | Project | Detected in Release | Date Resolved | Status/Comments
1
2
3
4
5
6
7
8
9
10
Defects Log
The Defect Log is where all user and developer reported defects are recorded.
The Defects Log should contain:
# Details of who reported the defect and when.
# A description of the defect including the exact text of any messages produced.
# Version Of The Product With The Defect.
# What you have done or will do to fix the defect.
# The status of the defect.
Can sometimes expand to a catch all in particular encompassing Change and Ideas.
During release cycles that are inperfect there is an enormous temptation to overload the Defect Log try to avoid that temptation.

## Risks (RMM)
Risk Management Matrix (Risk Register)
Project: |  |  | Project Title Here | [5 empty] | Project #: | Project Number Here
Project Manager: |  |  | Project Manager Name Here | [5 empty] | Sponsor: | Sponsor Name Here
Project Artifacts: |  |  | Location of Project Documents Here | [5 empty] | Last Update: | Date of Last Update
Accounting Code: |  |  | PLCF0011
ID | Risk Description | Probability | Impact | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
1 | What is this risk? |  |  |  | 0 |  | What act or event initiates either the risk occurrence or precipitates the response strategy? | How will you respond to this risk and what actions will you take to match that response? | If the risk becomes a reality, what will you do in response, as a backup, or alternative/ workaround? | Who monitors this risk?
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
Note on D6: Probability: 4: Highly likely/probable (76%-100%) 3: Likely (51%-75%) 2: Somewhat likely (26%-50%) 1: Unlikely/improbable (0%-25%)
Note on E6: Impact: 4: Critical: Threatens the viability of the business or represents failure of the project 3: Severe: Threatens the achievement of business vision or severely reduces project benefits 2: Moderate: May delay achievement of the vision or reduce project benefits 1: Minimal/minor: No impact on business vision but may increase project costs and timescales
Note on F6: Detectability: 4: Determined after impact has been realized 3: Realized upon trigger event 2: Immediately prior to trigger event; can be mitigated prior to trigger if monitored 1: Determined well in advance of occurrence or trigger event
Note on H6: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Note on J6: Options are: Avoidance Transference Mitigation Acceptance Include a description of what actions are taken to implement the response.
Note on M6: Options are: Open Closed
Ranking Program Risks
At this point, the team has all the information needed to rank the risks. If using the Risk Matrix tool, this process is simple and automated. Risk rankings are calculated using the Borda voting method. The Borda method ranks risks from most-to-least critical on the basis of multiple evaluation criteria. Appendix A provides more details about the Borda method.
If the team chooses not to use an automated tool, an alternative is to use a multi-voting technique. With this method, each team member receives votes equal to approximately half the number of risks. Team members vote individually for items with perceived highest priority. The votes are tallied and the top risks are selected and ranked accordingly.
Managing Program Risks
All risks need some form of management, whether it involves a plan for handling risks (action plan) or merely keeping watch.
After the risks are ranked, the team should identify the risks that are high priority, need to be managed, and require resources (identify the top N risks). The team should meet with the program manager to discuss the results and achieve agreement on the top N risks to be tracked and actively worked.
Decisions for handling the top N risks will vary. Some risks will be eliminated because the requirements changed; others will be transferred to other organizations (like a contractor) for action because the program team does not have the proper resources to handle the risks or because it's more appropriate for the other organization to handle them; and others will require mitigation strategies. The remaining risks (the ones not in the top N) should be watched.
NOTE: For the baseline assessment, teams are not required to create action plans for the top N risks, though they are strongly encouraged to do so. A brief summary of the action plans for each risk can be entered in the Manage/Mitigate column in the template. Details about the action plans can be entered in the Action Plan worksheet tab.
Managing Action Plans
Whenever feasible (usually after an initial Baseline Assessment), the program team should develop detailed action plans and enter an initial status, assign the Office of Primary Responsibility (OPR), and determine exit criteria for the top N risks. The status of each action plan should be reviewed and assessed periodically (approximately each week or month if possible), and the risks rankings adjusted accordingly.
The PLCF tool provides an Action Plan worksheet for tracking risk action plans and adjusting the risk rankings based on the action plan status.
Continuously Assessing Risks
Continuously assessing risks is essential to good program risk management. As a program progresses, risks should be reassessed periodically (perhaps monthly or quarterly) to determine whether their level of importance has changed or whether new risks have developed that should be identified, assessed, ranked, and managed.
What is a Risk Matrix?
Baseline Risk Assessment Process
A good risk assessment and management process is essential to the success of any program.
The process summarized here consists of:
• Planning for Risk Assessment
• Identifying Program Objectives or Requirements
• Defining Program Risks
• Ranking Program Risks
• Managing Program Risks
• Managing Action Plans
• Continuously Assessing Program Risks.
More details about the process are described in the annotated briefing, Establishing A
Program Risk Baseline.
Planning for Risk Assessment
The first stage of a risk assessment is to plan the activity. A program manager may begin this process by selecting the risk assessment team, setting forth ground rules, and determining the supporting risk management tools. The risk assessment team should include representatives from all areas of the program, not just technical experts. In addition, a facilitator and recorder should be selected to assist the team.
Identifying Program Objectives or Requirements
Once the Program Manager identifies the risk assessment team and tools, the team identifies the key program objectives or requirements. The program objectives and requirements should assist the team in identifying risks.
Defining Program Risks
A team facilitator leads the team through a structured brainstorming process to identify the program risks. For example, each team member individually writes down risk ideas. Next, the facilitator asks each person to present one idea in sequence or pass in a rotation until all candidate risks are offered. Once all ideas are heard, an affinity diagram is created to group, merge, and eliminate duplicate risks, and to identify dependent risks. An affinity diagram is "…a technique for organizing verbal information into a visual pattern." The facilitator has the team silently arrange candidate risks into related groups of one or more risks. Through this process, risks may be merged if similar or dependent, and eliminated if the same.
Next, the team agrees on category titles for each group. Collaboratively the team identifies complete risk statements for each risk on the affinity diagram. A suggested format for a complete risk statement may be in the form of “If a risk condition, then the consequences.” The recorder documents each complete risk.
Following the identification of the risks, the team assigns various attributes to each risk. At a minimum, relevant time frame, impact, and probability of occurrence are assigned. Time frame is the beginning and end dates of when a risk may occur. Then the team sets impact definitions.
The Risk Matrix impact definitions are:
C (Critical): If the risk event occurs, the program will fail. Minimum acceptable requirements will not be met.
S (Serious): If the risk event occurs, the program will encounter major cost/schedule increases. Minimum acceptable requirements will be met. Secondary requirements may not be met.
Mo (Moderate): If the risk event occurs, the program will encounter moderate cost/schedule increases. Minimum acceptable requirements will be met. Some secondary requirements may not be met.
Mi (Minor): If the risk event occurs, the program will encounter small cost/schedule increases. Minimum acceptable requirements will be met. Most secondary requirements will be met.
N (Negligible): If the risk event occurs, it will have no effect on the program. All requirements will be met.
Probability of occurrence is the team’s assessment of the likelihood of a risk happening. Estimating the probability of occurrence may be difficult in practice. Fortunately, all that matters when using Risk Matrix is the relative order of the probability estimates (which risks are more likely to occur). For this purpose, it is sufficient to estimate probabilities using a relative scale:
• 0-10%: very unlikely the risk will occur
• 11-40%: unlikely the risk will occur
• 41-60%: even likelihood the risk will occur
• 61-90%: likely the risk will occur
• 91-100%: very likely the risk will occur.
This approach may be used to translate subjective probability estimates into numbers in the absence of hard data. However, if hard data is available for some risks, the other probability estimates must be chosen to be consistent with the hard data.
Ranking Program Risks
At this point, the team has all the information needed to rank the risks. If using the Risk Matrix tool, this process is simple and automated. Risk rankings are calculated using the Borda voting method. The Borda method ranks risks from most-to-least critical on the basis of multiple evaluation criteria. Appendix A provides more details about the Borda method.
If the team chooses not to use an automated tool, an alternative is to use a multi-voting technique. With this method, each team member receives votes equal to approximately half the number of risks. Team members vote individually for items with perceived highest priority. The votes are tallied and the top risks are selected and ranked accordingly.
Managing Program Risks
All risks need some form of management, whether it involves a plan for handling risks (action plan) or merely keeping watch.
After the risks are ranked, the team should identify the risks that are high priority, need to be managed, and require resources (identify the top N risks). The team should meet with the program manager to discuss the results and achieve agreement on the top N risks to be tracked and actively worked.
Decisions for handling the top N risks will vary. Some risks will be eliminated because the requirements changed; others will be transferred to other organizations (like a contractor) for action because the program team does not have the proper resources to handle the risks or because it's more appropriate for the other organization to handle them; and others will require mitigation strategies. The remaining risks (the ones not in the top N) should be watched.
NOTE: For the baseline assessment, teams are not required to create action plans for the top N risks, though they are strongly encouraged to do so. A brief summary of the action plans for each risk can be entered in the Manage/Mitigate column in the template. Details about the action plans can be entered in the Action Plan worksheet tab.
Managing Action Plans
Whenever feasible (usually after an initial Baseline Assessment), the program team should develop detailed action plans and enter an initial status, assign the Office of Primary Responsibility (OPR), and determine exit criteria for the top N risks. The status of each action plan should be reviewed and assessed periodically (approximately each week or month if possible), and the risks rankings adjusted accordingly.
The PLCF tool provides an Action Plan worksheet for tracking risk action plans and adjusting the risk rankings based on the action plan status.
Continuously Assessing Risks
Continuously assessing risks is essential to good program risk management. As a program progresses, risks should be reassessed periodically (perhaps monthly or quarterly) to determine whether their level of importance has changed or whether new risks have developed that should be identified, assessed, ranked, and managed.
What is a Risk Matrix?
Baseline Risk Assessment Process
A good risk assessment and management process is essential to the success of any program.
The process summarized here consists of:
• Planning for Risk Assessment
• Identifying Program Objectives or Requirements
• Defining Program Risks
• Ranking Program Risks
• Managing Program Risks
• Managing Action Plans
• Continuously Assessing Program Risks.
More details about the process are described in the annotated briefing, Establishing A
Program Risk Baseline.
Planning for Risk Assessment
The first stage of a risk assessment is to plan the activity. A program manager may begin this process by selecting the risk assessment team, setting forth ground rules, and determining the supporting risk management tools. The risk assessment team should include representatives from all areas of the program, not just technical experts. In addition, a facilitator and recorder should be selected to assist the team.
Identifying Program Objectives or Requirements
Once the Program Manager identifies the risk assessment team and tools, the team identifies the key program objectives or requirements. The program objectives and requirements should assist the team in identifying risks.
Defining Program Risks
A team facilitator leads the team through a structured brainstorming process to identify the program risks. For example, each team member individually writes down risk ideas. Next, the facilitator asks each person to present one idea in sequence or pass in a rotation until all candidate risks are offered. Once all ideas are heard, an affinity diagram is created to group, merge, and eliminate duplicate risks, and to identify dependent risks. An affinity diagram is "…a technique for organizing verbal information into a visual pattern." The facilitator has the team silently arrange candidate risks into related groups of one or more risks. Through this process, risks may be merged if similar or dependent, and eliminated if the same.
Next, the team agrees on category titles for each group. Collaboratively the team identifies complete risk statements for each risk on the affinity diagram. A suggested format for a complete risk statement may be in the form of “If a risk condition, then the consequences.” The recorder documents each complete risk.
Following the identification of the risks, the team assigns various attributes to each risk. At a minimum, relevant time frame, impact, and probability of occurrence are assigned. Time frame is the beginning and end dates of when a risk may occur. Then the team sets impact definitions.
The Risk Matrix impact definitions are:
C (Critical): If the risk event occurs, the program will fail. Minimum acceptable requirements will not be met.
S (Serious): If the risk event occurs, the program will encounter major cost/schedule increases. Minimum acceptable requirements will be met. Secondary requirements may not be met.
Mo (Moderate): If the risk event occurs, the program will encounter moderate cost/schedule increases. Minimum acceptable requirements will be met. Some secondary requirements may not be met.
Mi (Minor): If the risk event occurs, the program will encounter small cost/schedule increases. Minimum acceptable requirements will be met. Most secondary requirements will be met.
N (Negligible): If the risk event occurs, it will have no effect on the program. All requirements will be met.
Probability of occurrence is the team’s assessment of the likelihood of a risk happening. Estimating the probability of occurrence may be difficult in practice. Fortunately, all that matters when using Risk Matrix is the relative order of the probability estimates (which risks are more likely to occur). For this purpose, it is sufficient to estimate probabilities using a relative scale:
• 0-10%: very unlikely the risk will occur
• 11-40%: unlikely the risk will occur
• 41-60%: even likelihood the risk will occur
• 61-90%: likely the risk will occur
• 91-100%: very likely the risk will occur.
This approach may be used to translate subjective probability estimates into numbers in the absence of hard data. However, if hard data is available for some risks, the other probability estimates must be chosen to be consistent with the hard data.

## Issues
Issues Log
Project: |  | Project Title Here |  | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here |  | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here |  | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
ID | Issue Description | Project Impact | Action Plan/Resolution | Owner | Importance | Date Entered | Date to Review | Date Resolved
1 | What is the issue? | How will this impact scope, schedule & cost? | How do you intend to deal with this issue? | Who manages this issue?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
Note on G6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
Issue Log (Form)
Resolve Project Issues quickly and efficiently by using this Issue Log Form.
Regardless of the project management issues experienced, this Issue Log will help you to record each issue clearly and take action to resolve it.
By using this Issue Log Form, you can resolve project management issues with ease, helping you to deliver your project on time and within budget.
This project management Issue Log Form will help you to:
* Identify issues throughout the project life cycle
* Complete a detailed description of each issue
* Assess the impact that issues are having on the project
* Recommend the actions needed to resolve issues
* Gain management approval for these actions
You can also use this Issue Log Form to:
* Monitor and control all issues within the project
* Report business critical issues to senior management
* Ensure your project is not delayed by issues which arise
* Resolve issues more quickly and easily than before
To ensure you meet your objectives, you need to resolve project issues before they have an effect on your project. Otherwise they can result in delays, additional costs and risk of non-delivery. Instead, using this Issue Log Form to record all issues as they arise, you can speedily resolve each issue and ensure that your project remains on track.
What is an Issue Form?
An Issue Form is filled in by a team member to formally raise issues to their manager. While an Issue Form is used to raise project management issues, an Issue Form may equally be used to raise operational issues to management for resolution.
When do I use an Issue Log Form?
An Issue Log Form should be used when you have issues that need to be resolved immediately. On the Issue Log Form, you can specify a description of the issue, its impact on your role and recommended actions for resolving it. The Issue Log Form should then be presented to management for approval. Once approved, the actions stated on the Issue Log Form can be completed. This Issue Log Form helps you resolve issues quickly and easily.

## Action
Action Items
Project: |  | Project Title Here |  |  | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here |  |  | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
ID | Action Item | Owner | Status | Date Entered | Planned Completion | Actual Completion | Comments
1 | What is the item to be completed? | Who manages this issue?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Note on D6: Options are: Open Closed
Action Items Tracking
The Action Items sheet allows you to track and monitor action items assigned to team members. Action items are tasks that must be done but are too insignificant from a time perspective to track in your project schedule.

## Deliverables
Deliverable Milestones
Project: |  | Project Title Here |  |  | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here |  |  | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
ID | Milestone | Description | Planned Completion | Actual Completion | Objectives | Assumptions | Constraints
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Milestone Deliverables
Milestone achievement needs deliverables. Was it achieved on time and how are costs progressing, have all the deliverables arrived...
When looking at monitoring project management cost and timescale the best measure is the 'milestone'. Remember 'only promise what you know you can deliver'.
The Project Manager needs to know how the project is progressing. It isn't good enough for team members to say certain activities are complete. What does this mean? Without evidence there is no proof that a particular point in the project has been reached.
Deliverables provide this evidence.
It would be impractical to produce deliverables for every task in a schedule. So, when is it best to have them? They are best defined at key milestones in the project.
Clearly the number will depend upon the nature of the project. A large project may require them monthly, whereas a 2 month project may need them weekly. There may be natural breaks in the project leading to milestones e.g. the completion of a phase of work.
The decision on the number of milestones will aid in project control. A project that is 'getting away' from the Project Manager may indicate that more milestones are required.
These are a measure of the progress of a project and as such are tangible items.
It may not be good enough to say that a phase of a project has been completed as this is often subjective and open to misinterpretation. Deliverables need to be well defined and agreed and could include reports, prototypes, other documents etc.
As an aid to monitoring project progress it is a good idea to produce deliverables at interim points, usually in support of the end of a particular phase.
If you produce a prototype make sure it is not suddenly mistaken for the end product. It is what it says, a prototype. Once the prototype has been completed remove it so no one mistakes it for the end product. .
MILESTONES AND DELIVERABLES:
Managers need information. As software is intangible, this information can only be provided as document that describes the state of the software being developed. Without this information, it is important to judge progress and cost estimates and schedules cannot be updated.
When planning a project, a series of milestones should be established where a milestone is an end-point of a software process activity. At each milestone, there should be a formal output, such as a report, they can be represented to management. Milestone reports don't need large documents. They may simply be a short report of achievements in a project activity. Milestones should represent the end of a distinct, logical stage in the project. Indefinite milestones such as "Coding 80% complete" which are impossible to validate are useless for project management.
A "deliverable" is a project result that is delivered to the customer. It is usually delivered at the end of some major project phase such as specification, design, etc.
Deliverables are usually milestones but milestones need not to be deliverables. Milestones may be internal project results that are used by the major project manager to check project progress but which are not delivered to the customers.
To establish milestones, the software process must be broken down into basic activities with associated outputs.

## Project Milestones Schedule
Project Milestones
Project: | Project Title Here |  | Project #: | Project Number Here
Project Manager: | Project Manager Name Here |  | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
Date | Milestone if any | Height | Dummy | Milestone
2009-05-01 | Project Kickoff | 1 | 0 | Project Kickoff
2009-06-01 | First Prototype | 2 | 0 | First Prototype
2009-07-01 | Executive Review | 2.5 | 0 | Executive Review
2009-08-01 | Investor Presentation | 3 | 0 | Investor Presentation
2009-09-01 | Alpha Out | 4 | 0 | Alpha Out
2009-10-01 | Feed Back | 3.5 | 0 | Feed Back
2009-11-01 | Private Beta Out | 3 | 0 | Private Beta Out
2009-12-01 | Public Beta | 2 | 0 | Public Beta
2010-01-01 | User Manual | 1.5 | 0 | User Manual
2010-02-01 | Roll-out | 1 | 0 | Roll-out
2010-03-01 | Post Report | 0.5 | 0 | Post Report
2010-04-01 | Close-out | 0.25 | 0 | Close-out
2010-05-01 | Plan for Future | 2 | 0 | Plan for Future

## Gantt Box Schedule
Gantt Box Project Schedule
Project: |  | Project Title Here |  |  | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here |  |  | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
Task | Start | Best Case | Realistic | Worst Case | Start2 | Realistic3 | Worst
Project Kickoff | 2010-06-01 | 2010-06-05 | 2010-06-09 | 2010-06-14 | 4 | 4 | 5
Gather Requirements | 2010-06-06 | 2010-06-13 | 2010-06-18 | 2010-06-23 | 7 | 5 | 5
Design Module 1 | 2010-06-11 | 2010-06-17 | 2010-06-20 | 2010-06-27 | 6 | 3 | 7
Design Module 2 | 2010-06-11 | 2010-06-16 | 2010-06-19 | 2010-06-26 | 5 | 3 | 7
Develop | 2010-06-20 | 2010-06-29 | 2010-07-15 | 2010-07-22 | 9 | 16 | 7
Test | 2010-07-21 | 2010-07-27 | 2010-07-29 | 2010-08-05 | 6 | 2 | 7
Implement | 2010-08-08 | 2010-08-14 | 2010-08-16 | 2010-08-23 | 6 | 2 | 7
Formulas:
Worst Case = [Realistic]+7
Best Case = [Start]+6
Realistic = [Best Case]+2
Start = [Worst Case, row above]+3
How to use this?
1) Set up your project plan using the table staring in row 10.
2) Just enter first 5 columns of dates.
3) Last 3 columns are calculated. Do not mess with them.
4) If you have Excel 2007 or above, the calculated columns should automatically update when you add new rows to the table.
6) The chart now shows the project plan as a Gantt Box Chart.
7) Adjust horizontal / date axis scaling and major units to see dates clearly.

## CPM Schedule
Critcal Path Method
Project: |  | Project Title Here | [5 empty] | Project #: |  | Project Number Here
Project Manager: |  | Project Manager Name Here | [5 empty] | Sponsor: |  | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here | [5 empty] | Last Update: |  | Date of Last Update
Accounting Code: |  | PLCF0011
| Start Date |  | Duration
| 2010-01-11 08:00 |  | 20 | Days
Finish Date
| 2010-01-31 08:00 |  | 4 | Weeks
Times (in Days)
[6 empty] | Time Distribution: | Triangular | [5 empty] | [42] | [28 empty] | Series Used in the Gantt Chart | [7 empty] | Weeks | Days
ID | Task Name | Predecessors (Enter one ID per cell) |  |  | O (min) | M (most likely) | P (max) | Duration (exp. time) | ES | EF | LS | LF | Slack | EF of Predecessors | [9 empty] | Successors | [8 empty] | LS of Successors | [8 empty] | ES | Critical | +T | -T | Duration | +T | -T | Slack | Events | Events | Axis
10 | Start | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20 | 30 | [7 empty] | 0 | 3.6667 | [6 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | -0.5
20 | Task A | 10 |  |  | 2 | 4 | 6 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 40 | 50 | [7 empty] | 4 | 8.3333 |  |  |  |  | 0 | 4 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 0.5
30 | Task B | 10 |  |  | 3 | 5 | 9 | 5.6667 | 0 | 5.6667 | 3.6667 | 9.3333 | 3.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 60 | [8 empty] | 9.3333 |  |  |  | 0 | #N/A | #N/A | #N/A | 5.6667 | 3.3333 | 2.6667 | 3.6667 | #N/A | #N/A | 1.5
40 | Task C | 20 |  |  | 4 | 5 | 7 | 5.3333 | 4 | 9.3333 | 4 | 9.3333 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 60 | [8 empty] | 9.3333 |  |  |  | 4 | 5.3333 | 1.6667 | 1.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 2.5
50 | Task D | 20 |  |  | 4 | 6 | 10 | 6.6667 | 4 | 10.6667 | 8.3333 | 15 | 4.3333 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 70 | [8 empty] | 15 |  |  | 4 | #N/A | #N/A | #N/A | 6.6667 | 3.3333 | 2.6667 | 4.3333 | #N/A | #N/A | 3.5
60 | Task E | 30 | 40 |  | 4 | 5 | 7 | 5.3333 | 9.3333 | 14.6667 | 9.3333 | 14.6667 | 0 | 5.6667 | 9.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 80 | [8 empty] | 14.6667 |  | 9.3333 | 5.3333 | 1.6667 | 1.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 4.5
70 | Task F | 50 |  |  | 3 | 4 | 8 | 5 | 10.6667 | 15.6667 | 15 | 20 | 4.3333 | 10.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 90 | [8 empty] | 20 | 10.6667 | #N/A | #N/A | #N/A | 5 | 3 | 2 | 4.3333 | #N/A | #N/A | 5.5
80 | Task G | 60 |  |  | 3 | 5 | 8 | 5.3333 | 14.6667 | 20 | 14.6667 | 20 | 0 | 14.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 90 | [8 empty] | 20 | 14.6667 | 5.3333 | 2.6667 | 2.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 6.5
90 | Finish | 70 | 80 |  |  |  |  | 0 | 20 | 20 | 20 | 20 | 0 | 15.6667 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4 | 20 | 7.5
[42]
Note on B14: Task ID: Normally, you would start by assigning IDs as 10, 20, 30, etc. However, the ID can be anything you want, including text.
Note on C14: Task Name: The task name is a description that will show up in the gantt chart. The task name will be bolded if the task is a critical task. This is done through conditional formatting.
Note on D14: Predecessors: The set of events immediately preceding the task. In a network diagram or PERT chart, the predecessors for a particular task are all the tasks which have arrows pointing to that particular task. - Each predecessor needs to refer to the ID in column A. - If you need more than 6 predecessors, you can unhide columns I-L to increase the amount to 10. Successors: The set of events immediately following a particular task. In a network diagram or PERT chart, arrows are drawn from a task to its successors.
Note on N14: Optimistic Time (O): The minimum time required to complete the task. Assumes that everything proceeds faster than normal.
Note on O14: Most Likely Time (M): The most likely time required to complete the task, assuming everything proceeds as normal.
Note on P14: Pessimistic Time (P): The maximum time required to complete the task. Assumes that everything proceeds faster than normal.
Note on Q14: Duration or Expected Time: Using a Beta distribution, where O is the minimum, P is the maximum, and M is the most likely value, the formula for calculating the mean or expected time is: Duration = (O+4M+P)/6 Using a Triangular distribution, the mean of the distribution would be: Duration = (O+M+P)/3
Note on R14: Early Start Time: The ES is the maximum EF of all predecessors, except for the first task where the ES=0.
Note on S14: Early Finish Time: The EF time is the ES time plus the duration (EF=ES+Duration).
Note on T14: Late Start Time: The LS time is calculated as the LF time minus the duration (LS=LF-Duration).
Note on U14: Late Finish Time: The LF time is the minimum LS of all the successors, except for the last task where LF equals EF.
Note on V14: Slack Time: The Slack time is calculated as LF minus EF. It can also be calculated as LS minus ES. If the slack is zero, then the task is on the critical path.

## Panel Chart
Data Defect Panel Charts
Project: |  | Project Title Here |  |  | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here |  |  | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
Regular Charts
Panel Charts
DATA TABLE | [5 empty] | Comments
New Defects in Modules for Last 4 Weeks | [5 empty] | Type in comments here regarding the chart analysis.
Week | Week | Defects | Patch 1 | New Defects | Patch 2
W1 | W1 | 100 | 90 | 34 | 16
| W2 | 120 | 93 | 30 | 21
| W3 | 130 | 24 | 32 | 42
W4 | W4 | 140 | 12 | 31 | 3
New Defects in Modules for Last 4 Weeks
New Defects in Modules for Last 4 Weeks
Excel Panel Charts
Use this template to create Executive management reports for your project. Simply change the chart titles and values in the Data Table as you need. Remember always save a back-up copy when working with charts for they can act quirky.

## Project Org
Project/Governace Organizational Chart
Project: | Project Title Here | Project #: | Project Number Here
Project Manager: | Project Manager Name Here | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
Project
Manager
Business Analysis Manager
Engineering Manager
Implementation Manager
Training
Manager
Software
Vendor Project Manager
Project Business Analysis Manager
Coordinator
Internal
Team
Consulting
Staff
Software Development Team
Hardware / Networking
Team
Internal
Staff
Vendor
Staff
Consulting
Staff

## WBS
Work Breakdown Structure
Project: |  | Project Title Here |  |  |  | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here |  |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here |  |  |  | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
ID | Task | Dependencies | Status | Effort Hours | Cost | Start Date | Planned Completion | Estimate to Completion | Actual Completion | Resource
1 |  | ID # of task
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Note: Suggest using Microsoft Project, Visio and other WBS software to replace this form.
Note on D6: Options are: Open Closed
WBS
The Work Breakdown Structure is a tree structure, which shows a subdivision of effort required to achieve an objective; for example a program, project, and contract. In a project or contract, the WBS is developed by starting with the end objective and successively subdividing it into manageable components in terms of size, duration, and responsibility (e.g., systems, subsystems, components, tasks, subtasks, and work packages) which include all steps necessary to achieve the objective.
The Work Breakdown Structure provides a common framework for the natural development of the overall planning and control of a contract and is the basis for dividing work into definable increments from which the statement of work can be developed and technical, schedule, cost, and labor hour reporting can be established.
A work breakdown structure permits summing of subordinate costs for tasks, materials, etc., into their successively higher level “parent” tasks, materials, etc. For each element of the work breakdown structure, a description of the task to be performed is generated. This technique (sometimes called a System Breakdown Structure) is used to define and organize the total scope of a project.
The WBS is organised around the primary products of the project (or planned outcomes) instead of the work needed to produce the products (planned actions). Since the planned outcomes are the desired ends of the project, they form a relatively stable set of categories in which the costs of the planned actions needed to achieve them can be collected. A well-designed WBS makes it easy to assign each project activity to one and only one terminal element of the WBS. In addition to its function in cost accounting, the WBS also helps map requirements from one level of system specification to another, for example a requirements cross reference matrix mapping functional requirements to high level or low level design documents.

## WBS Chart
Work Breakdown Structure Chart
Project: | Project Title Here | Project #: | Project Number Here
Project Manager: | Project Manager Name Here | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
WBS Chart
The Work Breakdown Structure is a tree structure, which shows a subdivision of effort required to achieve an objective; for example a program, project, and contract. In a project or contract, the WBS is developed by starting with the end objective and successively subdividing it into manageable components in terms of size, duration, and responsibility (e.g., systems, subsystems, components, tasks, subtasks, and work packages) which include all steps necessary to achieve the objective.
The Work Breakdown Structure provides a common framework for the natural development of the overall planning and control of a contract and is the basis for dividing work into definable increments from which the statement of work can be developed and technical, schedule, cost, and labor hour reporting can be established.
A work breakdown structure permits summing of subordinate costs for tasks, materials, etc., into their successively higher level “parent” tasks, materials, etc. For each element of the work breakdown structure, a description of the task to be performed is generated. This technique (sometimes called a System Breakdown Structure) is used to define and organize the total scope of a project.
The WBS is organised around the primary products of the project (or planned outcomes) instead of the work needed to produce the products (planned actions). Since the planned outcomes are the desired ends of the project, they form a relatively stable set of categories in which the costs of the planned actions needed to achieve them can be collected. A well-designed WBS makes it easy to assign each project activity to one and only one terminal element of the WBS. In addition to its function in cost accounting, the WBS also helps map requirements from one level of system specification to another, for example a requirements cross reference matrix mapping functional requirements to high level or low level design documents.
Mgmt. Tracking System
1
Initiation
1.1
Planning
1.2
Execution
1.3
Control
1.4
Create Preliminary Scope Statement
1.2.1
Closeout
1.5
Evaluation & Recommendations
1.1.1
Develop Project Charter
1.1.2
Deliverable: Submit Project Charter
1.1.3
Project Sponsor Reviews Project Charter
1.1.4
Project Charter Signed/Approved
1.1.5
Determine Project Team
1.2.2
Project Team Kickoff Meeting
1.2.3
Develop Project Plan
1.2.4
Submit Project Plan
1.2.5
Milestone: Project Plan Approved
1.2.6
Project Kickoff Meeting
1.3.1
Verify & Validate User Requirements
1.3.2
Design System
1.3.3
Procure Hardware/Software
1.3.4
Install Development System
1.3.5
Testing Phase
1.3.6
Install Live System
1.3.7
User Training
1.3.8
Go Live
1.3.9
Project Management
1.4.1
Project Status Meetings
1.4.2
Risk Management
1.4.3
Update Project Management Plan
1.4.4
Audit Procurement
1.5.1
Document Lessons Learned
1.5.2
Update Files/ Records
1.5.3
Gain Formal Acceptance
1.5.4
Archive Files/ Documents
1.5.5

## Roster
Roster
Project: |  | Project Title Here |  |  | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here |  |  | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
Name | Core/ Extended Team | Title | Dept. | Phone | Cell Phone | E-Mail | Project Role

## RASCI
RASCI Chart
(Responsible, Accountable, Supportive, Consulted, Informed)
Project: | Project Title Here |  |  | Project #: | Project Number Here
Project Manager: | Project Manager Name Here |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  |  | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
Functional Roles
Activity | Project Sponsor | Business Project Owner | IT Project Owner | IT Business Partner | Business SME | Business Project Manager | IT Project Manager
Project Proposal Document | A | S | C | R | C | I | I
Project Kick Off Meeting | I | I | S | C | I | I | R
Business Requirements Document | I | A | C | R | C | S | I
Functional Spec Document | I | A | R | S | C | S | I
Vendor Recommendation | I | A | R | C | C | I | I
Project Charter | I | C | A | C | I | C | R
Financial Review & Approval | A | S | R | S | I | I | S
Baseline Project Schedule | I | A | S | I | S | S | R
RASCI Definitions: |  |  |  | Stakeholder Definitions:
R - Responsible. Owns the work, process, issues or resource to complete the activity |  |  |  | • Project Sponsor - Person funding the project
A - Accountable. Approves costs, scope and in some cases the timeline. It is assumed that the Approver has financial authority or prior financial approval. |  |  |  | • Business Project Owner - Person who owns the implementation of the project or product for the business.
S - Supportive. Provides resources or can play a supporting role in implementation. |  |  |  | • IT Project Owner - Person who owns the IT implementation of the project and the technical support of the final solution.
C - Consulted. Has information and/or capability needed to complete the work. |  |  |  | • IT Business Partner - Person who liases between the business and IT.
I - Informed. Must be notified on results, but do not needn to be involved in the decision-making process. |  |  |  | • Business SME - Person who provides expertise in requirements gathering and overall expertise in the product or solution.
• Business Project Manager - Person who coordinates the project deliverables from the business side.
• IT Project Manager - Person who coordinates the IT components of the project.
Using RACI Charts to Improve Processes
With all the pressures on IT to deliver effective, efficient and economical services that also are compliant, process design is more important than ever.
In understanding current processes, as well as designing new processes, it is vital to recognize the roles and responsibilities required. To this end, processes can be flow-charted and then mapped using a RACI chart in order to understand and clarify responsibilities.
The RACI chart (pronounced “racey”) allows for each task step to be identified; then each stakeholder and their responsibilities can be identified. The resulting chart can be scrutinized for opportunities for improvement.
With a standard RACI, there are four responsibilities and issues to consider with each opportunity:
• Responsible [R] – This is the person or group responsible for performing a task. Bear in mind the adage that when nobody is responsible for getting something done, then nothing gets done. Also, a similar situation can occur when too many people are potentially responsible with little to no coordination and oversight to ensure that the task is completed. Another issue to consider is when a person has lots of “R’s”. Are they doing too much?
• Accountable [A] – This is the person who is held accountable for the task being complete. In some cases, risks can be managed by segregating the responsible and accountable roles. In general, one person should be accountable for a task being performed. At the same time, if a person is accountable for most of the steps in a procedure, one must consider if there is a segregation of duties issue wherein the person(s) controls too much.
Supports [S] - Some groups add this in as a fifth responsibility. “S” identifies a person or group who provide resources for a task to be completed. When charts include this category, they are referred to as “RASCI charts,” but otherwise are identical to RACI charts.
• Consulted [C] – These are the people communicated with prior to a task being performed. Essentially, their input is sought and factored in prior to any action. As the number of parties consulted increases, the speed with which action can be taken decreases. Conversely, too few and improper decisions may be made.
• Informed [I] – These are the parties who are notified about a task after it has been performed. If the correct parties aren’t informed in some situations, then incidents can arise from groups wondering what changed. At the same time, if there are lots of people being informed, is it necessary?
RACI charts are very useful both in terms of understanding the current responsibilities within a given process and also for discussing revised processes, clarifying roles and responsibilities, etc.
Now, let’s take an example process and use the RACI technique to identify responsibilities for each task and role combination.
Step 1: The business manager is both responsible for completing a new user form and is accountable for it being complete. The system owner is informed of the new request form being initiated.
Step 2: The system owner is both responsible and accountable for the review and approval of the new user account form. Security is consulted with to ensure the request is consistent with current security policies. Finally, Security is notified of the authorized form as is the Service Desk. (Note, for simplicity we aren’t covering the rejection of a request which would be another branch in the flow chart for this particular procedure.
Step 3: The Security group is responsible for the creation of the user profile on the system in question. The IT Manager for the department is held accountable for the task being completed according to defined standards. Note that the accountability lies with one person ideally. Diffused accountability reduces accountability! In addition, after the account has been created, the Business Manager and the Service Desk are informed of the task being completed.
Step 4: The documentation supporting the request is then filed according to defined standards by the Security group and, again, the IT Manager is accountable for the task being completed. The Service Desk is informed that the documentation has been appropriately filed, which essentially means the work has been completed in this case. Step 5: The Service Desk is then responsible for informing the Business Manager that the new user account has been successfully created.
When reviewing the charts, look vertically down the columns to see how each stakeholder is involved. Additionally, look horizontally at how each stakeholder is involved with each task. Look for lack of accountability, excessive workload, and segregation of duties issues, too many people being informed or consulted, and so on.
In closing, when attempting to understand processes, both those currently in place as well as new ones, RACI charts can be a useful tool in their formal documentation and then discussion with groups to try and ensure proper design.

## R&R
Roles and Responsibilities
Project: | Project Title Here |  |  |  | Project #: | Project Number Here
Project Manager: | Project Manager Name Here |  |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  |  |  | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
Name | Core/ Extended Team | % Assigned | Deliverables Leading | Deliverables Participating On | Project Role | Responsibility | Other Project Assignments
Standard Roles and Responsibilities
This describes typical roles and responsibilities for projects. Roles may be assigned to one or more individuals. Conversely, individuals may play one or more roles.
1.1 Sponsor
1) Has ultimate authority and responsibility for a project or program
2) Provides funding for the project (initial funding, additional funds)
3) Approves changes to scope, as required
4) Removes obstacles that prevent the project from moving forward
5) Approves scope, project role matrix, schedule, milestone, deliverables, etc.
6) If project is a strategic initiative, provides updates to Executive Steering Committee.
1.2 Steering Team / Advisory Team
1) Provides information and expert advice about campus plans for other projects or system developments that impact project timelines, deliverables, or resources
2) Advises on strategic partnerships
3) Provides campus wide leadership in support of the project
4) Advises/resolves issues escalated by the Project Manager or core team
5) Resolves or forwards policy issues to appropriate decision-making bodies
1.3 Core Team
1) Meets regularly to review issues and monitor project progress
2) Provides status updates on open action items
3) Approves investigation of proposed change requests
4) Reviews and makes recommendations on change orders
5) Reviews and approves/rejects change requests
1.4 Customer Project Director
1) Participates in the development of the project plan (includes but not limited to scope with deliverables, project acceptance criteria, project role matrix, and schedule) in collaboration with the Customer Project Lead, IT Project Director and Project Manager
2) Coordinates and ensures the availability of functional resources to participate in the project
3) Participates in budget development
4) With IT Project Director and Project Manager, presents draft scope, project role matrix, and schedule (milestones) to Project Sponsor for approval
5) Responsible for working with Project Sponsor to acquire project funding and additional funding, as needed
6) If ITSS is tracking budget, works with IT Project Director/Sponsor to acquire approval to spend funds
7) If Customer is tracking budget, works with IT Project Director/Sponsor to acquire approval to spend funds; notifies Customer accountant to spend funds.
8) Works with IT Project Director in vendor/contract negotiations
9) Works with Purchasing Dept for procurement of product and services that are not on state contract
10) Completes IT approval form for computer-related purchases exceeding the BOR threshold and sends to IT for approval
11) Collaborates with Project Manager, IT Project Director, and others, as needed, regarding issues and unplanned expenditures that may impact the budget
12) Attends and actively participates in core team and sponsor update meetings
13) Responsible for making decisions in a timely manner, outside of regularly scheduled meetings, as customer project-related decisions are needed
14) Keeps upper management informed of project status
15) Removes obstacles to project progress
16) Work with Project Manager, IT Project Director, and Customer Lead as needed, to resolve issues
17) Approves change orders; and presents those change orders which impact the project scope, for the Sponsor’s approval.
Standard Roles and Responsibilities
1.7 Customer Project Lead
1) Assigned by the Customer to participate in project activities
2) Responsible for contributing to overall project objectives
3) Participates in the development of the project plan (includes but not limited to scope with deliverables, project acceptance criteria, project role matrix, and schedule) in collaboration with the project directors and Project Manager
4) Participates in budget development, as needed
5) Liaise with the Project Manager to ensure that all required functional activities of the Business Units are incorporated into the project plan
6) Responsible for ensuring that all stakeholders are identified and included in the public relations communication plan
7) Attends and actively participates in core team meetings
8) Notifies Project Manager of any risks and issues
9) Works with Project Manager to resolve identified risks and issues
10) Responsible for making and communicating decisions in a timely manner.
11) Provide overall leadership for functional teams to ensure that all required functional areas of the Business Units are incorporated into the project
12) Responsible for working with the Customer Project Director in developing the Business Continuity Plan
13) Responsible for working with the Customer Project Director in developing the Business Units portion of the Disaster Recovery plan
1.8 Team Lead
1) Manages the team and vigorously pursues the team’s given objectives (i.e. project tasks)
2) Provides regular status updates to the Project Manager, including but not limited to task start and end dates, estimated time to completion, cause of variances, etc., as defined by the project
3) Attends and actively participates in project team meetings
4) Obtains estimates for change requests and change orders and provides to Project Manager
5) Responsible for contributing to overall project objectives and specific team deliverables
6) Contributes to project plan development in collaboration with project manager
7) Ensures tasks for their team are completed on time
8) Schedules and conducts routine team meetings with project team and provides them status updates and project documentation, when necessary
9) Coordinates team activities related to project plan
10) Provides forecast estimates of work to complete to project manager
11) Notifies Project Manager of any issues and risks
12) Works to resolve issues and address identified risks
13) Responsible for making and communicating decisions in a timely manner.
14) Advises Project Manager of potential schedule task delays
15) Escalates issues to project manager for referral to appropriate policy making bodies
16) Coordinates completion of the Information Security Review form (Technical Team Lead)
1.9 Team Member
1) Contributes to project schedule development in collaboration with project manager
2) Responsible for contributing to overall project objectives and specific team deliverables
3) Escalates issues to team lead
4) Attends and actively participates in team meetings
5) Provides estimate to complete for assigned activities and updates remaining work Maintains appropriate records of work in progress which includes any necessary documentation
6) Notifies the team lead of any expected difficulties or issues arising
7) Responsible for making and communicating decisions in a timely manner.
Standard Roles and Responsibilities
1.5 IT Project Director
1) Participates in the development of the project plan (includes but not limited to scope with deliverables, project role matrix, and schedule) in collaboration with Customer Project Director, Customer Project Lead and Project Manager
2) Participates in budget development, as needed
3) With Customer Project Director and Project Manager, presents draft scope, project role matrix, and schedule (milestones) to Project Sponsor for approval
4) Responsible for working with Customer Project Director and Project Sponsor to acquire additional project funding, as needed
5) If ITSS is tracking budget, works with Customer Project Director/Sponsor to acquire approval to spend funds; notifies IT Accountant to spend funds
6) If Customer is tracking budget, works with Customer Project Director/Sponsor to acquire approval to spend funds; Customer Project Director notifies their accountant to spend funds.
7) Works with Customer Project Director in vendor/contract negotiations
8) Works with Purchasing Dept for procurement of product and services that are not on state contract
9) Obtains IT approval for computer-related purchases
10) Collaborates with Project Manager, Customer Project Director, and others, as needed, regarding issues and unplanned expenditures that may impact the budget
11) Attends and actively participates in core team and sponsor update meetings
12) Responsible for making and communicating decisions in a timely manner, outside of regularly scheduled meetings, as IT project-related decisions are needed
13) Keeps upper management informed of project status
14) Removes obstacles to project progress
15) Works with Project Manager, Customer Project Director, and Customer Lead as needed, to resolve issues
1.6 Project Manager
1) Reports to and receives direction from Sponsor and/or Project Directors
2) Participates in the development of the project plan (includes but not limited to scope with deliverables, project acceptance criteria, project role matrix, and schedule) in collaboration with the project directors, resource managers, and Customer Project Lead
3) Maintains project plan (scope, project acceptance criteria, project role matrix, schedule, etc.)
4) Participates in development of project plan deliverables
5) Participates in budget development, as needed
6) Responsible for identification of project team roles and works with resource managers and Customers to construct project teams.
7) Provides an orientation to the assigned project resources on the Project Role Matrix including their roles and responsibilities.
8) Ensures all given objectives and responsibilities of the team are properly documented and approved
9) Works with resource managers to schedule project resources
10) Manages assigned staff, vendors and contractors
11) Creates regular status reports and distributes to core team
12) Recommends resource and policy changes to the Steering Committee
13) Conducts regular core team meetings to review issues and monitor project progress
14) Motivates and coaches team leads and team members
15) Monitors contract compliance
16) Documents and maintains change requests
17) Analyzes change request impacts to schedule, budget, and resources
18) Presents change orders to Project Directors
19) Conducts risk management analysis
20) Conduct ongoing cost analysis of the project
21) Provides reports to senior management as needed - such as milestone reports, project cost analysis reports, etc.
22) Escalates issues to Project Director(s) for referral to appropriate policy making bodies
23) Documents issues and obtains updates
24) Works with IT Project Director in vendor/contract negotiations
25) Removes obstacles to project progress

## RAM
Responsibility Assignment Matrix
Project: | Project Title Here |  |  |  | Project #: |  |  |  | Project Number Here
Project Manager: | Project Manager Name Here |  |  |  | Sponsor: |  |  |  | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  |  |  | Last Update: |  |  |  | Date of Last Update
Accounting Code: | PLCF0011
|  | Business End Users | Business Sponsor | IT Sponsor | Business Driver | Business Project Lead | Project Manager | Business Sys. Analyst | Data Modeler | DBA | Data Staging Designer | Trainer | Appl'n Developer | Tech/Security Architect | Tech Support Specialist | Data Staging Programmer | Data Steward | QA Analyst
Project Management and Requirements
Project Task
Initiation
1 | Develop preliminary project scope
2 | Identify business need
3 | Develop preliminary budget
4 | Identify preliminary return on investment
5 | Complete project charter
Planning
1 | Establish project identity
2 | Identify project team/resources
3 | Conduct stakeholder analysis
4 | Prepare draft project schedule
5 | Conduct project kickoff meeting
6 | Gather detailed user requirements
7 | Define current business processes (as is)
8 | Revise project schedule
9 | Develop project communication plan
10 | Develop project organizational structure
11 | Identify training plan
12 | Develop project quality plan
13 | Develop scope management plan
14 | Develop risk management plan
15 | Develop change management plan
16 | Develop cost management plan
17 | Develop schedule management plan
18 | Develop technical specifications
19 | Develop technical architecture
20 | Conduct project procurement
21 | Finalize project budget
22 | Finalize return on investment
23 | Ongoing project management
Execution
1 | Develop training materials
2 | Execute communication plan
3 | Develop software
4 | Develop new business processes (to be)
5 | Deploy new software
6 | Conduct training
Closing
1 | Get deliverable acceptance
2 | Close out contracts
3 | Finalize budget
4 | Finalize return on investment
5 | Conduct closure survey
6 | Conduct/document lessons learned
7 | Archive project
What is the Responsibility Assignment Matrix (RAM)?
So you've constructed your work breakdown structure (WBS) and your organizational breakdown structure (OBS). You have a schedule tentatively made. What's missing? Perhaps you should create a responsibility assignment matrix as well, which also known referred to as a RACI or RASCI. The responsibility assignment matrix links activities to resources. It makes sure that every task is completed by someone. The matrix itself is a chart you can create using Microsoft Excel listing human resources across the top and activities down the left-hand side. The matrix can be as simple as placing a check mark under the resources name for a particular task, or it can get more complicated, indicating precisely which role any given resource has in completing the task.
Why Should you Use a Responsibility Assignment Matrix?
I already mentioned the benefit of knowing exactly whom is responsible for what when using a responsibility assignment matrix. This, while the main reason for creating this beneficial chart, isn't the only reason you might want to create it. By creating a responsibility assignment matrix, you can quickly see whether you have enough resources to complete the project in the time allotted. You can also avoid confusion - especially if you use the roles listed below - over who is assigned to do what when. This prevents Joe from saying "But I thought it was assigned to Mary." Finally, when trying to gain funding for your project, you can paint a realistic picture for perspective investors by showing exactly how many resources are required to finish the project.
How do you Create Responsibility Assignment Matrix? RAM
The first step in creating a responsibility assignment matrix is to decompose your project and create a work breakdown structure. Once you have completed this important first step, you will know what the project deliverables will be. If you compose an organizational breakdown structure - breaking the project down into a hierarchy of departments, it will facilitate the process of assigning deliverables to responsible parties. Creating this second chart is an option that is highly recommended.
Once you have the list of deliverables, go down the left-hand side list each deliverable. If there were intermediate deliverables discovered in the process of creating the work breakdown structure, list those as well.
After listing each deliverable down the side, list each resource across the top of the table.
Now, you will assign deliverables to resources using the following code for roles:
• A - Approves the deliverable
• R - Reviews the deliverable (and provides feedback).
• C - Creates the deliverable (could be C (1) for primary, C (2) for backup). Usually there is only one person who is responsible for creating a deliverable, although many people may provide input.
• I - Provides input
• N – Is notified when a deliverable is complete
• M - Manages the deliverables (such as a librarian, or person responsible for the document repository)
In assigning roles, you will use at least the first four listed above RACI. Assign each deliverable to at least one responsible party. Assign each deliverable exactly one accountable party. Continue until everything has been assigned. Distribute the responsibility assignment matrix monist the staff and make explicit your expectations for each of them.
Legend:
A: Approves the deliverable
R: Reviews
C: Creates and or C1 primary, C2 Backup
I: Provides input
N: Is notified when deliverable is complete
M: Manages the deliverables

## Timesheet
Team Member Timesheet
Project: | Project Title Here |  |  |  |  | Project #: |  | Project Number Here
Project Manager: | Project Manager Name Here |  |  |  |  | Sponsor: |  | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  |  |  |  | Last Update: |  | Date of Last Update
Accounting Code: | PLCF0011
Name | Insert name here
Effort Hours Spent
Task | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## RCM
Resource Commitment Matrix
Project: | Project Title Here |  |  |  |  | Project #: |  | Project Number Here
Project Manager: | Project Manager Name Here |  |  |  |  | Sponsor: |  | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  |  |  |  | Last Update: |  | Date of Last Update
Accounting Code: | PLCF0011
Effort Hours Committed
Names | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B6: List all team members and enter their committed hours per month.

## A&C
Assumptions and Constraints
Project: |  | Project Title Here | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
ID | Description | Comments | Type | Status | Date Entered
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Note on D6: Options are: A: assumption C: constraint
Note on E6: Options are: Open Closed
Assumptions & Constraints
Assumptions are factors considered in planning phase to be true, real, or certain and involve a degree of risk (e.g.: if an activity needs a special equipment, the project manager may assume that it will be available).
Constraints are restrictions that affect the performance of the project. The most popular constraint is the budget, which limits the scope, staffing and schedule.
Both assumptions and constraints are important issues to be considered along the project life cycle.

## Decision
Decision Log
Project: |  | Project Title Here | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
ID | Decision Description | Comments | Owner | Status | Date Entered
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Note on D6: Who made the decision?
Note on E6: Options are: Open Closed
What is Decision Log?
Track all decision discussions by topic (description) comments, who owns the decision, current status and when the decision was made.

## Comm
Communication Plan
Project: |  | Project Title Here | Project # | Project Number Here
Project Manager: |  | Project Manager Name Here | Sponsor | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here | Updated | Date of Last Update
Accounting Code: |  | PLCF0011
ID | Communication | Description | Frequency | Format | Owner | Recipient/ Attendees
1 | What type of communication is this? | What is the description of the contents/purpose of this communication? |  |  | Who sends? | Who gets?
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
Note on B7: Examples: Executive status report Team status report
Note on E6: Examples: E-mail Meeting
Communication Plan Guidelines
Whether or not your project or your customer requires a delivered Communications Plan, you should still have one…especially if you are dealing with an external customer rather than an internal organization. Every time I’ve delivered a project plan to the customer, they have been pleasantly surprised and pleased that the communications on the project have been put in writing at the earliest possible point and in sufficient detail.
The high-level items that should be covered in the Communications Plan are:
• Introduction
• Methods for Gathering and Storing Information
• Distribution Structure
• Formal Project Communication Matrix
• Signoff Page
Introduction
This is merely a high-level description of what the document covers. It should also identify the delivering team or organization and the customer or internal organization that the project is being performed for (and likely paid by).
Methods for Gathering and Storing Information
This section is for identifying both the formal and informal communication and how this information will be stored and shared across team members on both sides. Formal communication includes weekly status meetings and the dissemination of information through weekly status reports, revised project schedules and issues and risks lists. Informal project communications include email and phone ad-hoc transactions required to update, clarify and disseminate relevant project status information.
Distribution Structure
The distribution structure section of the Communications Plan identifies how the formal communication on the project will happen and who will be involved. The distribution structure contains sub-sections for each type of formal communication and outlines specific information for each type…Project Status Meetings, Project Status Reporting, Project Schedule, and any shared distribution or posting site such as a sharepoint site or wiki.
For each of these formal communication items, the plan identifies how each is delivered, who receives them and how often they are delivered and reviewed.
Formal Project Communication Matrix
The formal project communication matrix is basically a visual representation of the distribution structure for any formal project communications. This can be through the use of a graphic or table that provides the delivery team and the customer with a quick reference of the communications that happen on the project.
At a minimum, the matrix should include:
• The type of communication
• It’s originator
• Who receives the communication or attends the meeting
• The frequency that the communication or meeting occurs
• And the source of the communication or meeting
Signoff Page
Whether the Communications Plan is a formal deliverable on your project is up to you – or possibly your customer. Either way, I strongly believe that a formal signoff is important as it sets the stage for all communications and information expectations for both project teams going forward. Therefore, the final page of the Communications Plan should be a signoff page for the Project Manager and the customer-side project sponsor and this document should be retained, managed and modified as needed (with signoff on any changes) as the project progresses and any necessary communication methods are added or changed.

## Stake
Stakeholder Analysis
Project: |  | Project Title Here | Project #: | Project Number Here
Project Manager: |  | Project Manager Name Here | Sponsor | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
ID | Stakeholder | Role | Impact | Influence | Risk Tolerance | Needs | Responsibility
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Note on D6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
Note on E6: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
For example, your boss is likely to have high power and influence over your projects and high interest. Your family may have high interest, but are unlikely to have power over it.
Someone's position on the grid shows you the actions you have to take with them:
* High power, interested people: these are the people you must fully engage with, and make the greatest efforts to satisfy.
* High power, less interested people: put enough work in with these people to keep them satisfied, but not so much that they become bored with your message.
* Low power, interested people: keep these people adequately informed, and talk to them to ensure that no major issues are arising. These people can often be very helpful with the detail of your project.
* Low power, less interested people: again, monitor these people, but do not bore them with excessive communication.
3. Understanding your key stakeholders:
You now need to know more about your key stakeholders. You need to know how they are likely to feel about and react to your project. You also need to know how best to engage them in your project and how best to communicate with them.
Key questions that can help you understand your stakeholders are:
* What financial or emotional interest do they have in the outcome of your work? Is it positive or negative?
* What motivates them most of all?
* What information do they want from you?
* How do they want to receive information from you? What is the best way of communicating your message to them?
* What is their current opinion of your work? Is it based on good information?
* Who influences their opinions generally, and who influences their opinion of you? Do some of these influencers therefore become important stakeholders in their own right?
* If they are not likely to be positive, what will win them around to support your project?
* If you don't think you will be able to win them around, how will you manage their opposition?
* Who else might be influenced by their opinions? Do these people become stakeholders in their own right?
A very good way of answering these questions is to talk to your stakeholders directly – people are often quite open about their views, and asking people's opinions is often the first step in building a successful relationship with them.
You can summarize the understanding you have gained on the stakeholder map, so that you can easily see which stakeholders are expected to be blockers or critics, and which stakeholders are likely to be advocates and supporters or your project. A good way of doing this is by color coding: showing advocates and supporters in green, blockers and critics in red, and others who are neutral in orange.
Figure 2 above shows an example of this - in this example, you can see that a lot of effort needs to be put into persuading Piers and Michael of the benefits of the project – Janet and Amanda also need to managed well as powerful supporters.
Example:
You can create your own example of stakeholder analysis at work - whether for your current role, a job you want to do or a new project.
Conduct a full stakeholder analysis. Ask yourself whether you are communicating as effectively as you should be with your stakeholders. What actions can you take to get more from your supporters or win over your critics?
Key points:
As the work you do and the projects you run become more important, you will affect more and more people. Some of these people have the power to undermine your projects and your position. Others may be strong supporters of your work.
Stakeholder Management is the process by which you identify your key stakeholders and win their support. Stakeholder Analysis is the first stage of this, where you identify and start to understand your most important stakeholders.
The first stage of this is brainstorm who your stakeholders are. The next step is to prioritize them by power and interest, and to plot this on a Power/Interest Grid. The final stage is to get an understanding of what motivates your stakeholders and how you need to win them around.
Stakeholder Analysis
Winning Support for your Projects
"Stakeholder management is critical to the success of every project in every organization I have ever worked with. By engaging the right people in the right way in your project, you can make a big difference to its success... and to your career."
As you become more successful in your career, the actions you take and the projects you run will affect more and more people. The more people you affect, the more likely it is that your actions will impact people who have power and influence over your projects. These people could be strong supporters of your work – or they could block it.
Stakeholder Management is an important discipline that successful people use to win support from others. It helps them ensure that their projects succeed where others fail.
There are two major elements to Stakeholder Management: Stakeholder Analysis and Stakeholder Planning. Stakeholder Analysis is the technique used to identify the key people who have to be won over. You then use Stakeholder Planning to build the support that helps you succeed.
The benefits of using a stakeholder-based approach are that:
*You can use the opinions of the most powerful stakeholders to shape your projects at an early stage. Not only does this make it more likely that they will support you, their input can also improve the quality of your project.
*Gaining support from powerful stakeholders can help you to win more resources – this makes it more likely that your projects will be successful.
*By communicating with stakeholders early and often, you can ensure that they know what you are doing and fully understand the benefits of your project – this means they can support you actively when necessary.
*You can anticipate what people's reaction to your project may be, and build into your plan the actions that will win people's support.
How to Use the Tool:
The first step in Stakeholder Analysis is to identify who your stakeholders are. The next step is to work out their power, influence and interest, so you know who you should focus on. The final step is to develop a good understanding of the most important stakeholders so that you can work out how to win their support. You record this analysis on a stakeholder map.
After you have used this tool and created a stakeholder map, you can use the stakeholder planning tool to plan how you will communicate with each stakeholder.
The steps of Stakeholder Analysis are explained below:
1. Identifying Your Stakeholders:
The first step in your stakeholder analysis is to brainstorm who your stakeholders are. As part of this, think of all the people who are affected by your work, who have influence or power over it, or have an interest in its successful or unsuccessful conclusion.
Remember that although stakeholders may be both organizations and people, ultimately you can only communicate with individual people. Make sure that you identify the correct individual stakeholders within a stakeholder organization.
2. Prioritize Your Stakeholders:
You may now have a long list of people and organizations that are affected by your work. Some of these may have the power either to block or advance it. Some may be interested in what you are doing, others may not care.
Map out your stakeholders on a Power/Interest Grid on our free template as shown in figure 1, and classify them by their power over your work and by their interest in your work.

## Expectations
Expectations
Project: | Project Title Here | Project #: |  | Project Number Here
Project Manager: | Project Manager Name Here | Sponsor: |  | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here | Last Update: |  | Date of Last Update
Accounting Code: | PLCF0011
ID | Expectation Description | Source | Must Have | Want to Have | Nice to Have | Date Identified
Managing Project Expectations
Regardless of where you fall in your project's food chain, managing expectations is the key to being successful and saving your sanity. Let's face it, everyone wants new systems and projects delivered yesterday, even if they don't have a clue about the amount of work involved in delivering a quality system that aligns with critical business objectives.
I don't know about you, but my schooling never included "Manage Expectations 101" and it hasn't exactly been offered during training at any of the companies where I've worked. So why is it so important and what can you do about it?
Importance
Perception is reality and all IT projects are really just a reality that someone in the organization would like to see. As a result, everything is really just made up — the deliverables, the timelines, and the expectations. That doesn't mean it's not important and doesn't have merit, it simply means that there is someone somewhere in the organization (maybe that someone is you) who is the pivotal person whose expectations you need to manage.
The good news is that project timelines aren't based on the irrefutable laws of nature such as gravity, so there is always some wiggle room. Your job is to manage your sphere of influence regarding the project; i.e., the piece of the pie that you can actually directly impact via your work responsibilities. No one is immune from the need to manage expectations, it is only your place on the project food chain that defines at what level and how formally you need to manage these expectations.
To add some perspective to this nebulous expectation thing, let me give you some examples of situations that fall into the manage expectations category. Some are obvious, and some are less obvious but equally important.
* You're a manager and need to formally agree to timelines and deliverables. You're managing expectations of your customer, your management, and your team.
* As a project manager, you need to formally manage the ongoing status and outstanding issues related to the project as it progresses. You're managing the expectations of your management, your customer, and the people working for you.
* As a developer, you need to manage your project leader's expectations. You need to ensure the project lead is committing the team to deliverables that are realistic based on the actual work at hand. You're the subject matter expert giving all the managers a sanity check.
The expectation continuum is fluid and constantly moving based on challenges that arise as you move along the timeline. This means you need to be consciously managing expectations on a daily basis.
Six Keys to Successfully Managing Expectations
1. Know Your Capabilities
Like anything in life, it is important to understand what you (and your team) can bring to the table before committing to anything. The principle of "know thyself" is very important. Know what you can deliver (even if it requires the help of some outside contractors) before you commit to anything. Nothing spoils current and future relationships faster than saying "We can do that" and having that be entirely untrue.
2. Set Clearly Defined Expectations
Do not assume. You need to start the process of defining expectations early. Expectations include more than just the requirements for the system. Expectations define how your team will work together as a group and with the customer. It also addresses the often neglected but important pieces such as how and how often status will be reported, how progress will be measured, what happens if priorities shift, and how issues that arise will be handled, to name a few.
When defining expectations, resort back to the SMART rule of goal setting: Specific, Measurable, Attainable, Realistic, and Time-bound. Most importantly, make sure all parties are in agreement with what the expectations are from all parties. Again, perception is reality.
3. Educate and Empathize
Unless you educate your customer you cannot truly reach an agreement because not everyone will know what they are agreeing to. While I am not saying you need to educate your customers in great detail about the technology and what is involved (they don't care, otherwise they would've chosen to work in IT), you do need to educate them on the fact that completing their project is not something that can be done in the snap of your fingers. Simply educate them so they can have a healthy appreciation of the work involved and the time and resources it takes to accomplish what they want.
That being said, you need to listen and empathize. It is equally important that you understand the business drivers behind the project and let the other person know that you are on board with how important the project is to them. Reassure them that you are committed to their success.
4. Be Realistic
Over the course of any project timeline, there will be challenges, unforeseen circumstances, and shifting priorities. Build a little sanity into your timelines and the expectations you set with others. Practice under-promising and over-delivering. It is attractive to all involved and results in win-win outcomes.
5. Continuous Monitoring
Nothing is more damaging to reputations and business relationships than the dreaded big bad surprise. No one wants to be blindsided to find out key targets will not be met at the last minute. It puts the customer in an awkward situation and damages your credibility and trust.
Continuously monitor the progress of the project and make sure you manage expectations on an ongoing basis. Clearly set the status, communication, and issue reporting expectations early on and you will have a built-in system that supports you in managing expectations.
6. Communicate Early and Often
Communication is the key to it all. communicate early and often; and if in doubt, communicate some more. Put a good communicator from your team in the role of interfacing with all the stakeholders. Ideally you should use a single point of contact for project status discussions to minimize potential miscommunications and confusion.
Communication is a two-way street. You need to keep your finger on the pulse of what the customer is thinking as much as you report status to them. System prototypes are an ideal way to communicate in a visual, hands-on way. Prototypes can help bridge the gap between what the customer says he wants versus what he really means he wants. In the end you need to deliver what they really want if you are to be truly successful.

## Proj Chg Log
Project Change Control Log
Project: |  | Project Title Here | [5 empty] | Project #: | Sponsor Name Here
Project #: |  | Project Number Here | [5 empty] | Sponsor: | Location of Project Documents Here
Project Artifacts: |  | Project Manager Name Here | [5 empty] | Last Update: | Date of Last Update
Accounting Code: |  | Sponsor Name Here
Change Control # | Change Request Description | Priority | Requested By | Request Date | Deadline to Resolve | ScheduleImpact Delay (days) | Impact on Cost ($) | Evaluator | Status | Date of Decision | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Note on C7: Options are: 5: High 4: Medium-high 3: Medium 2: Low-medium 1: Low
Note on D7: Who identified the change needed?
Note on I7: Who will decide what action is taken on the change?
Note on J7: Options are: In review Rejected Deferred Approved
Project Change Control System
The Change Control process is fundamental to the successful delivery of the project. The Change Control process ensures that each change introduced to the project environment is appropriately defined, evaluated and approved prior to implementation.
Change Control will be introduced to the project, through the implementation of five key processes:
* A formal process for the submission and receipt of change requests
* A formal process for the review and logging of change requests
* A formal process for the determination of the feasibility of change requests
* A formal process for the approval of change requests
* A formal process for the implementation and closure of change requests
Submit Change Request
This process provides the ability for any member of the project team to submit a request for change to the project. The following is the standard procedure.
* Change Requestor identifies a requirement for change to any aspect of the project (e.g. scope, deliverables, schedules, budget, expenditure, organisation, etc.).
* Change Requestor completes a Change Request (CR) and distributes the form to the Change Manager. The CR provides a summary of the change required, including the:
° Change description
° Reasons for change (including business drivers)
° Benefits of change
° Costs of change
° Impacts of change
° Supporting documentation
Review Change Request
This process allows the Change Manager to review the CR and determine whether or not a full feasibility study is required in order for the Change Control Board (CCB) to assess the full impact of the change. The decision will be based primarily on the:
* Number of change options presented
* Complexity of the change options requested
* Scale of the change solutions proposed
The Change Manager will open a ‘Change Request’ in the Change Log and record whether or not a change feasibility study is required.
Identify Change Feasibility
This process involves the completion of a full change feasibility study, in order to ensure that all change options have been investigated and presented accordingly. The change feasibility study will involve definition of the:
* Change requirements
* Change options
* Change costs and benefits
* Change risks and issues
* Change impact
* Change recommendations & plan
A quality review of the feasibility study is then performed in order to ensure that it has been conducted as requested and the final deliverable is approved – ready for release to the CCB.
All change documentation is then collated by the change manager and submitted to the CCB for final review. This documentation includes:
* The original Change Request
* The approved Change Feasibility Study report
* Any supporting documentation
Approve Change Request
This process involves the formal review of the change request, by the CCB. The CCB will chose one of the following outcomes regarding the change proposed:
* Reject the change
* Request more information related to the change
* Approve the change as requested
* Approve the change subject to specified conditions
The change decision will be primarily based on the following criteria:
* Risk to the project in implementing the change
* Risk to the project in NOT implementing the change
* Impact to the project in implementing the change (time, resources, finance, quality)
Implement Change Request
This process involves the complete implementation of the change. This includes:
* Identifying the change schedule (i.e. date for implementation of the change)
* Testing the change prior to implementation
* Implementing the change
* Reviewing the success of the change implementation
* Communicating the success of the change implementation
* Closing the change in the change log
Change Roles
Define the roles and responsibilities for all resources (both within and external to the project) involved with the initiation, review and implementation of changes within the project.
EXAMPLE
Change Requestor
The Change Requestor initially recognises a need for change to the project and formally communicates this requirement to the Change Manager. The Change Requestor is formally responsible for:
* The early identification of a need to make a change to the project
* The formal documentation of that need, through the completion of a Change Request Form
* The submission of the Change Request to the Change Manager for review
Change Manager
The Change Manager receives, logs, monitors and controls the progress of all changes within a project. The Change Manager is formally responsible for:
* Receiving all change requests and logging those requests in the Change Log
* Categorising and prioritising all change requests
* Reviewing all change requests in order to determine is additional information is required in order to present the submission to the CCB
* Determining whether or not a formal Change Feasibility Study is required in order to complete a change request submission
* Initiating the Change Feasibility Study
* Monitoring the progress of all change requests in order to ensure process timeliness
* Escalating all change request issues and risks to the CCB
* Reporting and communicating all decisions made by the CCB
Change Feasibility Group
The Change Feasibility Group complete formal feasibility studies for change requests issued by the Change Manager. The Change Feasibility Group is formally responsible for:
* Performing a research exercise in order to determine the likely options for change, costs, benefits and impacts of change
* Documenting all findings within a Change Feasibility Study Report
* Performing a quality review of the report and approving the report for submission
* Forwarding the report to the Change Manager for CCB submission
Change Control Board (CCB)
The CCB determines the authorisation of all change requests forwarded by the Change Manager. The CCB is formally responsible for:
* The review of all change requests forwarded by the Change Manager
* The consideration of all supporting change documentation
* Approving / rejecting each change request based on its relevant merits
* Resolving change conflict (where 2 or more changes overlap)
* Resolving change issues
* Determining the change implementation timetable (for approved changes)
Change Implementation Group
The Change Implementation Group schedule, carry out and review the implementation of all changes within a project. The Change Implementation Group is formally responsible for:
* The scheduling of all changes (subject to the general timeframes provided by the CCB)
* The testing of all changes, prior to implementation
* The implementation of all changes within the project
* The review of the success of a change, following implementation
* The request for closure of a change within the change log
Change Log
(The ‘Change Log’ is the log / database within which all requests for changes are registered and tracked through to resolution).
Describe the purpose and usage of the ‘project change register’. Insert a copy of the actual change register below.
Change Forms
Insert a copy of each of the forms required (e.g. Change Request) in order to initiate, undertake, implement and measure the effects of a change within the project.

## Deliver (DAR)
Deliverable Acceptance Register
Project: |  | Project Title Here | Project #: | Project Number Here
Project #: |  | Project Manager Name Here | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
ID | Deliverable Description | Comments | Evaluator | Status | Date of Decision
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
Note on E7: Options are: In review Rejected Accepted
Acceptance Register
The Acceptance Register helps you to keep track of your acceptance testing results within your project.
After each deliverable has been completed, you will want to gain your customers agreement that each deliverable fully meets their needs. To do this, you need to perform a suite of acceptance tests.
These acceptance tests allow your customer to review the deliverables produced and to decide whether they fully meet their requirements.
This acceptance form allows you to track the results of each test and to quickly resolve the issues which arise.
The Acceptance Register or acceptance log helps you to:
* List the deliverables which need acceptance tests
* Identify when each deliverable is ready to be tested
* Schedule each test and involve your customers when needed
* Monitor the status of each acceptance test and identify when complete
You can also use this Acceptance Register to:
* Log the results of each acceptance test
* Flag issues, where the criteria and standards have not been met
* Identify the corrective actions used to improve your deliverables
* Gain your customers acceptance for each deliverable finally completed
By recording all of this information in the Acceptance Register, you can constantly monitor and control the acceptance testing activities throughout your project. This will help you to produce deliverables which meet your customers requirements and to gain a high level of customer satisfaction.

## Man Power Effort
Man Power Estimate
Project: |  | Project Title Here |  |  |  |  | Project #: |  | Project Number Here
Project #: |  | Project Manager Name Here |  |  |  |  | Sponsor: |  | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here |  |  |  |  | Last Update: |  | Date of Last Update
Accounting Code: |  | PLCF0011
Effort Hours Spent
Resource Name |  | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Total
A | plan | [12 empty] | 0
| act | [12 empty] | 0
B | plan | [12 empty] | 0
| act | [12 empty] | 0
C | plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
| plan | [12 empty] | 0
| act | [12 empty] | 0
TOTAL | plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| act | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| VAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assumptions & Constraints
Assumptions are factors considered in planning phase to be true, real, or certain and involve a degree of risk (e.g.: if an activity needs a special equipment, the project manager may assume that it will be available).
Constraints are restrictions that affect the performance of the project. The most popular constraint is the budget, which limits the scope, staffing and schedule.
Both assumptions and constraints are important issues to be considered along the project life cycle.

## Burndown Chart
Project Burn Down Chart
Project: |  |  | Project Title Here |  |  |  | Project #: | Project Number Here
Project Manager: |  |  | Project Manager Name Here |  |  |  | Sponsor: | Sponsor Name Here
Project Artifacts: |  |  | Location of Project Documents Here |  |  |  | Last Update: | Date of Last Update
Accounting Code: |  |  | PLCF0011
| Burned down |  | Balance |  | Daily Completed | Comments
Day | Planned | Actual | Planned | Actual
0 |  |  | 250 | 250 | #N/A
1 | 12 | 8 | 238 | 242 | 8
2 | 18 | 10 | 220 | 232 | 10
3 | 11 | 0 | 209 | 232 | 0
4 | 4 | 12 | 205 | 220 | 12
5 | 5 | 19 | 200 | 201 | 19
6 | 6 | 13 | 194 | 188 | 13
7 | 10 | 8 | 184 | 180 | 8
8 | 20 | 2 | 164 | 178 | 2
9 | 20 |  | 144 | #N/A | #N/A
10 | 18 | 2 | 126 | 176 | 2
11 | 6 |  | 120 | #N/A | #N/A
12 | 13 | 2 | 107 | 174 | 2
13 | 7 | 34 | 100 | 140 | 34
14 | 14 |  | 86 | #N/A | #N/A
15 | 12 |  | 74 | #N/A | #N/A
16 | 14 |  | 60 | #N/A | #N/A
17 | 12 |  | 48 | #N/A | #N/A
18 | 11 |  | 37 | #N/A | #N/A
19 | 19 |  | 18 | #N/A | #N/A
20 | 18 |  | 0 | #N/A | #N/A
Gantt charts are very good to understand a project progress and status. But they are heavy on planning side. They give little insight in to what is happening. A burn down chart on the other hand is good for understanding the project progress and how deliverables are coming along.
According to Wikipedia,
A burn down chart is graphical representation of work left to do versus time. The outstanding work (or backlog) is often on the vertical axis, with time along the horizontal. That is, it is a run chart of outstanding work. It is useful for predicting when all of the work will be completed.
Step 1: Arrange the data for making a burn down chart
To make a burn down chart, you need to have 2 pieces of data. The schedule of actual and planned burn downs. As with most of the charts, we need to massage the data. I am showing the 3 additional columns that I have calculated to make the burn down chart. You can guess what the formulas are. (Hint: there is a NA() too).
Step 2: Make a good old line chart
Just select the Balance Planned and Balance Actual series and create a line chart. Use the first column (days) in the above table for x-axis labels.
Step 3: Add the daily completed values to burn down chart
Select the “daily completed” column and add it to the burn down chart. Once added, change the chart type for this series to bar chart (read how you can combine 2 different chart types in one).
Step 4: Adjust formatting and colors
Remove or set grid lines as you may want. Adjust colors and add legend if needed.
Step 5:
There is no step 5, just go burn down some work.

## PERT
PERT Analysis
Project: |  | Project Title Here | [5 empty] | Project #: |  | Project Number Here
Project #: |  | Project Manager Name Here | [5 empty] | Sponsor: |  | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here | [5 empty] | Last Update: |  | Date of Last Update
Accounting Code: |  | PLCF0011
ID | Task | Most Likely | Min | Max | PERT Est | 15/15 Comp'ed Est | Std Dev | +1 Std Dev | -1 Std Dev | +2 Std Dev | -2 Std Dev | +3 Std Dev | -3 Std Dev
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PERT Technique - Program Evaluation and Review Technique
Regardless of the technique you use, the tendency in project estimation is to provide one number for each estimate. In other words, if you have 100 activities on your schedule, each activity would have one estimate associated with it. This is generally viewed as the “most likely” estimate.In many cases you can be more accurate by applying a simple PERT (Program Evaluation and Review Technique) model. PERT is an estimating technique that uses a weighted average of three numbers (see below) to come up with a final estimate.
* The most pessimistic (P) case when everything goes wrong
* The most optimistic (O) case where everything goes right
* The most likely (M) case given normal problems and opportunities
The resulting PERT estimate is calculated as (O + 4M + P)/6. This is called a “weighted average” since the most likely estimate is weighted four times as much as the other two values. You’ll notice that the final PERT estimate is moved slightly toward either the optimistic or pessimistic value - depending on which one is furthest from the most likely. Generally this ends up moving the final estimate toward the worst case, since the worst case value tends to be further out from the most likely that the optimistic number.
For example, let’s say you estimate a piece of work to most likely take 10 hours. The best case (everything goes right) is six hours. The worst case (everything goes wrong) is 26 hours. The PERT estimate is (6 + 4(10) + 26)/6. The answer is 72/6, or 12 hours. Notice that the number was pulled a little toward the far extreme of the pessimistic estimate, but not by much, since the result is still weighted heavily toward the most likely value.
You can use the PERT estimates two ways. You can provide these three estimates for all activities in your schedule or you can only use the PERT formula for those activities that are of high risk. These are the ones where you’re not really sure of the estimate so there’s a wide variation between the optimistic and pessimistic values.
Speaking of variation - if you subtract your pessimistic value from the optimistic value and divide the result by six, you would have the standard deviation, which is a measure of the volatility of the estimate. In our example above, the standard deviation would be 3.34 ((26 - 6) / 6). The larger this standard deviation is, the less confidence you have in your estimate, since it would mean you have a large range between the optimistic and pessimistic estimates. If the standard deviation was small, it would mean you were pretty confident in your estimate, since the optimistic and pessimistic estimates would be close.
Remember the PERT formula and use it to make estimates when you have a high level of uncertainly.

## Delphi
Delphi Exercise
Project: | Project Title Here |  |  |  |  | Project #: |  | Project Number Here
Project #: | Project Manager Name Here |  |  |  |  | Sponsor: |  | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  |  |  |  | Last Update: |  | Date of Last Update
Accounting Code: | PLCF0011
Score: 1 = Low to 5 = High
Task | Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 14 | 1.75
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Task | Sample task here Name 1: Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Task | Sample task here Name 1: Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Task | Sample task here Name 1: Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Task | Sample task here Name 1: Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Task | Sample task here Name 1: Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Task | Sample task here Name 1: Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Task | Sample task here Name 1: Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Task | Sample task here Name 1: Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Task | Sample task here Name 1: Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Task | Sample task here Name 1: Sample task here
Team members | Name 1 | Name 2 | Name 3 | Name 4 | Name 5 | Name 6 | Name 7 | Name 8 | Total | Average
Most likely | [8 empty] | 0
Minimum | [8 empty] | 0
Maximum | [8 empty] | 0
Delphi Method
How it works
The power of the Delphi method in gaining consensus is first that comments are anonymous, which helps people avoid defending their original position. It also allows them to be gradually swayed by the majority but without undue direct social pressure. Being able to see what others have said or scored and then rethinking your own position can act as a very effective influence.
How to use it
Define the problem: Identify the problem that you want to work on, writing it down in a clear way that is easy to understand. This can be in various forms, from a questionnaire to a broad and open question.
You can work on one problem and you can work on several problems at once. The constraint is usually the bandwidth and expertize of the people in the Delphi group.
Give everyone the problem
Recruit people to the Delphi group. This includes anyone who has been selected to contribute thinking on this project. There is seldom a meeting needed for Delphi work, making it ideal for virtual teams.
Delphi thinking can be done with a small group and it can be done with hundreds of people. Around 20 people is a fairly common size.
Send the problem or problems to everyone who is in the group and ask them respond. You will have to handle a lot of feedback, so asking for short bullet-points will make things much easier to deal with than rambling text.
Collate the responses
Take the responses that people send back to you and collate these into a single anonymous list or sets of lists.
Make this as easy as possible for the people to read when you send it back out again, but be aware of causing inappropriate bias. For example you may group responses into appropriate headings, but with the caution that this might presuppose particular thinking.
On the other hand, if you are seeking creative ideas you may deliberately mix up the answers. Give everyone the collation
Send the collation back out to everyone with the request to score each item on a given scale (typically 1 to 5). You may also allow them to add further items as appropriate.
Remember to include the original problem at the top of the page, along with instructions on what to do. You can also make responding easier by putting the items in a table with space for the score.
Repeat as necessary
The process may now be repeated as many times as is deemed appropriate. If you are seeking consensus and there was a wide range of responses, then this may require several iterations. In particular at least a second round to see how others have scored can be very useful.
In analysing the scores, one method used in Delphi analysis for smaller groups and especially when percentage scores are used is to use the formula: (lowest score + highest score + 4 x average score) / 6. This gives more weight to the average whilst also allowing some influence from outliers.

## Size Est
Initial Project Size Estimate
Project: |  | Project Title Here | Project #: | Project Number Here
Project #: |  | Project Manager Name Here | Sponsor: | Sponsor Name Here
Project Artifacts: |  | Location of Project Documents Here | Last Update: | Date of Last Update
Accounting Code: |  | PLCF0011
Scope Estimate
Technology Systems Impacted
|  | 1 to 2 | 3 to 5 | 6 or more
# of Business Requirements | Less than 50 | Automatically do; no approval needed
51 - 100
| 100 or more |  |  | Approval required
Cost Estimate
# of Resources Involved
|  | Less than 10 | 11 to 50 | 51 or More
# of Business Requirements | Less than 50 | Automatically do; no approval needed
51 - 100
| 100 or more |  |  | Approval required
Cost Estimate
# of Resources Involved
|  | Less than 10 | 11 to 50 | 51 or More
Benefit | Low |  |  | Avoid
Medium
| High | Automatically do; no approval needed
Software Project Estimation
Effective software project estimation is one of the most challenging and important activities in software development. Proper project planning and control is not possible without a sound and reliable estimate. As a whole, the software industry doesn’t estimate projects well and doesn’t use estimates appropriately. We suffer far more than we should as a result and we need to focus some effort on improving the situation.
Under-estimating a project leads to under-staffing it (resulting in staff burnout), under-scoping the quality assurance effort (running the risk of low quality deliverables), and setting too short a schedule (resulting in loss of credibility as deadlines are missed). For those who figure on avoiding this situation by generously padding the estimate, over-estimating a project can be just about as bad for the organization! If you give a project more resources than it really needs without sufficient scope controls it will use them. The project is then likely to cost more than it should (a negative impact on the bottom line), take longer to deliver than necessary (resulting in lost opportunities), and delay the use of your resources on the next project.

## Res Load
Resource Loading
Project: | Project Title Here |  | Project #: | Project Number Here
Project Manager: | Project Manager Name Here |  | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
Effort Hours Committed
ID | Names | Estimate of Total Effort | Activity Duration | Commitment Level | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total: | 0 | 0 | 0 | 0
Resource Loading
Resource loading mainly involves your manpower or employees. In resource loading, each employee is assigned a task or a percentage of a project (x% of the whole). Usually, it's 25 percent of the whole. Then the employee is assigned other tasks until he or she reaches 100 percent booked. This would then mean that the employees cannot take on any additional work.
With resource loading, a project manager can predict an employee's hours for the year and see how tasks can be assigned. This also allows the project manager
to decide whether or not additional employees or contractors are needed to complete the scheduled projects.
The downside to resource loading is that employees cannot be 100 percent booked. Other things may arise to take away their time, such as unexpected problems that need to be fixed. An employee should always be under 100 percent booked. Resource loading increases the chance that a project will not be completed on time because employees are overloaded with projects.
Resource Leveling
While resource loading mainly deals with manpower, resource leveling deals with both time (starting and ending date) and resources, including manpower and budget. Resource leveling tries to balance the conflicting interests of projects with the available resources.
Resource leveling generally breaks things down into two categories: time and available resources. Some projects need to be finished within a certain timeframe. These projects will use all the available resources (money and manpower) to complete the project by a certain date. For a complete overview of resource leveling, read my article "What is Resource Leveling?"
Projects that aren't as pressing can be spread out for an indefinite period of time until resources do become available. These projects are usually ones that are not on the critical path and will not affect the project completion date.
Like resource loading, resource leveling also has its problems. It is hard to determine in the beginning which tasks will be on the critical path. Also, delaying a task could cause the entire project to fall behind schedule.

## IT-QA Testing
IT/QA Requirements Test Matrix
Project: |  |  | Project Title Here |  |  |  | Project #: |  |  |  | Project Number Here
Project #: |  |  | Project Manager Name Here |  |  |  | Sponsor: |  |  |  | Sponsor Name Here
Project Artifacts: |  |  | Location of Project Documents Here |  |  |  | Last Update: |  |  |  | Date of Last Update
Accounting Code: |  |  | PLCF0011
The release contains the following features:
1
2
3
4
5
Testing Type |  |  |  | Required (Y or N) | Business Sponsor | IT Sponsor | Business Driver | Business Project Lead | Project Manager | Storage Engineer | Systems Engineer | DBA | Infrastructure | Architecture | Appl'n Developer | Lead Engineer | QA Department Head | QA Manager | QA Project Lead | QA Supervisor
Quality Testing Requirements
QA Round 1
1 |  |  | Security
2 |  |  | Operational Issues
3 |  |  | Baseline Development
4 |  |  | Initial fail over testing
5
QA Round 2
1 |  |  | Load Testing
2 |  |  | Performance Testing
3 |  |  | 3rd Party Connectivity
4 |  |  | Orchestration (internal system interfaces)
5 |  |  | Validate fail over
6 |  |  | Run Book review (internal system interfaces)
7 |  |  | Product Support Issues (check that logs do not fill up)
8
QA Round 3
1 |  |  | Endurance (run at 75-80% capacity for 72 hours minimum)
2 |  |  | Security (external interfaces)
3
4
5
QA Round 4
1
2
3
4
5
Legend
| Creates the deliverable |  |  | C1: primary creator; C2: contributor
| Input required |  |  | I
| Reviews the deliverable |  |  | R
| Approves the deliverable |  |  | A
| Notified when the deliverable is complete |  |  | N
| Owns the deliverable upon completion |  |  | O
What is requirements test matrix?
The requirements test matrix is a project management tool for tracking and managing testing efforts, based on requirements, throughout the project's life cycle.
The requirements test matrix is a table, where requirement descriptions are put in the rows of the table, and the descriptions of testing efforts are put in the column headers of the same table.
The requirements test matrix is similar to the requirements traceability matrix, which is a representation of user requirements aligned against system functionality. The requirements traceability matrix ensures that all user requirements are addressed by the system integration team and implemented in the system integration effort.
The requirements test matrix is a representation of user requirements aligned against system testing. Similarly to the requirements traceability matrix, the requirements test matrix ensures that all user requirements are addressed by the system test team and implemented in the system testing effort.

## Qual Metrics
Project Quality Metrics
Project: | Project Title Here |  | Project #: | Project Number Here
Project Manager: | Project Manager Name Here |  | Sponsor: | Sponsor Name Here
Project Artifacts: | Location of Project Documents Here |  | Last Update: | Date of Last Update
Accounting Code: | PLCF0011
ID | Critical Success Criteria | Potential Quality Metric |  | Priority | Metric Target | Action Plan
Project Quality Metrics
Purpose: Quality metrics are the objective measures used to determine whether or not the project and its components are meeting the goals as established early in the project.
Application: Quality metrics are set early in the project and incorporate some means of measurement that allows for regular interim assessments of progress toward the established objective. Once established, the metrics are used to highlight variance and areas of the project that may require remediation. They can be used to focus on a single area of attention or on multiple areas of concern.
Content: Quality metrics come in a wide variety of forms and formats, largely dependent on the project type. They consist of an objective measure of the preproject state and a related measure on the same scale of the desired postproject state. An environmental remediation project, for example, might cite the parts per million (ppm) of a given contaminant and the desired postproject ppm count. In a drug research project, a certain level of long-term stability for the output might be measured. For a deliverable within a project, the metrics might include timing, fit, finish, or capacity. Quality metrics can be virtually anything relating to the project or component’s desired state that can be effectively measured.
Approaches: Because quality metrics are measurable, they are most often reflected in bar or line graphs for comparative analysis. They are clear and simple. The key is to be able to identify, in a metric form, what constitutes project success.
Considerations: Some quality metrics reports may have dozens of tables, each displaying a different subset of information. Effective use of quality metrics means ensuring that each of the metrics chosen is a meaningful measure to determine the potential success of the project.

## NPV
NPV Calculator
Add custom cash flows or create auto-generated cash flow series (uniform, gradient, and exponential series).
You can delete, copy, and insert new columns, but make sure the Sum column is correct after making changes.
The Net Present Value for each series is calculated, along with the Total NPV. Edit the light-blue cells.
The IRR function is used to calculate the overall Internal Rate of Return. It requires an initial guess.
|  | NPV | 14649.4886
|  | IRR | 9.054%
|  | Discount Rate (i) | 6%
Auto-Generated Cash Flow Series
|  | Series Type: | Uniform (A) | Gradient (G) | Exp Grad | none
|  | Value (A, G, or Eo): | 100 | 100 | 100
|  | g (for Exp Grad): |  |  | 5%
|  | Periods: | 5 | 10 | 7 |  |  | Custom Cash Flow Series
|  | NPV: | 421.2364 | 2960.2321 | 674.0775 | 0 | 2148.665 | 4471.6974 | -1872.9475 | 5846.5278
[6 empty] | IRR: | 16.34% | 9.635% | 4.144% | 8.663%
| Period | Sum | Series 1 | Series 2 | Series 3 | Series 4 | Label 1 | Label 2 | Label 3 | Label 4
| 0 | -150000 | 0 | 0 | 0 | 0 |  | -40000 | -40000 | -70000
| 1 | 18205 | 100 | 0 | 105 | 0 | -10000 | 8000 | 8000 | 12000
| 2 | 36710.25 | 100 | 100 | 110.25 | 0 | 3000 | 9200 | 9200 | 15000
| 3 | 42615.7625 | 100 | 200 | 115.7625 | 0 | 4200 | 10000 | 10000 | 18000
| 4 | 52321.5506 | 100 | 300 | 121.5506 | 0 | 6800 | 12000 | 12000 | 21000
| 5 | 55627.6282 | 100 | 400 | 127.6282 | 0 |  | 14500 | 14500 | 26000
| 6 | -8365.9904 | 0 | 500 | 134.0096 | 0 |  |  | -9000
| 7 | 740.71 | 0 | 600 | 140.71 | 0
| 8 | 700 | 0 | 700 | 0 | 0
| 9 | 800 | 0 | 800 | 0 | 0
| 10 | 900 | 0 | 900 | 0 | 0
| 11 | 0 | 0 | 0 | 0 | 0
| 12 | 0 | 0 | 0 | 0 | 0
| 13 | 0 | 0 | 0 | 0 | 0
| 14 | 0 | 0 | 0 | 0 | 0
| 15 | 0 | 0 | 0 | 0 | 0
| 16 | 0 | 0 | 0 | 0 | 0
| 17 | 0 | 0 | 0 | 0 | 0
| 18 | 0 | 0 | 0 | 0 | 0
| 19 | 0 | 0 | 0 | 0 | 0
| 20 | 0 | 0 | 0 | 0 | 0
| 21 | 0 | 0 | 0 | 0 | 0
| 22 | 0 | 0 | 0 | 0 | 0
| 23 | 0 | 0 | 0 | 0 | 0
| 24 | 0 | 0 | 0 | 0 | 0
| 25 | 0 | 0 | 0 | 0 | 0
| 26 | 0 | 0 | 0 | 0 | 0
| 27 | 0 | 0 | 0 | 0 | 0
| 28 | 0 | 0 | 0 | 0 | 0
| 29 | 0 | 0 | 0 | 0 | 0
| 30 | 0 | 0 | 0 | 0 | 0
| 31 | 0 | 0 | 0 | 0 | 0
| 32 | 0 | 0 | 0 | 0 | 0
| 33 | 0 | 0 | 0 | 0 | 0
| 34 | 0 | 0 | 0 | 0 | 0
| 35 | 0 | 0 | 0 | 0 | 0
| 36 | 0 | 0 | 0 | 0 | 0
| 37 | 0 | 0 | 0 | 0 | 0
| 38 | 0 | 0 | 0 | 0 | 0
| 39 | 0 | 0 | 0 | 0 | 0
| 40 | 0 | 0 | 0 | 0 | 0
Example IRR and NPV Calculation
Fig 1. Sample series of cash flows with NPV and IRR calculation.
Example Cash Flow Diagram
Fig 2. Cash flow diagram.
Net Present Value is defined as the "difference between the present value (PV) of the future cash flows from an investment and the amount of investment" [1] (emphasis added).
This is an excellent definition because it explains why the NPV formula in Excel is not really complete, and what you need to do to use it correctly. The word "Net" in NPV implies subtracting something from something else. The Excel NPV function really only calculates the sum of the present value of future cash flows. Note the emphasis on "future", which means cash flows starting at time t=1 or 1 period in the future from the present time t=0.
To calculate NPV, you must also subtract the value of the initial investment, or in other words, add the cash flow at time t=0 (which is a negative value). So in Figure 1 above, the equation for NPV is:
=NPV(rate, values_t1_to_tn) + value_t0
=NPV(B1,B5:B8)+B4
The formula for the internal rate of return (IRR) in Figure 1 is:
=IRR(values_t0_to_tn, guess)
=IRR(B4:B8,0.1)
It would be a good idea to read the Help document on the NPV and IRR functions, so that you can understand some of the limitations and requirements.
It is educational to note that the NPV formula is identical to calculating the present value of all future cash flows using the PV formula and summing them as shown in Figure 1. This can also be done using an array formula as explained by Timothy Mayers in reference [2] below. The array formula is actually more powerful than the NPV function, because you can include the initial cash flow at t=0 to avoid having to add it in separately, and you can have multiple values for the same period or even have the periods out of order.
=SUM(PV(rate, periods_t0_to_tn, 0, -values))
Using the XNPV and XIRR Formulas to Calculate NPV and IRR
The second worksheet in the NPV Calculator spreadsheet is set up to help you calculate the Net Present Value and Internal Rate of Return for a series of scheduled cash flows that are non-periodic. The XNPV and XIRR functions require you to enter dates in addition to the cash flow values and the discount rate. They use a 365-day year to calculate present value based on an initial negative value (investment).
XIRR is to XNPV as IRR is to NPV
The following array formula can be used in place of the XNPV formula if you need to use a 360-day year or don't want to require the use of the Analysis ToolPak. Because it is an array formula, you need to press Ctrl+Shift+Enter after adding or editing it.
=SUM(values/((1+rate)^((dates-INDEX(dates,1))/365)))
Disclaimer: This NPV Calculator spreadsheet and the information on this page is for illustrative and educational purposes only. We do not guarantee the results or the applicability to your unique financial situation. You should seek the advice of qualified professionals regarding financial decisions.
Need to Estimate Return on Investment Projects?
ModelSheetSoft.com has developed a new technology that lets you create an easy-to-use, professional Investment Analysis Excel spreadsheet in minutes, by first customizing the specifications using an online form. You can then download your customized template that includes mixed equity, debt and lease financing, and many more options. It models sales, working capital, and fixed/variable expenses to evaluate and report on net present value, return on capital, and internal rate of return.
Customize the Investment Analysis template!
How to Calculate IRR and NPV in Excel
To calculate NPV or IRR, you first need to have a predicted or estimated series of periodic cash flows. This will usually involve some initial lump payment as the initial investment (negative cash flow) at time t=0, followed by both inflows (income) and outflows (payments) at regular intervals t=1, t=2, t=3, etc. The image below shows an example.

## XNPV
XIRR, XNPV Calculator
This worksheet uses the XNPV function to calculate the Net Present Value
for a schedule of cash flows that are not necessarily periodic. The XNPV
function requires the Analysis ToolPak add-in (see Help on XNPV function).
It assumes 365 days in the year. The XIRR function is used to calculated
the Internal Rate of Return. The dates do not need to be in order. You can
have multiple cash flows with the same date.
| Discount Rate | 8%
[5 empty] | Days in Year | 365
| NPV | #VALUE! | NPV | 2180.5133 | NPV | 2180.5133
| IRR | #VALUE! | IRR | 37.34%
| Using Dynamic Ranges |  | Using the Exact Range |  | Using an Array Formula
| Date | Value | Date | Value | Date | Value
| 2008-01-01 | -10000 | 2008-01-01 | -10000 | 2008-01-01 | -10000
| 2008-03-01 | 2750 | 2008-03-01 | 2750 | 2008-03-01 | 2750
| 2008-10-30 | 4250 | 2008-10-30 | 4250 | 2008-10-30 | 4250
| 2009-02-15 | 3250 | 2009-02-15 | 3250 | 2009-02-15 | 3250
| 2009-04-01 | 2750 | 2009-04-01 | 2750 | 2009-04-01 | 2750

## Net Present Value
NET PRESENT VALUE CALCULATOR
|  | Investment/ Project A |  | Investment/ Project B |  | Investment/ Project C
Discount Rate | : | 10% |  | 11% |  | 12%
Period (Year) | : | 5 |  | 6 |  | 7
Initial Cash Flow | : | 125000 |  | 150000 |  | 170000
Project NPV | : | 137145.2916 |  | 168963.0943 |  | 160641.8541
Difference | : | 12145.2916 |  | 18963.0943 |  | -9358.1459
Percentage | : | 9.716% |  | 12.64% |  | -5.505%
| Y | Cashflow | Y | Cashflow | Y | Cashflow
| 0 | -125000 | 0 | -150000 | 0 | -170000
| 1 | 50000 | 1 | 50000 | 1 | 50000
| 2 | 70000 | 2 | 70000 | 2 | 70000
| 3 | 90000 | 3 | 90000 | 3 | 90000
| 4 | 90000 | 4 | 120000 | 4 | 120000
| 5 | 70000 | 5 | 90000 | 5 | 90000
|  |  | 6 | 70000 | 6 | 70000
[5 empty] | 7 | 50000