## GUIDANCE NOTES
Annual Financial Reporting Guidelines
Using This Template
1. Before preparing your annual financial report, you should read the full guidance notes. This reporting format asks you to report on expenditure over the last financial year (Annual Financial Report tab) as well as summarising expenditure over the life of your project (Financial Summary tab).
2. To insert additional rows, right click on the row number below where you wish to insert the new row and choose INSERT.
3. To delete a row, right click on the row number you wish to remove and choose DELETE.
4. The NOTES ON VARIANCE column should be used to identify which lines have additional information on the VARIANCE NOTES tab.
5. You can access the notes on variance pages by clicking on any of the the NOTES ON VARIANCE tabs below.
6. The NOTES ON VARIANCE (Annual report) tab should be used to record explanations on why there was a variance of + or - 10% on the annual report.
Submission Deadlines: Annual financial reports are required to be submitted with the annual narrative progress reports according to the deadlines identified in your Grant Arrangement or in subsequent guidance (If your project began after 31st March 2011, the financial report is due on 30th April 2012. All other projects must submit their reports by 30 June 2012 - please note that these timings may change for future years).
What goes into the Annual Financial Report? The annual financial report must be presented using the CSCF Financial Report template. The annual financial report must include the following components :
(a) Budget Headings & Budget Amounts: The Annual Financial report’s budget headings and budget lines should follow the same structure and level of detail as the most up-to-date agreed budget used for the preparation of your current Grant Funding Agreement (or Revised Grant Funding Agreement). It is important to NOTE that the Annual Financial Report budget must include a detailed breakdown of budget items and NOT be based on the summary Budget headings only (which are normally used on quarterly claim forms).
(b) Actual Expenditure for the Financial Year: This column should capture (for every individual budget line) the actual expenditures incurred over all four quarters of the relevant financial year. Figures are required for both the total project expenditure against the total project budget and the DFID only expenditure against the DFID only budget. The total of the "DFID Actual Expenditure” should normally equal the sum of all the actual expenditures reported on the quarterly claim forms submitted for the project in the relevant financial year. Please note that DFID's funding policy defines "Actual Expenditure" as expenditures that have actually been incurred and paid for within the reporting year. Actual Expenditures should NOT include accruals and/or commitments
(c) Variances (Amounts and Percentages): Your report should include a calculation of the differences between the budgeted amounts and actual expenditures for each budget item. The variance amount is computed for each budget line by subtracting the actual expenditures from the budgeted amounts. A positive result denotes an under-spend and a negative result denotes an over-spend. The report also requires the calculation of the variance as a percentage (i.e. the item variance amount divided by the by the budget amount and multiplied by 100%).
(d) Variance Explanations: Once the variances have been calculated, all variances above 10% need to be supported by detailed justification irrespective of whether they are negative or positive. Justifications should include why unit costs have changed and why the total number of units forecast for each budget item has changed. The explanations should not be generic. Please refer to budget heading numbering and also to logframe outputs and indicators as applicable and include explanations of any changes to the total number of units compared to forecast, or the cost per unit. Please note that the Terms and Conditions of CSCF grants require grant holders to request approval in advance for any transfer of funds between budget sub-headings and any transfers of >10% within budget sub-headings. If the variance has already been approved, please include the date of the confirmation of approval
What goes into the Financial Summary? The Financial Summary report must presented using the CSCF Financial Summary template. The financial summary must include the following components :
(a) Budget Headings & Budget Amounts: The Financial Summary's budget headings and budget items should follow the same structure and level of detail as the most up-to-date agreed budget used for the preparation of your current Grant Funding Agreement (or Revised Grant Funding Agreement). It is important to NOTE that the Financial Summary must include a detailed breakdown of budget items and NOT be based on the summary Budget headings only (which are normally used on quarterly claim forms).
(b) Actual Expenditure for the every Financial Year: These columns should capture (for every individual budget item) the actual expenditures incurred over all four quarters of the relevant financial year. You are required to report on the expenditure for every financial year of the project to-date. Figures are required for both the total project expenditure against the total project budget and the DFID grant expenditure against the DFID contribution. The total of the "DFID Actual Expenditure” should equal the sum of all the actual expenditures reported on the quarterly claim forms submitted for the project to-date. Please note that DFID's funding policy defines "Actual Expenditure" as expenditures that have actually been incurred and paid for within the reporting year. Actual Expenditures should NOT include accruals and/or commitments
Please check that the information you are submitting is complete and accurate • Does the report include a detailed breakdown of the agreed budget for the period 1st April to March 31st March, for both total budget and the DFID contribution? • Does the total DFID budget for the year correspond to the most recently agreed Grant Agreement or revised Grant Agreement for the period? • Does the breakdown of expenditure per main budget sub-heading agree with the expenditure reported on the cumulative claim forms over the year? • Have significant budget variances been clearly explained? If there was an approval of these variances has this been clearly stated?

## Annual Financial Report
ORGANISATION NAME | ChildHope UK
PROJECT TITLE | Sexual Exploitation, No! Mobilising young people and duty bearers in Rio de Janeiro
CSCF PROJECT No. | 533
ANNUAL REPORT FOR FINANCIAL YEAR | 04 / 2012 - 3/2013 |  |  |  | DATE SENT TO TRIPLE LINE |  | 2013-04-30
TOTAL COST OF PROJECT | 152021
DFID CONTRIBUTION (in GBP) | 132508
OWN/OTHER CONTRIBUTION (in GBP) | 19343
BUDGET HEADINGS | TOTAL PROJECT BUDGET (including DFID and Other contributions) |  |  |  | DFID CONTRIBUTION (Only DFID contributions) |  |  |  | NOTES ON VARIANCE OF +/-10%
Please complete the headings following those used in your latest full budget. The headings below are for guidance only. Details are required under each heading. | TOTAL PROJECT BUDGET | TOTAL ACTUAL PROJECT EXPENDITURE | TOTAL VARIANCE IN | TOTAL VARIANCE IN | AGREED DFID | DFID ACTUAL | VARIANCE IN | VARIANCE IN | NOTE No.
[5 empty] | BUDGET FOR | EXPENDITURE
| FY 12/13 | FY 12/13 | £ | % | FY 12/13 | FY 12/13 | £ | %
| A | B | C (A-B) | D (C/Ax100) | E | F | G (E-F) | H (G/Ex100)
CAPITAL EXPENDITURE
Project equipment PL (2 Laptops for staff and community activities, 1 Video Camera) | 0 |  | 0 | 0 | 0 |  | 0 | 0
Project equipment PMO (2 Laptops for PMO staff and community activities) | 0 |  | 0 | 0 | 0 |  | 0 | 0
Sub-total | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
LOCAL STAFF
Sub-total | 78747 | 77807 | 940 | 1.194% | 72787 | 69289 | 3498 | 4.806%
OVERSEAS ADMIN
% Rent and utilities relating to project (PL) | 931 | 1291 | -360 | -38.6681 | 931 | 1291 | -360 | -38.6681 | 2
% Rent and utilities relating to project (PMO) | 931 | 932 | -1 | -0.10741 | 931 | 932 | -1 | -0.10741
Audit Costs (PL) | 3045 | 3054 | -9 | -0.29557 | 3045 | 3054 | -9 | -0.29557
Audit Costs (PMO) | 3045 | 3044 | 1 | 0.032841 | 3045 | 3044 | 1 | 0.032841
Banking costs and foreign exchange taxes (PL) | 451 | 995 | -544 | -120.6208 | 451 | 975 | -524 | -116.1863 | 3
Sub-total | 8403 | 9316 | -913 | -10.87% | 8403 | 9296 | -893 | -10.63%
PROJECT ACTIVITIES
Work with children and youth and families
Provision of specialised legal defense and social assistance in cases of sexual exploitation (40 cases years 2-4) (PL) | 2474 | 2398 | 76 | 3.0719 | 2474 | 2398 | 76 | 3.0719
Training workshops for 25 vulnerable youth per year from 4 communities (PL) | 4805 | 5357 | -552 | -11.488 | 4805 | 5357 | -552 | -11.488 | 4
Production & distribution of educational materials on CSE (PL) | 1050 | 1226 | -176 | -16.7619 | 1050 | 1226 | -176 | -16.7619 | 5
Youth-led cultural and recreational activities for community prevention and awareness in 4 high risk localities (PL) | 5887 | 11499 | -5612 | -95.3287 | 5887 | 7189 | -1302 | -22.1165 | 6
Production of visual media to document youth life stories (PL) | 3155 | 3202 | -47 | -1.4897 | 3155 | 3202 | -47 | -1.4897
Building capacity of local civil society and Child Protection Networks
Capacity building workshops for child protection officials from CT and specialised assistance units working with exploited children and youth (PL) | 963 | 943 | 20 | 2.0768 | 963 | 943 | 20 | 2.0768
Survey pre-post training questionnaires to trained professionals (PMO) | 745 | 745 | 0 | 0 | 745 | 745 | 0 | 0
CH technical support and ongoing mentoring to build partners' capacity for child participation in monitoring and evaluation and integrating child protection into their work (CH) | 405 | 405 | 0 | 0 | 405 | 405 | 0 | 0
Project learning exchange and reflection between ChildHope, Projeto Legal, and Promundo (CH) | 400 | 400 | 0 | 0 | 400 | 400 | 0 | 0
Influencing government
Publishing and dissemination of exemplary case studies to influence government policy and bi-annual newsletter Yrs 2-4 (PL) | 1896 | 2148 | -252 | -13.2911 | 1896 | 2148 | -252 | -13.2911 | 7
CSO joint actions, forums and lobbying of inter-sectoral networks and local government to monitor programmes and policies on CSE (PL) | 1397 | 1459 | -62 | -4.4381 | 1397 | 1459 | -62 | -4.4381
Annual public hearings with government departments (Health, Education, Justice) to influence policy and practice (PL) | 596 | 756 | -160 | -26.8456 | 596 | 756 | -160 | -26.8456 | 8
Sub-total | 23773 | 30538 | -6765 | -28.46% | 23773 | 26228 | -2455 | -10.33%
INFORMATION & DISSEMINATION
Research paper on CSE to disseminate policy recommendations and project learning (PL) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Awareness-raising campaign to reduce public tolerance and prevent CSE in 4 communities (eduational, radio, community media) (PL) | 12370 | 12948 | -578 | -4.6726 | 12370 | 12948 | -578 | -4.6726
Final dissemination event to secure commitment (PL) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-total | 12370 | 12948 | -578 | -4.673% | 12370 | 12948 | -578 | -4.673%
MONITORING & EVALUATION
Develop shared instruments and setting up of participatory project M&E and learning system (with ChildHope) (PL & PMO) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baseline research and mapping of CSE in 4 communities and developing focus group discussions and meetings in communities each yr with project participants for community-based local monitoring and evaluation of project. (PMO) | 1490 | 6599 | -5109 | -342.8859 | 1490 | 1495 | -5 | -0.33557 | 9
Joint Management Committee and Partner M&E Meetings (PL) | 447 | 184 | 263 | 58.8367 | 447 | 184 | 263 | 58.8367 | 10
Final external evaluation (PL) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participatory planning, monitoring and support visits by CH (CH) | 3268 | 3268 | 0 | 0 | 3268 | 3268 | 0 | 0
Sub-total | 5205 | 10051 | -4846 | -93.1% | 5205 | 4947 | 258 | 4.957%
TOTAL (OVERSEAS BUDGET) | 128498 | 140660 | -12162 | -135.9% | 122538 | 122708 | -170 | -13.87%
UK EXPENDITURE
Sub-Total | 11361 | 11361 | 0 | 0% | 9970 | 9970 | 0 | 0%
BUILDING SUPPORT FOR DEVELOPMENT
|  |  | 0 | 0% |  |  | 0 | 0%
|  |  | 0 | 0% |  |  | 0 | 0%
Sub-total | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
GRAND TOTAL | 139859 | 152021 | -12162 | -8.6959 | 132508 | 132678 | -170 | -0.12829

## Variance Notes (Annual Report)
ANNUAL FINANCIAL REPORT - VARIANCE NOTES
Note No. | Notes
1 | Additional research activity was budgeted and paid for by a match funder: Allan and Nesta Ferguson foundation, this involved an increase in research personnel involved.
2 | During the year, Projeto Legal received less income from a govt partner than planned and therefore, had to divide office rent costs between remaining partners. PL organisational budget has been revised for the coming year to ensure that this does not happen in year 3 of the project.
3 | Bank taxes and administration charges for receiving international transfers have increased this year. PL has investigated alternative options but has not found a cheaper solution. One extra international transfer at a cost of £20, however this cost was covered by the match funder.
4 | Due to increased demand from CYP (179 instead of planned 100) participating in workshops, despite cost efficiencies, overall costs increased.
5 | Cost of production of information, education and communication materials increased as the preferred supplier shut down. Partners sought 3 quotes from new suppliers and selected the supplier offering the best value for money. Also, the reach of distribution was increased to campaigns carried out by the project team against sexual exploitation across the State.
6 | Includes the cost of daily payments to casual community facilitators to support the implementation of workshops in the community. Additional activity funded by match funding from the Allan and Nesta Ferguson Trust to provide transport for youth participation in recreative cultural events outside of the slum communities.
7 | Slight increase in the number of publications and disseminations to use in larger state events for advocacy.
8 | It was necessary to rent spaces for the public audiences due to the increased number of participants, instead of using Projeto Legal meeting facilities.
9 | Increased activity funded by match funding from the Allan and Nesta Ferguson Trust to carry out house to house surveys of the community as part of the baseline work and qualitative interviews with beneficiaries.
10 | Lower costs here as efficiencies made by hosting events in project team offices.
10
11
12
13
14