## Slide 1: Project Procurement Management
Notes: <number>

## Slide 2: Project Quality Management
“The processes to purchase or acquire the products, services, or results needed from outside the project team to perform the work”
Notes: <number>

## Slide 3: Why Procurement Management?
Most all projects will need to acquire some resources from outside
Not understanding the different ways to contract could result in unnecessary risk for the project
Note for Test Takers: PMI Procurement questions are from the BUYERS perspective unless noted otherwise
Notes: <number>

## Slide 4: How Do We Manage Procurement?
Four processes
  Plan Procurements
  Conduct Procurements
  Administer Procurements
  Close Procurements
Conduct Procurements
Administer
Procurements
Plan Procurements
Close Procurements
Notes: <number>

## Slide 5: Plan Procurements
Scope Baseline
Requirements Documentation
Teaming Agreements
Risk Register
Risk-Related Contract Decisions
Activity Resource Requirements
Project Schedule
Activity Cost Estimates
Cost Performance Baseline
Enterprise Environmental Factors
Organizational Process Assets
Make or Buy Analysis
Expert Judgment
Contract Types
Inputs
Outputs
Tools & Techniques
Procurement Management Plan
Procurement Statements of Work
Procurement Documents
Source Selection Criteria
Change Requests
Make or Buy Decisions
Conduct Procurements
Administer
Procurements
Plan Procurements
Close Procurements
Notes: <number>

## Slide 6: Contract Types
Fixed Price (Lump Sum) Contracts
Cost-Reimbursable Contracts
  Cost Plus Fee (CPF)
    Cost Plus Percentage of Cost (CPPC)
  Cost Plus Fixed Fee (CPFF)
  Cost Plus Incentive Fee (CPIF)
Time and Material (T&M) Contracts
Which type of contract is the highest risk for the Buyer? Seller?
Notes: <number>

## Slide 7: Conduct Procurements
Project Management Plan
Procurement Documents
Source Selection Criteria
Qualified Sellers List
Seller Proposals
Project Documents
Make-or-Buy Decisions
Teaming Agreements
Organizational Process Assets
Bidder Conference
Proposal Evaluation Techniques
Independent Estimates
Expert Judgment
Advertising
Internet Search
Procurement Negotiations
Inputs
Outputs
Tools & Techniques
Selected Seller
Procurement Contract Award
Resource Calendars
Change Requests
Project Management Plan Updates
Project Document Updates
Conduct Procurements
Administer
Procurements
Plan Procurements
Close Procurements
Notes: <number>

## Slide 8: Types of Scopes of Work
Performance
  What the project wants, how accomplished and project needs defined by seller
Functional or Detailed
  Defines what end product should be as well as minimum requirements
Design
  Defines exactly what is required and how to accomplish it
Notes: <number>

## Slide 9: Procurement Documents
Request for Proposal (RFP)
  Asks for the price and how/who will do the work
Invitation for Bid (IFB)
  One simple price to do the work
Request for Quotation (RFQ)
  Price per unit quote
Notes: <number>

## Slide 10: Negotiating Tactics
Attacks – Argue a point
Personal Insults – Attack other sides negotiator
Good Guy/Bad Guy
Deadline – The offer stands until…
Lying
Limited Authority – I need to check with ____
Missing Man – She is out today, I will have to get back tomorrow
Fair and Reasonable
Delay – Tabling issues important to the other side
Extreme Demands
Withdrawal – Feigning interest
Fait Accompli – Done Deal, this is how we have to do it….
These are all tactics, but not necessarily good tactics!
Notes: <number>

## Slide 11: Administer Procurements
Procurement Documents
Project Management Plan
Contract
Performance Reports
Approved Change Requests
Work Performance Information
Contract change control system
Procurement performance review
Inspections and audits
Performance reporting
Payment systems
Claims administration
Records management system
Inputs
Outputs
Tools & Techniques
Procurement Documentation
Organizational Process Assets Updates
Change Requests
Project Management Plan Updates
Conduct Procurements
Administer
Procurements
Plan Procurements
Close Procurements
Notes: <number>

## Slide 12: Contract Closure
Project Management Plan
Procurement Documentation
Procurement audits
Negotiated Settlements
Records management system
Inputs
Outputs
Tools & Techniques
Closed Procurments
Organizational Process Assets Updates
Conduct Procurements
Administer
Procurements
Plan Procurements
Close Procurements
Notes: <number>

## Slide 13: Procurement Terms
Arbitration – Third party dispute resolution
Breach/Default – When a contract provision is not met
Force Majeure – Riots, wars, weather, or other “Acts of God”
Indemnification – Who is liable
Liquidated Damages – Estimated damages for specific types of defaults as defined in the contract
Material Breach – A violation of the contract of sufficient magnitude that the contract cannot be completed
Notes: <number>

## Slide 14: Procurement Terms Continued
Retainage – Monies withheld to ensure performance at the end of the contract
Termination – Stopping the work before it is completed
Waiver – Statements in the contract that indicate that rights cannot be ignored or modified without written agreement between the two parties
Time is of the essence – Seller is placed on notice that delivery agreements are strictly binding
Work for Hire – At the end of the contract the work product generated will be owned by the buyer
Notes: <number>