## Task_Table
DISTRICT PROJECT SCHEDULE TEMPLATE (Excel.xlsx format)
Instructions: You can find instructions for completing this template in the Project Management Guide (TIS-M001) which is posted in the QAM area of the District’s website. Please note: this document is also available in Project.mpp format from the Project Management Office (PMO). If you have questions or would like additional information, contact the TIS Project Management Office (PMO) by email at "Project Office" or you may call 503-399-3031.
ID | Name |  |  | Operational | Small | Med | Large | Duration | Start | Finish | Resources | % Done | Predecessors
1 | 1) APPROVE & PRIORITIZE PROJECT
2 |  | Request for Service Received
3 |  | Project Tracking Number Assigned (SSR, HSR, ETC)
4 |  | Does work qualify as a project?
5 |  | Project Sized
6 |  | Resources Allocated
7 |  | Gateway: Work Approved, Prioritized and Scheduled
8 | 2) SETUP PROJECT
9 |  | Contact Affected Departments (TIS, Purchasing, Facilities, etc)
10 |  | Research/Options
11 |  | Go / No Go Decision
12 |  | Assign Project Manager
13 |  | Determine project management tools
14 |  | Review lessons learned from prior projects
15 |  | Develop Project Charter (TIS-F009)
16 |  | Gateway: Project Charter Approved
17 | 3) PLAN PROJECT
18 |  | Schedule & Resource Plan (Project Schedule Template TIS-F011 or TIS-F020)
19 |  | Communication Plan (TIS-F016)
20 |  | Scope Management Plan (part of TIS-010) for Change Management
21 |  | Budget Management Plan (part of TIS-010) and Budget
22 |  | Quality Management Plan (part of TIS-F010) & Results
23 |  | Contract Management Plan (part of TIS-F010)
24 |  | Risk Management Plan (part of TIS-F010) & Risk Register (MS Project)
25 |  | Risk Planning Evaluation Checklist (TIS-F014)
26 |  | Issues Management Plan (part of TIS-F010) & Issues Register (MS Project)
27 |  | Human Resources Management Plan (Part of TIS-F010) or Detail HR Plan (TIS-F015)
28 |  | Gateway: Plan Walkthrough
29 | 4a) EXECUTE PROJECT
30 |  | COMMUNICATION
31 |  |  | Review Communication Plan & Schedule with Affected People
32 |  |  | Execute & Manage Communication Plan
33 |  | PURCHASING (work with Purchasing)
34 |  |  | Market Research & Best Practices (before RFP begins)
35 |  |  | Define Selection Process and Participants
36 |  |  | Create RFP
37 |  |  | RFP Approved by Stakeholders
38 |  |  | Wait for Vendor Responses
39 |  |  | Bidder's Conference
40 |  |  | Demonstrations and Clarifications
41 |  |  | Site Visits
42 |  |  | Evaluate Proposals
43 |  |  | Select Apparent Winner
44 |  |  | Negotiate Contract
45 |  |  | Document Key Vendor Roles & Contacts
46 |  | PREPARE THE SOLUTION
47 |  | CREATE DOCUMENTATION
48 |  | TEST THE SOLUTION
49 |  | TRAINING
50 |  | PILOT (limited implementation)
51 |  | IMPLEMENTATION
52 |  | TERMINATE OLD SYSTEM
53 |  | STAKEHOLDERS AGREE PROJECT IS COMPLETE
54 | 4b) MANAGE PROJECT
55 |  | Review Schedule & Resource Plan
56 |  | Review Communication Plan
57 |  | Review Scope Management Plan (Change Management)
58 |  | Review Budget Management Plan and Budget
59 |  | Review Quality Management Plan & Results
60 |  | Review Contract Management Plan
61 |  | Review Risk Management Plan & Risk Register
62 |  | Review Issues Management Plan & Issues Register
63 |  | Review the Human Resources Management Plan
64 |  | Gateway: Final Implementation Approval
65 | 5) CLOSE THE PROJECT
66 |  | Transfer To Ongoing Operations
67 |  | Document Lessons Learned (TIS-018)
68 |  | Finalize Project Documentation
69 |  | Closed Project Summary (TIS-F019)
70 |  | Gateway: Closed Project Summary Approved
71 |  | Celebrate!