## Slide 2: Monitoring and Control
Monitoring is the collection, recording, and reporting of project information
Control uses the monitored data to bring actual performance into agreement with the plan
Monitoring and control are the opposite sides of project selection and planning
  Project selection dictates what to monitor
  Project planning identifies the elements to be controlled

## Slide 3: Plan-Monitor-Control Cycle
The plan–monitor-control cycle constitutes a “closed loop” process
  Continues until the project is completed
With complex projects, there is a temptation to minimize the planning–monitoring–controlling effort so that “real work” can be done
  It is these projects that need the planning–monitoring–controlling process the most

## Slide 4: Project Authorization and Expenditure Control System Information Flow
Figure 7-1

## Slide 5: Designing the Monitoring System
Identify special characteristics of scope, cost, and time that need to be controlled
  Specific performance characteristics should be set for each level of detail in the project
Real-time data must be identified to measure achievement against the plan
It is important to avoid the tendency to focus on easily collected data

## Slide 6: Data Collection and Reporting
Once data to monitor has been decided, mechanisms to collect this data must be designed
Analysis is used to transform data into information
A number of questions come up:
  Should we use special forms?
  Should data be collected before/after milestones?
  Should time and cost data be collected at the same time?

## Slide 7: Data Collecting
Frequency counts
Raw numbers
Subjective numeric ratings
Indicators and surrogates
Verbal characterizations

## Slide 8: Data Analysis
Data analysis techniques
  Simple aggregation
    Averaging, for example
  Fitting statistical distribution functions to the data
  Curve fitting
Significant differences from the plan should be flagged

## Slide 9: Data Analysis Examples
Figures 7-2, 7-3, 7-4

## Slide 10: Reporting and Report Types
Routine performance reports
  Project status reports
  Time/Cost reports
  Variance reports
Avoid periodic or routine reports
Not all stakeholders need to receive same information
Electronic media makes it possible to customize information for difference audiences
Reports should be timed to allow control to be exercised before completion of the task in question

## Slide 11: Report Types
Routine
  Status, progress, and forecast reports
Exception
  A report used for special decisions or unexpected situations where affected team members need to be made aware, and the change itself documented
Special analysis
  The results of a special study which documents a particular opportunity or problem within the project itself

## Slide 12: Additional Report Benefits
They provide the mutual understanding between stakeholders in a project
They help communicate the need for coordination among those working on project
They establish and maintain a communication network for global projects
Reports can communicate information about changes to a project
They help maintain the visibility of the project
They improve motivation

## Slide 13: Meetings
Many reports are delivered at meetings
Meetings range from regular, highly formalized and structured sessions to informal, off-the-cuff get-togethers
  Presentations
  Question and answer sessions
Meetings must be well run to be effective

## Slide 14: Meeting Guidelines
Meetings should be used primarily for group decision making, not for mere progress reports
Distribute written agenda in advance of meeting to ensure that all attendees are properly prepared for the meeting
For a crisis meeting, restrict discussion to that issue
Meeting should take minutes
  Avoid attributing remarks to individuals in the minutes
Avoid excessive formality
If meeting is held to address specific crisis, restrict meeting to this issue alone

## Slide 15: Virtual Reports, Meetings, and Project Management
The Internet can be used to communicate and report about the project’s status
  Irrespective of the location of the project team members
Software programs allow the project manager to utilize the organization’ local area network or intranet
Virtual project teams have members spread worldwide

## Slide 16: Earned Value
The earned value (EV) of a task or project is the budgeted cost of the work actually done
  It is calculated by multiplying the budgeted cost of the task by the percentage completion of the task
  Process is more difficult than it sounds
    Budgeted cost of a task is clear
    Percentage of completion is not
The percent of a task’s budget actually spent is not good indicator of percent completion

## Slide 17: Conventions Used to Estimate Progress on Tasks
50-50
  Task is listed as 50% complete when initiated and the remaining 50% added when task is completed
100%
  The task is 100% complete when finished … and zero percent before that
  projects will always appear to be “behind schedule”
Ratio of cost (or time) expended to cost (or time) budgeted
  Neither is an accurate estimator of percentage completion
These conventions are meant for application only to individual tasks on a project, not to the project as a whole

## Slide 18: Earned Value Chart
Figure 7-5

## Slide 19: Two Simple Rules for Variances
A negative variance is bad and a positive variance is good
The spending and schedule variances are calculated as the earned value minus some other measure

## Slide 20: Variances
Cost/Spending variance
  Earned value (EV) – actual cost (AC)
Schedule variance
  Earned value (EV) – planned cost (PV)
CPI (cost performance index)
  Earned value (EV)/actual cost (AC)
SPI (schedule performance index)
  Earned value (EV)/planned cost (PV)

## Slide 21: Example
Work on a project was expected to cost $1,500
Workers were originally scheduled to finish today
However, as of today…
  Actually spent $1,350
  About 2/3 finsished

## Slide 22: Various Variances Visually
Figure 7-6
a: Positive schedule variance, negative spending variance
b: Negative schedule variance, negative spending variance
c: Negative schedule variance, positive spending variance

## Slide 23: Calculations for Example

## Slide 24: Additional Items of Interest
Estimated remaining cost to completion
  ETC = (BAC – EV) / CPI
    ETC: estimated cost to completion
    BAC: budget at completion
    EV: earned value
    CPI: cost performance index
Estimated total cost at completion
  EAC = ETC + AC
    EAC: estimated at completion
    ETC: estimated cost to completion
    AC: actual cost

## Slide 25: Additional Calculations for Example
BAC = 1500
EV = 1500 (2/3) = 1000
CPI = .74 (calculated earlier)
AC = 1350
ETC = (BAC – EV) / CPI = (1500 – 1000) / .74 = 676
EAC = ETC + AC = 676 + 1350 = 2026

## Slide 26: Microsoft Project Status Report for DVD Project
Table 7-1

## Slide 27: Project Control
Control, the act of reducing differences between the plan and actuality
It is the final element in the planning-monitoring-controlling cycle
It is to no avail if actions are not taken when reality deviates significantly from what was planned
Control is a difficult task
  It involves human behavior
  Problems are rarely clear cut so the need for change and redirection is also fuzzy

## Slide 28: Purposes of Control
Stewardship of organizational assets
  Physical asset control
  Human resources management
  Financial control through the use of accounting tools
Regulation of results through the alteration of activities
  This step involves taking action when reality deviates from plan
  It includes both mechanistic and human elements

## Slide 29: Purposes of a Control System
Primary purpose is to correct errors
  Not to identify and punish the guilty
  Managers must realize that the past cannot be changed
Control the investment, subject to diminishing returns
Consider impact on creativity and innovation
The control system should employ the lowest degree of hassle consistent with accomplishing its goals

## Slide 30: Primary Mechanisms by which Project Manager Exerts Control
Process reviews
  An analysis of the process of reaching the project objectives
Personnel assignment
  Control can also be exercised through personnel assignments based on past productivity
Resource allocation
  Resources are usually allocated to the more productive or important tasks and this can significantly influence the attainment of project results

## Slide 31: Common Mistakes
Emphasizing short-run results at the expense of long-run objectives
Excessive control directed to specific objectives can result in sacrificing other project objectives
Across-the-board cuts in resource allocations tend to reward those who have already overspent or over hired while penalizing the frugal and efficient
Focusing on certain items for control can distract the attention of team members from other, equally important items

## Slide 32: Control System Components
Sensor
  Its purpose is to measure any aspect that one wishes to control
Standard
  The control system must have a standard of items to measure against
Comparator
  Compares the output of the sensor with the standard
Decision maker
  To decide if the difference between what is measured and the standard is large enough to warrant attention.
Effector
  If some action is required to reduced the difference, the effector must then take action

## Slide 33: Types of Control Systems
Cybernetic control systems
  A control system that uses all five components of a control system
  Also known as steering controls
Go/no-go controls
  A predetermined standard must be met for permission to be granted to continue
Post-control (post-performance reviews)
  Applied after the project has been completed
  Purpose is to allow future projects to learn from past project experience

## Slide 34: Tools for Control
Some already covered
  Variance analysis
  Trend projections
  Earned value
Critical ratio
  Indicates when a task is becoming unacceptable
    When the ratio drops below one
  CR = (actual progress/scheduled progress)  (budgeted cost/actual cost)

## Slide 35: Critical Ratio Calculations
Table 7-3

## Slide 36: More Tools for Control
Control chart
  Any measure can be plotted and tracked on a control chart
  Control limits set by project manager
Benchmarking
  Make comparisons to “best in class” practices across organizations, or divisions, or even departments within an organization

## Slide 37: Two Sample Control Charts
Figures 7-9 and 7-10

## Slide 38: Scope Creep and Change Control
Midcourse changes to a project must be controlled
  Called scope creep
The later changes are made to a project, the more difficult and costly they become
All projects face change
The best approach is a well-controlled, formal process for change

## Slide 39: Purpose of Change Control System
Review all requested changes
Identify all impacts
Translate impacts into performance, schedule, and cost
Evaluate the benefits and disadvantages
Have appropriate person accept or reject
Communicate accepted changes
Ensure changes are implemented properly
Prepare report

## Slide 40: Rules for Controlling Scope Creep
Include a change control system in every project contract
Require all changes be introduced by a change order
Require approval in writing by the client’s agent and senior management
Consult with project manager prior to preparation of change order
Amend master plan to reflect changes

## Slide 41: Copyright
Copyright © 2014 John Wiley & Sons, Inc.
All rights reserved. Reproduction or translation of this work beyond that permitted in Section 117 of the 1976 United States Copyright Act without express permission of the copyright owner is unlawful. Request for further information should be addressed to the Permissions Department, John Wiley & Sons, Inc. The purchaser may make back-up copies for his/her own use only and not for distribution or resale. The Publisher assumes no responsibility for errors, omissions, or damages, caused by the use of these programs or from the use of the information herein.