## Slide 1: 14. Project closure
<number>
An information system project must be administratively closed once its product is successfully delivered to the customer.
A failed project must also be administratively closed.
A deadlocked project (drastic change of focus, support, personnel, executive decision, etc.) must be administratively closed.

## Slide 2: 14. Project closure
<number>
Three broad activities are carried out at the closing stage of the project:
  Administrative closure of contracts and accounts
  Performance appraisal and individual evaluation
  Project audit

## Slide 3: 14. Administrative closure
<number>
Following activities must be address in the project closure plan:
  Identifying tasks necessary to close the project
  Assigning individuals to carry out closure tasks
  Monitoring implementation
  Ending closure process

## Slide 4: 14. Administrative closure
<number>
Important tasks:
  Project accounts closure:
    Outside vendors
    Partners
    Information system professionals
    Temporary workers
  Outside vendors and professionals should be evaluated for:
    Responsiveness
    Reliability
    Service quality
    Adherence to contract terms

## Slide 5: 14. Administrative closure
<number>
  Obtaining delivery acceptance from the customer
    Stops scope creep
    Confirms delivery date and the end of the project
  Equipment and facility release
    Avoids inaccurate accounting
    Helps proper use of organizational resources
  Project personnel release
    Sometimes, team members develop psychological link with the project and want to continue indefinitely

## Slide 6: 14. Administrative closure
<number>
  Acknowledgements and awards
    Acknowledge and reward individuals, departments and centers that influenced the project success
    Organizing a social event is appropriate to hand out awards and announce the project closure
    Sometimes, organizations use such events to launch new services or systems that benefits customers and employees

## Slide 7: 14. Assigning individuals
<number>
The project manager must assign individuals to carry out administrative closure tasks.
Key individuals are good candidates for closure activities
Timelines should be established for different activities to help monitoring and control

## Slide 8: 14. Implementation
<number>
The project manager must ensure implementation of closure activities
  Assign individuals to monitor progress
  Use time table to ensure progress – given the fact that most information system projects are over budget and behind schedule, this phase helps timely closure of accounts, contracts, facilities, and the like that could be charged because of time lapses.

## Slide 9: 14. Ending closure
<number>
Even closure must have an ending
  You don’t want to extend ‘scope creep’ into the closure phase of the project development life cycle.
  The post-closure date could begin following the social event when the closure is formally announced and documented.

## Slide 10: 14. Performance appraisal
<number>
Objectives:
  To evaluate contribution that individuals make to the project success
  To provide feedback to the individual regarding career development
Most organizations have established standards for performance appraisal
  Helps consistency
    Across individuals
    Over time

## Slide 11: 14. Performance appraisal
<number>
In appraising an individual consider
  Innovation and creativity
  Responsiveness
  Team work
  Customer relations
  Learning and adaptability
  Triple constraints (time, cost, focus)
  Value added contribution to the project
One-on-one conference with individual team members

## Slide 12: 14. Project Audit
<number>
Project audit is done during and after projects are complete. The outcome of project audit is a report that suggests:
  Are we doing the right thing (at each milestone)? Did we do the right thing (for completed projects)?
  Are we doing it right (at each milestone)? Did we do it right (for completed projects)?
  The lessons learned? What adjustments are necessary?
Lessons from successes? From failures?

## Slide 13: 14. Project Audit
<number>
Auditing a project is not about:
  Finger pointing
  Who did what wrong?
  Judging
  Punishment
Auditing a project is about:
  Project success issues
  Prevention
  Learning from mistakes
  Continuous improvement

## Slide 14: 14. Project Audit
<number>
For an on-going project, audit helps to decide:
  Are we making adequate progress? Can performance be improved?
  Have organizational priorities changed affecting project priorities? Is closure necessary now?
  Are stakeholders and top management still supportive of the project?
  Is the project team functioning as expected?
  Are there significant issues of internal, external, morale, and the like that impact project outcome?

## Slide 15: 14. Project Audit
<number>
For a completed project, audit helps to decide:
  Did the project meet customer satisfaction?
  What are the lessons learned for future projects?
    Leadership lessons?
    Team interaction lessons?
    Organizational lessons?
    Top management support?
    External entities, vendors?
  Group performance measures

## Slide 16: 14. Project closure checklist
<number>

## Slide 17
<number>

## Slide 18: 14. Discussion questions
<number>
What are the main differences between auditing a marketing project versus auditing an information system project? What are similarities?
How would you justify cost, effort, and time spent on auditing an on-going project? A completed project?

## Slide 19: 14. Discussion questions
<number>
It is suggested that project audit creates anxiety among team members and may lead to internal politics among departments and in turn make the whole process dysfunctional. Describe benefits of project audit and suggest ways of implementation that avoids these problems.

## Slide 20: 14. Discussion questions
<number>
Design a survey questionnaire for team performance measure. Include in this survey:
  Who should respond to your survey,
  The instruction for respondents,
  A scale,
  Six questions,
  Describe your reasons for the way you designed your survey. For example, why you chose the scale that you did? Why the set of questions that you picked?
Hint - use the reverse of “input-process-output” model for designing your survey.

## Slide 21: 14. Discussion questions
<number>
Why is it difficult to perform a truly independent, objective audit?
What personal characteristics and skills would you look for in selecting a project audit leader?
Comment on the following statement: “We cannot afford to terminate the project now. We have already spent more than 50% of the project budget.”

## Slide 22: 14. Discussion questions
<number>
Performance review of team members is an important activity that if done properly will improve member behavior and be a base for reward and promotion.
  What are important characteristics of an effective performance review?
  What would you include in your performance review list?
  What would you not include in your performance review list?

## Slide 23: 14. Discussion questions
<number>
“It is difficult to be both a coach and a judge.” Managers tend to be concerned with justifying their decision than engaging in a meaningful discussion on how the employees can improve their performance. That is why many experts on performance appraisal recommend that organizations separate performance reviews from pay reviews.
What are the pros and cons of this approach? As a project manager, which approach would be more effective for you?

## Slide 24: 14. Discussion questions
<number>
Consider performance evaluation from these two perspectives:
  You as an employee being evaluated. What approach would be most beneficial to you? What you would not like? Like?
  You as a manager evaluating your employees? What approach would be most practical to you? Most beneficial? What you would not like? Like?

## Slide 25: 14. Discussion questions
<number>
Comment on this statement: “You cannot manage what you cannot measure.” Is this statement true for information system project management? Why?