## Menu
Proj. 1234 |  | Project Status and Performance Tracking Tool
| Project Schedule data |  | Tasks Status | Project Performance
| MS Project Schedule |  | Major Milestones Status | Project Dashboard
| Build Project Team |  | Due Tasks List | Project level EVA
| Import PlanView Data |  | Unfinished Tasks List | Resource Level EVA
| Cumm used hours |  | Tasks Audit Trail | Lead Resource Performance
| Monthly used hours |  | Tasks x Res Alloc Plan | EVA Setup
| ResWE used hours |  | Resource Status
| WERes monthly used |  | Resources Allocation | Quality Assurance
| Refresh Cummulative Data |  | Extension Forecast
| Allocation Variance |  | Res x A/c Task hours
| WERes detail hours |  | A/c Task x Res hours
| WERes total hours |  | Res monthly used hours
| WERes Rem hours |  | Res Extension requests
Note on D5: This macro does the following updates. 1) It imports Gantt Chart View of Microsoft Schedule through MAP onto tab "AllTasks" and indents tasks names in a way that matches the indenting by Microsoft Schedules. 2) Then it updates several sheets of this work book. - StatSum - DueTasks - Sch_PV - TaskSum - ResBLW - ResEVA 3) Before running this macro, run macro associated with RDTCD1 update.
Note on D6: Team Status information consisting of information like resource name, PAR status, actual used and remaining hours as per PlanView, Burn Rate, available rate, and schedules allocations etc. This information is used for identifying PAR extension requirements or hours by analyzing currect allocations, burn rate, and available rate. It is also used to identify and analyze variances between schedule allocations and actual time logged. This information is not available from Earned Value Ananlysis which give variances at summary tasks or project level i.e. not at resource level. (Though conceptually, the EVA concept can be used at resource level.):
Note on D8: This update requires following tasks to be done. 1) Process R_DT_CD1 PlanView report for the whole duration of project. - In Parameters keep "From date" and "To date" fields blank. - Preview report - Export report into Excel format and store in the same folder in which this excel is stored. 2) Open this exported Excel and copy / paste this excel sheet on to Tab "RDTCD1". 3) Run the update macro which primarily updates the Team Status on tab "Team". It also puts "Upd Team" in column A of tab "RDTCD1" against each name. By inspecting column A, you can identify if new team members have been allocated in PlanView. In this case you have to re-run this macro one time more. 4) After this update, inspect the team status for correctness of update.
Note on D9: This update requires following tasks to be done. 1) Process R_DT_CD1 PlanView report for the desired period (Weekly or Bi-Weekly or Monthly selected from a list in Cell "C1" of tab "ActHist"). - In Parameters give correct values to "From date" and "To date" fields. - Preview report - Export report into Excel format and store in the same folder in which this excel is stored. 2) Open this exported Excel and copy / paste this excel sheet on to Tab "RDTCD1MM". 3) Run the update macro. Primarily this macro updates the Actual used hours history tab "ActHist". It will ask you if the report "RDTCD1MM" is for a new period or for the last (most recent) period. Respond appropriately. Depending upon the reponse, this macro adds a new column after column E or replaces values in an existing column F. If you have to replace values in a column corresponding to a past period, consider that the update is for a new period. After doing the update as explained in step 3), cut & paste values from column F onto the desired existing column. After this, delete the newly added column (Column F). 4) After this update, inspect tab "ActHist" for new additions of names.
Note on D10: This update requires following tasks to be done. 1) Process R_TR_001 PlanView report. - In Parameters, do not enter anything. - Preview report - Export report into Excel format and store in the same folder in which this excel is stored. 2) Open this exported Excel and copy / paste this excel sheet on to Tab "RTR001". 3) Run the update macro which will update following tabs. - ResWEHrs - WEResHrs - ActHrs - RemHrs 4) After this update, inspect these tabs for accuracy of update.
Note on D13: Resourcewise schedule hours v/s PV allocation hours variance
Note on D14: PlanView Work Entity x Resources Schedule, Plan, Used & Rem Hours
Note on D15: Work Entity x Resource wise total actual used hours
Note on D16: Work Entity x Resource wise remaining hours
Import
Team
Update
Update
Update
Update
Refresh
Refresh
Refresh
Refresh
eMail
Index

## Whats
| ??? | About this Project Tracking Tool
|  | Description | Remarks
- |  | What was the need to create this tool?
To integrate and analyze project monitoring and control information available from various sources.
Automate repeatative functions to save planner's time and direct focus to Control and Decision Support functions
- |  | What do you do with this tool?
Track Team Status
PlanView Allocation Planning
Track schedule status
Calculate PAR ext hours
EVA at Tasks level
EVA at Resource / Lead resource level
Track and balance EVA
Continuously improve Project Planning Processes.
- |  | What are the main features of this tool?
Using Quantitative Analysis for decision support
Focus on applying EVA
Interface with MS Project through MAP
Interface with Outlook for resources contact information
Interface with PlanView through export to Excel
Refresh macros for recalculating
Two dimensional organization of information
- |  | What are the benefits of using this tool?
To increase effectiveness of project monitoring and control support to Project Manager
Saving of time and quick relection on demand by PM
Availability of additional analysis information
- |  | What are the preconditions of successful use?
Tool functioning should match individual's work style
Formal Support
Desire to improve continuously
- |  | What are the risks of using this tool?
Over relying on quantitative analysis may be harmful to team work
Possible overloading of work as now more can be done
- |  | What improvements are planned in near future?
Interface with Primavera
Integrate with planning tool
- |  | What is the purpose of this Presentation
To walkthrough and share views if this tool can be useful to PMs / Planners.
- |  | Rating statements Rating Scale 1-> Lowest, 10 -> Highest
Does this tool provide conprehensive analytical information to monitor project status and take control decisions?
Does this tool save project planner's time used for routine repeatative calculations and bringing information togather in usable form ?
How much at ease are you with tool's user interface?
Would you recommond this tool to be used by other planners?
Would you recommond this tool to be evaluated by Project Office?
+/-

## Team
| Proj. 1234 | L0MK; JD16; JGP4; A22H; LO9A; C53Q; GYUV; HKCE; GH4V; IV1P; H503; A2KO; L2O5; JYHJ; JH2T; GBHZ; J0ZU; A1BO; BR7P; GJ78; LL7M; J4SV; NBUD; J5OY; NAKR; GDP4; CS8K; H48H | Team Status as on |  |  |  | 2003-06-10 |  |  |  | 12103 | 2001-07-25 | 2002-07-15 |  |  |  | 9266.5 |  | 3299.96 | [5 empty] | -627.7236 | -9894.2236 | 0 |  |  | 10526
Sr No | Name as in PlanView Report R_DT_CD1 | Authorized (Y/N) | Personal Details | [5 empty] | Internal/External | Is a Lead? | PAR Information | [12 empty] | PAR Extension Forecast |  |  |  | Sch v/s PV Allocation variance
|  |  | Name as MS Outlook Directory | ActiveStatus ? | Assigned Role | mail alias | Desk Loc | SF Office Tel No |  |  | Assigned Hours | Start date | Finish date | No of Weeks | Hours / week | Average Loading % | Todate Total used Hrs | Avg. Burn Rate /Week | Remaining Hrs | Available Hrs/week | Availablity Req % | Used+Rem Hours | PV - UR | Allocation till date | Actual use Forecast | Additional Use Forecast | Additional PAR Hours | Resource Name | Sch - PV Hrs | Total Sch Hrs
1 | Bommisetti Amarnath |  | Amarnath Bommisetti | 1 | Systems Analyst | L0MK | K-4 | 735-9066 | E | N | 1827 | 2002-07-01 | 2003-12-18 | 76.4286 | 23.9047 | 59.76% | 1747 | 1.3905 | 135.93 | -0.1152 | -0.288% | 1882.93 | -55.93 | 2003-04-22 | 58.5986 | -1688.4014 | 0 | Amar | -476.56 | 1350.44 | 2003-10-06 | 2003-10-13
2 | Kumar Ashok |  | Ashok Kumar | 1 | Proj Planner | JD16 | L-2 | 735-3244 | E | N | 739 | 2002-05-06 | 2003-09-30 | 73.1429 | 10.1035 | 25.26% | 514 | 0.40652 | 224.98 | -0.18886 | -0.4721% | 738.98 | 0.02 | 2003-04-22 | 20.3838 | -493.6162 | 0 | Ashok | -86.82 | 652.18 | 2003-09-30 | 2003-09-30
3 | Malone Bill |  | Bill Malone | 1 | Systems Analyst | JGP4 | M-4 | 763-7598 | I | N | 300 | 2002-10-18 | 2003-12-18 | 60.8571 | 4.9296 | 12.32% | 193.5 | 0.15594 | 106.5 | -0.090256 | -0.2256% | 300 | 0 | 2003-04-22 | 4.1436 | -189.3564 | 0 | Bill | 66.53 | 366.53 | 2003-09-15 | 2003-07-10
4 | Brown Brian [GS03] |  | Brian Brown | 1 | Systems Analyst | GS03 | M-4 | 766-9471 | E | Y | 164 | 2002-11-18 | 2003-09-30 | 45.1429 | 3.6329 | 9.082% | 100 | 0.08088 | 63.97 | -0.053699 | -0.1342% | 163.97 | 0.03 | 2003-04-22 | 1.7909 | -98.2091 | 0 | Brian | -84 | 80 | 2003-07-15 | 2003-09-30
5 | Elam Carol |  | Carol Elam | 1 | Proj Manager | A22H | M-4 | 763-4256 | I | Y | 1014 | 2002-05-06 | 2003-09-30 | 73.1429 | 13.8633 | 34.66% | 547.5 | 0.43301 | 466.98 | -0.392 | -0.98% | 1014.48 | -0.48 | 2003-04-22 | 21.7124 | -525.7876 | 0 | Carol | -29.64 | 984.36 | 2003-09-30 | 2003-09-30
6 | Rogers Charlie |  | Charlie Rogers | 1 |  | NMLR | H-4 | 766-8157 | E | N | 40 | 2003-05-01 | 2003-09-30 | 21.7143 | 1.8421 | 4.605% | 12 | 0.009893 | 28.23 | -0.023698 | -0.05924% | 40.23 | -0.23 |  | -53.3404 | -65.3404 | 0 | Charlie | -40
7 | Stern David |  | David Stern | 1 | Security Analyst | LO9A | K-2 | 766-6872 | I | Y | 65 | 2002-09-30 | 2003-05-27 | 34.1429 | 1.9038 | 4.759% | 75 | 0.060318 |  | 0 | -0% | 75 | -10 | 2003-04-22 | 1.7578 | -73.2422 | 0 | David | -28.74 | 36.26 | 2003-09-30 | 2003-05-27
8 | Mohandass Duzianthan |  | Duzianthan Mohandass | 1 | Security Analyst | J0TY | K-4 | 735-6808 | E | N | 12 | 2003-04-28 | 2003-05-16 | 2.5714 | 4.6667 | 11.67% | 8 | 0.006593 | 8 | -0.006607 | -0.01652% | 16 | -4 |  | -35.5449 | -43.5449 | 0 | Duzianthan | -12
9 | Weidenbenner Ed |  | Ed Weidenbenner | 1 | Business Analyst | C53Q | DEERFIELD PARK | 417-888-6122 | I | Y | 556 | 2002-05-06 | 2003-09-30 | 73.1429 | 7.6016 | 19% | 499 | 0.39465 | 56.97 | -0.047823 | -0.1196% | 555.97 | 0.03 | 2003-04-22 | 19.789 | -479.211 | 0 | Ed | -49.12 | 506.88 | 2003-09-30 | 2003-09-30
10 | Gullixon Eric |  | Eric Gullixon | 1 | Systems Analyst | GYUV | M-4 | 766-8964 | I | Y | 202 | 2002-05-06 | 2003-07-16 | 62.2857 | 3.2431 | 8.108% | 117.5 | 0.092929 | 84.98 | -0.070692 | -0.1767% | 202.48 | -0.48 | 2003-04-22 | 4.6597 | -112.8403 | 0 | Eric | -4.97 | 197.03 | 2003-06-25 | 2003-06-20
11 | Scott Gary |  | Gary Scott | 1 | Planner(backup) | JGB7 | M-4 | 735-6017 | E | Y | 30 | 2003-05-15 | 2003-06-16 | 4.5714 | 6.5625 | 16.41% | 4 | 0.0033031 | 26 | -0.021552 | -0.05388% | 30 | 0 |  | -17.8161 | -21.8161 | 0 | Gary | -30
12 | Murthy J |  | J Murthy | 1 | Systems Analyst | HKCE | L-3 | 735-9081 | E | Y | 1700 | 2002-05-06 | 2003-09-30 | 73.1429 | 23.2422 | 58.11% | 1447 | 1.1444 | 310.98 | -0.26105 | -0.6526% | 1757.98 | -57.98 | 2003-04-22 | 57.3841 | -1389.6159 | 0 | Murthy | -324.54 | 1375.46 | 2003-09-30 | 2003-09-30
13 | Nutt John |  | John Nutt | 1 | Systems Analyst | IV1P | M-4 | 735-8786 | I | N | 300 | 2002-10-18 | 2003-09-15 | 47.4286 | 6.3253 | 15.81% | 144 | 0.11605 | 155.98 | -0.1307 | -0.3268% | 299.98 | 0.02 | 2003-04-22 | 3.0836 | -140.9164 | 0 | John | -45.47 | 254.53 | 2003-09-15 | 2003-09-15
14 | Shanmugam Kasi |  | Kasi Shanmugam | 1 | Systems Analyst | LU1B | M-3 | 763-5310 | E | N | 120 | 2002-12-23 | 2003-09-30 | 40.1429 | 2.9893 | 7.473% | 54 | 0.043852 | 65.97 | -0.055378 | -0.1384% | 119.97 | 0.03 |  | -235.6313 | -289.6313 | 0 | Kasi | -120 |  | 2003-09-30 | 2003-09-30
15 | Miller Kim |  | Kim Miller | 1 | Systems Analyst | A0CA | JACKSONVILLE OP CNTR, Florida | 888-758-1908 | I | N | 50 | 2002-12-06 | 2003-09-30 | 42.5714 | 1.1745 | 2.936% | 63 | 0.05106 |  | 0 | -0% | 63 | -13 |  | -274.2381 | -337.2381 | 0 | Kim | -50 |  | 2003-09-30 | 2003-09-30
16 | Reddy Lakshmi Narayana |  | Lakshmi Narayana Reddy | 1 | Systems Analyst | H503 | K-4 | 735-1199 | E | Y | 302 | 2002-05-06 | 2003-09-30 | 73.1429 | 4.1289 | 10.32% | 144 | 0.11389 | 157.97 | -0.13261 | -0.3315% | 301.97 | 0.03 | 2003-04-22 | 5.7107 | -138.2893 | 0 | Lakshmi | 145.08 | 447.08 | 2003-09-30 | 2003-09-30
17 | Lee Mary Kasley |  | Mary Kasley Lee | 1 | Systems Analyst | A2KO | H-3 | 763-3729 | I | N | 124 | 2002-07-15 | 2003-05-07 | 42.2857 | 2.9324 | 7.331% | 92.25 | 0.073541 | 31.75 | -0.026194 | -0.06548% | 124 | 0 | 2003-04-22 | 2.9521 | -89.2979 | 0 | Mary | 95.96 | 219.96 | 2003-04-30 | 2003-04-30
18 | Celeschi Michelle |  | Michelle Celeschi | 1 | OSS(ASA) | L2O5 | M-4 | 766-7646 | I | N | 354 | 2002-05-06 | 2003-09-30 | 73.1429 | 4.8398 | 12.1% | 226.75 | 0.17933 | 144.97 | -0.12169 | -0.3042% | 371.72 | -17.72 | 2003-04-22 | 8.9923 | -217.7577 | 0 | Michelle | 87.76 | 441.76 | 2003-04-28 | 2003-09-30
19 | Baugh Sally |  | Sally Baugh | 1 | Test Technicial | H43F | M-4 | 763-8058 | I | N | 20 | 2002-12-02 | 2003-09-30 | 43.1429 | 0.46358 | 1.159% | 23.5 | 0.019038 |  | 0 | -0% | 23.5 | -3.5 |  | -102.2369 | -125.7369 | 0 | Sally | -20 |  | 2003-12-31 | 2003-12-31
20 | Ramachandran Santosh [H6Z5] |  | Santosh Ramachandran | 1 | Scripting | NCWF | K-4 | 763-3097 | E | N | 25 | 2003-04-28 | 2003-05-30 | 4.5714 | 5.4688 | 13.67% | 6 | 0.0049448 | 19 | -0.015718 | -0.03929% | 25 | 0 |  | -26.6586 | -32.6586 | 0 | Santosh | -25
21 | Durnan Steve |  | Steve Durnan | 1 | MQ series | JYHJ | M-2 | 735-1604 | I | N | 162 | 2002-10-18 | 2003-09-30 | 49.5714 | 3.268 | 8.17% | 171.5 | 0.13821 | 20.47 | -0.017183 | -0.04296% | 191.97 | -29.97 | 2003-04-22 | 3.6725 | -167.8275 | 0 | Durnan | 43 | 205 | 2003-09-30 | 2003-09-30
22 | Hall Steve |  | Steve Hall | 1 | Test Specialist | JH2T | L-4 | 763-7830 | I | Y | 775 | 2002-05-06 | 2003-09-30 | 73.1429 | 10.5957 | 26.49% | 675 | 0.53385 | 182 | -0.15278 | -0.3819% | 857 | -82 | 2003-04-22 | 26.7687 | -648.2313 | 0 | SteveH | -199.37 | 575.63 | 2003-09-30 | 2003-09-30
23 | Witter Steve |  | Steve Witter | 1 | Systems Analyst | GBHZ | L-3 | 763-3870 | I | N | 775 | 2002-07-15 | 2003-11-18 | 70.1429 | 11.0489 | 27.62% | 809 | 0.64493 | 14.98 | -0.012649 | -0.03162% | 823.98 | -48.98 | 2003-04-22 | 25.8892 | -783.1108 | 0 | Witter | -187.36 | 587.64 | 2003-09-26 | 2003-09-26
24 | Saha Sushit |  | Sushit Saha | 1 | Security Analyst | J0ZU | K-4 | 766-4883 | I | N | 117 | 2002-10-21 | 2003-09-30 | 49.1429 | 2.3808 | 5.952% | 62 | 0.049984 | 61.98 | -0.052029 | -0.1301% | 123.98 | -6.98 | 2003-04-22 | 1.3067 | -60.6933 | 0 | Sushit | -79.47 | 37.53 | 2003-09-30 | 2003-09-30
25 | Dobrinich Tina L |  | Tina L Dobrinich | 1 | Business Analyst | A1BO | K-4 | 763-3613 | I | Y | 550 | 2002-05-06 | 2003-09-30 | 73.1429 | 7.5195 | 18.8% | 444.5 | 0.35155 | 141 | -0.11836 | -0.2959% | 585.5 | -35.5 | 2003-04-22 | 17.6277 | -426.8723 | 0 | Tina | -114.31 | 435.69 | 2003-09-30 | 2003-09-30
26 | Hartness Ty |  | Ty Hartness | 1 | Systems Analyst | BR7P | M-1 | 766-6133 | I | N | 134 | 2002-07-15 | 2003-05-06 | 42.1429 | 3.1797 | 7.949% | 116 | 0.092474 | 17.75 | -0.014642 | -0.03661% | 133.75 | 0.25 | 2003-04-22 | 3.7122 | -112.2878 | 0 | Ty | 57.56 | 191.56 | 2003-04-30 | 2003-03-13
27 | Dejaynes Vance |  | Vance Dejaynes | 1 | Project Coordinator | GJ78 | K-4 | 763-3867 | I | Y | 990 | 2002-07-25 | 2003-09-30 | 61.7143 | 16.0417 | 40.1% | 325 | 0.25938 | 671 | -0.56327 | -1.408% | 996 | -6 | 2003-04-22 | 10.0418 | -314.9582 | 0 | Vance | 14 | 1004 | 2003-08-19 | 2003-08-19
28 | Awan Zafar |  | Zafar Awan | 1 | Test Analyst | BE36 | H-2 | 763-8880 | I | N | 50 | 2002-10-21 | 2003-09-30 | 49.1429 | 1.0174 | 2.544% | 48 | 0.038697 | 1.98 | -0.0016621 | -0.004155% | 49.98 | 0.02 | 2003-04-22 | 1.0117 | -46.9883 | 0 | Zafar | -50 |  | 2003-09-30 | 2003-09-30
29 | Woodman Andrew | Y | Andrew Woodman | 2 | Systems Analyst | H2K0 | M-4 | 766-5076 | I | N | 57 | 2003-03-20 | 2003-07-31 | 19 | 3 | 7.5% | 22 | 0.018048 | 35.48 | -0.029567 | -0.07392% | 57.48 | -0.48 |  | -97.201 | -119.201 | 0 | Andrew | -57
30 | McKinney Brian | Y | Brian McKinney | 2 | Business Analyst | CWA1 | M-4 | 766-0358 | I | N | 11 | 2003-03-17 | 2003-09-30 | 28.1429 | 0.39086 | 0.9772% | 23.5 | 0.019272 |  | 0 | -0% | 23.5 | -12.5 |  | -103.7836 | -127.2836 | 0 | Brian | -11
31 | Paige Charles | Y | Charles Paige | 2 | IIA-Team Coordinator | LL7M | H-3 | 735-4568 | E | Y | 70 | 2002-10-07 | 2003-05-07 | 30.2857 | 2.3113 | 5.778% | 56.5 | 0.045476 | 13.5 | -0.011138 | -0.02784% | 70 | 0 | 2003-04-22 | 1.2798 | -55.2202 | 0 | Charles | -20 | 50 | 2003-06-12 | 2003-05-05
32 | Lade Daniel | Y | Daniel Lade | 2 | IIA-Network Impact Assessment Analyst | J4SV | H-4 | 763-9136 | E | N | 55 | 2002-10-07 | 2003-09-30 | 51.1429 | 1.0754 | 2.689% | 47.5 | 0.038232 | 7.48 | -0.0062791 | -0.0157% | 54.98 | 0.02 | 2003-04-22 | 1.076 | -46.424 | 0 | Daniel | -30 | 25 | 2003-09-30 | 2003-09-30
33 | Sanders Dave | Y | Dave Sanders | 2 | IIA-Windows Performance Analyst | NBUD | H-3 | 766-5836 | E | N | 11 | 2002-10-07 | 2003-09-30 | 51.1429 | 0.21508 | 0.5377% | 10.75 | 0.0086526 |  | 0 | -0% | 10.75 | 0.25 | 2003-04-22 | 0.24351 | -10.5065 | 0 | Dave | 39 | 50 | 2003-09-30 | 2003-09-30
34 | Saenz Gilbert | Y | Gilbert Saenz | 2 | IIA-IBM MF Performamnce Analyst | J5OY | H-4 | 763-4304 | E | N | 25 | 2002-10-07 | 2003-08-26 | 46.1429 | 0.5418 | 1.354% | 8 | 0.0064391 | 16.97 | -0.014186 | -0.03546% | 24.97 | 0.03 | 2003-04-22 | 0.18122 | -7.8188 | 0 | Gilbert | 0 | 25 | 2003-08-26 | 2003-08-26
35 | Ma Harry | Y | Harry Ma | 2 | IIA-Proactive Performance Engineering Analyst | NAKR | H-4 | 766-2968 | E | N | 100 | 2002-10-07 | 2003-09-30 | 51.1429 | 1.9553 | 4.888% | 78.75 | 0.063385 | 21.23 | -0.017821 | -0.04455% | 99.98 | 0.02 | 2003-04-22 | 1.7838 | -76.9662 | 0 | Harry | 100 | 200 | 2003-09-30 | 2003-09-30
36 | Isaacson John | Y | John Isaacson | 2 | ? | GDP4 | K-4 | 763-3958 | I | N | 40 | 2002-08-01 | 2003-02-28 | 30.1429 | 1.327 | 3.318% | 40.5 | 0.032349 |  | 0 | -0% | 40.5 | -0.5 | 2003-04-22 | 1.22 | -39.28 | 0 | JohnI | -40 |  | 2003-04-22 | 2003-02-28
37 | Flannelly Lynn C | Y | Lynn C Flannelly | 2 |  | A6AK | C-3 | 766-8107 | I | N |  | 2002-11-01 | 2003-02-28 | 17 | 0 | 0% |  | 0 |  | 0 | -0% | 0 | 0 | 2003-04-22 | 0 | 0 | 0 | Lynn | 41.2 | 41.2 | 2003-04-22 | 2003-02-28
38 | Frey Michael | Y | Michael Frey | 2 | Systems Analyst | CS8K | VISALIA | 625-6920 | I | Y | 212 | 2002-05-06 | 2003-02-28 | 42.5714 | 4.9799 | 12.45% | 290 | 0.22936 |  | 0 | -0% | 290 | -78 | 2003-04-22 | 11.5006 | -278.4994 | 0 | Michael | -51.72 | 160.28 | 2003-04-04 | 2003-02-28
39 | Leslie Sherrill |  | Sherrill Leslie | 2 | IIA-Network Performance Analyst | H48H | H-4 | 735-3968 | I | N | 25 | 2002-10-07 | 2003-06-25 | 37.2857 | 0.6705 | 1.676% | 20 | 0.016098 | 4.98 | -0.0041324 | -0.01033% | 24.98 | 0.02 | 2003-04-22 | 0.45304 | -19.547 | 0 | Sherrill | 0 | 25 | 2003-06-25 | 2003-06-25
40 | Austin Brenda |  | Brenda Austin | 4 | ISC Contact Person | AAZW | ALPHARETTA OP CNTR | 770-521-7054 | I | N |  |  |  | 0 | 0 | 0% |  | 0 |  | 0 | -0% | 0 | 0 |  | 0 | 0 | 0 | Brenda | 0
41 | Voyles Carey |  | Carey Voyles | 4 |  | LLGX | K-4 | 763-5149 | E | N |  |  |  | 0 | 0 | 0% |  | 0 |  | 0 | -0% | 0 | 0 |  | 0 | 0 | 0 | Carey | 0
42 | Houchin Janie |  | Janie Houchin | 4 |  | AKIC | M-4 | 766-5375 | I | N |  |  |  | 0 | 0 | 0% |  | 0 |  | 0 | -0% | 0 | 0 |  | 0 | 0 | 0 | Janie | 0
43 | Fry Liz |  | Liz Fry | 4 |  | GCJE | C-3 | 766-0659 | I | N |  |  |  | 0 | 0 | 0% |  | 0 |  | 0 | -0% | 0 | 0 |  | 0 | 0 | 0 | Liz | 0
Note on B1: L968;JQL2; C4ZZ; HSQC; GB8T; GDQM; JLC1; INZO; LMX7; HU6Z; LFRO; I10H; I0BG; HWS4; LOB8; HO83; I0QE; JN42; HMXI; LNJK; G3B8;H6KX; BH4J
Note on B2: This column contains the names of persons as written in PlanView. In PlanView Second name is written first followed by first name. Therefore if a resource is not allocated in PlanView, this column will be BLANK. Information in this column is pasted from a direct cut from R_DT_CD1 report generated from PlanView. You may have to export this report to excel and sort it on name. If a new name is added in PlanView, a row has to be inserted at proper place to enter information about new person. Similarly you have to identify if a person is removed from PlanView. In this case you have to move this person to the end of this list for retaining record i.e. information is not deleted.
Note on C2: Y - indicates that this resource is authorized I.e. not allocated in PlanView. Allocation is indicated by a BLANK value.
Note on D2: Except assigned role, all personal information is taken from Outlook global address address. Information is updated mannually. Assigned role information is taken initially from team roaster and later from PAR.
Note on D11: Backup for Sushit Shah.
Note on E3: 1 = Active & Allocated 2 = Active & Authorized 3 = Inactive at present 4 = No more in project
Note on F3: PP - Project Planner WTA - Web Technology Analyst MQS - MQ Series MWA - Middleware Analyst TechC - Technical Coordinator NOSR - NOS Rep TC - Testing Coordinator DS - Data Security PM - Project Manager NTA - Network Tech Analyst HS - Hardware Specialist
Note on K2: I = Internal E = External
Note on M3: Assigned hours are initially (at the begining of the project) taken from PlanView Report R_TR_001 and later updated based on PAR or correction to PlanView remaining hours. Normally this figure should be equal to sum of cummulative used hours and remaining hours. When a person is authisized instead of allocated in PlanView, this cell value should be set to the cell value in actual used hours column i.e. used hours becomes the assigned hours. This column is normally updated manually.
Note on R3: Assigned Hours Average Loading % = ---------------------- Work Days * 7.75 Work Days = (To date - from date) *5/7 Where 7.75 is working hours per day. 5 is working days per week 7 is days in week. (to date - from date) is calender days. This index indicates that the person is likely to devote this much %age of available work time to this project. Total available work time being 100%.
Note on T3: This column contains the actual cummulative logged hours in Time Reporter by a person. Values in this column are updated by pasting direct cut from R_DT_CD1 PlanView report. (R_DT_CD1 have to be exported to xls and then sorted on name before cut and paste operation).
Note on AC3: Internal Resources Needing less than 25 hours may be authorized rather than submitting a PAR extension.
Note on AH3: Values in Red Color are excess allocations. Values is black are short of allocations.
OL Address
Refresh Team Address 79
AddressList
SetupMeeting
◄▬Menu

## AllTasks
Proj. 1234 | Proj. 1234 All Tasks List |  | as on | 2003-06-10 |  | 32 | 1900-06-27
Lead | Task Code | Task Name | % Work Completed | Work in Hours | Duration in Days | Planned Start Date | Planned Finish date | Duration Completed | Successors | BaseLine Work | Earned Value | Summary Yes/No | Indent Level | Predecessor | Resources | Baseline Start date | Baseline Finish date | Datelast Updated
| 1 | Auto Necho - Auto Apps Efficiency | 87% | 10,779.01 h | 372.87 d | 2002-05-06 | 2003-09-26 | 82% |  | 10,709.01 h | 8921.48 | Yes | 1 |  |  | 2002-05-06 08:00 | 2003-08-28 09:44 | NA
| 2 | Planning/Admin/Meetings/Coordination | 79% | 4,287.01 h | 371.87 d | 2002-05-06 | 2003-09-25 | 74% |  | 4,287 h | 3080.48 | Yes | 1.1 |  |  | 2002-05-06 08:00 | 2003-09-12 15:00 | NA
Carol | 3 | MS: Project Activated | 100% | 0 h | 0 d | 2002-05-06 | 2002-05-06 | 0% | 11 | 0 h | 0 | No | 1.1.1 |  |  | 2002-05-06 08:00 | 2002-05-06 08:00 | NA
| 4 | Project Admin & Cordination | 82% | 3,514 h | 342.35 d | 2002-05-06 | 2003-08-15 | 80% |  | 3,514 h | 2571.23 | Yes | 1.1.2 |  |  | 2002-05-06 08:00 | 2003-09-05 15:33 | NA
Ashok | 5 | Project Management Activities | 84% | 750 h | 342 d | 2002-05-06 | 2003-08-15 | 81% |  | 699 h | 587.16 | No | 1.1.2.1 |  | Carol[35%] | 2002-05-06 08:00 | 2003-04-21 16:15 | NA
Ashok | 6 | Project Coordination Activities | 80% | 964 h | 281 d | 2002-07-26 | 2003-08-15 | 77% |  | 964 h | 771.2 | No | 1.1.2.2 |  | Vance[63%] | 2002-07-26 08:00 | 2003-04-21 15:30 | NA
Ashok | 7 | SSS activities | 85% | 350 h | 342 d | 2002-05-06 | 2003-08-15 | 81% |  | 349 h | 296.65 | No | 1.1.2.3 |  | Michelle[17%] | 2002-05-06 08:00 | 2003-04-21 16:15 | NA
Ashok | 8 | Team Weekly Meetings | 83% | 1,000 h | 341.99 d | 2002-05-06 | 2003-08-15 | 81% |  | 712 h | 590.96 | No | 1.1.2.4 |  | Carol[4%],Michelle[3%],Ashok[3%],Ed[3%],Eric[3%],Murthy[3%],Jill[3%],Lakshmi[4%],Witter[3%],SteveH[3%],Tina[3%],Ty[3%],Mary[3%],Amar,John,Bill | 2002-05-06 08:00 | 2003-04-21 16:15 | NA
Ashok | 9 | Project Schedule / PlanView Maintenance, and Status Reporting | 78% | 450 h | 267 d | 2002-08-15 | 2003-08-15 | 76% |  | 417 h | 325.26 | No | 1.1.2.5 |  | Ashok[29%] | 2002-08-15 08:00 | 2003-04-21 10:15 | NA
| 10 | Project Charter, Plan & Schedule | 100% | 358 h | 151.74 d | 2002-05-21 | 2002-12-16 | 100% |  | 358 h | 358 | Yes | 1.1.3 |  |  | 2002-05-21 08:00 | 2002-11-20 10:45 | NA
Carol | 11 | Prepare & Review Project Charter | 100% | 67 h | 35 d | 2002-05-21 | 2002-07-05 | 100% | 12,14,15,29FS-2 d | 67 h | 67 | No | 1.1.3.1 | 3 | Carol[16%],Ashok[3%],Michelle[3%],Ed[8%],Eric[8%],Murthy[5%],Jill[5%],Lakshmi[5%],Witter[5%],SteveH[5%],Tina[5%] | 2002-05-21 08:00 | 2002-06-17 11:00 | NA
Carol | 12 | MS: Project Charter Reviewed | 100% | 0 h | 0 d | 2002-07-05 | 2002-07-05 | 100% | 13 | 0 h | 0 | No | 1.1.3.2 | 11 |  | 2002-06-17 11:00 | 2002-06-17 11:00 | NA
Carol | 13 | MS: Project Charter Authorized | 100% | 0 h | 0 d | 2002-08-30 | 2002-08-30 | 100% | 23 | 0 h | 0 | No | 1.1.3.3 | 12 |  | 2002-06-17 11:00 | 2002-06-17 11:00 | NA
Carol | 14 | Facilitation management Processes | 100% | 33 h | 55 d | 2002-07-05 | 2002-09-19 | 100% |  | 33 h | 33 | No | 1.1.3.4 | 11 | Carol[4%],Ashok[3%],Michelle[3%],Ed[5%],Eric[5%],Murthy[5%],Jill[5%],Lakshmi[5%],Witter[5%],SteveH[5%],Tina[5%] | 2002-06-17 11:00 | 2002-07-08 16:00 | NA
Carol | 15 | Prepare & review Project Plan | 100% | 38 h | 64 d | 2002-07-05 | 2002-10-01 | 100% | 16,18FF | 38 h | 38 | No | 1.1.3.5 | 11 | Carol[16%],Ashok[2%],Michelle[3%],Ed[5%],Eric[5%],Murthy[5%],Jill[5%],Lakshmi[5%],Witter[5%],SteveH[5%],Tina[5%] | 2002-06-17 11:00 | 2002-07-05 16:15 | NA
Carol | 16 | MS: Project Plan Reviewed | 100% | 0 h | 0 d | 2002-10-01 | 2002-10-01 | 100% | 17FS+3 d | 0 h | 0 | No | 1.1.3.6 | 15 |  | 2002-07-05 16:15 | 2002-07-05 16:15 | NA
Carol | 17 | MS: Project Plan Authorized | 100% | 0 h | 0 d | 2002-10-04 | 2002-10-04 | 100% |  | 0 h | 0 | No | 1.1.3.7 | 16FS+3 d |  | 2002-07-05 16:15 | 2002-07-05 16:15 | NA
Ashok | 18 | Project Schedule Development -1 | 100% | 110 h | 60 d | 2002-05-28 | 2002-08-16 | 100% | 19 | 110 h | 110 | No | 1.1.3.8 | 15FF | Ashok[10%],Carol[16%],Ed[8%],Eric[8%],Murthy[5%],Jill[5%],Lakshmi[5%],Witter[5%],Tina[5%] | 2002-05-28 08:00 | 2002-08-16 09:00 | NA
Ashok | 19 | MS: Performance Measurement Baseline - 1 Established | 100% | 0 h | 0 d | 2002-08-16 | 2002-08-16 | 100% |  | 0 h | 0 | No | 1.1.3.9 | 18 |  | 2002-08-16 09:00 | 2002-08-16 09:00 | NA
Ashok | 20 | Project Schedule Development -2 | 100% | 110 h | 43 d | 2002-09-18 | 2002-11-15 | 100% | 21 | 110 h | 110 | No | 1.1.3.10 | 92FS-40 d | Ashok[17%],Carol[16%],Ed[8%],Eric[8%],Murthy[5%],Jill[5%],Lakshmi[5%],Witter[6%],Tina[6%] | 2002-10-09 10:30 | 2002-11-19 11:00 | NA
Ashok | 21 | MS: Performance Measurement Baseline - 2 Established | 100% | 0 h | 0 d | 2002-12-16 | 2002-12-16 | 100% |  | 0 h | 0 | No | 1.1.3.11 | 20 |  | 2002-11-19 11:00 | 2002-11-20 10:45 | NA
| 22 | SP/IP | 50% | 40 h | 280 d | 2002-09-06 | 2003-09-25 | 90% |  | 40 h | 20 | Yes | 1.1.4 |  |  | 2002-11-05 14:30 | 2003-04-21 08:15 | NA
Vance | 23 | Create Initial SPIP Participant Charts | 100% | 20 h | 86 d | 2002-09-06 | 2003-01-06 | 100% |  | 20 h | 20 | No | 1.1.4.1 | 13 | Carol[26%] | 2002-11-05 14:30 | 2002-11-19 10:59 | NA
Carol | 24 | Authorize final SPIP for transition | 0% | 20 h | 10 d | 2003-09-11 | 2003-09-25 | 0% |  | 20 h | 0 | No | 1.1.4.2 | 373FS-11 d | Carol[26%] | 2003-04-07 10:45 | 2003-04-21 08:15 | NA
|  | IIA | 35% | 375 h | 230 d | 2002-10-07 | 2003-08-18 | 1% |  | 0 h | 131.25 | Yes | 1.1.5 |  |  | NA | NA | NA
Ashok | 24a | IIA Team (Performance Impact Accessment) | 35% | 375 h | 230 d | 2002-10-07 | 2003-08-18 | 1% |  | 375 h | 131.25 | No | 1.1.5.1 |  | Charles,Daniel,Sherrill,Dave,Harry[18%],Gilbert | 2002-10-07 08:00 | 2003-08-18 15:30 | NA
| 25 | Reqs Analysis and Solution Def/Specs | 100% | 2,054 h | 126 d | 2002-06-13 | 2002-12-04 | 100% |  | 2,271 h | 2054 | Yes | 1.2 |  |  | 2002-06-13 11:30 | 2002-11-15 11:30 | NA
| 26 | SRA / SDS | 100% | 1,731 h | 119.29 d | 2002-06-13 | 2002-11-22 | 100% |  | 1,848 h | 1731 | Yes | 1.2.1 |  |  | 2002-06-13 11:30 | 2002-10-30 10:00 | NA
ED | 27 | Determine Business Requirements | 100% | 10 h | 24 d | 2002-06-13 | 2002-07-16 | 100% | 30FS+6 d,80,46SS,74,52,57,62,70 | 10 h | 10 | No | 1.2.1.1 | 11FS-2 d | Ed[3%],Tina[3%] | 2002-06-13 11:30 | 2002-07-16 14:30 | NA
ED | 28 | Review Testable Business Requirements | 100% | 24 h | 1 d | 2002-07-24 | 2002-07-25 | 100% | 94,32FS+5 d,31FS+1 d | 24 h | 24 | No | 1.2.1.2 | 29FS+6 d | Ed[26%],Carol[50%],Ashok[40%],Eric[40%],Murthy,Jill[40%],Lakshmi,Witter[40%],SteveH[40%],Tina,Amar,Michelle[40%] | 2002-07-24 13:00 | 2002-07-25 11:45 | NA
ED | 29 | Review Business Requirements | 100% | 8 h | 1 d | 2002-07-26 | 2002-07-29 | 100% | 34,41FS+1 d | 8 h | 8 | No | 1.2.1.3 | 30FS+1 d | Ed,Carol[50%],Tina,Eric[26%] | 2002-07-26 11:30 | 2002-07-29 11:15 | NA
ED | 30 | MS: Business Req approved | 100% | 0 h | 0 d | 2002-08-01 | 2002-08-01 | 100% | 33FS+2 d | 0 h | 0 | No | 1.2.1.4 | 30FS+5 d |  | 2002-08-01 10:30 | 2002-08-01 10:30 | NA
Ashok | 32 | Technical discussion meetings | 100% | 480 h | 64 d | 2002-08-05 | 2002-11-08 | 100% |  | 480 h | 480 | No | 1.2.1.5 | 91FF,32FS+2 d | Ed[8%],Eric[8%],Murthy[10%],Jill[8%],Lakshmi[11%],Witter[8%],SteveH[8%],Tina[10%],Ty[8%],Mary[8%],Amar[8%],John[8%] | 2002-08-05 10:00 | 2002-10-30 10:00 | NA
Amar | 33 | Create New ECHO Screen Layout | 100% | 5 h | 3 d | 2002-07-29 | 2002-08-01 | 100% |  | 5 h | 5 | No | 1.2.1.6 | 31 | Tina[22%] | 2002-07-29 11:15 | 2002-08-01 10:30 | NA
| 34 | Domain Specs | 100% | 13 h | 42 d | 2002-07-30 | 2002-09-25 | 100% |  | 13 h | 13 | Yes | 1.2.1.7 |  |  | 2002-07-30 11:00 | 2002-09-27 16:45 | NA
Jill | 35 | DOMAIN - review existing territory validation | 100% | 3 h | 24 d | 2002-07-30 | 2002-08-30 | 100% |  | 3 h | 3 | No | 1.2.1.7.1 |  | Jill[39%] | 2002-07-30 11:00 | 2002-07-31 10:45 | NA
Jill | 36 | DOMAIN - review existing IRG validation | 100% | 3 h | 23 d | 2002-07-31 | 2002-08-30 | 100% |  | 3 h | 3 | No | 1.2.1.7.2 |  | Jill[8%] | 2002-07-31 10:45 | 2002-08-07 09:30 | NA
Jill | 37 | DOMAIN - review existing driver's license validation | 100% | 3 h | 23 d | 2002-07-31 | 2002-08-30 | 100% | 44 | 3 h | 3 | No | 1.2.1.7.3 |  | Jill[8%] | 2002-07-31 10:45 | 2002-08-07 09:30 | NA
Jill | 38 | Create SRA 4/SDS 3.1 identifying impacted reusable service areas | 100% | 4 h | 18 d | 2002-08-30 | 2002-09-25 | 100% | 90 | 4 h | 4 | No | 1.2.1.7.4 | 44SS | Jill[2%],Ed[40%],Tina[40%] | 2002-09-27 08:00 | 2002-09-27 16:45 | NA
| 39 | AUTO Specs | 100% | 45 h | 19 d | 2002-07-30 | 2002-08-23 | 100% |  | 45 h | 45 | Yes | 1.2.1.8 |  |  | 2002-07-30 11:00 | 2002-08-23 15:15 | NA
Eric | 40 | AUTO - review existing territory validation | 100% | 15 h | 19 d | 2002-07-30 | 2002-08-23 | 100% | 42FF,44,43FF | 15 h | 15 | No | 1.2.1.8.1 | 31FS+1 d | Eric[10%] | 2002-07-30 11:00 | 2002-08-23 15:15 | NA
Eric | 41 | AUTO - review existing IRG validation | 100% | 15 h | 19 d | 2002-07-30 | 2002-08-23 | 100% |  | 15 h | 15 | No | 1.2.1.8.2 | 41FF | Eric[10%] | 2002-07-30 11:00 | 2002-08-23 15:15 | NA
Eric | 42 | AUTO - review existing driver's license validation | 100% | 15 h | 19 d | 2002-07-30 | 2002-08-23 | 100% | 90 | 15 h | 15 | No | 1.2.1.8.3 | 41FF | Eric[10%] | 2002-07-30 11:00 | 2002-08-23 15:15 | NA
Ty | 43 | Determine Validation Components for ECHO & AUI | 100% | 48 h | 18 d | 2002-08-30 | 2002-09-25 | 100% | 39SS,87SS+10 d,106SS+5 d,109FF | 48 h | 48 | No | 1.2.1.9 | 41,38 | Eric[6%],Ty,Mary,Tina,Jill[6%],Witter[6%] | 2002-08-23 15:15 | 2002-09-26 17:00 | NA
| 44 | ECHO Specs | 100% | 988 h | 105.71 d | 2002-06-13 | 2002-11-04 | 100% |  | 1,076 h | 988 | Yes | 1.2.1.10 |  |  | 2002-06-13 11:30 | 2002-10-21 08:30 | NA
Amar | 45 | Understand existing ECHO APPS System | 100% | 240 h | 50 d | 2002-06-13 | 2002-08-20 | 100% |  | 240 h | 240 | No | 1.2.1.10.1 | 29SS | Murthy[70%],Amar[70%] | 2002-06-13 11:30 | 2002-07-12 15:00 | NA
| 46 | Address Standradisation- Auto Main Screen | 100% | 88 h | 60 d | 2002-07-29 | 2002-10-18 | 100% |  | 88 h | 88 | Yes | 1.2.1.10.2 |  |  | 2002-07-29 16:45 | 2002-09-27 | NA
Amar | 47 | Analysing the requirements(69) | 100% | 36 h | 46 d | 2002-07-29 | 2002-09-30 | 100% | 49 | 36 h | 36 | No | 1.2.1.10.2.1 |  | Amar[52%] | 2002-07-29 16:45 | 2002-08-09 14:30 | NA
Amar | 48 | Design the Highlevel Specs(70) | 100% | 44 h | 10 d | 2002-09-30 | 2002-10-14 | 100% | 50 | 44 h | 44 | No | 1.2.1.10.2.2 | 48 | Amar[36%],Lakshmi,Tina | 2002-09-09 08:00 | 2002-09-20 14:30 | NA
Amar | 49 | Review of Highlevel Specs(71) | 100% | 8 h | 4 d | 2002-10-14 | 2002-10-18 | 100% | 77 | 8 h | 8 | No | 1.2.1.10.2.3 | 49 | Amar[6%],Lakshmi,Tina | 2002-09-23 09:00 | 2002-09-27 | NA
| 50 | VIN Validation | 100% | 56 h | 20.1 d | 2002-09-03 | 2002-09-30 | 100% |  | 56 h | 56 | Yes | 1.2.1.10.3 |  |  | 2002-08-01 08:00 | 2002-09-16 11:00 | NA
Amar | 51 | Analysing the requirements(59) | 100% | 25 h | 10 d | 2002-09-03 | 2002-09-16 | 100% | 53,54 | 25 h | 25 | No | 1.2.1.10.3.1 | 29 | Murthy[33%],Amar | 2002-08-01 08:00 | 2002-08-14 14:30 | NA
Amar | 52 | Design the Highlevel Specs-1(60) | 100% | 8 h | 4 d | 2002-09-16 | 2002-09-20 | 100% |  | 8 h | 8 | No | 1.2.1.10.3.2 | 52 | Murthy[26%] | 2002-08-14 14:30 | 2002-09-02 13:45 | NA
Amar | 53 | Design the Highlevel Specs-2(61) | 100% | 15 h | 9.1 d | 2002-09-16 | 2002-09-27 | 100% | 55 | 15 h | 15 | No | 1.2.1.10.3.3 | 52 | Murthy[9%],Amar,Lakshmi,Tina | 2002-09-02 13:45 | 2002-09-13 11:15 | NA
Amar | 54 | Review of Highlevel Specs(62) | 100% | 8 h | 1 d | 2002-09-27 | 2002-09-30 | 100% | 83 | 8 h | 8 | No | 1.2.1.10.3.4 | 54 | Murthy[103%],Amar,Lakshmi,Tina[39%] | 2002-09-13 11:15 | 2002-09-16 11:00 | NA
| 55 | MQseries/EUI Interface. | 100% | 88 h | 53.32 d | 2002-08-05 | 2002-10-15 | 100% |  | 88 h | 88 | Yes | 1.2.1.10.4 |  |  | 2002-08-05 09:30 | 2002-09-11 13:18 | NA
Amar | 56 | Analysing the requirements(64) | 100% | 34 h | 20 d | 2002-08-05 | 2002-09-13 | 100% | 58 | 34 h | 34 | No | 1.2.1.10.4.1 | 29 | Murthy[73%] | 2002-08-05 09:30 | 2002-08-13 | NA
Amar | 57 | Design the Highlevel Specs-1(65) | 100% | 12 h | 11 d | 2002-08-13 | 2002-09-27 | 100% | 59 | 12 h | 12 | No | 1.2.1.10.4.2 | 57 | Murthy[52%] | 2002-08-13 08:00 | 2002-08-15 16:15 | NA
Amar | 58 | Design the Highlevel Specs-2(66) | 100% | 34 h | 10 d | 2002-09-27 | 2002-10-11 | 100% | 60 | 34 h | 34 | No | 1.2.1.10.4.3 | 58 | Murthy[15%],Lakshmi,Tina | 2002-08-15 16:15 | 2002-09-09 15:45 | NA
Amar | 59 | Review of Highlevel Specs(67) | 100% | 8 h | 2 d | 2002-10-11 | 2002-10-15 | 100% | 83 | 8 h | 8 | No | 1.2.1.10.4.4 | 59 | Murthy[103%],Lakshmi[19%],Tina[19%] | 2002-09-09 15:45 | 2002-09-11 13:18 | NA
| 60 | Driver's Licence Validation | 100% | 91 h | 47.43 d | 2002-08-02 | 2002-10-07 | 100% |  | 91 h | 91 | Yes | 1.2.1.10.5 |  |  | 2002-08-02 10:30 | 2002-09-10 13:15 | NA
Amar | 61 | Analysing the requirements(51) | 100% | 25 h | 38 d | 2002-08-02 | 2002-09-24 | 100% | 63 | 25 h | 25 | No | 1.2.1.10.5.1 | 29 | Amar[32%] | 2002-08-02 10:30 | 2002-08-16 | NA
Amar | 62 | Design the Highlevel Specs(52) | 100% | 58 h | 9 d | 2002-09-20 | 2002-10-04 | 100% | 64 | 58 h | 58 | No | 1.2.1.10.5.2 | 62 | Murthy[29%],Amar,Lakshmi,Tina | 2002-08-16 08:00 | 2002-09-09 13:30 | NA
Amar | 63 | Review of Highlevel Specs(53) | 100% | 8 h | 1 d | 2002-10-04 | 2002-10-07 | 100% | 77 | 8 h | 8 | No | 1.2.1.10.5.3 | 63 | Murthy[103%],Lakshmi[26%],Tina[26%],Amar[26%] | 2002-09-09 13:30 | 2002-09-10 13:15 | NA
| 68 | Address Standradisation- Residence Address Scrn | 100% | 48 h | 29 d | 2002-09-16 | 2002-10-24 | 100% |  | 48 h | 48 | Yes | 1.2.1.10.6 |  |  | 2002-07-29 16:45 | 2002-09-16 15:00 | NA
Amar | 69 | Analysing the requirements(73) | 100% | 20 h | 15 d | 2002-09-16 | 2002-10-04 | 100% | 67 | 20 h | 20 | No | 1.2.1.10.6.1 |  | Amar[30%],Lakshmi[2%] | 2002-07-29 16:45 | 2002-08-28 09:30 | NA
Amar | 70 | Design the Highlevel Specs(74) | 100% | 20 h | 10 d | 2002-10-04 | 2002-10-18 | 100% | 68 | 20 h | 20 | No | 1.2.1.10.6.2 | 66 | Amar[18%],Lakshmi,Tina | 2002-08-28 09:30 | 2002-09-10 16:00 | NA
Amar | 71 | Review of Highlevel Specs(75) | 100% | 8 h | 4 d | 2002-10-18 | 2002-10-24 | 100% | 77 | 8 h | 8 | No | 1.2.1.10.6.3 | 67 | Amar[6%],Lakshmi,Tina | 2002-09-10 16:00 | 2002-09-16 15:00 | NA
| 72 | Teritory Validation | 100% | 120 h | 26 d | 2002-09-10 | 2002-10-15 | 100% |  | 120 h | 120 | Yes | 1.2.1.10.7 |  |  | 2002-09-10 08:00 | 2002-10-08 10:45 | NA
Amar | 73 | Analysing the requirements(47) | 100% | 48 h | 24 d | 2002-09-10 | 2002-10-11 | 100% |  | 48 h | 48 | No | 1.2.1.10.7.1 | 29 | Murthy[46%] | 2002-09-10 08:00 | 2002-09-23 14:30 | NA
Amar | 74 | Design the Highlevel Specs(48) | 100% | 64 h | 10 d | 2002-09-30 | 2002-10-14 | 100% | 72 | 64 h | 64 | No | 1.2.1.10.7.2 |  | Murthy[134%],Lakshmi,Tina | 2002-09-23 14:30 | 2002-10-07 11:00 | NA
Amar | 75 | Review of Highlevel Specs(49) | 100% | 8 h | 1 d | 2002-10-14 | 2002-10-15 | 100% | 77 | 8 h | 8 | No | 1.2.1.10.7.3 | 71 | Murthy[103%],Lakshmi[39%],Tina[39%] | 2002-10-07 11:00 | 2002-10-08 10:45 | NA
| 76 | AUI Driver Information Screen | 100% | 125 h | 81.71 d | 2002-07-16 | 2002-11-04 | 100% |  | 125 h | 125 | Yes | 1.2.1.10.8 |  |  | 2002-07-16 14:30 | 2002-10-21 08:30 | NA
Amar | 77 | Design of New screen(77) | 100% | 20 h | 5 d | 2002-07-16 | 2002-07-23 | 100% | 75 | 20 h | 20 | No | 1.2.1.10.8.1 | 29 | Amar[46%],Lakshmi | 2002-07-16 14:30 | 2002-07-23 13:15 | NA
Amar | 78 | Analysis of Flow of Data(78) | 100% | 25 h | 42 d | 2002-07-23 | 2002-09-18 | 100% | 76 | 25 h | 25 | No | 1.2.1.10.8.2 | 74 | Amar[31%],Lakshmi | 2002-07-23 13:15 | 2002-08-06 09:45 | NA
Amar | 79 | Analysis of Validations(79) | 100% | 32 h | 20 d | 2002-08-06 | 2002-10-07 | 100% | 77 | 32 h | 32 | No | 1.2.1.10.8.3 | 75 | Amar[46%] | 2002-08-06 09:45 | 2002-08-16 16:30 | NA
Amar | 80 | Design the Highlevel Specs(80) | 100% | 32 h | 8 d | 2002-10-24 | 2002-11-04 | 100% | 78SS | 32 h | 32 | No | 1.2.1.10.8.4 | 76,64,68,50,72 | Amar[66%],Lakshmi[142%],Tina | 2002-10-08 10:45 | 2002-10-21 08:30 | NA
Amar | 81 | Review of Highlevel Specs(81) | 100% | 16 h | 8 d | 2002-10-24 | 2002-11-04 | 100% | 85 | 16 h | 16 | No | 1.2.1.10.8.5 | 77SS | Amar[19%],Lakshmi,Tina | 2002-10-08 10:45 | 2002-10-21 08:30 | NA
| 82 | AUI request Screen | 100% | 132 h | 78.26 d | 2002-07-16 | 2002-10-30 | 100% |  | 132 h | 132 | Yes | 1.2.1.10.9 |  |  | 2002-07-16 14:30 | 2002-10-01 08:15 | NA
Amar | 83 | Design of New screen(83) | 100% | 20 h | 3 d | 2002-07-16 | 2002-07-19 | 100% | 81 | 20 h | 20 | No | 1.2.1.10.9.1 | 29 | Murthy[68%],Amar,Lakshmi | 2002-07-16 14:30 | 2002-07-19 13:45 | NA
Amar | 84 | Analysis of Flow of Data(84) | 100% | 66 h | 32 d | 2002-07-19 | 2002-09-16 | 100% | 82FF+2 d | 66 h | 66 | No | 1.2.1.10.9.2 | 80 | Murthy[77%],Amar,Lakshmi | 2002-07-19 13:45 | 2002-08-02 10:15 | NA
Amar | 85 | Design the Highlevel Specs-1(85) | 100% | 8 h | 24 d | 2002-08-02 | 2002-09-18 | 100% | 83 | 8 h | 8 | No | 1.2.1.10.9.3 | 81FF+2 d | Murthy[34%] | 2002-08-02 10:15 | 2002-08-07 09:29 | NA
Amar | 86 | Design the Highlevel Specs-2(86) | 100% | 28 h | 10 d | 2002-10-15 | 2002-10-29 | 100% | 84 | 28 h | 28 | No | 1.2.1.10.9.4 | 82,55,60 | Murthy[21%],Amar,Lakshmi,Tina | 2002-09-16 11:00 | 2002-09-30 08:30 | NA
Amar | 87 | Review of Highlevel Specs(87) | 100% | 10 h | 1 d | 2002-10-29 | 2002-10-30 | 100% | 85 | 10 h | 10 | No | 1.2.1.10.9.5 | 83 | Murthy[52%],Amar,Lakshmi,Tina | 2002-09-30 08:30 | 2002-10-01 08:15 | NA
Amar | 88 | MS: ECHO Specs completed | 100% | 0 h | 0 d | 2002-11-04 | 2002-11-04 | 100% | 90 | 0 h | 0 | No | 1.2.1.10.10 | 78,84 |  | 2002-10-21 08:30 | 2002-10-21 08:30 | NA
| 89 | AUI Specs | 100% | 75 h | 26 d | 2002-09-13 | 2002-10-18 | 100% |  | 75 h | 75 | Yes | 1.2.1.11 |  |  | 2002-09-06 11:45 | 2002-10-17 13:15 | NA
Witter | 90 | AUI - design address Std | 100% | 25 h | 10 d | 2002-09-13 | 2002-09-26 | 100% | 88,89 | 25 h | 25 | No | 1.2.1.11.1 | 44SS+10 d | Witter[32%] | 2002-09-06 11:45 | 2002-09-20 09:15 | NA
Witter | 91 | AUI - design driver's license validation | 100% | 25 h | 16 d | 2002-09-27 | 2002-10-18 | 100% |  | 25 h | 25 | No | 1.2.1.11.2 | 87 | Witter[25%] | 2002-09-20 09:15 | 2002-10-03 15:45 | NA
Witter | 92 | AUI - design VIN validation | 100% | 25 h | 16 d | 2002-09-27 | 2002-10-18 | 100% |  | 25 h | 25 | No | 1.2.1.11.3 | 87 | Witter[20%] | 2002-10-03 15:45 | 2002-10-17 13:15 | NA
ED | 96 | Update Delivery Specs Doc | 100% | 20 h | 1 d | 2002-11-04 | 2002-11-05 | 100% | 91 | 20 h | 20 | No | 1.2.1.12 | 43,39,85 | Ed[129%],Tina[129%] | 2002-10-22 08:15 | 2002-10-25 16:15 | NA
ED | 97 | Review SDS Doc | 100% | 15 h | 1 d | 2002-11-05 | 2002-11-06 | 100% | 33FF,92 | 15 h | 15 | No | 1.2.1.13 | 90 | Carol[97%],Michelle[13%],Ashok[13%],Ed[13%],Eric[13%],Murthy[13%],Jill[13%],Lakshmi[13%],Witter[13%],SteveH[13%],Tina[13%],Ty[13%],Mary[13%],Amar,John | 2002-10-25 16:15 | 2002-10-29 15:45 | NA
Carol | 98 | MS: SDS Doc Authorized | 100% | 0 h | 0 d | 2002-11-22 | 2002-11-22 | 100% | 20FS-40 d | 0 h | 0 | No | 1.2.1.14 | 91 |  | 2002-10-29 15:45 | 2002-10-29 15:45 | NA
| 99 | Testing Strategy and Test Plans | 100% | 111 h | 41.87 d | 2002-07-25 | 2002-09-20 | 100% |  | 211 h | 111 | Yes | 1.2.2 |  |  | 2002-07-25 11:45 | 2002-11-15 11:30 | NA
SteveH | 100 | Create Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 50 h | 32 d | 2002-07-25 | 2002-09-06 | 100% |  | 50 h | 50 | No | 1.2.2.1 | 30 | SteveH[59%] | 2002-07-25 11:45 | 2002-08-09 09:00 | NA
SteveH | 101 | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 11 h | 31 d | 2002-08-09 | 2002-09-20 | 100% |  | 11 h | 11 | No | 1.2.2.2 |  | SteveH[0%],Carol[0%],Ashok[0%],Ed[0%],Murthy[1%],Eric[0%],Jill[0%],Lakshmi[6%],Witter[0%],Tina[89%],Amar[0%],Ty[0%],Mary[0%] | 2002-08-09 09:00 | 2002-08-26 08:00 | NA
SteveH | 102 | Create Defect Tracking Strategy | 100% | 40 h | 10 d | 2002-08-26 | 2002-09-06 | 100% | 97 | 40 h | 40 | No | 1.2.2.3 |  | SteveH[52%] | 2002-08-26 08:00 | 2002-09-06 14:30 | NA
SteveH | 103 | Review Defect Tracking Strategy | 100% | 10 h | 5 d | 2002-09-06 | 2002-09-13 | 100% |  | 10 h | 10 | No | 1.2.2.4 | 96 | SteveH[1%],Carol[50%],Ashok[40%],Ed,Murthy,Eric[40%],Jill[40%],Lakshmi,Witter[40%],Tina,Amar,Ty,Mary | 2002-09-06 14:30 | 2002-09-13 13:15 | NA
| 108 | AIP | 100% | 212 h | 99.61 d | 2002-07-19 | 2002-12-04 | 100% |  | 212 h | 212 | Yes | 1.2.3 |  |  | 2002-07-19 08:00 | 2002-11-07 08:30 | NA
| 109 | AIP 1 - Assess Existing Technology Architecture | 100% | 36 h | 9 d | 2002-07-19 | 2002-07-31 | 100% |  | 36 h | 36 | Yes | 1.2.3.1 |  |  | 2002-07-19 08:00 | 2002-07-31 14:45 | NA
Ty | 110 | Identify Architectural Constraints - AIP 1.1 | 100% | 20 h | 5 d | 2002-07-19 | 2002-07-25 | 100% | 101 | 20 h | 20 | No | 1.2.3.1.1 |  | Mary[52%] | 2002-07-19 08:00 | 2002-07-25 15:45 | NA
Ty | 111 | Inventory Development Tools Standards and Procedures - AIP 1.3 | 100% | 4 h | 1 d | 2002-07-25 | 2002-07-26 | 100% | 102 | 4 h | 4 | No | 1.2.3.1.2 | 100 | Mary[52%] | 2002-07-25 15:45 | 2002-07-26 15:30 | NA
Ty | 112 | Identify Existing Network Topology - AIP 1.2 | 100% | 4 h | 1 d | 2002-07-26 | 2002-07-29 | 100% | 103 | 4 h | 4 | No | 1.2.3.1.3 | 101 | Mary[52%] | 2002-07-26 15:30 | 2002-07-29 15:15 | NA
Ty | 113 | Inventory Existing Hardware and System Software - AIP 1.4 | 100% | 4 h | 1 d | 2002-07-29 | 2002-07-30 | 100% | 104 | 4 h | 4 | No | 1.2.3.1.4 | 102 | Mary[52%] | 2002-07-29 15:15 | 2002-07-30 15:00 | NA
Ty | 114 | Assemble Architecture Assessment - AIP 1.5 | 100% | 4 h | 1 d | 2002-07-30 | 2002-07-31 | 100% |  | 4 h | 4 | No | 1.2.3.1.5 | 103 | Mary[52%] | 2002-07-30 15:00 | 2002-07-31 14:45 | NA
| 115 | AIP 2 - Design Technology Architecture | 100% | 140 h | 81 d | 2002-08-14 | 2002-12-04 | 100% |  | 140 h | 140 | Yes | 1.2.3.2 |  |  | 2002-08-14 08:15 | 2002-11-07 08:30 | NA
Ty | 116 | Design Network - AIP 2.1 | 100% | 10 h | 10 d | 2002-08-14 | 2002-09-16 | 100% | 107SS+9 d,108FS-5 d,117SS+20 d,120SS+20 d | 10 h | 10 | No | 1.2.3.2.1 | 44SS+5 d | Mary[6%],Ty[9%] | 2002-08-14 08:15 | 2002-09-11 10:21 | NA
Ty | 117 | Define Operating Systems - AIP 2.2 | 100% | 10 h | 10 d | 2002-08-26 | 2002-09-09 | 100% |  | 10 h | 10 | No | 1.2.3.2.2 | 106SS+9 d | Mary[6%],Ty[9%] | 2002-09-11 10:21 | 2002-09-24 16:51 | NA
Ty | 118 | Define Hardware Configuration - AIP 2.3 | 100% | 20 h | 13 d | 2002-09-09 | 2002-09-25 | 100% |  | 20 h | 20 | No | 1.2.3.2.3 | 106FS-5 d | Mary[13%],Ty[19%] | 2002-09-11 10:21 | 2002-09-24 16:51 | NA
Ty | 119 | Define Data Distribution - AIP 2.4 | 100% | 20 h | 10 d | 2002-09-09 | 2002-09-25 | 100% | 111FS-4 d,110FF | 20 h | 20 | No | 1.2.3.2.4 | 44FF | Mary[13%],Ty[19%] | 2002-09-13 10:30 | 2002-09-26 17:00 | NA
Ty | 120 | Define Middleware Req. - AIP 2.5 | 100% | 20 h | 5 d | 2002-09-19 | 2002-09-25 | 100% | 121SS+5 d | 20 h | 20 | No | 1.2.3.2.5 | 109FF | Mary[77%],Ty[52%] | 2002-09-27 08:00 | 2002-10-10 14:30 | NA
Ty | 121 | Define Application Service Distribution - AIP 2.6 | 100% | 20 h | 10 d | 2002-09-19 | 2002-10-02 | 100% | 112 | 20 h | 20 | No | 1.2.3.2.6 | 109FS-4 d | Mary[13%],Ty[19%] | 2002-09-27 08:00 | 2002-10-10 14:30 | NA
Ty | 122 | Define Security Infrastructure - AIP 2.7 | 100% | 20 h | 41 d | 2002-10-02 | 2002-11-29 | 100% | 113 | 20 h | 20 | No | 1.2.3.2.7 | 111 | Mary[13%],Ty[19%] | 2002-10-10 14:30 | 2002-10-24 11:00 | NA
Ty | 123 | Define System Topology - AIP 2.8 | 100% | 20 h | 5 d | 2002-11-08 | 2002-12-04 | 100% | 114 | 20 h | 20 | No | 1.2.3.2.8 | 112 | Mary[77%],Ty[52%] | 2002-10-24 11:00 | 2002-11-07 08:30 | NA
Ty | 124 | MS: Technology Architecture Documentation complete | 100% | 0 h | 0 d | 2002-12-04 | 2002-12-04 | 100% |  | 0 h | 0 | No | 1.2.3.3 | 113 | Mary[13%] | 2002-11-07 08:30 | 2002-11-07 08:30 | NA
| 125 | AIP 4 - Validate Technology Architecture | 100% | 36 h | 20.83 d | 2002-09-10 | 2002-10-08 | 100% |  | 36 h | 36 | Yes | 1.2.3.4 |  |  | 2002-09-10 11:15 | 2002-09-25 08:30 | NA
| 126 | Engineer for Performance | 100% | 14 h | 6 d | 2002-09-10 | 2002-09-18 | 100% |  | 14 h | 14 | Yes | 1.2.3.4.1 |  |  | 2002-09-10 11:15 | 2002-09-18 09:45 | NA
Ty | 127 | Submit initial IIA questionnaire | 100% | 4 h | 1 d | 2002-09-10 | 2002-09-11 | 100% | 118 | 4 h | 4 | No | 1.2.3.4.1.1 | 106SS+20 d | Mary[26%],Ty | 2002-09-10 11:15 | 2002-09-11 11:00 | NA
Ty | 128 | Infrastructure Impact Assessment - Level 2 review (if necessary) | 100% | 10 h | 5 d | 2002-09-11 | 2002-09-18 | 100% |  | 10 h | 10 | No | 1.2.3.4.1.2 | 117 | Mary[13%],Ty | 2002-09-11 11:00 | 2002-09-18 09:45 | NA
| 129 | SFTA Review | 100% | 22 h | 20.83 d | 2002-09-10 | 2002-10-08 | 100% |  | 22 h | 22 | Yes | 1.2.3.4.2 |  |  | 2002-09-10 11:15 | 2002-09-25 08:30 | NA
Ty | 130 | Assemble information for SFTA review | 100% | 10 h | 14 d | 2002-09-10 | 2002-09-27 | 100% |  | 10 h | 10 | No | 1.2.3.4.2.1 | 106SS+20 d | Mary[13%],Ty | 2002-09-10 11:15 | 2002-09-17 10:00 | NA
Ty | 131 | Submit SFTA Design Review | 100% | 2 h | 1 d | 2002-09-25 | 2002-09-26 | 100% | 122 | 2 h | 2 | No | 1.2.3.4.2.2 | 110SS+5 d | Mary[13%],Ty | 2002-09-17 10:00 | 2002-09-18 09:45 | NA
Ty | 132 | SFTA Review process | 100% | 10 h | 8 d | 2002-09-26 | 2002-10-08 | 100% | 123 | 10 h | 10 | No | 1.2.3.4.2.3 | 121 | Mary[8%],Ty | 2002-09-18 09:45 | 2002-09-25 08:30 | NA
Ty | 133 | MS: Authorized SFTA documentation | 100% | 0 h | 0 d | 2002-10-08 | 2002-10-08 | 100% |  | 0 h | 0 | No | 1.2.3.4.3 | 122 | Mary[26%] | 2002-09-25 08:30 | 2002-09-25 08:30 | NA
| 201 | Pkg -1 Design/Build/Test/Implement | 100% | 479 h | 84.29 d | 2002-10-21 | 2003-02-14 | 100% |  | 554 h | 489 | Yes | 1.3 |  |  | 2002-10-21 08:00 | 2003-03-12 09:00 | NA
| 202 | MS: Pkg -1 work started | 100% | 0 h | 0 d | 2002-10-21 | 2002-10-21 | 100% | 128,137,161 | 0 h | 0 | No | 1.3.1 |  |  | 2002-10-21 08:00 | 2002-10-21 08:00 | NA
| 203 | AUI Address Std (TSD/TPD/UPD) | 100% | 85 h | 34 d | 2002-10-21 | 2002-12-06 | 100% |  | 85 h | 85 | Yes | 1.3.2 |  |  | 2002-10-21 08:00 | 2002-12-06 16:30 | NA
Witter | 204 | AUI Address Std - RSC Entry | 100% | 2 h | 5 d | 2002-11-22 | 2002-12-03 | 100% |  | 2 h | 2 | No | 1.3.2.1 | 130FF | Witter[5%] | 2002-11-22 09:45 | 2002-12-03 08:30 | NA
Witter | 205 | AUI Address Std - Analysis & Design | 100% | 10 h | 3 d | 2002-10-21 | 2002-10-23 | 100% | 129,154 | 10 h | 10 | No | 1.3.2.2 | 125 | Witter[43%] | 2002-10-21 08:00 | 2002-10-23 16:15 | NA
Witter | 206 | AUI Address Std - Coding | 100% | 40 h | 9 d | 2002-10-23 | 2002-11-05 | 100% | 130FS+13 d,148 | 40 h | 40 | No | 1.3.2.3 | 128 | Witter[57%] | 2002-10-23 16:15 | 2002-11-05 14:00 | NA
Witter | 207 | AUI Address Std - Unit Test Cases/Testing | 100% | 20 h | 5 d | 2002-11-22 | 2002-12-03 | 100% | 131,127FF | 20 h | 20 | No | 1.3.2.4 | 129FS+13 d | Witter[52%] | 2002-11-22 09:45 | 2002-12-03 08:30 | NA
Witter | 208 | AUI Address Std - Integration Testing | 100% | 13 h | 4 d | 2002-12-03 | 2002-12-06 | 100% | 133FS-2 d,155 | 13 h | 13 | No | 1.3.2.5 | 130 | Witter[42%] | 2002-12-03 08:30 | 2002-12-06 16:30 | NA
| 209 | AUI VIN Validation (TSD/TPD/UPD) | 100% | 28 h | 9.19 d | 2002-12-05 | 2002-12-17 | 100% |  | 28 h | 28 | Yes | 1.3.3 |  |  | 2002-12-05 08:00 | 2002-12-17 16:15 | NA
Witter | 210 | AUI VIN Validation - Analysis & Design | 100% | 10 h | 2 d | 2002-12-05 | 2002-12-06 | 100% | 134,154,135SS | 10 h | 10 | No | 1.3.3.1 | 131FS-2 d | Witter[65%] | 2002-12-05 08:00 | 2002-12-06 16:30 | NA
Witter | 211 | AUI VIN Validation - Coding | 100% | 10 h | 7 d | 2002-12-06 | 2002-12-17 | 100% | 148 | 10 h | 10 | No | 1.3.3.2 | 133 | Witter[18%] | 2002-12-06 16:30 | 2002-12-17 14:45 | NA
Witter | 212 | AUI VIN Validation - Unit Test cases/Testing | 100% | 8 h | 6 d | 2002-12-10 | 2002-12-17 | 100% | 155 | 8 h | 8 | No | 1.3.3.3 | 133SS | Witter[17%] | 2002-12-10 08:45 | 2002-12-17 16:15 | NA
| 213 | NECHO DLV (TSD/TPD/UPD) | 100% | 121 h | 59.84 d | 2002-11-04 | 2003-01-27 | 100% |  | 121 h | 121 | Yes | 1.3.4 |  |  | 2002-11-04 08:00 | 2003-01-02 15:45 | NA
Murthy | 215 | NECHO -DLV - Design Low level Specs (TSD3.2) | 100% | 20 h | 3 d | 2002-11-04 | 2002-11-06 | 100% | 143SS,138,154 | 20 h | 20 | No | 1.3.4.1 | 125 | Murthy[86%] | 2002-11-04 08:00 | 2002-11-06 16:15 | NA
Murthy | 216 | NECHO -DLV - Design Test Cases (TSD8.3) | 100% | 40 h | 6 d | 2002-11-06 | 2002-11-14 | 100% | 139 | 40 h | 40 | No | 1.3.4.2 | 137 | Murthy[86%] | 2002-11-06 16:15 | 2002-11-14 14:45 | NA
Murthy | 217 | NECHO - DLV - Coding | 100% | 30 h | 6 d | 2002-11-14 | 2002-11-22 | 100% | 140SS+1 d,149 | 30 h | 30 | No | 1.3.4.3 | 138 | Murthy[65%] | 2002-11-14 14:45 | 2002-11-22 13:15 | NA
Murthy | 218 | NECHO -DLV - Unit Testing | 100% | 29 h | 9 d | 2002-11-15 | 2002-12-02 | 100% | 156FS-5 d,277SS+6 d,141 | 29 h | 29 | No | 1.3.4.4 | 139SS+1 d | Murthy[13%],Amar[29%] | 2002-11-15 14:30 | 2002-12-02 11:15 | NA
Murthy | 214 | NECHO DLV - RSC Entry | 100% | 2 h | 1 d | 2003-01-27 | 2003-01-27 | 100% |  | 2 h | 2 | No | 1.3.4.5 | 140 | Murthy[26%] | 2003-01-01 16:00 | 2003-01-02 15:45 | NA
| 219 | NECHO VIN Validation (TSD/TPD/UPD) | 100% | 50 h | 29 d | 2002-11-04 | 2002-12-16 | 100% |  | 50 h | 50 | Yes | 1.3.5 |  |  | 2002-11-04 08:00 | 2002-12-16 08:45 | NA
Amar | 220 | NECHO VIN Validation - Analysis (TSD3.2) | 100% | 10 h | 2 d | 2002-11-04 | 2002-11-05 | 100% | 144 | 10 h | 10 | No | 1.3.5.1 | 137SS | Amar[65%] | 2002-11-04 08:00 | 2002-11-05 16:30 | NA
Amar | 221 | NECHO VIN Validation - Analysis (TSD8.3) | 100% | 15 h | 2 d | 2002-11-05 | 2002-11-07 | 100% | 145,154 | 15 h | 15 | No | 1.3.5.2 | 143 | Amar[97%] | 2002-11-05 16:30 | 2002-11-07 16:00 | NA
Amar | 222 | NECHO VIN Validation - Coding | 100% | 15 h | 2 d | 2002-11-07 | 2002-11-11 | 100% | 146,149 | 15 h | 15 | No | 1.3.5.3 | 144 | Amar[97%] | 2002-11-07 16:00 | 2002-11-11 15:30 | NA
Amar | 223 | NECHO VIN Validation - Unit Testing | 100% | 10 h | 23 d | 2002-11-11 | 2002-12-16 | 100% | 156FS-5 d | 10 h | 10 | No | 1.3.5.4 | 145 | Amar[6%] | 2002-11-11 15:30 | 2002-12-16 08:45 | NA
| 224 | Pkg-1 Consolidated Tech Doc | 100% | 16 h | 18.68 d | 2002-11-22 | 2002-12-20 | 100% |  | 16 h | 16 | Yes | 1.3.6 |  |  | 2002-11-22 13:15 | 2002-12-20 14:00 | NA
Ty | 225 | Pkg-1 - Review AUI Tech System Design - TSD 9.2 | 100% | 3 h | 3 d | 2002-12-17 | 2002-12-20 | 100% | 150FF | 3 h | 3 | No | 1.3.6.1 | 129,134 | Ty[39%],Mary | 2002-12-17 14:45 | 2002-12-20 14:00 | NA
Ty | 226 | Pkg-1 - Review NECHO Tech System Design - TSD 9.2 | 100% | 10 h | 5 d | 2002-11-22 | 2002-12-03 | 100% |  | 10 h | 10 | No | 1.3.6.2 | 139,145 | Ty[26%] | 2002-11-22 13:15 | 2002-12-03 11:00 | NA
Ty | 227 | Pkg-1 - Review Consolidated Tech Doc - TPD 7.1 | 100% | 3 h | 2 d | 2002-12-18 | 2002-12-20 | 100% |  | 3 h | 3 | No | 1.3.6.3 | 148FF | Ty[39%],Mary[14%] | 2002-12-18 14:30 | 2002-12-20 14:00 | NA
| 228 | Pkg -1 Systems Acceptance Test (SAT) | 100% | 129 h | 43.77 d | 2002-11-11 | 2003-01-13 | 100% |  | 174 h | 129 | Yes | 1.3.7 |  |  | 2002-11-11 08:30 | 2003-01-13 11:45 | NA
SteveH | 229 | Establish Test Environment Needs - Pkg-1 | 100% | 10 h | 2 d | 2002-11-13 | 2002-11-15 | 100% |  | 10 h | 10 | No | 1.3.7.1 |  | SteveH[65%] | 2002-11-13 16:45 | 2002-11-15 16:15 | NA
SteveH | 230 | Establish Test Environment - Pkg-1 | 100% | 20 h | 5 d | 2002-11-11 | 2002-11-15 | 100% |  | 20 h | 20 | No | 1.3.7.2 |  | SteveH[52%] | 2002-11-11 08:30 | 2002-11-15 16:15 | NA
ED | 232 | Create Acceptance Test Cases - Pkg-1 | 100% | 10 h | 2 d | 2002-12-06 | 2002-12-10 | 100% |  | 10 h | 10 | No | 1.3.7.3 | 128,133,137,144 | Ed[7%],Lynn[57%] | 2002-12-06 16:30 | 2002-12-10 16:00 | NA
ED | 233 | AUI Acceptance Testing - Pkg-1 | 100% | 29 h | 4 d | 2002-12-17 | 2002-12-23 | 100% | 158,157 | 29 h | 29 | No | 1.3.7.4 | 131,135 | Ed[26%],Lynn,SteveH[40%] | 2002-12-17 16:15 | 2002-12-23 15:15 | NA
ED | 234 | NECHO Acceptance Testing - Pkg-1 | 100% | 30 h | 21 d | 2002-12-09 | 2003-01-07 | 100% | 170FS+7 d,158FS-1 d,157 | 30 h | 30 | No | 1.3.7.5 | 146FS-5 d,140FS-5 d | Ed[11%],Lynn,SteveH[40%] | 2002-12-09 10:00 | 2002-12-24 16:00 | NA
ED | 235 | MS: Pkg-1 SAT Completed | 100% | 0 h | 0 d | 2003-01-08 | 2003-01-08 | 100% |  | 0 h | 0 | No | 1.3.7.6 | 155,156 |  | 2003-01-08 13:30 | 2003-01-08 13:30 | NA
SteveH | 236 | Create Acceptance Test Summary Report - Pkg-1 | 100% | 10 h | 9 d | 2002-12-23 | 2003-01-06 | 100% | 159 | 10 h | 10 | No | 1.3.7.7 | 155,156FS-1 d | SteveH[65%] | 2002-12-23 16:15 | 2003-01-06 14:00 | NA
SteveH | 237 | Review / Authorize Acceptance Test Summary Report - Pkg-1 | 100% | 20 h | 5 d | 2003-01-06 | 2003-01-13 | 100% |  | 20 h | 20 | No | 1.3.7.8 | 158 | SteveH[52%] | 2003-01-06 14:00 | 2003-01-13 11:45 | NA
| 238 | Pkg -1 Communication | 100% | 25 h | 56.19 d | 2002-10-25 | 2003-01-14 | 100% |  | 25 h | 25 | Yes | 1.3.8 |  |  | 2002-10-25 08:00 | 2003-02-12 15:00 | NA
ED | 239 | Pkg-1 Draft Communication | 100% | 10 h | 2 d | 2002-10-25 | 2002-10-28 | 100% | 162 | 10 h | 10 | No | 1.3.8.1 | 125 | Ed[65%] | 2002-10-25 08:00 | 2002-10-28 16:30 | NA
ED | 240 | Pkg-1 Communication Review by Proj Team | 100% | 5 h | 14 d | 2002-10-29 | 2002-11-15 | 100% | 163 | 5 h | 5 | No | 1.3.8.2 | 161 | Ed[5%] | 2002-10-29 08:00 | 2002-11-15 13:30 | NA
ED | 241 | Pkg-1 UPD Walkthrough with SPIP group | 100% | 5 h | 8 d | 2002-11-18 | 2002-11-29 | 100% |  | 5 h | 5 | No | 1.3.8.3 | 162 | Ed[13%] | 2002-11-18 08:00 | 2002-11-29 15:00 | NA
Lynn | 242 | MS: Pkg-1 Create Agency pilot communications | 100% | 0 h | 0 d | 2002-12-30 | 2002-12-30 | 100% |  | 0 h | 0 | No | 1.3.8.4 | 165FF-5 d |  | 2002-12-30 15:15 | 2002-12-30 15:15 | NA
Lynn | 243 | MS: Pkg-1 Publish Agency pilot communications | 100% | 0 h | 0 d | 2003-01-06 | 2003-01-06 | 100% | 164FF-5 d | 0 h | 0 | No | 1.3.8.5 | 171FF-10 d |  | 2003-01-06 14:00 | 2003-01-06 14:00 | NA
Lynn | 244 | MS: Pkg-1 Create Agency cowide communications | 100% | 0 h | 0 d | 2003-01-07 | 2003-01-07 | 100% |  | 0 h | 0 | No | 1.3.8.6 | 167FF-5 d |  | 2003-01-20 10:30 | 2003-01-20 10:30 | NA
Lynn | 245 | MS: Pkg-1 Publish Agency cowide communications | 100% | 0 h | 0 d | 2003-01-14 | 2003-01-14 | 100% | 166FF-5 d | 0 h | 0 | No | 1.3.8.7 | 172FF-10 d |  | 2003-01-27 09:15 | 2003-01-27 09:15 | NA
ED | 246 | Pkg-1 Publish Communication | 100% | 5 h | 5 d | 2002-12-27 | 2003-01-02 | 100% |  | 5 h | 5 | No | 1.3.8.8 |  | Ed[13%] | 2003-02-05 16:15 | 2003-02-12 15:00 | NA
| 250 | Pkg -1 Implementation | 100% | 25 h | 30.97 d | 2003-01-03 | 2003-02-14 | 100% |  | 55 h | 35 | Yes | 1.3.9 |  |  | 2003-01-03 14:15 | 2003-03-12 09:00 | NA
Amar | 251 | Necho Pkg-1 Prep for pilot issuance | 100% | 10 h | 2 d | 2003-01-03 | 2003-01-07 | 100% | 171 | 10 h | 10 | No | 1.3.9.1 | 156FS+7 d | Amar[65%] | 2003-01-03 14:15 | 2003-01-07 13:45 | NA
Amar | 252 | MS: Pkg-1 Pilot Necho | 100% | 0 h | 0 d | 2003-01-07 | 2003-01-07 | 100% | 165FF-10 d,172FS+15 d | 0 h | 0 | No | 1.3.9.2 | 170 |  | 2003-01-20 10:30 | 2003-01-20 10:30 | NA
Amar | 255 | MS: NECHO Pkg-1 cowide Issuance | 100% | 0 h | 0 d | 2003-01-28 | 2003-01-28 | 100% | 173,167FF-10 d | 0 h | 0 | No | 1.3.9.3 | 171FS+15 d |  | 2003-02-07 15:45 | 2003-02-07 15:45 | NA
ED | 256 | Pkg 1-Post implementation questions | 100% | 15 h | 11 d | 2003-01-31 | 2003-02-14 | 100% | 174 | 25 h | 25 | No | 1.3.9.4 | 172 | Ed[18%] | 2003-02-12 15:00 | 2003-03-12 09:00 | NA
ED | 257 | MS: Pkg-1 Implemented | 100% | 0 h | 0 d | 2003-02-14 | 2003-02-14 | 100% |  | 0 h | 0 | No | 1.3.9.5 | 173 |  | 2003-03-12 09:00 | 2003-03-12 09:00 | NA
| 301 | Pkg -2 Design/Build/Test/Implement | 92% | 1,273 h | 201.81 d | 2002-10-28 | 2003-07-31 | 88% |  | 1,273 h | 1065.5 | Yes | 1.4 |  |  | 2002-10-28 08:00 | 2003-06-20 11:00 | NA
| 302 | MS: Pkg -2 work started | 100% | 0 h | 0 d | 2002-10-28 | 2002-10-28 | 100% | 212,190FS+6 d,217FS+16 d,236 | 0 h | 0 | No | 1.4.1 |  |  | 2002-10-28 08:00 | 2002-10-28 08:00 | NA
| 303 | Security Support - David | 100% | 35 h | 51.77 d | 2002-12-19 | 2003-02-28 | 100% |  | 25 h | 35 | Yes | 1.4.2 |  |  | 2002-12-19 08:00 | 2003-05-14 16:30 | NA
David | 305 | SDS 5.2 Specify Security and Control Requirements | 100% | 15 h | 36 d | 2003-01-13 | 2003-02-28 | 100% |  | 15 h | 15 | No | 1.4.2.1 |  | David[5%] | 2003-05-07 09:00 | 2003-05-14 16:30 | NA
David | 306 | Build Test Ids/Rules | 100% | 10 h | 26 d | 2002-12-19 | 2003-01-24 | 100% |  | 10 h | 10 | No | 1.4.2.2 |  | David[5%] | 2002-12-19 08:00 | 2003-03-03 10:45 | NA
David | 604a | Create production ids/rules | 100% | 10 h | 20 d | 2003-01-06 | 2003-01-31 | 100% |  | 10 h | 10 | No | 1.4.2.3 |  |  | 2003-01-06 13:15 | 2003-01-31 16:15 | NA
| 307 | Test Environment Setup | 100% | 90 h | 111.58 d | 2002-12-23 | 2003-05-24 | 100% |  | 90 h | 90 | Yes | 1.4.3 |  |  | 2002-12-23 16:15 | 2003-04-21 16:15 | NA
SteveH | 308 | Establish Test Environment needs | 100% | 10 h | 3 d | 2002-12-23 | 2002-12-27 | 100% | 183SS,184SS,185SS,186 | 10 h | 10 | No | 1.4.3.1 | 191,198,212,288FS-3 d | SteveH[43%] | 2002-12-23 16:15 | 2002-12-27 15:30 | NA
SteveH | 309 | Set-up AUI Integration/System Test Environment | 100% | 20 h | 18 d | 2002-12-23 | 2003-01-17 | 100% | 223 | 20 h | 20 | No | 1.4.3.2 | 182SS | SteveH[26%] | 2002-12-23 16:15 | 2003-01-07 13:45 | NA
SteveH | 310 | Set-up NECHO Integration/System Test Environment | 100% | 20 h | 18 d | 2002-12-23 | 2003-01-17 | 100% | 304 | 20 h | 20 | No | 1.4.3.3 | 182SS | SteveH[26%] | 2002-12-23 16:15 | 2003-01-07 13:45 | NA
SteveH | 311 | Determine FIT Test Environment Needs | 100% | 20 h | 9 d | 2002-12-23 | 2003-01-06 | 100% | 343 | 20 h | 20 | No | 1.4.3.4 | 182SS | SteveH[43%] | 2002-12-23 16:15 | 2003-01-07 13:45 | NA
SteveH | 312 | Set-up FIT Test Environment | 100% | 20 h | 91.87 d | 2003-01-21 | 2003-05-24 | 100% | 345 | 20 h | 20 | No | 1.4.3.5 | 182 | SteveH[4%] | 2003-01-21 08:00 | 2003-04-21 16:15 | NA
| 313 | AUI - DLV | 91% | 1,148 h | 195.81 d | 2002-11-04 | 2003-07-31 | 83% |  | 1,148 h | 940.5 | Yes | 1.4.4 |  |  | 2002-11-04 15:30 | 2003-06-20 11:00 | NA
| 314 | DLV - Mid Tier(TSD/TPD/UPD) | 100% | 129 h | 52.71 d | 2002-11-04 | 2003-01-17 | 100% |  | 129 h | 129 | Yes | 1.4.4.1 |  |  | 2002-11-04 15:30 | 2003-01-01 10:15 | NA
John | 315 | DLV - Mid Tier - RSC Entry | 100% | 4 h | 36 d | 2002-11-28 | 2003-01-17 | 100% |  | 4 h | 4 | No | 1.4.4.1.1 | 192SS | Bill[5%],John | 2002-11-28 08:00 | 2003-01-01 10:15 | NA
John | 316 | DLV - Mid Tier - Logical Design Interface | 100% | 24 h | 5 d | 2002-11-04 | 2002-11-18 | 100% | 191,199,222 | 24 h | 24 | No | 1.4.4.1.2 | 176FS+6 d | John[62%] | 2002-11-04 15:30 | 2002-11-18 14:15 | NA
John | 317 | DLV - Mid Tier - Logical Design Interface Walkthrough | 100% | 9 h | 4 d | 2002-11-19 | 2002-11-22 | 100% | 192,182 | 9 h | 9 | No | 1.4.4.1.3 | 190 | John[10%],EricH,Jeff | 2002-11-19 08:00 | 2002-11-22 16:00 | NA
John | 318 | DLV - Mid Tier - Coding | 100% | 60 h | 18 d | 2002-11-22 | 2002-12-20 | 100% | 189SS,193FF,194FF,195FF | 60 h | 60 | No | 1.4.4.1.4 | 191 | John[52%] | 2002-11-22 16:00 | 2002-12-20 10:30 | NA
John | 319 | DLV - Mid Tier - Code Walk Through | 100% | 6 h | 14 d | 2002-11-28 | 2002-12-20 | 100% | 225,233 | 6 h | 6 | No | 1.4.4.1.5 | 192FF | John[3%],Jeff[3%] | 2002-11-28 15:00 | 2002-12-20 10:30 | NA
John | 320 | DLV - Mid Tier - Unit Test Review | 100% | 20 h | 16 d | 2002-11-28 | 2002-12-20 | 100% |  | 20 h | 20 | No | 1.4.4.1.6 | 192FF | John[258%] | 2002-11-28 15:00 | 2002-12-20 16:15 | NA
John | 321 | DLV - Mid Tier - Unit Testing | 100% | 6 h | 16 d | 2002-11-28 | 2002-12-20 | 100% | 223 | 6 h | 6 | No | 1.4.4.1.7 | 192FF | John[3%],Jeff[3%] | 2002-11-28 15:00 | 2002-12-20 16:15 | NA
| 322 | DLV - Host - (TSD/TPD/UPD) | 100% | 316 h | 68 d | 2002-11-04 | 2003-02-07 | 100% |  | 316 h | 316 | Yes | 1.4.4.2 |  |  | 2002-11-04 16:45 | 2003-02-10 14:15 | NA
Bill | 323 | DLV - Host RSC Entry | 100% | 4 h | 11 d | 2003-01-06 | 2003-01-20 | 100% |  | 4 h | 4 | No | 1.4.4.2.1 | 202 | Bill[7%] | 2002-12-20 15:15 | 2002-12-30 14:00 | NA
Bill | 324 | DLV - Host - Develop Design Specs | 100% | 30 h | 25 d | 2002-11-04 | 2002-12-11 | 100% | 201,182 | 30 h | 30 | No | 1.4.4.2.2 | 200FF+2 d | Bill[19%] | 2002-11-04 16:45 | 2002-12-11 09:30 | NA
Bill | 325 | DLV - Host - Physical Design Interface | 100% | 20 h | 4 d | 2002-11-18 | 2002-11-22 | 100% | 200 | 20 h | 20 | No | 1.4.4.2.3 | 190 | Bill[65%] | 2002-11-18 14:15 | 2002-11-22 13:15 | NA
Bill | 326 | DLV - Host - Physical Design Interface Walkthrough | 100% | 6 h | 2 d | 2002-11-26 | 2002-11-29 | 100% | 198FF+2 d | 6 h | 6 | No | 1.4.4.2.4 | 199 | Bill,EricH[19%] | 2002-11-26 08:00 | 2002-11-29 16:30 | NA
Bill | 327 | DLV - Host - Design Specs Walkthrough | 100% | 6 h | 1 d | 2002-12-12 | 2002-12-12 | 100% | 202,222 | 6 h | 6 | No | 1.4.4.2.5 | 198 | Bill[39%],EricH[39%] | 2002-12-12 08:00 | 2002-12-12 16:45 | NA
Bill | 328 | DLV - Host - Code/Gen IMS transaction | 100% | 50 h | 6 d | 2002-12-12 | 2002-12-20 | 100% | 203SS,204FF,197 | 50 h | 50 | No | 1.4.4.2.6 | 201 | Bill[108%] | 2002-12-12 16:45 | 2002-12-20 15:15 | NA
Bill | 329 | DLV - Host - Code Wrapper | 100% | 50 h | 6 d | 2002-12-12 | 2002-12-20 | 100% | 204FF | 50 h | 50 | No | 1.4.4.2.7 | 202SS | Bill[108%] | 2002-12-12 16:45 | 2002-12-20 15:15 | NA
Bill | 330 | DLV - Host - Code Walkthrough | 100% | 6 h | 3 d | 2002-12-17 | 2002-12-20 | 100% | 205,225,233 | 6 h | 6 | No | 1.4.4.2.8 | 202FF,203FF | Bill[13%],EricH | 2002-12-17 16:00 | 2002-12-20 15:15 | NA
Bill | 331 | DLV - Host - Unit test IMS transaction | 100% | 50 h | 16 d | 2002-12-20 | 2003-01-14 | 100% | 206SS,207 | 50 h | 50 | No | 1.4.4.2.9 | 204 | Bill[43%] | 2002-12-20 15:15 | 2003-01-13 10:30 | NA
Bill | 332 | DLV - Host - Unit test Wrapper | 100% | 50 h | 16 d | 2002-12-20 | 2003-01-14 | 100% | 207 | 50 h | 50 | No | 1.4.4.2.10 | 205SS | Bill[43%] | 2002-12-20 15:15 | 2003-01-13 10:30 | NA
Bill | 333 | DLV - Host - Review Test Results | 100% | 6 h | 3 d | 2003-01-14 | 2003-01-17 | 100% | 223 | 6 h | 6 | No | 1.4.4.2.11 | 206,205 | Bill[26%],EricH[13%] | 2003-01-13 10:30 | 2003-01-16 09:45 | NA
Bill | 334 | DLV - Host - Security Analyst Setup | 100% | 10 h | 5 d | 2003-01-10 | 2003-01-17 | 100% |  | 10 h | 10 | No | 1.4.4.2.12 | 223FF-16 d | David[26%] | 2003-01-07 11:30 | 2003-01-14 10:15 | NA
Bill | 335 | DLV - Host - AUI/DLV Security -NT | 100% | 20 h | 11 d | 2002-12-31 | 2003-01-17 | 100% |  | 20 h | 20 | No | 1.4.4.2.13 | 223FF-17 d | Bill[26%] | 2002-12-31 13:45 | 2003-01-14 10:15 | NA
Bill | 336 | DLV - Host - Mid Tier /Host Integration Test Reveiew | 100% | 8 h | 2 d | 2003-02-05 | 2003-02-07 | 100% |  | 8 h | 8 | No | 1.4.4.2.14 | 223 | Bill[13%],John,EricH,Jeff | 2003-02-05 15:00 | 2003-02-10 14:15 | NA
| 337 | AUI - DLV (TSD/TPD/UPD) | 100% | 152 h | 53.06 d | 2002-11-18 | 2003-01-31 | 100% |  | 152 h | 152 | Yes | 1.4.4.3 |  |  | 2002-11-18 13:00 | 2003-01-08 13:15 | NA
Witter | 339 | AUI - DLV - Analysis & Design | 100% | 20 h | 5 d | 2002-11-18 | 2002-11-25 | 100% | 222,182,225,213 | 20 h | 20 | No | 1.4.4.3.1 | 176 | Witter[52%] | 2002-11-18 13:00 | 2002-11-25 10:45 | NA
Witter | 340 | AUI - DLV - Coding | 100% | 80 h | 20 d | 2003-01-06 | 2003-01-31 | 100% | 214SS,215SS | 80 h | 80 | No | 1.4.4.3.2 | 212 | Witter[103%] | 2002-12-13 08:45 | 2002-12-24 15:45 | NA
Witter | 341 | AUI - DLV - Unit Testing | 100% | 50 h | 20 d | 2003-01-06 | 2003-01-31 | 100% |  | 50 h | 50 | No | 1.4.4.3.3 | 213SS | Witter[81%] | 2002-12-24 15:45 | 2003-01-08 13:15 | NA
Witter | 338 | AUI - DLV - RSC Entry | 100% | 2 h | 5 d | 2003-01-27 | 2003-01-31 | 100% |  | 2 h | 2 | No | 1.4.4.3.4 | 213SS | Witter[5%] | 2003-01-01 14:30 | 2003-01-08 13:15 | NA
| 342 | AUI -Chgs for NECHO (TSD/TPD/UPD) | 100% | 115 h | 94.35 d | 2002-11-18 | 2003-03-28 | 100% |  | 40 h | 40 | Yes | 1.4.4.4 |  |  | 2002-11-18 13:00 | 2002-12-26 14:30 | NA
Witter | 343 | AUI -Chgs for NECHO - Analysis & design | 100% | 10 h | 4 d | 2002-11-18 | 2002-11-22 | 100% | 218,222 | 10 h | 10 | No | 1.4.4.4.1 | 176FS+16 d | Witter[32%] | 2002-11-18 13:00 | 2002-11-22 11:00 | NA
Witter | 344 | AUI -Chgs for NECHO - Coding | 100% | 20 h | 16 d | 2002-11-22 | 2002-12-17 | 100% | 219 | 20 h | 20 | No | 1.4.4.4.2 | 217 | Witter[16%] | 2002-11-22 11:00 | 2002-12-17 16:00 | NA
Witter | 345 | AUI -Chgs for NECHO - Unit Testing | 100% | 10 h | 6 d | 2002-12-17 | 2002-12-26 | 100% | 223 | 10 h | 10 | No | 1.4.4.4.3 | 218 | Witter[22%] | 2002-12-17 16:00 | 2002-12-26 14:30 | NA
Witter | 345a | MVR Message Chnages - Coding/UT | 100% | 75 h | 14 d | 2003-03-11 | 2003-03-28 | 100% | 226 | 0 h | 0 | No | 1.4.4.4.4 |  |  | NA | NA | NA
| 346 | AUI -DLV Int Testing | 100% | 230 h | 66.84 d | 2003-01-06 | 2003-04-04 | 100% |  | 210 h | 210 | Yes | 1.4.4.5 |  |  | 2002-12-20 15:15 | 2003-03-05 09:00 | NA
SteveH | 347 | AUI - Create AUI System Test Plan | 100% | 20 h | 10 d | 2003-01-06 | 2003-01-17 | 100% |  | 20 h | 20 | No | 1.4.4.5.1 | 212,190,201,217 | SteveH[26%] | 2003-01-06 08:00 | 2003-01-17 14:30 | NA
SteveH | 348 | AUI-DLV Mid Tier / Host Int Test | 100% | 60 h | 14 d | 2003-01-17 | 2003-02-05 | 100% | 209FF-17 d,208FF-16 d,210,224 | 60 h | 60 | No | 1.4.4.5.2 | 195,207,183,219 | Bill[23%],John[36%],SteveH[23%] | 2003-01-16 09:45 | 2003-02-05 15:00 | NA
SteveH | 349 | AUI-DLV Web / Mid Tier / Host System Testing (Initial) | 100% | 80 h | 15 d | 2003-02-05 | 2003-02-26 | 100% | 227 | 80 h | 80 | No | 1.4.4.5.3 | 223 | SteveH[40%],Witter[26%],John,Bill | 2003-02-05 15:00 | 2003-02-26 10:15 | NA
ED | 350 | AUI-DLV Acceptance Test Cases developed | 100% | 20 h | 4 d | 2003-02-11 | 2003-02-14 | 100% |  | 20 h | 20 | No | 1.4.4.5.4 | 193,204,212 | Ed[65%] | 2002-12-20 15:15 | 2003-01-13 10:30 | NA
Witter | 350a | AUI-DLV Web / Mid Tier / Host System Testing (Additional) | 100% | 20 h | 5 d | 2003-03-28 | 2003-04-04 | 100% | 227FF | 0 h | 0 | No | 1.4.4.5.5 | 220 |  | NA | NA | NA
ED | 351 | AUI-DLV Acceptance Testing | 100% | 30 h | 28.19 d | 2003-02-26 | 2003-04-04 | 100% | 246,242SS,229FS-25 d | 30 h | 30 | No | 1.4.4.5.6 | 224,226FF | Ed[18%] | 2003-02-26 10:15 | 2003-03-05 09:00 | NA
|  | Performance Testing Pkg-2 | 69% | 90 h | 74.45 d | 2003-03-05 | 2003-06-13 | 44% |  | 70 h | 57.5 | Yes | 1.4.4.6 |  |  | 2003-03-05 09:00 | 2003-03-25 14:15 | NA
SteveH | 351a | Setup Perf. Testing Pkg-2 | 100% | 20 h | 28 d | 2003-03-05 | 2003-04-11 | 100% | 230,231 | 20 h | 20 | No | 1.4.4.6.1 | 227FS-25 d | SteveH[6%],PerTeam[5%] | 2003-03-05 09:00 | 2003-03-11 16:45 | NA
SteveH | 351b | Execute Perf. Testing Pkg-2 | 75% | 50 h | 45 d | 2003-04-15 | 2003-06-13 | 38% | 246 | 50 h | 37.5 | No | 1.4.4.6.2 | 229 | SteveH[10%],PerTeam[40%] | 2003-03-11 16:45 | 2003-03-25 14:15 | NA
SteveH | 351c | Implementation testing execution pkg-2 | 25% | 20 h | 31 d | 2003-05-02 | 2003-06-13 | 1% | 246 | 0 h | 0 | No | 1.4.4.6.3 | 229 | SteveH[52%],Witter[6%],John,Bill | NA | NA | NA
| 352 | Pkg-2 Consolidated Tech Doc | 100% | 6 h | 8 d | 2002-12-24 | 2003-01-06 | 100% |  | 6 h | 6 | Yes | 1.4.4.7 |  |  | 2002-12-24 15:45 | 2003-01-07 13:30 | NA
Ty | 353 | AUI - DLV - Review Technical System Design - TSD 9.2 | 100% | 3 h | 8 d | 2002-12-24 | 2003-01-06 | 100% | 234SS | 3 h | 3 | No | 1.4.4.7.1 | 193,204 | Ty[2%],Mary[2%] | 2002-12-24 15:45 | 2003-01-06 13:45 | NA
Ty | 354 | Pkg-2 - Review AUI Technical System Design - TSD 9.2 | 100% | 3 h | 8 d | 2002-12-24 | 2003-01-06 | 100% |  | 3 h | 3 | No | 1.4.4.7.2 | 233SS | Ty[26%],Mary[31%] | 2003-01-06 13:45 | 2003-01-07 13:30 | NA
| 355 | Pkg -2 Communication | 67% | 45 h | 97.32 d | 2003-02-17 | 2003-06-27 | 89% |  | 45 h | 30 | Yes | 1.4.4.8 |  |  | 2002-12-31 08:00 | 2003-05-19 09:15 | NA
ED | 356 | Pkg-2 Draft Communication | 100% | 10 h | 1 d | 2003-02-17 | 2003-02-17 | 100% | 237 | 10 h | 10 | No | 1.4.4.8.1 | 176 | Ed[129%] | 2002-12-31 08:00 | 2003-01-15 14:00 | NA
ED | 357 | Pkg-2 Communication Review by Proj Team | 100% | 5 h | 5 d | 2003-02-17 | 2003-02-24 | 100% | 238 | 5 h | 5 | No | 1.4.4.8.2 | 236 | Ed[13%] | 2003-01-15 14:00 | 2003-01-22 11:45 | NA
ED | 358 | Pkg-2 UPD Walkthrough with SPIP group | 100% | 5 h | 4 d | 2003-02-24 | 2003-02-28 | 100% |  | 5 h | 5 | No | 1.4.4.8.3 | 237 | Ed[16%] | 2003-01-22 11:45 | 2003-01-31 10:00 | NA
Lynn | 359 | MS: Pkg-2 Create Agency cowide communications | 0% | 0 h | 0 d | 2003-06-20 | 2003-06-20 | 0% |  | 0 h | 0 | No | 1.4.4.8.4 | 240FF-5 d |  | 2003-05-12 10:30 | 2003-05-12 10:30 | NA
Lynn | 360 | MS: Pkg-2 Publish Agency cowide communications | 0% | 0 h | 0 d | 2003-06-27 | 2003-06-27 | 0% | 239FF-5 d | 0 h | 0 | No | 1.4.4.8.5 | 249FF-5 d |  | 2003-05-19 09:15 | 2003-05-19 09:15 | NA
ED | 361 | Pkg-2 Publish Communication | 0% | 5 h | 1 d | 2003-06-23 | 2003-06-23 | 0% |  | 5 h | 0 | No | 1.4.4.8.6 | 249FF-9 d | Ed[65%] | 2003-05-05 11:45 | 2003-05-12 10:30 | NA
Vance | 362 | Create Pkg-2 SFQ Solutions | 100% | 10 h | 37 d | 2003-03-21 | 2003-05-09 | 100% | 243FS+10 d | 10 h | 10 | No | 1.4.4.8.7 | 227SS | Vance[12%] | 2003-02-26 10:15 | 2003-03-11 16:45 | NA
Vance | 363 | MS: ISC Review Pkg-2 SFQ Solutions | 0% | 0 h | 0 d | 2003-05-23 | 2003-05-23 | 0% | 244 | 0 h | 0 | No | 1.4.4.8.8 | 242FS+10 d |  | 2003-03-25 14:15 | 2003-03-25 14:15 | NA
Vance | 364 | Populate pkg-2 SFQ Solutions | 0% | 10 h | 5 d | 2003-05-23 | 2003-05-30 | 0% |  | 10 h | 0 | No | 1.4.4.8.9 | 243 | Vance[26%] | 2003-03-25 14:15 | 2003-04-01 12:00 | NA
| 365 | Pkg -2 Implementation | 0% | 65 h | 35 d | 2003-06-13 | 2003-07-31 | 0% |  | 65 h | 0 | Yes | 1.4.4.9 |  |  | 2003-04-21 15:45 | 2003-06-20 11:00 | NA
John | 366 | Mid Tier-Host Prep cowide issuance | 0% | 20 h | 10 d | 2003-06-13 | 2003-06-27 | 0% | 247 | 20 h | 0 | No | 1.4.4.9.1 | 227,230,231 | John[26%] | 2003-04-21 15:45 | 2003-04-25 14:45 | NA
John | 367 | MS: Mid Tier-Host cowide issuance | 0% | 0 h | 0 d | 2003-06-27 | 2003-06-27 | 0% | 248 | 0 h | 0 | No | 1.4.4.9.2 | 246 |  | 2003-05-12 08:00 | 2003-05-12 08:00 | NA
Witter | 368 | AUI Pkg-2 Prep for cowide issaunce | 0% | 20 h | 5 d | 2003-06-27 | 2003-07-04 | 0% | 249 | 20 h | 0 | No | 1.4.4.9.3 | 247 | Witter[52%] | 2003-05-14 08:00 | 2003-05-20 15:45 | NA
Witter | 369 | MS: AUI Pkg-2 cowide Issuance | 0% | 0 h | 0 d | 2003-07-04 | 2003-07-04 | 0% | 250,240FF-5 d,241FF-9 d | 0 h | 0 | No | 1.4.4.9.4 | 248 |  | 2003-05-26 08:00 | 2003-05-26 08:00 | NA
ED | 370 | Pkg 2-Post implemetation questions | 0% | 25 h | 20 d | 2003-07-04 | 2003-07-31 | 0% | 251 | 25 h | 0 | No | 1.4.4.9.5 | 249 | Ed[16%] | 2003-05-26 08:00 | 2003-06-20 11:00 | NA
ED | 371 | MS: Pkg-2 Completed | 0% | 0 h | 0 d | 2003-07-31 | 2003-07-31 | 0% |  | 0 h | 0 | No | 1.4.4.9.6 | 250 |  | 2003-06-20 11:00 | 2003-06-20 11:00 | NA
| 401 | Pkg -3 Design/Build/Test/Implement | 89% | 2,610 h | 238.84 d | 2002-10-28 | 2003-09-19 | 79% |  | 2,484 h | 2232.5 | Yes | 1.5 |  |  | 2002-10-28 08:00 | 2003-08-11 16:15 | NA
| 402 | MS: Pkg -3 work started | 100% | 0 h | 0 d | 2002-10-28 | 2002-10-28 | 100% | 256,261,273,349 | 0 h | 0 | No | 1.5.1 |  |  | 2002-10-28 08:00 | 2002-10-28 08:00 | NA
| 403 | NECHO - all Remaining Changes (TSD/TPD/UPD) | 99% | 2,164 h | 167.16 d | 2002-10-28 | 2003-06-13 | 87% |  | 2,108 h | 2091.5 | Yes | 1.5.2 |  |  | 2002-10-28 08:00 | 2003-04-11 11:15 | NA
| 404 | Security Support - Sushit | 100% | 31 h | 69.19 d | 2002-11-01 | 2003-02-07 | 100% |  | 31 h | 31 | Yes | 1.5.2.1 |  |  | 2002-11-01 08:00 | 2003-02-07 08:15 | NA
Sushit | 405 | SRA 4.2 Establish Security and Control, Requirements | 100% | 6 h | 23 d | 2002-11-01 | 2002-12-05 | 100% | 257,258 | 6 h | 6 | No | 1.5.2.1.1 | 253 | Sushit[3%] | 2002-11-01 08:00 | 2002-12-05 10:15 | NA
Sushit | 406 | SDS 5.2 Specify Security and Control Requirements | 100% | 15 h | 26 d | 2002-12-19 | 2003-01-24 | 100% |  | 15 h | 15 | No | 1.5.2.1.2 | 256 | Sushit[13%] | 2002-12-19 08:00 | 2003-01-24 09:30 | NA
Sushit | 407 | Build Test Ids/Rules | 100% | 10 h | 31 d | 2002-12-27 | 2003-02-07 | 100% |  | 10 h | 10 | No | 1.5.2.1.3 | 256 | Sushit[5%] | 2002-12-27 08:00 | 2003-02-07 08:15 | NA
| 408 | MQSeries | 97% | 145 h | 166.68 d | 2002-10-28 | 2003-06-13 | 84% |  | 145 h | 140 | Yes | 1.5.2.2 |  |  | 2002-10-28 08:00 | 2003-03-28 14:45 | NA
| 409 | TSD 3.2 phase doc | 100% | 55 h | 20 d | 2002-10-28 | 2002-11-22 | 100% |  | 55 h | 55 | Yes | 1.5.2.2.1 |  |  | 2002-10-28 08:00 | 2002-11-22 11:00 | NA
Durnan | 410 | MQ Q/A High Level Review (req’d objects id’d) | 100% | 20 h | 17 d | 2002-10-28 | 2002-11-19 | 100% | 262SS+6 d | 20 h | 20 | No | 1.5.2.2.1.1 | 253 | Durnan[15%] | 2002-10-28 08:00 | 2002-11-19 11:45 | NA
Durnan | 411 | MQ design Infra Diagram (message flow) | 100% | 30 h | 14 d | 2002-11-04 | 2002-11-22 | 100% | 263FF | 30 h | 30 | No | 1.5.2.2.1.2 | 261SS+6 d | Durnan[28%] | 2002-11-04 15:30 | 2002-11-22 11:00 | NA
Durnan | 412 | MQ Q/A Detail Level Review (design Walkthrough) | 100% | 5 h | 5 d | 2002-11-15 | 2002-11-22 | 100% | 265FS+24 d | 5 h | 5 | No | 1.5.2.2.1.3 | 262FF | Durnan[13%] | 2002-11-15 13:15 | 2002-11-22 11:00 | NA
| 413 | TSD 8.3 phase doc | 100% | 30 h | 17 d | 2002-12-30 | 2003-01-22 | 100% |  | 30 h | 30 | Yes | 1.5.2.2.2 |  |  | 2002-12-30 14:00 | 2003-01-22 08:45 | NA
Durnan | 414 | MQ Objects on Dev Host (coding) | 100% | 10 h | 7 d | 2002-12-30 | 2003-01-08 | 100% | 266 | 10 h | 10 | No | 1.5.2.2.2.1 | 263FS+24 d | Durnan[18%] | 2002-12-30 14:00 | 2003-01-08 11:15 | NA
Durnan | 415 | MQ Create Host Test Cases | 100% | 10 h | 5 d | 2003-01-08 | 2003-01-15 | 100% | 267 | 10 h | 10 | No | 1.5.2.2.2.2 | 265 | Durnan[26%] | 2003-01-08 11:15 | 2003-01-15 10:00 | NA
Durnan | 416 | MQ Execute & Doc Host Test Cases | 100% | 10 h | 5 d | 2003-01-15 | 2003-01-22 | 100% | 269 | 10 h | 10 | No | 1.5.2.2.2.3 | 266 | Durnan[26%] | 2003-01-15 10:00 | 2003-01-22 08:45 | NA
| 417 | MQ Regional Office MVS Dev Environment | 92% | 60 h | 81.68 d | 2003-02-24 | 2003-06-13 | 75% |  | 60 h | 55 | Yes | 1.5.2.2.3 |  |  | 2003-02-24 10:45 | 2003-03-28 14:45 | NA
Durnan | 418 | MQ Support NECHO Unit Testing | 100% | 20 h | 35 d | 2003-02-24 | 2003-04-11 | 100% |  | 20 h | 20 | No | 1.5.2.2.3.1 | 267 | Durnan[14%] | 2003-02-24 10:45 | 2003-03-19 15:15 | NA
Durnan | 420 | MQ Q/A App Code walkthrough | 100% | 20 h | 9 d | 2003-03-26 | 2003-04-07 | 100% |  | 20 h | 20 | No | 1.5.2.2.3.2 | 313FF-6 d | Durnan[43%] | 2003-03-17 08:15 | 2003-03-28 14:45 | NA
Durnan | 419 | MQ Integration Testing | 75% | 20 h | 49 d | 2003-04-09 | 2003-06-13 | 53% |  | 20 h | 15 | No | 1.5.2.2.3.3 | 313FF-5 d | Durnan[18%] | 2003-03-17 08:15 | 2003-03-28 14:45 | NA
| 421 | Host Addr Std/Terr | 100% | 60 h | 134.13 d | 2002-11-12 | 2003-05-16 | 100% |  | 60 h | 60 | Yes | 1.5.2.3 |  |  | 2002-11-12 16:45 | 2003-03-14 10:00 | NA
Brian | 422 | Host Addr Std/ terr-analysis | 100% | 20 h | 30 d | 2002-11-12 | 2002-12-27 | 100% | 274 | 20 h | 20 | No | 1.5.2.3.1 | 253 | Brian[14%] | 2002-11-12 16:45 | 2002-12-27 08:15 | NA
Brian | 423 | Host Addr Std/ terr-Coding | 100% | 40 h | 104.13 d | 2002-12-27 | 2003-05-16 | 100% |  | 40 h | 40 | No | 1.5.2.3.2 | 273 | Brian[26%] | 2002-12-27 08:15 | 2003-03-14 10:00 | NA
| 424 | NECHO - all Remaining Changes -(TSD) | 98% | 726 h | 154.77 d | 2002-11-13 | 2003-06-13 | 74% |  | 702 h | 690.5 | Yes | 1.5.2.4 |  |  | 2002-11-13 08:00 | 2003-04-11 11:15 | NA
Amar | 425 | Necho RSC Entry for Terr valid & Address Std | 25% | 2 h | 146 d | 2002-11-25 | 2003-06-13 | 0% |  | 2 h | 0.5 | No | 1.5.2.4.1 | 277SS | Amar[13%] | 2002-11-25 13:00 | 2003-03-31 14:30 | NA
Murthy | 426 | AUI Request Vehicle Information Screen - TSD 3.2 | 100% | 50 h | 12 d | 2002-11-25 | 2002-12-13 | 100% | 278SS,279SS,280SS,281SS,282SS,284FF,285FF,286FF,287FF,276SS | 50 h | 50 | No | 1.5.2.4.2 | 140SS+6 d | Murthy[161%] | 2002-11-25 13:00 | 2002-12-13 09:00 | NA
Murthy | 427 | MQ - Interface module - TSD 3.2 | 100% | 30 h | 15 d | 2002-12-03 | 2002-12-23 | 100% |  | 30 h | 30 | No | 1.5.2.4.3 | 277SS | Murthy[32%] | 2002-12-03 11:00 | 2002-12-23 16:15 | NA
Murthy | 428 | Incoming Interface - TSD 3.2 | 100% | 20 h | 15 d | 2002-12-03 | 2002-12-23 | 100% |  | 20 h | 20 | No | 1.5.2.4.4 | 277SS | Murthy[22%] | 2002-12-03 11:00 | 2002-12-23 16:15 | NA
Murthy | 429 | Outgoing Interface - TSD 3.2 | 100% | 20 h | 16 d | 2002-12-03 | 2002-12-24 | 100% |  | 20 h | 20 | No | 1.5.2.4.5 | 277SS | Murthy[16%] | 2002-12-03 11:00 | 2002-12-24 16:00 | NA
Murthy | 430 | Build Auto App Program - TSD 3.2 | 100% | 20 h | 15 d | 2002-12-03 | 2002-12-23 | 100% |  | 20 h | 20 | No | 1.5.2.4.6 | 277SS | Murthy[22%] | 2002-12-03 11:00 | 2002-12-23 16:15 | NA
Murthy | 431 | Warning Screen - TSD 3.2 | 100% | 20 h | 15 d | 2002-12-03 | 2002-12-23 | 100% |  | 20 h | 20 | No | 1.5.2.4.7 | 277SS | Murthy[22%] | 2002-12-03 11:00 | 2002-12-23 16:15 | NA
Amar | 432 | Auto Apps - Main Program - TSD 3.2 | 100% | 40 h | 17 d | 2002-11-13 | 2002-12-09 | 100% | 318 | 40 h | 40 | No | 1.5.2.4.8 |  | Amar[30%] | 2002-11-13 08:00 | 2002-12-09 11:45 | NA
Amar | 433 | Residence Address screen - TSD 3.2 | 100% | 20 h | 27 d | 2002-11-13 | 2002-12-23 | 100% |  | 20 h | 20 | No | 1.5.2.4.9 | 277FF | Amar[11%] | 2002-11-13 15:00 | 2002-12-23 16:15 | NA
Amar | 434 | AUI Request Driver Information Screen - TSD 3.2 | 100% | 50 h | 20 d | 2002-11-25 | 2002-12-24 | 100% |  | 50 h | 50 | No | 1.5.2.4.10 | 277FF | Amar[32%] | 2002-11-25 13:00 | 2002-12-24 16:00 | NA
Amar | 435 | Territory Validation (Options screen) - TSD 3.2 | 100% | 30 h | 19 d | 2002-11-25 | 2002-12-23 | 100% |  | 30 h | 30 | No | 1.5.2.4.11 | 277FF | Amar[24%] | 2002-11-25 13:00 | 2002-12-23 16:15 | NA
Amar | 436 | Pf Key format /Branching Program (PCS5F) - TSD 3.2 | 100% | 20 h | 20 d | 2002-11-25 | 2002-12-24 | 100% | 288FS+2 d | 20 h | 20 | No | 1.5.2.4.12 | 277FF | Amar[13%] | 2002-11-25 13:00 | 2002-12-24 16:00 | NA
Amar | 437 | NECHO - all Remaining Changes - Review TSD 3.2 Docs | 100% | 12 h | 18 d | 2002-12-27 | 2003-01-22 | 100% | 289SS,182FS-3 d,290SS,291SS,292SS,293SS,294SS,295SS,296SS,297SS,298SS,299SS | 12 h | 12 | No | 1.5.2.4.13 | 287FS+2 d | Amar[2%],Murthy[2%],Tina[2%],Lakshmi[2%],Ty,Mary | 2002-12-27 15:30 | 2003-01-22 10:00 | NA
Murthy | 438 | AUI Request Vehicle Information Screen - TSD 8.3 | 100% | 60 h | 18 d | 2002-12-27 | 2003-01-22 | 100% | 334,335,306 | 60 h | 60 | No | 1.5.2.4.14 | 288SS | Murthy[43%] | 2002-12-27 15:30 | 2003-01-22 10:00 | NA
Murthy | 439 | MQ - Interface module - TSD 8.3 | 100% | 30 h | 24 d | 2002-12-27 | 2003-01-30 | 100% | 334,335 | 30 h | 30 | No | 1.5.2.4.15 | 288SS | Murthy[16%] | 2002-12-27 15:30 | 2003-01-30 08:30 | NA
Murthy | 440 | Incoming Interface - TSD 8.3 | 100% | 20 h | 24 d | 2002-12-27 | 2003-01-30 | 100% | 334,335 | 20 h | 20 | No | 1.5.2.4.16 | 288SS | Murthy[11%] | 2002-12-27 15:30 | 2003-01-30 08:30 | NA
Murthy | 441 | Outgoing Interface - TSD 8.3 | 100% | 20 h | 21 d | 2002-12-27 | 2003-01-27 | 100% | 334,335 | 20 h | 20 | No | 1.5.2.4.17 | 288SS | Murthy[22%] | 2002-12-27 15:30 | 2003-01-27 09:15 | NA
Murthy | 442 | Build Auto App Program - TSD 8.3 | 100% | 20 h | 11 d | 2002-12-27 | 2003-01-10 | 100% | 334,335 | 20 h | 20 | No | 1.5.2.4.18 | 288SS | Murthy[23%] | 2002-12-27 08:00 | 2003-01-10 14:15 | NA
Murthy | 443 | Warning Screen - TSD 8.3 | 100% | 20 h | 15 d | 2002-12-27 | 2003-01-17 | 100% | 334,335 | 20 h | 20 | No | 1.5.2.4.19 | 288SS | Murthy[17%] | 2002-12-27 15:30 | 2003-01-17 10:45 | NA
Amar | 444 | Territory Validation (Options screen) - TSD 8.3 | 100% | 30 h | 20 d | 2002-12-27 | 2003-01-24 | 100% | 334,335 | 30 h | 30 | No | 1.5.2.4.20 | 288SS | Amar[48%] | 2002-12-27 15:30 | 2003-01-24 09:30 | NA
Amar | 445 | Pf Key format /Branching Program (PCS5F) - TSD 8.3 | 100% | 20 h | 20 d | 2002-12-27 | 2003-01-24 | 100% | 334,335 | 20 h | 20 | No | 1.5.2.4.21 | 288SS | Amar[32%] | 2002-12-27 15:30 | 2003-01-24 09:30 | NA
Amar | 446 | Auto Apps - Main Program - TSD 8.3 | 100% | 40 h | 20 d | 2002-12-27 | 2003-01-31 | 100% | 334,335 | 40 h | 40 | No | 1.5.2.4.22 | 288SS | Amar[32%] | 2002-12-27 15:30 | 2003-01-31 08:15 | NA
Amar | 447 | Residence Address screen - TSD 8.3 | 100% | 30 h | 20 d | 2002-12-27 | 2003-01-24 | 100% | 334,335 | 30 h | 30 | No | 1.5.2.4.23 | 288SS | Amar[19%] | 2002-12-27 15:30 | 2003-01-24 09:30 | NA
Amar | 448 | AUI Request Driver Information Screen - TSD 8.3 | 100% | 60 h | 24 d | 2002-12-27 | 2003-01-30 | 100% | 300FS+1 d,334,335 | 60 h | 60 | No | 1.5.2.4.24 | 288SS | Amar[32%] | 2002-12-27 15:30 | 2003-01-30 08:30 | NA
Amar | 449 | NECHO - all Remaining Changes - Review TSD 8.3 Docs | 100% | 8 h | 4 d | 2003-01-31 | 2003-02-05 | 100% | 334,335 | 8 h | 8 | No | 1.5.2.4.25 | 299FS+1 d | Amar[26%],Murthy[26%],Tina[26%],Lakshmi[26%] | 2003-01-31 08:15 | 2003-02-05 16:15 | NA
Amar | 449a | Driver Info warning Screen - Analysis TSD 3.2, TSD 8.3 | 100% | 24 h | 3 d | 2003-04-01 | 2003-04-03 | 100% | 328 | 0 h | 0 | No | 1.5.2.4.26 |  | Amar[103%] | NA | NA | NA
Durnan | 450 | MQ Q/A Transition to MQService Agreement | 0% | 10 h | 5 d | 2003-06-09 | 2003-06-13 | 0% |  | 10 h | 0 | No | 1.5.2.4.27 | 304 | Durnan[26%] | 2003-03-28 14:45 | 2003-04-11 11:15 | NA
| 451 | Pkg-3 NECHO Integration Testing | 100% | 120 h | 63 d | 2003-01-20 | 2003-04-15 | 100% |  | 120 h | 120 | Yes | 1.5.2.5 |  |  | 2003-01-20 10:30 | 2003-03-28 14:45 | NA
SteveH | 452 | Perform Integration Testing for NECHO Changes - pkg-2 | 100% | 120 h | 61 d | 2003-01-20 | 2003-04-15 | 100% | 302,336FS-1 d | 120 h | 120 | No | 1.5.2.5.1 | 184 | SteveH[3%],Murthy,Tina,Amar,Durnan,Brian | 2003-01-20 10:30 | 2003-03-28 14:45 | NA
| 453 | NECHO - all Remaining Changes -(TPD) | 100% | 1,082 h | 51.32 d | 2003-02-03 | 2003-04-11 | 100% |  | 1,050 h | 1050 | Yes | 1.5.2.6 |  |  | 2003-02-03 08:00 | 2003-03-28 14:45 | NA
Murthy | 454 | AUI Request Vehicle Information Screen - Coding | 100% | 80 h | 10 d | 2003-02-03 | 2003-02-14 | 100% | 307FF | 80 h | 80 | No | 1.5.2.6.1 | 289 | Murthy[103%] | 2003-02-03 08:00 | 2003-02-14 14:30 | NA
Murthy | 455 | AUI Request Vehicle Information Screen - UT/IT | 100% | 80 h | 10 d | 2003-02-03 | 2003-02-14 | 100% | 308 | 80 h | 80 | No | 1.5.2.6.2 | 306FF | Lakshmi[103%] | 2003-02-03 08:00 | 2003-02-14 14:30 | NA
Murthy | 456 | MQ - Interface module - Coding | 100% | 50 h | 38 d | 2003-02-14 | 2003-04-08 | 100% | 309FF | 50 h | 50 | No | 1.5.2.6.3 | 307 | Murthy[54%] | 2003-02-14 14:30 | 2003-03-04 10:30 | NA
Murthy | 457 | MQ - Interface module - UT/IT | 100% | 40 h | 38 d | 2003-02-14 | 2003-04-08 | 100% | 310FS-7 d | 40 h | 40 | No | 1.5.2.6.4 | 308FF | Murthy[43%] | 2003-02-14 14:30 | 2003-03-04 10:30 | NA
Murthy | 458 | Incoming Interface - Coding | 100% | 30 h | 4 d | 2003-03-07 | 2003-03-13 | 100% | 311FF | 30 h | 30 | No | 1.5.2.6.5 | 309FS-7 d | Murthy[97%] | 2003-03-04 10:30 | 2003-03-10 09:30 | NA
Murthy | 459 | Incoming Interface - UT/IT | 100% | 30 h | 4 d | 2003-03-07 | 2003-03-13 | 100% | 312,314,316 | 30 h | 30 | No | 1.5.2.6.6 | 310FF | Lakshmi[97%] | 2003-03-04 10:30 | 2003-03-10 09:30 | NA
Murthy | 460 | Build Auto App Program - Coding | 100% | 40 h | 19 d | 2003-03-13 | 2003-04-08 | 100% | 313FF | 40 h | 40 | No | 1.5.2.6.7 | 311 | Murthy[129%] | 2003-03-10 09:30 | 2003-03-17 08:15 | NA
Murthy | 461 | Build Auto App Program - UT/IT | 100% | 40 h | 19 d | 2003-03-13 | 2003-04-08 | 100% | 271FF-5 d,270FF-6 d | 40 h | 40 | No | 1.5.2.6.8 | 312FF | Lakshmi[129%] | 2003-03-10 09:30 | 2003-03-17 08:15 | NA
Murthy | 462 | Warning Screen - Coding | 100% | 30 h | 13 d | 2003-03-24 | 2003-04-09 | 100% | 315FF | 30 h | 30 | No | 1.5.2.6.9 | 311 | Murthy[32%] | 2003-03-17 08:15 | 2003-03-20 16:15 | NA
Murthy | 463 | Warning Screen - UT/IT | 100% | 30 h | 13 d | 2003-03-24 | 2003-04-09 | 100% |  | 30 h | 30 | No | 1.5.2.6.10 | 314FF | Lakshmi[32%] | 2003-03-17 08:15 | 2003-03-20 16:15 | NA
Murthy | 464 | Outgoing Interface - Coding | 100% | 30 h | 5 d | 2003-04-03 | 2003-04-09 | 100% | 317FF | 30 h | 30 | No | 1.5.2.6.11 | 311 | Murthy[97%] | 2003-03-20 16:15 | 2003-03-26 15:15 | NA
Murthy | 465 | Outgoing Interface - UT/IT | 100% | 30 h | 5 d | 2003-04-03 | 2003-04-09 | 100% | 329 | 30 h | 30 | No | 1.5.2.6.12 | 316FF | Lakshmi[97%] | 2003-03-20 16:15 | 2003-03-26 15:15 | NA
Amar | 466 | Auto Apps - Main Program - Coding | 100% | 60 h | 8 d | 2003-02-03 | 2003-02-12 | 100% | 319FF | 60 h | 60 | No | 1.5.2.6.13 | 283 | Amar[97%] | 2003-02-03 08:00 | 2003-02-12 15:00 | NA
Amar | 467 | Auto Apps - Main Program - UT/IT | 100% | 60 h | 8 d | 2003-02-03 | 2003-02-12 | 100% | 320 | 60 h | 60 | No | 1.5.2.6.14 | 318FF | Tina[97%] | 2003-02-03 08:00 | 2003-02-12 15:00 | NA
Amar | 468 | Residence Address screen - Coding | 100% | 40 h | 10 d | 2003-02-12 | 2003-02-26 | 100% | 321FF | 40 h | 40 | No | 1.5.2.6.15 | 319 | Amar[52%] | 2003-02-12 15:00 | 2003-02-26 11:30 | NA
Amar | 469 | Residence Address screen - UT/IT | 100% | 40 h | 10 d | 2003-02-12 | 2003-02-26 | 100% | 322,324 | 40 h | 40 | No | 1.5.2.6.16 | 320FF | Amar[52%] | 2003-02-12 15:00 | 2003-02-26 11:30 | NA
Amar | 470 | AUI Request Driver Information Screen - Coding | 100% | 80 h | 15 d | 2003-02-26 | 2003-03-18 | 100% | 323FF | 80 h | 80 | No | 1.5.2.6.17 | 321 | Amar[103%] | 2003-02-26 11:30 | 2003-03-12 09:00 | NA
Amar | 471 | AUI Request Driver Information Screen - UT/IT | 100% | 80 h | 23 d | 2003-02-26 | 2003-03-28 | 100% | 328FF | 80 h | 80 | No | 1.5.2.6.18 | 322FF | Tina[103%] | 2003-02-26 11:30 | 2003-03-12 09:00 | NA
Amar | 472 | Territory Validation (Options screen) - Coding | 100% | 60 h | 8 d | 2003-03-14 | 2003-03-25 | 100% | 325FF,326SS | 60 h | 60 | No | 1.5.2.6.19 | 321 | Amar[97%] | 2003-03-12 09:00 | 2003-03-25 15:30 | NA
Amar | 473 | Territory Validation (Options screen) - UT/IT | 100% | 60 h | 15 d | 2003-03-14 | 2003-04-03 | 100% |  | 60 h | 60 | No | 1.5.2.6.20 | 324FF | Amar[48%],Tina | 2003-03-12 09:00 | 2003-03-25 15:30 | NA
Amar | 474 | Pf Key format /Branching Program (PCS5F) - Coding | 100% | 20 h | 11 d | 2003-03-14 | 2003-03-28 | 100% | 327 | 20 h | 20 | No | 1.5.2.6.21 | 324SS | Amar[23%] | 2003-03-25 15:30 | 2003-03-28 14:45 | NA
Amar | 475 | Pf Key format /Branching Program (PCS5F) - UT/IT | 100% | 40 h | 4 d | 2003-03-28 | 2003-04-03 | 100% |  | 40 h | 40 | No | 1.5.2.6.22 | 326 | Tina[65%],Murthy | 2003-03-25 15:30 | 2003-03-28 14:45 | NA
Amar | 471a | Driver Info warning Screen -Coding, UT/IT | 100% | 32 h | 6 d | 2003-04-03 | 2003-04-11 | 100% | 329 | 0 h | 0 | No | 1.5.2.6.23 | 301,323FF | Amar[103%] | NA | NA | NA
Amar | 476 | MS: NECHO - all Remaining Changes -Coding/UT/IT completed | 100% | 0 h | 0 d | 2003-04-11 | 2003-04-11 | 100% | 331FS-3 d,336 | 0 h | 0 | No | 1.5.2.6.24 | 317,328 |  | 2003-03-28 14:45 | 2003-03-28 14:45 | NA
| 477 | Pkg-3 Consolidated Tech Doc | 100% | 6 h | 40.69 d | 2003-04-04 | 2003-05-30 | 100% |  | 6 h | 6 | Yes | 1.5.3 |  |  | 2003-03-28 14:45 | 2003-04-01 14:15 | NA
Ty | 478 | Pkg-3 - Review NECHO Technical System Design TSD 9.2 | 100% | 3 h | 39 d | 2003-04-04 | 2003-05-30 | 100% | 332FF | 3 h | 3 | No | 1.5.3.1 | 329FS-3 d | Ty[26%],Mary[31%] | 2003-03-28 14:45 | 2003-03-31 14:30 | NA
Ty | 479 | Pkg-3 - Review Consolidated Technical Documentation TPD 7.1 | 100% | 3 h | 29 d | 2003-04-04 | 2003-05-30 | 100% |  | 3 h | 3 | No | 1.5.3.2 | 331FF | Ty[13%],Mary[26%] | 2003-03-31 14:30 | 2003-04-01 14:15 | NA
| 480 | Pkg-3 Systems Acceptance Test (SAT) | 49% | 330 h | 151.68 d | 2003-01-06 | 2003-07-30 | 67% |  | 260 h | 130 | Yes | 1.5.4 |  |  | 2003-01-06 14:00 | 2003-06-20 08:45 | NA
SteveH | 481 | SAT - Create System/Acceptance Test Plan | 100% | 20 h | 10 d | 2003-02-05 | 2003-02-19 | 100% |  | 20 h | 20 | No | 1.5.4.1 | 289,290,291,292,293,294,295,296,297,298,299,300 | SteveH[26%] | 2003-02-05 16:15 | 2003-02-19 13:45 | NA
SteveH | 482 | SAT - Create System/Acceptance Test Cases | 100% | 40 h | 31 d | 2003-02-21 | 2003-04-04 | 100% |  | 40 h | 40 | No | 1.5.4.2 | 289,290,291,292,293,294,295,296,297,298,299,300 | SteveH[34%] | 2003-02-21 08:00 | 2003-03-13 13:15 | NA
ED | 483 | SAT -Perform System/Acceptance Testing pkg-3 | 100% | 50 h | 36.68 d | 2003-04-14 | 2003-06-02 | 100% | 337,344,345 | 50 h | 50 | No | 1.5.4.3 | 304FS-1 d,329 | Ed[26%] | 2003-03-31 08:00 | 2003-04-25 11:00 | NA
SteveH | 484 | SAT - Create System/Acceptance Test Summary Report | 0% | 10 h | 2 d | 2003-06-02 | 2003-06-04 | 0% | 338 | 10 h | 0 | No | 1.5.4.4 | 336 | SteveH[65%] | 2003-04-25 11:00 | 2003-04-30 10:15 | NA
SteveH | 485 | SAT - Authorize System/Acceptance Test Summary Report | 0% | 10 h | 5 d | 2003-06-04 | 2003-06-11 | 0% |  | 10 h | 0 | No | 1.5.4.5 | 337 | SteveH[26%] | 2003-04-30 10:15 | 2003-05-07 09:00 | NA
|  | Pkg-3 Perf Testing | 46% | 70 h | 30.48 d | 2003-05-05 | 2003-06-13 | 55% |  | 0 h | 0 | Yes | 1.5.4.6 |  |  | NA | NA | NA
SteveH | 491a | Setup Performance Test Environment -pkg3 | 100% | 20 h | 15.48 d | 2003-05-05 | 2003-05-24 | 100% | 341 | 0 h | 0 | No | 1.5.4.6.1 |  |  | NA | NA | NA
SteveH | 491b | Execute Performance Testing - pk3 | 25% | 50 h | 15 d | 2003-05-26 | 2003-06-13 | 8% | 345 | 0 h | 0 | No | 1.5.4.6.2 | 340 |  | NA | NA | NA
| 486 | Pkg-3 FIT Test (SAT) | 15% | 130 h | 151.68 d | 2003-01-06 | 2003-07-30 | 44% |  | 130 h | 20 | Yes | 1.5.4.7 |  |  | 2003-01-06 14:00 | 2003-06-20 08:45 | NA
SteveH | 487 | SAT - Create NECHO System/Acceptance Test Plan | 100% | 20 h | 34 d | 2003-01-06 | 2003-02-20 | 100% |  | 20 h | 20 | No | 1.5.4.7.1 | 185 | SteveH[17%] | 2003-01-06 14:00 | 2003-02-20 13:30 | NA
ED | 488 | SAT - Create FIT Test Cases | 0% | 40 h | 10 d | 2003-06-02 | 2003-06-16 | 0% | 345 | 40 h | 0 | No | 1.5.4.7.2 | 336 | Ed[52%] | 2003-04-11 14:30 | 2003-04-25 11:00 | NA
ED | 489 | SAT - Perform FIT Testing - Pkg-3 | 0% | 50 h | 18 d | 2003-06-16 | 2003-07-10 | 0% | 346,361,357SS | 50 h | 0 | No | 1.5.4.7.3 | 336,186,344,341 | Ed[36%] | 2003-04-25 11:00 | 2003-05-30 13:30 | NA
SteveH | 490 | SAT - Create FIT Test Summary Report | 0% | 10 h | 10 d | 2003-07-10 | 2003-07-23 | 0% | 347 | 10 h | 0 | No | 1.5.4.7.4 | 345 | SteveH[13%] | 2003-05-30 13:30 | 2003-06-13 10:00 | NA
SteveH | 491 | SAT - Authorize FIT Test Summary Report | 0% | 10 h | 5 d | 2003-07-23 | 2003-07-30 | 0% |  | 10 h | 0 | No | 1.5.4.7.5 | 346 | SteveH[26%] | 2003-06-13 10:00 | 2003-06-20 08:45 | NA
| 492 | Pkg-3 Communication | 11% | 45 h | 72.42 d | 2003-05-12 | 2003-08-18 | 3% |  | 45 h | 5 | Yes | 1.5.5 |  |  | 2003-04-07 08:00 | 2003-07-08 14:30 | NA
ED | 493 | Pkg-3 Draft Communication | 50% | 10 h | 46 d | 2003-05-12 | 2003-07-11 | 5% | 350 | 10 h | 5 | No | 1.5.5.1 | 253 | Ed[26%] | 2003-04-07 08:00 | 2003-04-14 15:30 | NA
ED | 494 | Pkg-3 Communication Review by Proj Team | 0% | 5 h | 5 d | 2003-07-11 | 2003-07-18 | 0% | 351 | 5 h | 0 | No | 1.5.5.2 | 349 | Ed[13%] | 2003-04-14 15:30 | 2003-04-21 14:15 | NA
ED | 495 | Pkg-3 UPD Walkthrough with SPIP group | 0% | 5 h | 5 d | 2003-07-18 | 2003-07-25 | 0% |  | 5 h | 0 | No | 1.5.5.3 | 350 | Ed[13%] | 2003-04-21 14:15 | 2003-04-30 11:30 | NA
Lynn | 496 | MS: Pkg-3 Create Agency pilot communications | 0% | 0 h | 0 d | 2003-07-11 | 2003-07-11 | 0% |  | 0 h | 0 | No | 1.5.5.4 | 353FF-5 d |  | 2003-06-04 11:45 | 2003-06-04 11:45 | NA
Lynn | 497 | MS: Pkg-3 Publish Agency pilot communications | 0% | 0 h | 0 d | 2003-07-18 | 2003-07-18 | 0% | 352FF-5 d | 0 h | 0 | No | 1.5.5.5 | 362FF-10 d |  | 2003-06-11 10:30 | 2003-06-11 10:30 | NA
Lynn | 498 | MS: Pkg-3 Create Agency cowide communications | 0% | 0 h | 0 d | 2003-08-04 | 2003-08-04 | 0% |  | 0 h | 0 | No | 1.5.5.6 | 355FF-5 d |  | 2003-06-24 17:00 | 2003-06-24 17:00 | NA
Lynn | 499 | MS: Pkg-3 Publish Agency cowide communications | 0% | 0 h | 0 d | 2003-08-11 | 2003-08-11 | 0% | 354FF-5 d | 0 h | 0 | No | 1.5.5.7 | 363FF-10 d |  | 2003-07-01 15:45 | 2003-07-01 15:45 | NA
ED | 500 | Pkg-3 Publish Communication | 0% | 5 h | 5 d | 2003-08-11 | 2003-08-18 | 0% |  | 5 h | 0 | No | 1.5.5.8 | 363FF-5 d | Ed[13%] | 2003-07-01 15:45 | 2003-07-08 14:30 | NA
Vance | 501 | Create Pkg-3 SFQ Solutions | 0% | 10 h | 10 d | 2003-06-16 | 2003-06-30 | 0% | 358FS+10 d | 10 h | 0 | No | 1.5.5.9 | 345SS | Vance[13%] | 2003-04-25 11:00 | 2003-05-09 08:30 | NA
Vance | 502 | MS: ISC Review Pkg-3 SFQ Solutions | 0% | 0 h | 0 d | 2003-07-11 | 2003-07-11 | 0% | 359 | 0 h | 0 | No | 1.5.5.10 | 357FS+10 d |  | 2003-05-22 15:00 | 2003-05-22 15:00 | NA
Vance | 503 | Populate pkg-3 SFQ Solutions | 0% | 10 h | 5 d | 2003-07-11 | 2003-07-18 | 0% |  | 10 h | 0 | No | 1.5.5.11 | 358 | Vance[26%] | 2003-05-22 15:00 | 2003-05-29 13:45 | NA
| 504 | Pkg-3 Implementation | 0% | 65 h | 53 d | 2003-07-10 | 2003-09-19 | 0% |  | 65 h | 0 | Yes | 1.5.6 |  |  | 2003-05-30 13:30 | 2003-08-11 16:15 | NA
Amar | 505 | Necho Pkg-3 Prep for pilot issuance | 0% | 10 h | 8 d | 2003-07-10 | 2003-07-21 | 0% | 362FS+9 d | 10 h | 0 | No | 1.5.6.1 | 345 | Amar[16%] | 2003-05-30 13:30 | 2003-06-11 10:30 | NA
Amar | 506 | MS: Pkg-3 Pilot Necho | 0% | 0 h | 0 d | 2003-08-01 | 2003-08-01 | 0% | 353FF-10 d,363FS+16 d,364FF | 0 h | 0 | No | 1.5.6.2 | 361FS+9 d |  | 2003-06-24 17:00 | 2003-06-24 17:00 | NA
Amar | 507 | MS: NECHO Pkg-3 cowide Issuance | 0% | 0 h | 0 d | 2003-08-22 | 2003-08-22 | 0% | 355FF-10 d,356FF-5 d,368,369,371,370FS+15 d,365 | 0 h | 0 | No | 1.5.6.3 | 362FS+16 d |  | 2003-07-15 13:15 | 2003-07-15 13:15 | NA
Durnan | 508 | MQ Pilot/Issuance | 0% | 20 h | 10 d | 2003-07-18 | 2003-08-01 | 0% |  | 20 h | 0 | No | 1.5.6.4 | 362FF | Durnan[26%] | 2003-06-11 10:30 | 2003-06-24 17:00 | NA
ED | 509 | Pkg-3-Post implemetation questions | 0% | 35 h | 20 d | 2003-08-25 | 2003-09-19 | 0% | 366 | 35 h | 0 | No | 1.5.6.5 | 363 | Ed[16%],Durnan | 2003-07-15 13:15 | 2003-08-11 16:15 | NA
ED | 510 | MS: Pkg-3 Completed | 0% | 0 h | 0 d | 2003-09-19 | 2003-09-19 | 0% |  | 0 h | 0 | No | 1.5.6.6 | 365 |  | 2003-08-11 16:15 | 2003-08-11 16:15 | NA
| 601 | Transition | 0% | 76 h | 25 d | 2003-08-25 | 2003-09-26 | 0% |  | 86 h | 0 | Yes | 1.6 |  |  | 2003-01-06 13:15 | 2003-08-18 15:00 | NA
Ty | 602 | Update design documents (AIP 2.6) to reflect implemented system | 0% | 2 h | 1 d | 2003-08-25 | 2003-08-25 | 0% |  | 2 h | 0 | No | 1.6.1 | 363 | Mary[19%],Ty[7%] | 2003-07-15 13:15 | 2003-07-16 12:00 | NA
Ty | 603 | Transition design documents to local architect | 0% | 4 h | 2 d | 2003-08-25 | 2003-08-26 | 0% |  | 4 h | 0 | No | 1.6.2 | 363 | Mary[9%],Ty[17%] | 2003-07-15 13:15 | 2003-07-17 11:45 | NA
Carol | 604 | MS: Lessons Learned doc | 0% | 0 h | 0 d | 2003-09-12 | 2003-09-12 | 0% |  | 0 h | 0 | No | 1.6.3 | 363FS+15 d |  | 2003-08-05 08:30 | 2003-08-05 08:30 | NA
Vance | 605 | Transition to Service | 0% | 30 h | 20 d | 2003-08-25 | 2003-09-19 | 0% | 372 | 30 h | 0 | No | 1.6.4 | 363 | David,Sushit[4%],Amar[4%],John[4%],Bill[4%],Witter[2%] | 2003-07-15 13:15 | 2003-08-11 16:15 | NA
Carol | 606 | Project Closure Tasks | 0% | 40 h | 5 d | 2003-09-19 | 2003-09-26 | 0% | 373 | 40 h | 0 | No | 1.6.5 | 371 | Carol[52%],Ashok[40%],Michelle[40%] | 2003-08-11 16:15 | 2003-08-18 15:00 | NA
Carol | 607 | MS: Project Completed | 0% | 0 h | 0 d | 2003-09-26 | 2003-09-26 | 0% | 24FS-11 d | 0 h | 0 | No | 1.6.6 | 372 |  | 2003-08-18 15:00 | 2003-08-18 15:00 | NA
NA
NA
Import Info
◄▬Menu

## MileStones
Proj. 1234 |  | Proj. 1234 Watch List Status Tracking
Sr.No. | Task Code | Description of item to be tracked or progress monitored | Target Completion | Percent Complete | As On 05/20/03 | As On 05/13/03 | As On 05/06/03 | As On 04/29/03 | As On 04/22/03 | As On 04/15/03
Dates to meet
1 | 348 | AUI-DLV Mid Tier / Host Int Test | 2003-02-05 15:00 | 100% | 2003-02-05 | 2003-02-05 | 2003-02-05 | 2003-02-05 | 2003-02-05 | 2003-02-05
2 | 349 | AUI-DLV Web / Mid Tier / Host System Testing | 2003-02-26 10:15 | 100% | 2003-02-26 | 2003-02-26 | 2003-02-26 | 2003-02-26 | 2003-02-26 | 2003-02-26
3 | 351 | AUI-DLV Acceptance Testing | 2003-03-05 09:00 | 100% | 2003-04-04 | 2003-04-04 | 2003-04-04 | 2003-04-04 | 2003-04-04 | 2003-04-04
4 | 351b | Execute Perf. Testing Pkg-2 | 2003-03-25 14:15 | 75% | 2003-05-23 | 2003-05-16 | 2003-05-02 | 2003-05-02 | 2003-05-01 | 2003-04-21
5 | 367 | MS: Mid Tier-Host cowide issuance | 2003-05-12 | 0% | 2003-06-09 | 2003-05-22 | 2003-05-13 | 2003-05-13 | 2003-05-12 | 2003-04-28
6 | 369 | MS: AUI Pkg-2 cowide Issuance | 2003-05-26 08:00 | 0% | 2003-06-16 | 2003-05-29 | 2003-05-26 | 2003-05-26 | 2003-05-26 | 2003-05-26
7 | 452 | Perform Integration Testing for NECHO Changes - pkg-2 | 2003-03-28 14:45 | 100% | 2003-04-15 | 2003-04-15 | 2003-04-15 | 2003-04-15 | 2003-04-15 | 2003-04-15
8 | 483 | SAT -Perform System/Acceptance Testing pkg-3 | 2003-04-25 11:00 | 75% | 2003-06-13 | 2003-05-16 | 2003-05-16 | 2003-05-16 | 2003-05-16 | 2003-05-16
9 | 489 | SAT - Perform FIT Testing - Pkg-3 | 2003-05-30 13:30 | 0% | 2003-07-23 | 2003-06-24 | 2003-06-24 | 2003-06-11 | 2003-06-11 | 2003-06-11
10 | 506 | MS: Pkg-3 Pilot Necho | 2003-06-24 17:00 | 0% | 2003-08-14 | 2003-07-17 | 2003-07-17 | 2003-07-03 | 2003-07-03 | 2003-07-03
11 | 507 | MS: NECHO Pkg-3 cowide Issuance | 2003-07-15 13:15 | 0% | 2003-09-05 | 2003-08-07 | 2003-08-07 | 2003-07-25 | 2003-07-24 | 2003-07-24
Progress
1 | 1 | Auto Necho - Auto Apps Efficiency | 2003-08-18 15:30 | 87% | 2003-10-09 | 2003-09-10 | 2003-09-10 | 2003-08-28 | 2003-08-28 | 2003-08-28
2 | 25 | Reqs Analysis and Solution Def/Specs | 2002-11-15 11:30 | 100% | 2002-12-04 | 2002-12-04 | 2002-12-04 | 2002-12-04 | 2002-12-04 | 2002-12-04
3 | 201 | Pkg -1 Design/Build/Test/Implement | 2003-03-12 09:00 | 100% | 2003-02-14 | 2003-02-14 | 2003-02-14 | 2003-02-14 | 2003-02-14 | 2003-02-14
4 | 301 | Pkg -2 Design/Build/Test/Implement | 2003-06-20 11:00 | 91% | 2003-07-11 | 2003-06-25 | 2003-06-20 | 2003-06-20 | 2003-06-20 | 2003-06-20
5 | 401 | Pkg -3 Design/Build/Test/Implement | 2003-08-11 16:15 | 88% | 2003-10-02 | 2003-09-04 | 2003-09-04 | 2003-08-21 | 2003-08-21 | 2003-08-21
zzz
Note on B2: Last Code in this column should be zzz.
Refresh
◄▬Menu

## LogChanges
|  |  | Proj. 1234 Log of Schedule Updates | [6 empty] | Go Back to LeadsList
Update date | Lead | Task Code | Task Name | % Work Completed | Work in Hours | Duration in Days | Planned Start Date | Planned Finish Date | Remarks
◄▬Menu

## AuditTrail
Proj. 1234 |  | Track Status Changes
Lead | Code | Task Name | 687 | Baseline 09-03-2002 |  |  | 2002-09-30 | 2002-08-31
| 1 | Auto Necho - Auto Apps Efficiency | %WC | 0% |  |  | 20% | 14%
|  |  | Hours | 11,910 h |  |  | 12,345 h | 11,910 h
|  |  | Duration | 268.06 d |  |  | 268.06 d | 268.06 d
|  |  | Start | 2002-05-06 |  |  | 2002-05-06 | 2002-05-06
|  |  | Finish | 2003-04-22 | L | 10 | 2003-05-02 | 2003-05-02
| 2 | Planning, Admin, meetings, Coord, phase-Docs | %WC | 0% |  |  | 33% | 27%
|  |  | Hours | 3,639 h |  |  | 4,014 h | 3,639 h
|  |  | Duration | 259 d |  |  | 259 d | 259 d
|  |  | Start | 2002-05-06 |  |  | 2002-05-06 | 2002-05-06
|  |  | Finish | 2003-04-21 |  |  | 2003-04-21 | 2003-04-21
Carol | 3 | MS: Project Activated | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-05-06 |  |  | 2002-05-06 | 2002-05-06
|  |  | Finish | 2002-05-06 |  |  | 2002-05-06 | 2002-05-06
| 4 | Project Admin & Cordination | %WC | 0% |  |  | 34% | 26%
|  |  | Hours | 3,141 h |  |  | 3,141 h | 3,141 h
|  |  | Duration | 259 d |  |  | 259 d | 259 d
|  |  | Start | 2002-05-06 |  |  | 2002-05-06 | 2002-05-06
|  |  | Finish | 2003-04-21 |  |  | 2003-04-21 | 2003-04-21
Ashok | 5 | Project Management Activities | %WC | 0% |  |  | 42% | 35%
|  |  | Hours | 699 h |  |  | 699 h | 699 h
|  |  | Duration | 259 d |  |  | 259 d | 259 d
|  |  | Start | 2002-05-06 |  |  | 2002-05-06 | 2002-05-06
|  |  | Finish | 2003-04-21 |  |  | 2003-04-21 | 2003-04-21
Ashok | 6 | Project Coordination Activities | %WC | 0% |  |  | 25% | 15%
|  |  | Hours | 964 h |  |  | 964 h | 964 h
|  |  | Duration | 198 d |  |  | 198 d | 198 d
|  |  | Start | 2002-07-26 |  |  | 2002-07-26 | 2002-07-26
|  |  | Finish | 2003-04-21 |  |  | 2003-04-21 | 2003-04-21
Ashok | 7 | SSS activities | %WC | 0% |  |  | 42% | 35%
|  |  | Hours | 349 h |  |  | 349 h | 349 h
|  |  | Duration | 259 d |  |  | 259 d | 259 d
|  |  | Start | 2002-05-06 |  |  | 2002-05-06 | 2002-05-06
|  |  | Finish | 2003-04-21 |  |  | 2003-04-21 | 2003-04-21
Ashok | 8 | Team Weekly Meetings | %WC | 0% |  |  | 42% | 35%
|  |  | Hours | 712 h |  |  | 712 h | 712 h
|  |  | Duration | 259 d |  |  | 259 d | 259 d
|  |  | Start | 2002-05-06 |  |  | 2002-05-06 | 2002-05-06
|  |  | Finish | 2003-04-21 |  |  | 2003-04-21 | 2003-04-21
Ashok | 9 | Project Schedule / PlanView Maintenance, and Status Reporting | %WC | 0% |  |  | 19% | 10%
|  |  | Hours | 417 h |  |  | 417 h | 417 h
|  |  | Duration | 183 d |  |  | 183 d | 183 d
|  |  | Start | 2002-08-15 |  |  | 2002-08-15 | 2002-08-15
|  |  | Finish | 2003-04-21 |  |  | 2003-04-21 | 2003-04-21
| 10 | Project Charter, Plan & Schedule | %WC | 0% |  |  | 67% | 52%
|  |  | Hours | 358 h |  |  | 358 h | 358 h
|  |  | Duration | 143.71 d |  |  | 143.71 d | 143.71 d
|  |  | Start | 2002-05-21 |  |  | 2002-05-21 | 2002-05-21
|  |  | Finish | 2002-11-20 | L | 12 | 2002-12-02 | 2002-12-02
Carol | 11 | Prepare & Review Project Charter | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 67 h |  |  | 67 h | 67 h
|  |  | Duration | 35 d |  |  | 35 d | 35 d
|  |  | Start | 2002-05-21 |  |  | 2002-05-21 | 2002-05-21
|  |  | Finish | 2002-06-17 | L | 18 | 2002-07-05 | 2002-07-05
Carol | 12 | MS: Project Charter Reviewed | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-06-17 | L | 18 | 2002-07-05 | 2002-07-05
|  |  | Finish | 2002-06-17 | L | 18 | 2002-07-05 | 2002-07-05
Carol | 13 | MS: Project Charter Authorized | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-06-17 | L | 74 | 2002-08-30 | 2002-08-30
|  |  | Finish | 2002-06-17 | L | 74 | 2002-08-30 | 2002-08-30
Carol | 14 | Facilitation management Processes | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 33 h |  |  | 33 h | 33 h
|  |  | Duration | 16 d |  |  | 55 d | 16 d
|  |  | Start | 2002-06-17 | L | 18 | 2002-07-05 | 2002-07-05
|  |  | Finish | 2002-07-08 | L | 73 | 2002-09-19 | 2002-07-29
Carol | 15 | Prepare & review Project Plan | %WC | 0% |  |  | 75% | 25%
|  |  | Hours | 38 h |  |  | 38 h | 38 h
|  |  | Duration | 46 d |  |  | 64 d | 46 d
|  |  | Start | 2002-06-17 | L | 18 | 2002-07-05 | 2002-07-05
|  |  | Finish | 2002-07-05 | L | 88 | 2002-10-01 | 2002-09-06
Carol | 16 | MS: Project Plan Reviewed | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-07-05 | L | 88 | 2002-10-01 | 2002-09-13
|  |  | Finish | 2002-07-05 | L | 88 | 2002-10-01 | 2002-09-13
Carol | 17 | MS: Project Plan Authorized | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-07-05 | L | 91 | 2002-10-04 | 2002-09-20
|  |  | Finish | 2002-07-05 | L | 91 | 2002-10-04 | 2002-09-20
Ashok | 18 | Project Schedule Development -1 | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 110 h |  |  | 110 h | 110 h
|  |  | Duration | 60 d |  |  | 60 d | 60 d
|  |  | Start | 2002-05-28 |  |  | 2002-05-28 | 2002-05-28
|  |  | Finish | 2002-08-16 |  |  | 2002-08-16 | 2002-08-16
Ashok | 19 | MS: Performance Measurement Baseline - 1 Established | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-08-16 |  |  | 2002-08-16 | 2002-08-16
|  |  | Finish | 2002-08-16 |  |  | 2002-08-16 | 2002-08-16
Ashok | 20 | Project Schedule Development -2 | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 110 h |  |  | 110 h | 110 h
|  |  | Duration | 30 d |  |  | 30 d | 30 d
|  |  | Start | 2002-10-09 | L | 12 | 2002-10-21 | 2002-10-21
|  |  | Finish | 2002-11-19 | L | 10 | 2002-11-29 | 2002-11-29
Ashok | 21 | MS: Performance Measurement Baseline - 2 Established | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-11-19 | L | 10 | 2002-11-29 | 2002-11-29
|  |  | Finish | 2002-11-20 | L | 12 | 2002-12-02 | 2002-12-02
| 22 | SP/IP | %WC | 0% |  |  | 37% | 0%
|  |  | Hours | 40 h |  |  | 40 h | 40 h
|  |  | Duration | 114.03 d |  |  | 166.23 d | 114.03 d
|  |  | Start | 2002-11-05 | E | -60 | 2002-09-06 | 2002-11-15
|  |  | Finish | 2003-04-21 |  |  | 2003-04-21 | 2003-04-21
Vance | 23 | Create Initial SPIP Participant Charts | %WC | 0% |  |  | 75% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 10 d |  |  | 52 d | 10 d
|  |  | Start | 2002-11-05 | E | -60 | 2002-09-06 | 2002-11-15
|  |  | Finish | 2002-11-19 | E | -4 | 2002-11-15 | 2002-11-29
Carol | 24 | Authorize final SPIP for transition | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2003-04-07 |  |  | 2003-04-07 | 2003-04-07
|  |  | Finish | 2003-04-21 |  |  | 2003-04-21 | 2003-04-21
ED | 31 | Write Announcement Memo | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 100 h |  |  | 100 h | 100 h
|  |  | Duration | 46 d |  |  | 46 d | 46 d
|  |  | Start | 2002-10-17 | L | 7 | 2002-10-24 | 2002-10-17
|  |  | Finish | 2002-12-19 | L | 6 | 2002-12-25 | 2002-12-19
| 25 | Reqs Analysis and Solution Def/Specs | %WC | 0% |  |  | 53% | 32%
|  |  | Hours | 2,271 h |  |  | 2,271 h | 2,271 h
|  |  | Duration | 122.71 d |  |  | 122.71 d | 122.71 d
|  |  | Start | 2002-06-13 |  |  | 2002-06-13 | 2002-06-13
|  |  | Finish | 2002-11-15 | L | 12 | 2002-11-27 | 2002-11-27
| 26 | SRA / SDS | %WC | 0% |  |  | 51% | 33%
|  |  | Hours | 1,848 h |  |  | 1,848 h | 1,848 h
|  |  | Duration | 110.39 d |  |  | 110.39 d | 110.39 d
|  |  | Start | 2002-06-13 |  |  | 2002-06-13 | 2002-06-13
|  |  | Finish | 2002-10-30 | L | 12 | 2002-11-11 | 2002-11-11
ED | 27 | Determine Business Requirements | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 10 h |  |  | 10 h | 10 h
|  |  | Duration | 24 d |  |  | 24 d | 24 d
|  |  | Start | 2002-06-13 |  |  | 2002-06-13 | 2002-06-13
|  |  | Finish | 2002-07-16 |  |  | 2002-07-16 | 2002-07-16
ED | 28 | Review Testable Business Requirements | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 24 h |  |  | 24 h | 24 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-07-24 |  |  | 2002-07-24 | 2002-07-24
|  |  | Finish | 2002-07-25 |  |  | 2002-07-25 | 2002-07-25
ED | 29 | Review Business Requirements | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 8 h |  |  | 8 h | 8 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-07-26 |  |  | 2002-07-26 | 2002-07-26
|  |  | Finish | 2002-07-29 |  |  | 2002-07-29 | 2002-07-29
ED | 30 | MS: Business Req approved | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-08-01 |  |  | 2002-08-01 | 2002-08-01
|  |  | Finish | 2002-08-01 |  |  | 2002-08-01 | 2002-08-01
Ashok | 32 | Technical discussion meetings | %WC | 0% |  |  | 20% | 20%
|  |  | Hours | 480 h |  |  | 480 h | 480 h
|  |  | Duration | 72.39 d |  |  | 72.39 d | 72.39 d
|  |  | Start | 2002-08-05 |  |  | 2002-08-05 | 2002-08-05
|  |  | Finish | 2002-10-30 | L | 12 | 2002-11-11 | 2002-11-11
Amar | 33 | Create New ECHO Screen Layout | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 5 h |  |  | 5 h | 5 h
|  |  | Duration | 3 d |  |  | 3 d | 3 d
|  |  | Start | 2002-07-29 |  |  | 2002-07-29 | 2002-07-29
|  |  | Finish | 2002-08-01 |  |  | 2002-08-01 | 2002-08-01
| 34 | Domain Specs | %WC | 0% |  |  | 100% | 17%
|  |  | Hours | 13 h |  |  | 13 h | 13 h
|  |  | Duration | 45 d |  |  | 42 d | 45 d
|  |  | Start | 2002-07-30 |  |  | 2002-07-30 | 2002-07-30
|  |  | Finish | 2002-09-27 | E | -2 | 2002-09-25 | 2002-09-27
Jill | 35 | DOMAIN - review existing territory validation | %WC | 0% |  |  | 100% | 25%
|  |  | Hours | 3 h |  |  | 3 h | 3 h
|  |  | Duration | 1 d |  |  | 24 d | 1 d
|  |  | Start | 2002-07-30 |  |  | 2002-07-30 | 2002-07-30
|  |  | Finish | 2002-07-31 | L | 30 | 2002-08-30 | 2002-07-31
Jill | 36 | DOMAIN - review existing IRG validation | %WC | 0% |  |  | 100% | 25%
|  |  | Hours | 3 h |  |  | 3 h | 3 h
|  |  | Duration | 5 d |  |  | 23 d | 5 d
|  |  | Start | 2002-07-31 |  |  | 2002-07-31 | 2002-07-31
|  |  | Finish | 2002-08-07 | L | 23 | 2002-08-30 | 2002-08-07
Jill | 37 | DOMAIN - review existing driver's license validation | %WC | 0% |  |  | 100% | 25%
|  |  | Hours | 3 h |  |  | 3 h | 3 h
|  |  | Duration | 5 d |  |  | 23 d | 5 d
|  |  | Start | 2002-07-31 |  |  | 2002-07-31 | 2002-07-31
|  |  | Finish | 2002-08-07 | L | 23 | 2002-08-30 | 2002-08-07
Jill | 38 | Create SRA 4/SDS 3.1 identifying impacted reusable service areas | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 4 h |  |  | 4 h | 4 h
|  |  | Duration | 1 d |  |  | 18 d | 1 d
|  |  | Start | 2002-09-27 | E | -28 | 2002-08-30 | 2002-09-27
|  |  | Finish | 2002-09-27 | E | -2 | 2002-09-25 | 2002-09-27
| 39 | AUTO Specs | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 45 h |  |  | 45 h | 45 h
|  |  | Duration | 19 d |  |  | 19 d | 19 d
|  |  | Start | 2002-07-30 |  |  | 2002-07-30 | 2002-07-30
|  |  | Finish | 2002-08-23 |  |  | 2002-08-23 | 2002-08-23
Eric | 40 | AUTO - review existing territory validation | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 15 h |  |  | 15 h | 15 h
|  |  | Duration | 19 d |  |  | 19 d | 19 d
|  |  | Start | 2002-07-30 |  |  | 2002-07-30 | 2002-07-30
|  |  | Finish | 2002-08-23 |  |  | 2002-08-23 | 2002-08-23
Eric | 41 | AUTO - review existing IRG validation | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 15 h |  |  | 15 h | 15 h
|  |  | Duration | 19 d |  |  | 19 d | 19 d
|  |  | Start | 2002-07-30 |  |  | 2002-07-30 | 2002-07-30
|  |  | Finish | 2002-08-23 |  |  | 2002-08-23 | 2002-08-23
Eric | 42 | AUTO - review existing driver's license validation | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 15 h |  |  | 15 h | 15 h
|  |  | Duration | 19 d |  |  | 19 d | 19 d
|  |  | Start | 2002-07-30 |  |  | 2002-07-30 | 2002-07-30
|  |  | Finish | 2002-08-23 |  |  | 2002-08-23 | 2002-08-23
Ty | 43 | Determine Validation Components for ECHO & AUI | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 48 h |  |  | 48 h | 48 h
|  |  | Duration | 25 d |  |  | 18 d | 25 d
|  |  | Start | 2002-08-23 | L | 7 | 2002-08-30 | 2002-08-23
|  |  | Finish | 2002-09-26 | E | -1 | 2002-09-25 | 2002-09-26
| 44 | ECHO Specs | %WC | 0% |  |  | 64% | 39%
|  |  | Hours | 1,076 h |  |  | 1,076 h | 1,076 h
|  |  | Duration | 102.71 d |  |  | 102.71 d | 102.71 d
|  |  | Start | 2002-06-13 |  |  | 2002-06-13 | 2002-06-13
|  |  | Finish | 2002-10-21 | L | 9 | 2002-10-30 | 2002-10-30
Amar | 45 | Understand existing ECHO APPS System | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 240 h |  |  | 240 h | 240 h
|  |  | Duration | 50 d |  |  | 50 d | 50 d
|  |  | Start | 2002-06-13 |  |  | 2002-06-13 | 2002-06-13
|  |  | Finish | 2002-07-12 | L | 39 | 2002-08-20 | 2002-08-20
| 46 | Address Standradisation- Auto Main Screen | %WC | 0% |  |  | 41% | 20%
|  |  | Hours | 88 h |  |  | 88 h | 88 h
|  |  | Duration | 60 d |  |  | 60 d | 60 d
|  |  | Start | 2002-07-29 |  |  | 2002-07-29 | 2002-07-29
|  |  | Finish | 2002-09-27 | L | 21 | 2002-10-18 | 2002-10-18
Amar | 47 | Analysing the requirements(69) | %WC | 0% |  |  | 100% | 50%
|  |  | Hours | 36 h |  |  | 36 h | 36 h
|  |  | Duration | 46 d |  |  | 46 d | 46 d
|  |  | Start | 2002-07-29 |  |  | 2002-07-29 | 2002-07-29
|  |  | Finish | 2002-08-09 | L | 52 | 2002-09-30 | 2002-09-30
Amar | 48 | Design the Highlevel Specs(70) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 44 h |  |  | 44 h | 44 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-09-09 | L | 21 | 2002-09-30 | 2002-09-30
|  |  | Finish | 2002-09-20 | L | 24 | 2002-10-14 | 2002-10-14
Amar | 49 | Review of Highlevel Specs(71) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 8 h |  |  | 8 h | 8 h
|  |  | Duration | 4 d |  |  | 4 d | 4 d
|  |  | Start | 2002-09-23 | L | 21 | 2002-10-14 | 2002-10-14
|  |  | Finish | 2002-09-27 | L | 21 | 2002-10-18 | 2002-10-18
| 50 | VIN Validation | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 56 h |  |  | 56 h | 56 h
|  |  | Duration | 25.45 d |  |  | 20.1 d | 25.45 d
|  |  | Start | 2002-08-01 | L | 33 | 2002-09-03 | 2002-08-30
|  |  | Finish | 2002-09-16 | L | 14 | 2002-09-30 | 2002-10-03
Amar | 51 | Analysing the requirements(59) | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 25 h |  |  | 25 h | 25 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-08-01 | L | 33 | 2002-09-03 | 2002-08-30
|  |  | Finish | 2002-08-14 | L | 33 | 2002-09-16 | 2002-09-13
Amar | 52 | Design the Highlevel Specs-1(60) | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 8 h |  |  | 8 h | 8 h
|  |  | Duration | 4 d |  |  | 4 d | 4 d
|  |  | Start | 2002-08-14 | L | 33 | 2002-09-16 | 2002-09-16
|  |  | Finish | 2002-09-02 | L | 18 | 2002-09-20 | 2002-09-19
Amar | 53 | Design the Highlevel Specs-2(61) | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 15 h |  |  | 15 h | 15 h
|  |  | Duration | 9.1 d |  |  | 9.1 d | 9.1 d
|  |  | Start | 2002-09-02 | L | 14 | 2002-09-16 | 2002-09-19
|  |  | Finish | 2002-09-13 | L | 14 | 2002-09-27 | 2002-10-02
Amar | 54 | Review of Highlevel Specs(62) | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 8 h |  |  | 8 h | 8 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-09-13 | L | 14 | 2002-09-27 | 2002-10-02
|  |  | Finish | 2002-09-16 | L | 14 | 2002-09-30 | 2002-10-03
| 55 | AUI-- LX375 DB updation | %WC | 0% |  |  | 52% | 23%
|  |  | Hours | 88 h |  |  | 88 h | 88 h
|  |  | Duration | 43.32 d |  |  | 52.32 d | 43.32 d
|  |  | Start | 2002-08-05 |  |  | 2002-08-05 | 2002-08-05
|  |  | Finish | 2002-09-11 | L | 33 | 2002-10-14 | 2002-10-02
Amar | 56 | Analysing the requirements(64) | %WC | 0% |  |  | 100% | 50%
|  |  | Hours | 34 h |  |  | 34 h | 34 h
|  |  | Duration | 11 d |  |  | 20 d | 11 d
|  |  | Start | 2002-08-05 |  |  | 2002-08-05 | 2002-08-05
|  |  | Finish | 2002-08-13 | L | 31 | 2002-09-13 | 2002-09-02
Amar | 57 | Design the Highlevel Specs-1(65) | %WC | 0% |  |  | 100% | 25%
|  |  | Hours | 12 h |  |  | 12 h | 12 h
|  |  | Duration | 11 d |  |  | 11 d | 11 d
|  |  | Start | 2002-08-13 |  |  | 2002-08-13 | 2002-08-13
|  |  | Finish | 2002-08-15 | L | 43 | 2002-09-27 | 2002-09-16
Amar | 58 | Design the Highlevel Specs-2(66) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 34 h |  |  | 34 h | 34 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-08-15 | L | 43 | 2002-09-27 | 2002-09-16
|  |  | Finish | 2002-09-09 | L | 32 | 2002-10-11 | 2002-09-30
Amar | 59 | Review of Highlevel Specs(67) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 8 h |  |  | 8 h | 8 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-09-09 | L | 32 | 2002-10-11 | 2002-09-30
|  |  | Finish | 2002-09-11 | L | 33 | 2002-10-14 | 2002-10-02
| 60 | Driver's Licence Validation | %WC | 0% |  |  | 59% | 7%
|  |  | Hours | 91 h |  |  | 91 h | 91 h
|  |  | Duration | 37 d |  |  | 47.43 d | 37 d
|  |  | Start | 2002-08-02 |  |  | 2002-08-02 | 2002-08-02
|  |  | Finish | 2002-09-10 | L | 27 | 2002-10-07 | 2002-09-23
Amar | 61 | Analysing the requirements(51) | %WC | 0% |  |  | 100% | 25%
|  |  | Hours | 25 h |  |  | 25 h | 25 h
|  |  | Duration | 27 d |  |  | 38 d | 27 d
|  |  | Start | 2002-08-02 |  |  | 2002-08-02 | 2002-08-02
|  |  | Finish | 2002-08-16 | L | 39 | 2002-09-24 | 2002-09-09
Amar | 62 | Design the Highlevel Specs(52) | %WC | 0% |  |  | 50% | 0%
|  |  | Hours | 58 h |  |  | 58 h | 58 h
|  |  | Duration | 9 d |  |  | 9 d | 9 d
|  |  | Start | 2002-08-16 | L | 35 | 2002-09-20 | 2002-09-09
|  |  | Finish | 2002-09-09 | L | 25 | 2002-10-04 | 2002-09-20
Amar | 63 | Review of Highlevel Specs(53) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 8 h |  |  | 8 h | 8 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-09-09 | L | 25 | 2002-10-04 | 2002-09-20
|  |  | Finish | 2002-09-10 | L | 27 | 2002-10-07 | 2002-09-23
| 64 | IRG Validation | %WC | 0% |  |  | 45% | 23%
|  |  | Hours | 88 h |  |  | 88 h | 88 h
|  |  | Duration | 51.13 d |  |  | 51.13 d | 51.13 d
|  |  | Start | 2002-07-16 |  |  | 2002-07-16 | 2002-07-16
|  |  | Finish | 2002-08-27 | L | 28 | 2002-09-24 | 2002-09-24
Amar | 65 | Analysing the requirements(55) | %WC | 0% |  |  | 50% | 25%
|  |  | Hours | 40 h |  |  | 40 h | 40 h
|  |  | Duration | 44 d |  |  | 44 d | 44 d
|  |  | Start | 2002-07-16 |  |  | 2002-07-16 | 2002-07-16
|  |  | Finish | 2002-07-30 | L | 45 | 2002-09-13 | 2002-09-13
Amar | 66 | Design the Highlevel Specs(56) | %WC | 0% |  |  | 50% | 25%
|  |  | Hours | 40 h |  |  | 40 h | 40 h
|  |  | Duration | 29 d |  |  | 29 d | 29 d
|  |  | Start | 2002-07-30 |  |  | 2002-07-30 | 2002-07-30
|  |  | Finish | 2002-08-26 | L | 25 | 2002-09-20 | 2002-09-20
Amar | 67 | Review of Highlevel Specs(57) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 8 h |  |  | 8 h | 8 h
|  |  | Duration | 2 d |  |  | 2 d | 2 d
|  |  | Start | 2002-08-26 | L | 25 | 2002-09-20 | 2002-09-20
|  |  | Finish | 2002-08-27 | L | 28 | 2002-09-24 | 2002-09-24
| 68 | Address Standradisation- Residence Address Scrn | %WC | 0% |  |  | 31% | 0%
|  |  | Hours | 48 h |  |  | 48 h | 48 h
|  |  | Duration | 25 d |  |  | 25 d | 25 d
|  |  | Start | 2002-07-29 | L | 49 | 2002-09-16 | 2002-09-16
|  |  | Finish | 2002-09-16 | L | 32 | 2002-10-18 | 2002-10-18
Amar | 69 | Analysing the requirements(73) | %WC | 0% |  |  | 75% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 11 d |  |  | 11 d | 11 d
|  |  | Start | 2002-07-29 | L | 49 | 2002-09-16 | 2002-09-16
|  |  | Finish | 2002-08-28 | L | 33 | 2002-09-30 | 2002-09-30
Amar | 70 | Design the Highlevel Specs(74) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-08-28 | L | 33 | 2002-09-30 | 2002-09-30
|  |  | Finish | 2002-09-10 | L | 34 | 2002-10-14 | 2002-10-14
Amar | 71 | Review of Highlevel Specs(75) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 8 h |  |  | 8 h | 8 h
|  |  | Duration | 4 d |  |  | 4 d | 4 d
|  |  | Start | 2002-09-10 | L | 34 | 2002-10-14 | 2002-10-14
|  |  | Finish | 2002-09-16 | L | 32 | 2002-10-18 | 2002-10-18
| 72 | Teritory Validation | %WC | 0% |  |  | 30% | 0%
|  |  | Hours | 120 h |  |  | 120 h | 120 h
|  |  | Duration | 21 d |  |  | 21 d | 21 d
|  |  | Start | 2002-09-10 |  |  | 2002-09-10 | 2002-09-10
|  |  | Finish | 2002-10-08 |  |  | 2002-10-08 | 2002-10-08
Amar | 73 | Analysing the requirements(47) | %WC | 0% |  |  | 75% | 0%
|  |  | Hours | 48 h |  |  | 48 h | 48 h
|  |  | Duration | 10 d |  |  | 15 d | 10 d
|  |  | Start | 2002-09-10 |  |  | 2002-09-10 | 2002-09-10
|  |  | Finish | 2002-09-23 | L | 7 | 2002-09-30 | 2002-09-23
Amar | 74 | Design the Highlevel Specs(48) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 64 h |  |  | 64 h | 64 h
|  |  | Duration | 10 d |  |  | 5 d | 10 d
|  |  | Start | 2002-09-23 | L | 7 | 2002-09-30 | 2002-09-23
|  |  | Finish | 2002-10-07 |  |  | 2002-10-07 | 2002-10-07
Amar | 75 | Review of Highlevel Specs(49) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 8 h |  |  | 8 h | 8 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-10-07 |  |  | 2002-10-07 | 2002-10-07
|  |  | Finish | 2002-10-08 |  |  | 2002-10-08 | 2002-10-08
| 76 | AUI Driver Information Screen | %WC | 0% |  |  | 55% | 45%
|  |  | Hours | 125 h |  |  | 125 h | 125 h
|  |  | Duration | 78.71 d |  |  | 78.71 d | 78.71 d
|  |  | Start | 2002-07-16 |  |  | 2002-07-16 | 2002-07-16
|  |  | Finish | 2002-10-21 | L | 9 | 2002-10-30 | 2002-10-30
Amar | 77 | Design of New screen(77) | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 5 d |  |  | 5 d | 5 d
|  |  | Start | 2002-07-16 |  |  | 2002-07-16 | 2002-07-16
|  |  | Finish | 2002-07-23 |  |  | 2002-07-23 | 2002-07-23
Amar | 78 | Analysis of Flow of Data(78) | %WC | 0% |  |  | 100% | 50%
|  |  | Hours | 25 h |  |  | 25 h | 25 h
|  |  | Duration | 21 d |  |  | 42 d | 21 d
|  |  | Start | 2002-07-23 |  |  | 2002-07-23 | 2002-07-23
|  |  | Finish | 2002-08-06 | L | 43 | 2002-09-18 | 2002-08-20
Amar | 79 | Analysis of Validations(79) | %WC | 0% |  |  | 75% | 75%
|  |  | Hours | 32 h |  |  | 32 h | 32 h
|  |  | Duration | 20 d |  |  | 20 d | 20 d
|  |  | Start | 2002-08-06 |  |  | 2002-08-06 | 2002-08-06
|  |  | Finish | 2002-08-16 | L | 52 | 2002-10-07 | 2002-09-06
Amar | 80 | Design the Highlevel Specs(80) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 32 h |  |  | 32 h | 32 h
|  |  | Duration | 9 d |  |  | 9 d | 9 d
|  |  | Start | 2002-10-08 | L | 10 | 2002-10-18 | 2002-10-18
|  |  | Finish | 2002-10-21 | L | 9 | 2002-10-30 | 2002-10-30
Amar | 81 | Review of Highlevel Specs(81) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 16 h |  |  | 16 h | 16 h
|  |  | Duration | 9 d |  |  | 9 d | 9 d
|  |  | Start | 2002-10-08 | L | 10 | 2002-10-18 | 2002-10-18
|  |  | Finish | 2002-10-21 | L | 9 | 2002-10-30 | 2002-10-30
| 82 | AUI request Screen | %WC | 0% |  |  | 71% | 43%
|  |  | Hours | 132 h |  |  | 132 h | 132 h
|  |  | Duration | 69.81 d |  |  | 77.26 d | 69.81 d
|  |  | Start | 2002-07-16 |  |  | 2002-07-16 | 2002-07-16
|  |  | Finish | 2002-10-01 | L | 28 | 2002-10-29 | 2002-10-18
Amar | 83 | Design of New screen(83) | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 3 d |  |  | 3 d | 3 d
|  |  | Start | 2002-07-16 |  |  | 2002-07-16 | 2002-07-16
|  |  | Finish | 2002-07-19 |  |  | 2002-07-19 | 2002-07-19
Amar | 84 | Analysis of Flow of Data(84) | %WC | 0% |  |  | 100% | 50%
|  |  | Hours | 66 h |  |  | 66 h | 66 h
|  |  | Duration | 32 d |  |  | 32 d | 32 d
|  |  | Start | 2002-07-19 |  |  | 2002-07-19 | 2002-07-19
|  |  | Finish | 2002-08-02 | L | 45 | 2002-09-16 | 2002-09-16
Amar | 85 | Design the Highlevel Specs-1(85) | %WC | 0% |  |  | 100% | 50%
|  |  | Hours | 8 h |  |  | 8 h | 8 h
|  |  | Duration | 24 d |  |  | 24 d | 24 d
|  |  | Start | 2002-08-02 |  |  | 2002-08-02 | 2002-08-02
|  |  | Finish | 2002-08-07 | L | 42 | 2002-09-18 | 2002-09-18
Amar | 86 | Design the Highlevel Specs-2(86) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 28 h |  |  | 28 h | 28 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-09-16 | L | 28 | 2002-10-14 | 2002-10-03
|  |  | Finish | 2002-09-30 | L | 28 | 2002-10-28 | 2002-10-17
Amar | 87 | Review of Highlevel Specs(87) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 10 h |  |  | 10 h | 10 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-09-30 | L | 28 | 2002-10-28 | 2002-10-17
|  |  | Finish | 2002-10-01 | L | 28 | 2002-10-29 | 2002-10-18
Amar | 88 | MS: ECHO Specs completed | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-10-21 | L | 9 | 2002-10-30 | 2002-10-30
|  |  | Finish | 2002-10-21 | L | 9 | 2002-10-30 | 2002-10-30
| 89 | AUI Specs | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 75 h |  |  | 75 h | 75 h
|  |  | Duration | 30 d |  |  | 30 d | 30 d
|  |  | Start | 2002-09-06 | L | 7 | 2002-09-13 | 2002-09-06
|  |  | Finish | 2002-10-17 | L | 7 | 2002-10-24 | 2002-10-17
Witter | 90 | AUI - design address standardization | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 25 h |  |  | 25 h | 25 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-09-06 | L | 7 | 2002-09-13 | 2002-09-06
|  |  | Finish | 2002-09-20 | L | 6 | 2002-09-26 | 2002-09-20
Witter | 91 | AUI - design driver's license validation | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 25 h |  |  | 25 h | 25 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-09-20 | L | 7 | 2002-09-27 | 2002-09-20
|  |  | Finish | 2002-10-03 | L | 7 | 2002-10-10 | 2002-10-03
Witter | 92 | AUI - design VIN validation | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 25 h |  |  | 25 h | 25 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-10-03 | L | 7 | 2002-10-10 | 2002-10-03
|  |  | Finish | 2002-10-17 | L | 7 | 2002-10-24 | 2002-10-17
Jill | 93 | Logical Interface Designs (one per each reusable service modified or created) - SDS 3.1 | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 25 h |  |  | 25 h | 25 h
|  |  | Duration | 5 d |  |  | 5 d | 5 d
|  |  | Start | 2002-10-11 | L | 12 | 2002-10-23 | 2002-10-23
|  |  | Finish | 2002-10-18 | L | 11 | 2002-10-29 | 2002-10-29
Jill | 94 | Logical Interface Design Walkthrough complete (one for each reusable service modified or created) | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 2 h |  |  | 2 h | 2 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-10-18 | L | 11 | 2002-10-29 | 2002-10-29
|  |  | Finish | 2002-10-21 | L | 9 | 2002-10-30 | 2002-10-30
Jill | 95 | Reusable Service Catalog entries are made | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 2 h |  |  | 2 h | 2 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-10-21 | L | 9 | 2002-10-30 | 2002-10-30
|  |  | Finish | 2002-10-22 | L | 9 | 2002-10-31 | 2002-10-31
ED | 96 | Update Delivery Specs Doc | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 4 d |  |  | 4 d | 4 d
|  |  | Start | 2002-10-22 | L | 9 | 2002-10-31 | 2002-10-31
|  |  | Finish | 2002-10-25 | L | 12 | 2002-11-06 | 2002-11-06
ED | 97 | Review SDS Doc | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 15 h |  |  | 15 h | 15 h
|  |  | Duration | 2 d |  |  | 2 d | 2 d
|  |  | Start | 2002-10-25 | L | 12 | 2002-11-06 | 2002-11-06
|  |  | Finish | 2002-10-29 | L | 10 | 2002-11-08 | 2002-11-08
Carol | 98 | MS: SDS Doc Authorized | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-10-29 | L | 10 | 2002-11-08 | 2002-11-08
|  |  | Finish | 2002-10-29 | L | 10 | 2002-11-08 | 2002-11-08
| 99 | Testing Strategy and Test Plans | %WC | 0% |  |  | 53% | 32%
|  |  | Hours | 211 h |  |  | 211 h | 211 h
|  |  | Duration | 91.71 d |  |  | 91.71 d | 91.71 d
|  |  | Start | 2002-07-25 |  |  | 2002-07-25 | 2002-07-25
|  |  | Finish | 2002-11-15 | L | 12 | 2002-11-27 | 2002-11-27
Steve | 100 | Create Test Strategy (SRA 6.5) for AUI and ECHO enhancements | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 50 h |  |  | 50 h | 50 h
|  |  | Duration | 11 d |  |  | 32 d | 11 d
|  |  | Start | 2002-07-25 |  |  | 2002-07-25 | 2002-07-25
|  |  | Finish | 2002-08-09 | L | 28 | 2002-09-06 | 2002-08-09
Steve | 101 | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | %WC | 0% |  |  | 100% | 75%
|  |  | Hours | 11 h |  |  | 11 h | 11 h
|  |  | Duration | 5 d |  |  | 31 d | 5 d
|  |  | Start | 2002-08-09 |  |  | 2002-08-09 | 2002-08-09
|  |  | Finish | 2002-08-26 | L | 25 | 2002-09-20 | 2002-08-26
Steve | 102 | Create Defect Tracking Strategy | %WC | 0% |  |  | 100% | 25%
|  |  | Hours | 40 h |  |  | 40 h | 40 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-08-26 |  |  | 2002-08-26 | 2002-08-26
|  |  | Finish | 2002-09-06 |  |  | 2002-09-06 | 2002-09-06
Steve | 103 | Review Defect Tracking Strategy | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 10 h |  |  | 10 h | 10 h
|  |  | Duration | 5 d |  |  | 5 d | 5 d
|  |  | Start | 2002-09-06 |  |  | 2002-09-06 | 2002-09-06
|  |  | Finish | 2002-09-13 |  |  | 2002-09-13 | 2002-09-13
Steve | 104 | Create FIT Test Plan | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 40 h |  |  | 40 h | 40 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-10-25 | L | 12 | 2002-11-06 | 2002-11-06
|  |  | Finish | 2002-11-08 | L | 12 | 2002-11-20 | 2002-11-20
Steve | 105 | Review & Approve FIT Test Plan | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 10 h |  |  | 10 h | 10 h
|  |  | Duration | 5 d |  |  | 5 d | 5 d
|  |  | Start | 2002-11-08 | L | 12 | 2002-11-20 | 2002-11-20
|  |  | Finish | 2002-11-15 | L | 12 | 2002-11-27 | 2002-11-27
Steve | 106 | Create Systems/Acceptance Test Plan | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 40 h |  |  | 40 h | 40 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-10-25 | L | 12 | 2002-11-06 | 2002-11-06
|  |  | Finish | 2002-11-08 | L | 12 | 2002-11-20 | 2002-11-20
Steve | 107 | Review & Approve Systems/Acceptance Test Plan | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 10 h |  |  | 10 h | 10 h
|  |  | Duration | 5 d |  |  | 5 d | 5 d
|  |  | Start | 2002-11-08 | L | 12 | 2002-11-20 | 2002-11-20
|  |  | Finish | 2002-11-15 | L | 12 | 2002-11-27 | 2002-11-27
| 108 | AIP | %WC | 0% |  |  | 75% | 19%
|  |  | Hours | 212 h |  |  | 212 h | 212 h
|  |  | Duration | 81.61 d |  |  | 75.61 d | 81.61 d
|  |  | Start | 2002-07-19 |  |  | 2002-07-19 | 2002-07-19
|  |  | Finish | 2002-11-07 | E | -8 | 2002-10-30 | 2002-11-07
| 109 | AIP 1 - Assess Existing Technology Architecture | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 36 h |  |  | 36 h | 36 h
|  |  | Duration | 9 d |  |  | 9 d | 9 d
|  |  | Start | 2002-07-19 |  |  | 2002-07-19 | 2002-07-19
|  |  | Finish | 2002-07-31 |  |  | 2002-07-31 | 2002-07-31
Ty | 110 | Identify Architectural Constraints - AIP 1.1 | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 5 d |  |  | 5 d | 5 d
|  |  | Start | 2002-07-19 |  |  | 2002-07-19 | 2002-07-19
|  |  | Finish | 2002-07-25 |  |  | 2002-07-25 | 2002-07-25
Ty | 111 | Inventory Development Tools Standards and Procedures - AIP 1.3 | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 4 h |  |  | 4 h | 4 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-07-25 |  |  | 2002-07-25 | 2002-07-25
|  |  | Finish | 2002-07-26 |  |  | 2002-07-26 | 2002-07-26
Ty | 112 | Identify Existing Network Topology - AIP 1.2 | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 4 h |  |  | 4 h | 4 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-07-26 |  |  | 2002-07-26 | 2002-07-26
|  |  | Finish | 2002-07-29 |  |  | 2002-07-29 | 2002-07-29
Ty | 113 | Inventory Existing Hardware and System Software - AIP 1.4 | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 4 h |  |  | 4 h | 4 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-07-29 |  |  | 2002-07-29 | 2002-07-29
|  |  | Finish | 2002-07-30 |  |  | 2002-07-30 | 2002-07-30
Ty | 114 | Assemble Architecture Assessment - AIP 1.5 | %WC | 0% |  |  | 100% | 100%
|  |  | Hours | 4 h |  |  | 4 h | 4 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-07-30 |  |  | 2002-07-30 | 2002-07-30
|  |  | Finish | 2002-07-31 |  |  | 2002-07-31 | 2002-07-31
| 115 | AIP 2 - Design Technology Architecture | %WC | 0% |  |  | 68% | 4%
|  |  | Hours | 140 h |  |  | 140 h | 140 h
|  |  | Duration | 63 d |  |  | 57 d | 63 d
|  |  | Start | 2002-08-14 |  |  | 2002-08-14 | 2002-08-14
|  |  | Finish | 2002-11-07 | E | -8 | 2002-10-30 | 2002-11-07
Ty | 116 | Design Network - AIP 2.1 | %WC | 0% |  |  | 100% | 25%
|  |  | Hours | 10 h |  |  | 10 h | 10 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-08-14 |  |  | 2002-08-14 | 2002-08-14
|  |  | Finish | 2002-09-11 | L | 5 | 2002-09-16 | 2002-09-11
Ty | 117 | Define Operating Systems - AIP 2.2 | %WC | 0% |  |  | 100% | 25%
|  |  | Hours | 10 h |  |  | 10 h | 10 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-09-11 | E | -16 | 2002-08-26 | 2002-08-26
|  |  | Finish | 2002-09-24 | E | -15 | 2002-09-09 | 2002-09-09
Ty | 118 | Define Hardware Configuration - AIP 2.3 | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 10 d |  |  | 13 d | 10 d
|  |  | Start | 2002-09-11 | E | -2 | 2002-09-09 | 2002-09-11
|  |  | Finish | 2002-09-24 | L | 1 | 2002-09-25 | 2002-09-24
Ty | 119 | Define Data Distribution - AIP 2.4 | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-09-13 | E | -4 | 2002-09-09 | 2002-09-13
|  |  | Finish | 2002-09-26 | E | -1 | 2002-09-25 | 2002-09-26
Ty | 120 | Define Middleware Req. - AIP 2.5 | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 10 d |  |  | 5 d | 10 d
|  |  | Start | 2002-09-27 | E | -8 | 2002-09-19 | 2002-09-27
|  |  | Finish | 2002-10-10 | E | -15 | 2002-09-25 | 2002-10-10
Ty | 121 | Define Application Service Distribution - AIP 2.6 | %WC | 0% |  |  | 75% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-09-27 | E | -8 | 2002-09-19 | 2002-09-27
|  |  | Finish | 2002-10-10 | E | -8 | 2002-10-02 | 2002-10-10
Ty | 122 | Define Security Infrastructure - AIP 2.7 | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-10-10 | E | -8 | 2002-10-02 | 2002-10-10
|  |  | Finish | 2002-10-24 | E | -8 | 2002-10-16 | 2002-10-24
Ty | 123 | Define System Topology - AIP 2.8 | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 20 h |  |  | 20 h | 20 h
|  |  | Duration | 10 d |  |  | 10 d | 10 d
|  |  | Start | 2002-10-24 | E | -8 | 2002-10-16 | 2002-10-24
|  |  | Finish | 2002-11-07 | E | -8 | 2002-10-30 | 2002-11-07
Ty | 124 | MS: Technology Architecture Documentation complete | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-11-07 | E | -8 | 2002-10-30 | 2002-11-07
|  |  | Finish | 2002-11-07 | E | -8 | 2002-10-30 | 2002-11-07
| 125 | AIP 4 - Validate Technology Architecture | %WC | 0% |  |  | 79% | 0%
|  |  | Hours | 36 h |  |  | 36 h | 36 h
|  |  | Duration | 14 d |  |  | 20.83 d | 14 d
|  |  | Start | 2002-09-10 |  |  | 2002-09-10 | 2002-09-10
|  |  | Finish | 2002-09-25 | L | 13 | 2002-10-08 | 2002-09-27
| 126 | Engineer for Performance | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 14 h |  |  | 14 h | 14 h
|  |  | Duration | 6 d |  |  | 6 d | 6 d
|  |  | Start | 2002-09-10 |  |  | 2002-09-10 | 2002-09-10
|  |  | Finish | 2002-09-18 |  |  | 2002-09-18 | 2002-09-18
Ty | 127 | Submit initial IIA questionnaire | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 4 h |  |  | 4 h | 4 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-09-10 |  |  | 2002-09-10 | 2002-09-10
|  |  | Finish | 2002-09-11 |  |  | 2002-09-11 | 2002-09-11
Ty | 128 | Infrastructure Impact Assessment - Level 2 review (if necessary) | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 10 h |  |  | 10 h | 10 h
|  |  | Duration | 5 d |  |  | 5 d | 5 d
|  |  | Start | 2002-09-11 |  |  | 2002-09-11 | 2002-09-11
|  |  | Finish | 2002-09-18 |  |  | 2002-09-18 | 2002-09-18
| 129 | SFTA Review | %WC | 0% |  |  | 66% | 0%
|  |  | Hours | 22 h |  |  | 22 h | 22 h
|  |  | Duration | 14 d |  |  | 20.83 d | 14 d
|  |  | Start | 2002-09-10 |  |  | 2002-09-10 | 2002-09-10
|  |  | Finish | 2002-09-25 | L | 13 | 2002-10-08 | 2002-09-27
Ty | 130 | Assemble information for SFTA review | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 10 h |  |  | 10 h | 10 h
|  |  | Duration | 5 d |  |  | 14 d | 5 d
|  |  | Start | 2002-09-10 |  |  | 2002-09-10 | 2002-09-10
|  |  | Finish | 2002-09-17 | L | 10 | 2002-09-27 | 2002-09-17
Ty | 131 | Submit SFTA Design Review | %WC | 0% |  |  | 100% | 0%
|  |  | Hours | 2 h |  |  | 2 h | 2 h
|  |  | Duration | 1 d |  |  | 1 d | 1 d
|  |  | Start | 2002-09-17 | L | 8 | 2002-09-25 | 2002-09-17
|  |  | Finish | 2002-09-18 | L | 8 | 2002-09-26 | 2002-09-18
Ty | 132 | SFTA Review process | %WC | 0% |  |  | 25% | 0%
|  |  | Hours | 10 h |  |  | 10 h | 10 h
|  |  | Duration | 8 d |  |  | 8 d | 8 d
|  |  | Start | 2002-09-18 | L | 8 | 2002-09-26 | 2002-09-18
|  |  | Finish | 2002-09-25 | L | 13 | 2002-10-08 | 2002-09-27
Ty | 133 | MS: Authorized SFTA documentation | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-09-25 | L | 13 | 2002-10-08 | 2002-09-27
|  |  | Finish | 2002-09-25 | L | 13 | 2002-10-08 | 2002-09-27
Ashok | 134 | Budget for remaining phases | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 6,000 h |  |  | 6,000 h | 6,000 h
|  |  | Duration | 129 d |  |  | 129 d | 129 d
|  |  | Start | 2002-10-29 | L | 10 | 2002-11-08 | 2002-11-08
|  |  | Finish | 2003-04-22 | L | 10 | 2003-05-02 | 2003-05-02
Ashok | 209 | MS: Project Completed | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2003-04-22 |  |  | 2003-04-22 | 2003-04-22
|  |  | Finish | 2003-04-22 |  |  | 2003-04-22 | 2003-04-22
| 210 | External Dependencies | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-07-29 |  |  | 2002-07-29 | 2002-07-29
|  |  | Finish | 2002-07-29 |  |  | 2002-07-29 | 2002-07-29
| 211 | MS: Rxxxxx-Address Standerization Approved Specs | %WC | 0% |  |  | 0% | 0%
|  |  | Hours | 0 h |  |  | 0 h | 0 h
|  |  | Duration | 0 d |  |  | 0 d | 0 d
|  |  | Start | 2002-07-29 |  |  | 2002-07-29 | 2002-07-29
|  |  | Finish | 2002-07-29 |  |  | 2002-07-29 | 2002-07-29
Fill Baseline
Update Changes
Upd Baseline
◄▬Menu

## StatSum
| Proj. 1234 | Schedule Tasks Status Summary as on | 2003-06-10
1. General Information:
| Schedule Tasks Status related Statistics (based on MS Project Schedule) Leadwise details are given on "TaskSum" tab | Total number of Tasks in the Schedule: | 303
|  | Total number of Tasks Finished till date: | 250
|  | Total number of in-progress Tasks: | 12
|  | Total number of Tasks slipped on Finish | 0
|  | Total number of Tasks slipped on Start | 6
|  | Total Schedule Hours for all Tasks | 10779
|  | Total completed hours for all Tasks | 9408.45
|  | Total hours completed as % of Total Schedule hours | 87.28%
| Earned Value Analysis done as on | Schedule Performance Index (SPI) as on 7/31/2002 | 90.23%
|  | Cost Performance Index (CPI as on 7/31/2002 | 103.4%
| 2002-07-31 | Total basline-1 scheduled hours as on 7/31/02 | 11910
|  | Total baselined Earned hours as on 7/31/2002 | 8661.1
|  | Total hours actually used by team as on 6/10/2003 | 9266.5
|  | Total remaining balance hours as on 6/10/2003 | 3299.98
|  | Total Remaining Hours to complete the project | 1290.2124
|  | Total Hours Estimated to Complete | 10556.7124
Tasks status updates from resource Leads
PARs submitted
Authorizations done
Attention Required (General comments)
Note on D19: Enter names of lead who have given tasks status update.
Note on D20: Enter names of lead who have not given tasks status update.
Note on D21: Enter name, hours, and period for all persons for whom PARs have been submitted.
Note on D22: Enter name and period for all persons for who have been authorized.
Note on E3: Enter total number of tasks in schedule here.
Note on E4: Enter total number of tasks finished till date.
Note on E5: Enter total number of remaining unfinished tasks
Note on E6: Enter total number of tasks that are not finished but should have completed by now.
Note on E7: Enter total number of tasks that have not started but should have by now.
Note on E11: Enter Current SPI calculated in EVA Excel.
Note on E12: Enter Current SPI calculated in EVA Excel.
◄▬Menu

## DueTasks
Proj. 1234 |  | Tasks that are over due to finish or start as on |  |  | 2003-06-10
Sr. No. | Lead | Code | Task Name | %WC | Start | Finish | Remarks
1 | Durnan | 450 | MQ Q/A Transition to MQService Agreement | 0% | 2003-06-09 | 2003-06-13 | Start date needs revision.
2 | ED | 488 | SAT - Create FIT Test Cases | 0% | 2003-06-02 | 2003-06-16 | Start date needs revision.
3 | SteveH | 484 | SAT - Create System/Acceptance Test Summary Report | 0% | 2003-06-02 | 2003-06-04 | Start/Finish dates need revision.
4 | SteveH | 485 | SAT - Authorize System/Acceptance Test Summary Report | 0% | 2003-06-04 | 2003-06-11 | Start date needs revision.
5 | Vance | 363 | MS: ISC Review Pkg-2 SFQ Solutions | 0% | 2003-05-23 | 2003-05-23 | Start/Finish dates need revision.
6 | Vance | 364 | Populate pkg-2 SFQ Solutions | 0% | 2003-05-23 | 2003-05-30 | Start/Finish dates need revision.
| NOTE: | Start / Finish dates may be needed to be revized if these dates are less than the as on status date.
Refresh
◄▬Menu

## Unfinished
Proj. 1234 |  |  | All Unfinished Tasks List as on | 2003-05-13
Sr. No. | Lead | Code | Task Name | %WC | Start | Finish | Remarks
1 | Amar | 425 | Necho RSC Entry for Terr valid & Address Std | 25% | 2002-11-25 | 2003-06-13
2 |  | 505 | Necho Pkg-3 Prep for pilot issuance | 0% | 2003-06-24 | 2003-07-04
3 |  | 506 | MS: Pkg-3 Pilot Necho | 0% | 2003-07-17 | 2003-07-17
4 |  | 507 | MS: NECHO Pkg-3 cowide Issuance | 0% | 2003-08-07 | 2003-08-07
5 | Brian | 423 | Host Addr Std/ terr-Coding | 75% | 2002-12-27 | 2003-05-16
6 | Carol | 604 | MS: Lessons Learned doc | 0% | 2003-08-28 | 2003-08-28
7 |  | 24 | Authorize final SPIP for transition | 0% | 2003-08-27 | 2003-09-09
8 |  | 606 | Project Closure Tasks | 0% | 2003-09-04 | 2003-09-10
9 |  | 607 | MS: Project Completed | 0% | 2003-09-10 | 2003-09-10
10 | Durnan | 419 | MQ Integration Testing | 50% | 2003-04-09 | 2003-05-28
11 |  | 450 | MQ Q/A Transition to MQService Agreement | 0% | 2003-06-09 | 2003-06-13
12 |  | 508 | MQ Pilot/Issuance | 0% | 2003-07-03 | 2003-07-17
13 | ED | 483 | SAT -Perform System/Acceptance Testing pkg-3 | 75% | 2003-04-14 | 2003-05-16
14 |  | 493 | Pkg-3 Draft Communication | 0% | 2003-05-12 | 2003-05-16
15 |  | 361 | Pkg-2 Publish Communication | 0% | 2003-05-12 | 2003-05-19
16 |  | 494 | Pkg-3 Communication Review by Proj Team | 0% | 2003-05-16 | 2003-05-23
17 |  | 488 | SAT - Create FIT Test Cases | 0% | 2003-05-16 | 2003-05-30
18 |  | 495 | Pkg-3 UPD Walkthrough with SPIP group | 0% | 2003-05-23 | 2003-05-30
19 |  | 489 | SAT - Perform FIT Testing - Pkg-3 | 0% | 2003-05-30 | 2003-06-24
20 |  | 370 | Pkg 2-Post implemetation questions | 0% | 2003-05-29 | 2003-06-25
21 |  | 371 | MS: Pkg-2 Completed | 0% | 2003-06-25 | 2003-06-25
22 |  | 500 | Pkg-3 Publish Communication | 0% | 2003-07-24 | 2003-07-31
23 |  | 509 | Pkg-3-Post implemetation questions | 0% | 2003-08-07 | 2003-09-04
24 |  | 510 | MS: Pkg-3 Completed | 0% | 2003-09-04 | 2003-09-04
25 | John | 366 | Mid Tier-Host Prep cowide issuance | 0% | 2003-05-16 | 2003-05-22
26 |  | 367 | MS: Mid Tier-Host cowide issuance | 0% | 2003-05-22 | 2003-05-22
27 | Lynn | 359 | MS: Pkg-2 Create Agency cowide communications | 0% | 2003-05-15 | 2003-05-15
28 |  | 360 | MS: Pkg-2 Publish Agency cowide communications | 0% | 2003-05-22 | 2003-05-22
29 |  | 496 | MS: Pkg-3 Create Agency pilot communications | 0% | 2003-06-26 | 2003-06-26
30 |  | 497 | MS: Pkg-3 Publish Agency pilot communications | 0% | 2003-07-03 | 2003-07-03
31 |  | 498 | MS: Pkg-3 Create Agency cowide communications | 0% | 2003-07-18 | 2003-07-18
32 |  | 499 | MS: Pkg-3 Publish Agency cowide communications | 0% | 2003-07-24 | 2003-07-24
33 | SteveH | 312 | Set-up FIT Test Environment | 75% | 2003-01-21 | 2003-05-16
34 |  | 351b | Execute Perf. Testing Pkg-2 | 75% | 2003-04-15 | 2003-05-16
35 |  | 351c | Implementation testing execution pkg-2 | 25% | 2003-05-02 | 2003-05-16
36 |  | 491a | Setup Performance Test Environment -pkg3 | 50% | 2003-05-05 | 2003-05-16
37 |  | 484 | SAT - Create System/Acceptance Test Summary Report | 0% | 2003-05-16 | 2003-05-21
38 |  | 491b | Execute Performance Testing - pk3 | 0% | 2003-05-16 | 2003-05-23
39 |  | 485 | SAT - Authorize System/Acceptance Test Summary Report | 0% | 2003-05-21 | 2003-05-28
40 |  | 490 | SAT - Create FIT Test Summary Report | 0% | 2003-06-24 | 2003-07-08
41 |  | 491 | SAT - Authorize FIT Test Summary Report | 0% | 2003-07-08 | 2003-07-15
42 | Ty | 478 | Pkg-3 - Review NECHO Technical System Design TSD 9.2 | 75% | 2003-04-04 | 2003-05-16
43 |  | 479 | Pkg-3 - Review Consolidated Technical Documentation TPD 7.1 | 75% | 2003-04-04 | 2003-05-16
44 |  | 602 | Update design documents (AIP 2.6) to reflect implemented system | 0% | 2003-08-07 | 2003-08-08
45 |  | 603 | Transition design documents to local architect | 0% | 2003-08-07 | 2003-08-11
46 | Vance | 362 | Create Pkg-2 SFQ Solutions | 75% | 2003-03-21 | 2003-05-09
47 |  | 363 | MS: ISC Review Pkg-2 SFQ Solutions | 0% | 2003-05-23 | 2003-05-23
48 |  | 364 | Populate pkg-2 SFQ Solutions | 0% | 2003-05-23 | 2003-05-30
49 |  | 501 | Create Pkg-3 SFQ Solutions | 0% | 2003-05-30 | 2003-06-12
50 |  | 502 | MS: ISC Review Pkg-3 SFQ Solutions | 0% | 2003-06-26 | 2003-06-26
51 |  | 503 | Populate pkg-3 SFQ Solutions | 0% | 2003-06-26 | 2003-07-03
52 |  | 605 | Transition to Service | 0% | 2003-08-07 | 2003-09-04
53 | Witter | 368 | AUI Pkg-2 Prep for cowide issaunce | 0% | 2003-05-22 | 2003-05-29
54 |  | 369 | MS: AUI Pkg-2 cowide Issuance | 0% | 2003-05-29 | 2003-05-29
Refresh
◄▬Menu

## AllocStat
| Proj. 1234 | Team Allocation Status as on |  |  |  |  | 2003-06-10
|  | 12103 |  |  | 9266.5 |  | 3299.96 |  |  | 12566.46
Sr No | Resource Name | Total PAR Hours | Start date | End date | Total used Hours | Avg. Burn Rate /Week | Remaining Hours | Available Hrs/week | Availablity Req % | Used+Rem Hours | PV - UR | Active / Status | Authorized
1 | Amarnath Bommisetti | 1827 | 2002-07-01 | 2003-12-18 | 1747 | 1.3905 | 135.93 | 0 | 0% | 1882.93 | -55.93 | 1 | 0
2 | Ashok Kumar | 739 | 2002-05-06 | 2003-09-30 | 514 | 0.40652 | 224.98 | 0 | 0% | 738.98 | 0.02 | 1 | 0
3 | Bill Malone | 300 | 2002-10-18 | 2003-12-18 | 193.5 | 0.15594 | 106.5 | 0 | 0% | 300 | 0 | 1 | 0
4 | Brian Brown | 164 | 2002-11-18 | 2003-09-30 | 100 | 0.08088 | 63.97 | 0 | 0% | 163.97 | 0.03 | 1
5 | Carol Elam | 1014 | 2002-05-06 | 2003-09-30 | 547.5 | 0.43301 | 466.98 | 0 | 0% | 1014.48 | -0.48 | 1 | 0
6 | Charlie Rogers | 40 | 2003-05-01 | 2003-09-30 | 12 | 0.009893 | 28.23 | 0 | 0% | 40.23 | -0.23 | 1 | 0
7 | David Stern | 65 | 2002-09-30 | 2003-05-27 | 75 | 0.060318 | 0 | 0 | 0% | 75 | -10 | 1 | 0
8 | Duzianthan Mohandass | 12 | 2003-04-28 | 2003-05-16 | 8 | 0.006593 | 8 | 0 | 0% | 16 | -4 | 1 | 0
9 | Ed Weidenbenner | 556 | 2002-05-06 | 2003-09-30 | 499 | 0.39465 | 56.97 | 0 | 0% | 555.97 | 0.03 | 1 | 0
10 | Eric Gullixon | 202 | 2002-05-06 | 2003-07-16 | 117.5 | 0.092929 | 84.98 | 0 | 0% | 202.48 | -0.48 | 1 | 0
11 | Gary Scott | 30 | 2003-05-15 | 2003-06-16 | 4 | 0.0033031 | 26 | 0 | 0% | 30 | 0 | 1 | 0
12 | J Murthy | 1700 | 2002-05-06 | 2003-09-30 | 1447 | 1.1444 | 310.98 | 0 | 0% | 1757.98 | -57.98 | 1 | 0
13 | John Nutt | 300 | 2002-10-18 | 2003-09-15 | 144 | 0.11605 | 155.98 | 0 | 0% | 299.98 | 0.02 | 1 | 0
14 | Kasi Shanmugam | 120 | 2002-12-23 | 2003-09-30 | 54 | 0.043852 | 65.97 | 0 | 0% | 119.97 | 0.03 | 1 | 0
15 | Kim Miller | 50 | 2002-12-06 | 2003-09-30 | 63 | 0.05106 | 0 | 0 | 0% | 63 | -13 | 1 | 0
16 | Lakshmi Narayana Reddy | 302 | 2002-05-06 | 2003-09-30 | 144 | 0.11389 | 157.97 | 0 | 0% | 301.97 | 0.03 | 1
17 | Mary Kasley Lee | 124 | 2002-07-15 | 2003-05-07 | 92.25 | 0.073541 | 31.75 | 0 | 0% | 124 | 0 | 1 | 0
18 | Michelle Celeschi | 354 | 2002-05-06 | 2003-09-30 | 226.75 | 0.17933 | 144.97 | 0 | 0% | 371.72 | -17.72 | 1 | 0
19 | Sally Baugh | 20 | 2002-12-02 | 2003-09-30 | 23.5 | 0.019038 | 0 | 0 | 0% | 23.5 | -3.5 | 1 | 0
20 | Santosh Ramachandran | 25 | 2003-04-28 | 2003-05-30 | 6 | 0.0049448 | 19 | 0 | 0% | 25 | 0 | 1 | 0
21 | Steve Durnan | 162 | 2002-10-18 | 2003-09-30 | 171.5 | 0.13821 | 20.47 | 0 | 0% | 191.97 | -29.97 | 1 | 0
22 | Steve Hall | 775 | 2002-05-06 | 2003-09-30 | 675 | 0.53385 | 182 | 0 | 0% | 857 | -82 | 1 | 0
23 | Steve Witter | 775 | 2002-07-15 | 2003-11-18 | 809 | 0.64493 | 14.98 | 0 | 0% | 823.98 | -48.98 | 1 | 0
24 | Sushit Saha | 117 | 2002-10-21 | 2003-09-30 | 62 | 0.049984 | 61.98 | 0 | 0% | 123.98 | -6.98 | 1 | 0
25 | Tina L Dobrinich | 550 | 2002-05-06 | 2003-09-30 | 444.5 | 0.35155 | 141 | 0 | 0% | 585.5 | -35.5 | 1 | 0
26 | Ty Hartness | 134 | 2002-07-15 | 2003-05-06 | 116 | 0.092474 | 17.75 | 0 | 0% | 133.75 | 0.25 | 1 | 0
27 | Vance Dejaynes | 990 | 2002-07-25 | 2003-09-30 | 325 | 0.25938 | 671 | 0 | 0% | 996 | -6 | 1 | 0
28 | Zafar Awan | 50 | 2002-10-21 | 2003-09-30 | 48 | 0.038697 | 1.98 | 0 | 0% | 49.98 | 0.02 | 1 | 0
29 | Andrew Woodman | 57 | 2003-03-20 | 2003-07-31 | 22 | 0.018048 | 35.48 | 0 | 0% | 57.48 | -0.48 | 2 | Y
30 | Brian McKinney | 11 | 2003-03-17 | 2003-09-30 | 23.5 | 0.019272 | 0 | 0 | 0% | 23.5 | -12.5 | 2 | Y
31 | Charles Paige | 70 | 2002-10-07 | 2003-05-07 | 56.5 | 0.045476 | 13.5 | 0 | 0% | 70 | 0 | 2 | Y
32 | Daniel Lade | 55 | 2002-10-07 | 2003-09-30 | 47.5 | 0.038232 | 7.48 | 0 | 0% | 54.98 | 0.02 | 2 | Y
33 | Dave Sanders | 11 | 2002-10-07 | 2003-09-30 | 10.75 | 0.0086526 | 0 | 0 | 0% | 10.75 | 0.25 | 2 | Y
34 | Gilbert Saenz | 25 | 2002-10-07 | 2003-08-26 | 8 | 0.0064391 | 16.97 | 0 | 0% | 24.97 | 0.03 | 2 | Y
35 | Harry Ma | 100 | 2002-10-07 | 2003-09-30 | 78.75 | 0.063385 | 21.23 | 0 | 0% | 99.98 | 0.02 | 2 | Y
36 | John Isaacson | 40 | 2002-08-01 | 2003-02-28 | 40.5 | 0.032349 | 0 | 0 | 0% | 40.5 | -0.5 | 2 | Y
37 | Lynn C Flannelly | 0 | 2002-11-01 | 2003-02-28 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 2 | Y
38 | Michael Frey | 212 | 2002-05-06 | 2003-02-28 | 290 | 0.22936 | 0 | 0 | 0% | 290 | -78 | 2 | Y
39 | Sherrill Leslie | 25 | 2002-10-07 | 2003-06-25 | 20 | 0.016098 | 4.98 | 0 | 0% | 24.98 | 0.02 | 2 | 0
40 | Brenda Austin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 4 | 0
41 | Carey Voyles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 4 | 0
42 | Janie Houchin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 4 | 0
43 | Liz Fry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 4 | 0
Note on C3: Assigned hours are initially (at the begining of the project) taken from PlanView Report R_TR_001 and later updated based on PAR or correction to PlanView remaining hours. Normally this figure should be equal to sum of cummulative used hours and remaining hours. When a person is authisized instead of allocated in PlanView, this cell value should be set to the cell value in actual used hours column i.e. used hours becomes the assigned hours. This column is normally updated manually.
Note on F3: This column contains the actual cummulative logged hours in Time Reporter by a person. Values in this column are updated by pasting direct cut from R_DT_CD1 PlanView report. (R_DT_CD1 have to be exported to xls and then sorted on name before cut and paste operation).
Refresh
◄▬Menu

## PAREFC
| Proj. 1234 | PAR Extension Forecast as on | [6 empty] | 2003-06-10
|  | 11960 |  |  | 3471.5 |  | 10740.18 |  |  |  | 2003-04-22 | -159122.7619 | 7518.2 |  | Y | Y | 0 | 11960
Sr No | Name as MS Outlook Directory | Current Total AlloCation Hours | Allocation Start date | Allocation Finish date | Current Total used Hrs from PlanView | Current Average Burn Rate / Week | Total hours allocated in schedule | Schedule Allocation Rate / week | Average of Schedule Alloc Rate & Burn Rate | Use this Burn Rate for Forecasting | Resource required to be on project till date | Hours use Forecast for Remaining period | Current Remaining Hours from PlanView | Forecasted Hours - Remaining Hours | Is Authorized? | Active / Inactive ? | Final Decision on Hours extension | Net Allocation hours after extension | Average Net Hours Available / week | Remarks
1 | Ashok Kumar | 500 | 2002-05-06 | 2003-04-22 | 293 | 0.23173 | 652.18 | 13.0064 | 6.6191 | 10 | 2003-04-22 | -12142.6159 | 215.93 | 0 |  | 1 | 0 | 500 | 9.9715
2 | Amarnath Bommisetti | 1700 | 2002-07-01 | 2003-04-22 | 744 | 0.59217 | 1254.44 | 29.7664 | 15.1793 | 27.1838 | 2003-04-22 | -33008.2486 | 1068.92 | 0 |  | 1 | 0 | 1700 | 40.339
3 | Carol Elam | 1000 | 2002-05-06 | 2003-04-22 | 316.5 | 0.25032 | 984.36 | 19.6311 | 9.9407 | 14.4469 | 2003-04-22 | -17542.314 | 696.97 | 0 |  | 1 | 0 | 1000 | 19.943
4 | Ed Weidenbenner | 1000 | 2002-05-06 | 2003-04-22 | 282 | 0.22303 | 326.88 | 6.519 | 3.371 | 7.4869 | 2003-04-22 | -9091.0305 | 121.92 | 0 |  | 1 | 0 | 1000 | 19.943
5 | Eric Gullixon | 1200 | 2002-05-06 | 2003-04-22 | 91 | 0.071971 | 247.03 | 4.9265 | 2.4992 | 3.6443 | 2003-04-22 | -4425.1496 | 110.45 | 0 |  | 1 | 0 | 1200 | 23.9316
6 | J Murthy | 1700 | 2002-05-06 | 2003-04-22 | 530 | 0.41917 | 1376.46 | 27.4508 | 13.935 | 13.0763 | 2003-04-22 | -15877.9973 | 1169.98 | 0 |  | 1 | 0 | 1700 | 33.9031
7 | Jill Kastello | 0 | 2002-05-06 | 2002-10-14 |  | 0 | 161.03 | 5.4193 | 2.7096 | 1.4173 | 2002-11-30 | -1749.8655 | 120 | 0 |  | 3 | 0 | 0 | 0
8 | Lakshmi Narayana Reddy | 300 | 2002-05-06 | 2003-04-22 | 41 | 0.032426 | 447.08 | 8.9161 | 4.4743 | 2.9371 | 2003-04-22 | -3566.4582 | 258.87 | 0 |  | 1 | 0 | 300 | 5.9829
9 | Mary Kasley Lee | 135 | 2002-07-15 | 2002-11-21 | 81.25 | 0.064772 | 237.53 | 12.0486 | 6.0567 | 5.457 | 2002-11-30 | -6737.725 | 56.72 | 0 |  | 1 | 0 | 135 | 6.8478
10 | Michelle Celeschi | 500 | 2002-05-06 | 2003-04-22 | 127.25 | 0.10064 | 441.76 | 8.81 | 4.4553 | 6.2943 | 2003-04-22 | -7642.9093 | 372.72 | 0 |  | 1 | 0 | 500 | 9.9715
11 | Steve Hall | 760 | 2002-05-06 | 2003-04-22 | 153 | 0.12101 | 589.99 | 11.7662 | 5.9436 | 5.5702 | 2003-04-22 | -6763.6583 | 606.92 | 0 |  | 1 | 0 | 760 | 15.1567
12 | Steve Witter | 200 | 2002-07-15 | 2003-04-22 | 203 | 0.16183 | 704.64 | 17.5533 | 8.8576 | 3.1851 | 2003-04-22 | -3867.4889 | 330.95 | 0 |  | 1 | 0 | 200 | 4.9822
13 | Tina L Dobrinich | 525 | 2002-05-06 | 2003-04-22 | 126 | 0.099652 | 425.69 | 8.4895 | 4.2946 | 4.0961 | 2003-04-22 | -4973.753 | 399.43 | 0 |  | 1 | 0 | 525 | 10.4701
14 | Ty Hartness | 135 | 2002-07-15 | 2002-11-21 | 92 | 0.073342 | 263.99 | 13.3908 | 6.7321 | 5.3639 | 2002-11-30 | -6622.7229 | 42.92 | 0 |  | 1 | 0 | 135 | 6.8478
15 | Vance Dejaynes | 990 | 2002-07-25 | 2003-06-28 | 163.5 | 0.13049 | 964 | 24.9004 | 12.5154 | 17.0084 | 2003-04-22 | -20652.6642 | 826.95 | 0 |  | 1 | 0 | 990 | 25.572
16 | John Isaacson | 16 | 2002-08-01 | 2003-04-22 | 23.5 | 0.01877 |  | 0 | 0.0093852 | 0.99674 | 2003-04-22 | -1210.3049 |  | 0 | Y | 2 | 0 | 16 | 0.42424
17 | Michael Frey | 44 | 2002-05-06 | 2003-04-04 | 55.5 | 0.043894 | 160.28 | 3.1965 | 1.6202 | 2.6748 | 2003-04-22 | -3247.8559 |  | 0 | Y | 2 | 0 | 44 | 0.87749
18 | Brenda Austin |  |  |  |  | 0 |  | 0 | 0 | 0 | 2003-04-22 | 0 |  | 0 |  | 4 | 0 | 0 | 0
19 | Carey Voyles |  |  |  |  | 0 |  | 0 | 0 | 0 | 2003-04-22 | 0 |  | 0 |  | 4 | 0 | 0 | 0
20 | Janie Houchin |  |  |  |  | 0 |  | 0 | 0 | 0 | 2003-04-22 | 0 |  | 0 |  | 4 | 0 | 0 | 0
21 | Liz Fry |  |  |  |  | 0 |  | 0 | 0 | 0 | 2003-04-22 | 0 |  | 0 |  | 4 | 0 | 0 | 0
22 | Lynn C Flannelly |  |  |  |  | 0 | 41.2 | 0.0076432 | 0.0038216 | 0 | 2003-04-22 | 0 |  | 0 |  | 4 | 0 | 0 | 0
23 | Sherrill Leslie | 25 | 2002-10-07 | 2002-04-30 | 7 | 0.0056342 | 25 | 0.88832 | 0.44698 |  | 2003-04-22 | 0 | 17.95 | 0 |  | 2 |  | 25 | 0.88832
24 | Bill Malone | 300 | 2002-10-18 | 2003-04-22 | 24.5 | 0.019745 | 361.53 | 13.606 | 6.8129 |  | 2003-04-22 | 0 | 275.47 | 0 |  | 1 |  | 300 | 11.2903
25 | Brian Brown | 100 | 2002-11-18 | 2003-05-31 | 20 | 0.016176 | 100 | 4.5161 | 2.2662 |  | 2003-04-22 | 0 | 80 | 0 |  | 1 |  | 100 | 4.5161
26 | David Stern | 50 |  |  | 3 | 0.00045422 | 42.26 | 0.0078398 | 0.004147 |  | 2003-04-22 | 0 | 49.98 | 0 |  | 1 |  | 50 | 0.0092757
27 | John Nutt | 300 | 2002-10-18 | 2003-04-22 | 13 | 0.010477 | 229.53 | 8.6382 | 4.3244 |  | 2003-04-22 | 0 | 286.9 | 0 |  | 1 |  | 300 | 11.2903
28 | Steve Durnan | 30 | 2002-10-18 | 2003-04-22 | 15.5 | 0.012492 | 315.79 | 11.8846 | 5.9485 |  | 2003-04-22 | 0 | 18.5 | 0 |  | 1 |  | 30 | 1.129
29 | Sushit Saha | 100 |  |  | 9 | 0.0013627 | 37.53 | 0.0069623 | 0.0041625 |  | 2003-04-22 | 0 | 96.98 | 0 |  | 1 |  | 100 | 0.018551
30 | Charles Paige | 50 | 2002-10-07 | 2002-04-30 | 23.75 | 0.019116 | 50 | 1.7766 | 0.89788 |  | 2003-04-22 | 0 | 26.22 | 0 |  | 2 |  | 50 | 1.7766
31 | Daniel Lade | 25 | 2002-10-07 | 2002-04-30 | 9 | 0.007244 | 25 | 0.88832 | 0.44778 |  | 2003-04-22 | 0 | 15.93 | 0 |  | 2 |  | 25 | 0.88832
32 | Dave Sanders | 50 | 2002-10-07 | 2002-04-30 | 5.25 | 0.0042257 | 50 | 1.7766 | 0.89044 |  | 2003-04-22 | 0 | 44.72 | 0 |  | 2 |  | 50 | 1.7766
33 | Gilbert Saenz | 25 | 2002-10-07 | 2002-04-30 | 2 | 0.0016098 | 25 | 0.88832 | 0.44497 |  | 2003-04-22 | 0 | 22.95 | 0 |  | 2 |  | 25 | 0.88832
34 | Harry Ma | 200 | 2002-10-07 | 2002-04-30 | 17 | 0.013683 | 200 | 7.1066 | 3.5601 |  | 2003-04-22 | 0 | 182.95 | 0 |  | 2 |  | 200 | 7.1066
Refresh
◄▬Menu

## Contact
| Proj. 1234 | Team Contact List
SrNo | Name | Role | ID | Loc | Tel No | From
1 | Amarnath Bommisetti | Systems Analyst | L0MK | K-4 | 735-9066 | Satyam
2 | Ashok Kumar | Proj Planner | JD16 | L-2 | 735-3244 | HTC
3 | Carol Elam | Proj Manager | A22H | M-4 | 763-4256 | SF
4 | Ed Weidenbenner | Business Analyst | C53Q | DEERFIELD PARK | 417-888-6122 | SF
5 | Eric Gullixon | Systems Analyst | GYUV | M-4 | 766-8964 | SF
6 | J Murthy | Systems Analyst | HKCE | L-3 | 735-9081 | Satyam
7 | Jill Kastello | Systems Analyst | GH4V | M-3 | 766-9060 | SF
8 | Lakshmi Narayana Reddy | Systems Analyst | H503 | K-4 | 735-1199 | Satyam
9 | Mary Kasley Lee | Systems Analyst | A2KO | H-3 | 763-3729 | SF
10 | Michelle Celeschi | OSS(ASA) | L2O5 | M-4 | 766-7646 | SF
11 | Steve Hall | Test Specialist | JH2T | L-4 | 763-7830 | SF
12 | Steve Witter | Systems Analyst | GBHZ | L-3 | 763-3870 | SF
13 | Tina L Dobrinich | Business Analyst | A1BO | K-4 | 763-3613 | SF
14 | Ty Hartness | Systems Analyst | BR7P | M-1 | 766-6133 | SF
15 | Vance Dejaynes | Project Coordinator | GJ78 | K-4 | 763-3867 | SF
16 | Charles Paige | IIA-Team Coordinator | LL7M | H-3 | 735-4568 | ROSE INTERNATIONAL
17 | Daniel Lade | IIA-Network Impact Assessment Analyst | J4SV | H-4 | 763-9136 | AVIANT
18 | Dave Sanders | IIA-Windows Performance Analyst | NBUD | H-3 | 766-5836 | LEVI,RAY & SHOUP, INC.
19 | Gilbert Saenz | IIA-IBM MF Performamnce Analyst | J5OY | H-4 | 763-4304 | NATIONAL COMPUTER SERVICES
20 | Harry Ma | IIA-Proactive Performance Engineering Analyst | NAKR | H-4 | 766-2968 | SCB COMPUTER TECH.
21 | John Isaacson | ? | GDP4 | K-4 | 763-3958 | SF
22 | Michael Frey | Systems Analyst | CS8K | VISALIA | 625-6920 | SF
23 | Sherrill Leslie | IIA-Network Performance Analyst | H48H | H-4 | 735-3968 | SF
Refresh
◄▬Menu

## SchPVAlloc
Proj. 1234 |  | Schedule v/s PlanView Allocation Analysis
Schedule Load (Hours)
Resource Name | Admin | SRA/SDS/AIP | Package-1 | Package-2 | Total Sch | PV Hrs | PV-Sch Hrs | Remarks
Amarnath Bommisetti | 51 | 440.91 | 77 | 696 | 1264.91 | 1700 | 435.09 | Excess allocation in PV
Ashok Kumar | 652 |  |  |  | 652 | 500 | -152 | Extend PAR
Bill Malone | 20 |  |  | 342 | 362 | 300 | -62 | Extend PAR
Carol Elam | 984 |  |  |  | 984 | 1000 | 16
Charles Paige | 50 |  |  |  | 50 | 50 | 0
Daniel Lade | 25 |  |  |  | 25 | 25 | 0
Dave Sanders | 50 |  |  |  | 50 | 50 | 0
David Stern |  |  |  | 42 | 42 | 50 | 8
Steve Durnan |  |  |  | 185 | 185 |  | -185 | Extend PAR
Ed Weidenbenner | 96.27 | 62.92 | 67.69 | 100 | 326.88 | 1000 | 673.12 | Excess allocation in PV
Eric Gullixon | 97.75 | 99.28 | 15 | 35 | 247.03 | 1200 | 952.97 | Excess allocation in PV
EricH |  |  |  | 17 | 17 |  | -17
Gilbert Saenz | 25 |  |  |  | 25 | 25 | 0
Harry Ma | 200 |  |  |  | 200 | 200 | 0 | Excess allocation in PV
Jeff |  |  |  | 11 | 11 |  | -11
John Nutt | 20 | 41 |  | 169 | 230 | 300 | 70
Lakshmi Narayana Reddy | 99.9 | 133.18 |  | 214 | 447.08 | 300 | -147.08 | Extend PAR
Lynn C Flannelly |  |  | 51.2 |  | 51.2 |  | -51.2 | Extend PAR
Mary Kasley Lee | 29.84 | 174.92 |  | 33 | 237.76 | 135 | -102.76 | Extend PAR
Michelle Celeschi | 442 |  |  |  | 442 | 500 | 58
J Murthy | 98.78 | 491.68 | 112 | 674 | 1376.46 | 1700 | 323.54 | Excess allocation in PV
Sherrill Leslie | 25 |  |  |  | 25 | 25 | 0
Steve Hall | 85.75 | 134.13 | 120.11 | 250 | 589.99 | 760 | 170.01 | Excess allocation in PV
Sushit Saha |  |  |  | 38 | 38 | 100 | 62 | Excess allocation in PV
Tina L Dobrinich | 98.78 | 132.91 |  | 194 | 425.69 | 525 | 99.31 | Excess allocation in PV
Ty Hartness | 29.84 | 138.92 | 35 | 60 | 263.76 | 135 | -128.76 | Extend PAR
Vance Dejaynes | 964 |  |  |  | 964 | 990 | 26
Steve Witter | 97.75 | 127.28 | 118 | 364 | 707.03 | 200 | -507.03 | Extend PAR
Totals | 4242.66 | 1977.13 | 596 | 3424 | 10239.79 | 11770 | 1530.21
◄▬Menu

## Sch_PV
Proj. 1234 | Schedule v/s PlanView Allocation Variance as on | [10 empty] | 2003-06-10
| -831.89 | 11436 | 10604.11 | 4287.05 | 2054.07 | 479 | 1168 | 2540 | 75.99 | 0 | 8919.74 | 8755 | 1684.37 | 3215.3 | -1613.93 | 0 | 0
Resource Name | Sch - PV Hrs | PV Hrs | Sch Hrs | R10481 - Planning/Admin/Meetings/Coordination | R10481 - Reqs Analysis and Solution Def/Specs | R10481 - Pkg -1 Design/Build/Test/Implement | R10481 - Pkg -2 Design/Build/Test/Implement | R10481 - Pkg -3 Design/Build/Test/Implement | R10481 - Transition |  | Schedule completed hours | PlanView Used hours " | Schedule Unfinished hours | PlanView Remaining hours | Sch Unifinished - PV Remaining hours
Amar | -476.56 | 1827 | 1350.44 | 51 | 440.91 | 80 |  | 772 | 6.53 |  | 1276.56 | 1747 | 73.88 | 135.93 | -62.05 | Bommisetti Amarnath
Ashok | -86.82 | 739 | 652.18 | 637.9 | 4.28 |  |  |  | 10 |  | 482.63 | 514 | 169.55 | 224.98 | -55.43 | Kumar Ashok | x
Bill | 66.53 | 300 | 366.53 | 20 |  |  | 340 |  | 6.53 |  | 335 | 193.5 | 31.53 | 106.5 | -74.97 | Malone Bill
Brian | -84 | 164 | 80 |  |  |  |  | 80 |  |  | 80 | 100 | 0 | 63.97 | -63.97 | Brown Brian [GS03]
Carol | -29.64 | 1014 | 984.36 | 957.98 | 6.38 |  |  |  | 20 |  | 740.69 | 547.5 | 243.67 | 466.98 | -223.31 | Elam Carol
Charles | -20 | 70 | 50 | 50 | [6 empty] | 26 | 56.5 | 24 | 13.5 | 10.5 | Paige Charles
Daniel | -30 | 55 | 25 | 25 | [6 empty] | 25 | 47.5 | 0 | 7.48 | -7.48 | Lade Daniel
Dave | 39 | 11 | 50 | 50 | [6 empty] | 26 | 10.75 | 24 |  | 24 | Sanders Dave
David | -28.74 | 65 | 36.26 |  |  |  | 35 |  | 1.26 |  | 35 | 75 | 1.26 |  | 1.26 | Stern David
Durnan | 43 | 162 | 205 |  |  |  |  | 205 |  |  | 160 | 171.5 | 45 | 20.47 | 24.53 | Durnan Steve
Ed | -49.12 | 556 | 506.88 | 96.27 | 62.92 | 57.69 | 100 | 190 |  |  | 317.75 | 499 | 189.13 | 56.97 | 132.16 | Weidenbenner Ed | x
Eric | -4.97 | 202 | 197.03 | 97.75 | 99.28 | [5 empty] | 162.22 | 117.5 | 34.81 | 84.98 | -50.17 | Gullixon Eric
EricH | 17 |  | 17 |  |  |  | 17 |  |  |  | 17 |  | 0 | 0 | 0 | EricH
Gilbert | 0 | 25 | 25 | 25 | [6 empty] | 25 | 8 | 0 | 16.97 | -16.97 | Saenz Gilbert
Harry | 100 | 100 | 200 | 200 | [6 empty] | 4 | 78.75 | 196 | 21.23 | 174.77 | Ma Harry | x
Jeff | 11 |  | 11 |  |  |  | 11 |  |  |  | 11 |  | 0 | 0 | 0 | Jeff
Jill | 161.03 |  | 161.03 | 97.75 | 63.28 | [5 empty] | 126.22 |  | 34.81 | 0 | 34.81 | Jill | x
John | -45.47 | 300 | 254.53 | 20 | 41 |  | 187 |  | 6.53 |  | 243 | 144 | 11.53 | 155.98 | -144.45 | Nutt John
Lakshmi | 145.08 | 302 | 447.08 | 99.9 | 133.18 |  |  | 214 |  |  | 409.46 | 144 | 37.62 | 157.97 | -120.35 | Reddy Lakshmi Narayana
Lynn | 41.2 |  | 41.2 |  |  | 41.2 |  |  |  |  | 41.2 |  | 0 |  | 0 | Flannelly Lynn C
Mary | 95.96 | 124 | 219.96 | 29.84 | 174.92 | 2.16 | 3.88 | 6.36 | 2.8 |  | 213.47 | 92.25 | 6.49 | 31.75 | -25.26 | Lee Mary Kasley
Michelle | 87.76 | 354 | 441.76 | 428.76 | 3 |  |  |  | 10 |  | 343.45 | 226.75 | 98.31 | 144.97 | -46.66 | Celeschi Michelle
Murthy | -324.54 | 1700 | 1375.46 | 98.78 | 491.68 | 101 |  | 684 |  |  | 1339.62 | 1447 | 35.84 | 310.98 | -275.14 | Murthy J
PerTeam | 49.36 |  | 49.36 |  |  |  | 49.36 |  |  |  | 35 |  | 14.36 | 0 | 14.36 | PerTeam
Sherrill | 0 | 25 | 25 | 25 | [6 empty] | 25 | 20 | 0 | 4.98 | -4.98 | Leslie Sherrill
SteveH | -199.37 | 775 | 575.63 | 85.75 | 134.13 | 70.11 | 155.64 | 130 |  |  | 497.68 | 675 | 77.95 | 182 | -104.05 | Hall Steve
Sushit | -79.47 | 117 | 37.53 |  |  |  |  | 31 | 6.53 |  | 31 | 62 | 6.53 | 61.98 | -55.45 | Saha Sushit
Tina | -114.31 | 550 | 435.69 | 98.78 | 132.91 |  |  | 204 |  |  | 399.7 | 444.5 | 35.99 | 141 | -105.01 | Dobrinich Tina L
Ty | 57.56 | 134 | 191.56 | 29.84 | 138.92 | 13.84 | 2.12 | 3.64 | 3.2 |  | 184.67 | 116 | 6.89 | 17.75 | -10.86 | Hartness Ty
Vance | 14 | 990 | 1004 | 964 |  |  | 20 | 20 |  |  | 781.2 | 325 | 222.8 | 671 | -448.2 | Dejaynes Vance
Witter | -187.36 | 775 | 587.64 | 97.75 | 127.28 | 113 | 247 |  | 2.61 |  | 525.22 | 809 | 62.42 | 14.98 | 47.44 | Witter Steve
[12 empty] | 59 | 0 | 0 | -59 | Frey Michael
[12 empty] | 24 | 0 | 0 | -24 | Isaacson John
[12 empty] | 0 | 0 | 50 | -50 | Awan Zafar
[12 empty] | 0 | 0 | 50 | -50 | Miller Kim
◄▬Menu

## TrSch_PV
Proj. 1234 |  | Schedule v/s PlanView Allocation Variance as on | [10 empty] | 2003-06-10
Resource Name | Total | Amarnath Bommisetti | Ashok Kumar | Bill Malone | Brian Brown | Carol Elam | Charles Paige | Daniel Lade | Dave Sanders | David Stern | Steve Durnan | Ed Weidenbenner | Eric Gullixon | EricH | Gilbert Saenz | Harry Ma | Jeff | Jill | John Nutt | Lakshmi Narayana Reddy | Lynn C Flannelly | Mary Kasley Lee | Michelle Celeschi | J Murthy | PerTeam | Sherrill Leslie | Steve Hall | Sushit Saha | Tina L Dobrinich | Ty Hartness | Vance Dejaynes | Steve Witter
Schedule - PlanView Alloc Difference | -831.89 | -476.56 | -86.82 | 66.53 | -84 | -29.64 | -20 | -30 | 39 | -28.74 | 43 | -49.12 | -4.97 | 17 | 0 | 100 | 11 | 161.03 | -45.47 | 145.08 | 41.2 | 95.96 | 87.76 | -324.54 | 49.36 | 0 | -199.37 | -79.47 | -114.31 | 57.56 | 14 | -187.36
Current PlanView Allocation Hours | 11436 | 1827 | 739 | 300 | 164 | 1014 | 70 | 55 | 11 | 65 | 162 | 556 | 202 |  | 25 | 100 |  |  | 300 | 302 |  | 124 | 354 | 1700 |  | 25 | 775 | 117 | 550 | 134 | 990 | 775
Current Schedule Assignment Hours | 10604.11 | 1350.44 | 652.18 | 366.53 | 80 | 984.36 | 50 | 25 | 50 | 36.26 | 205 | 506.88 | 197.03 | 17 | 25 | 200 | 11 | 161.03 | 254.53 | 447.08 | 41.2 | 219.96 | 441.76 | 1375.46 | 49.36 | 25 | 575.63 | 37.53 | 435.69 | 191.56 | 1004 | 587.64
Planning/Admin/Meetings/Coordination | 4287.05 | 51 | 637.9 | 20 |  | 957.98 | 50 | 25 | 50 |  |  | 96.27 | 97.75 |  | 25 | 200 |  | 97.75 | 20 | 99.9 |  | 29.84 | 428.76 | 98.78 |  | 25 | 85.75 |  | 98.78 | 29.84 | 964 | 97.75
Reqs Analysis and Solution Def/Specs | 2054.07 | 440.91 | 4.28 |  |  | 6.38 | [5 empty] | 62.92 | 99.28 |  |  |  |  | 63.28 | 41 | 133.18 |  | 174.92 | 3 | 491.68 |  |  | 134.13 |  | 132.91 | 138.92 |  | 127.28
Pkg -1 Design/Build/Test/Implement | 479 | 80 | [9 empty] | 57.69 | [8 empty] | 41.2 | 2.16 |  | 101 |  |  | 70.11 |  |  | 13.84 |  | 113
Pkg -2 Design/Build/Test/Implement | 1168 |  |  | 340 | [5 empty] | 35 |  | 100 |  | 17 |  |  | 11 |  | 187 |  |  | 3.88 |  |  | 49.36 |  | 155.64 |  |  | 2.12 | 20 | 247
Pkg -3 Design/Build/Test/Implement | 2540 | 772 |  |  | 80 | [5 empty] | 205 | 190 | [7 empty] | 214 |  | 6.36 |  | 684 |  |  | 130 | 31 | 204 | 3.64 | 20
Transition | 75.99 | 6.53 | 10 | 6.53 |  | 20 |  |  |  | 1.26 | [8 empty] | 6.53 |  |  | 2.8 | 10 |  |  |  |  | 6.53 |  | 3.2 |  | 2.61
0
Schedule completed hours | 8919.74 | 1276.56 | 482.63 | 335 | 80 | 740.69 | 26 | 25 | 26 | 35 | 160 | 317.75 | 162.22 | 17 | 25 | 4 | 11 | 126.22 | 243 | 409.46 | 41.2 | 213.47 | 343.45 | 1339.62 | 35 | 25 | 497.68 | 31 | 399.7 | 184.67 | 781.2 | 525.22
PlanView Used hours " | 8755 | 1747 | 514 | 193.5 | 100 | 547.5 | 56.5 | 47.5 | 10.75 | 75 | 171.5 | 499 | 117.5 |  | 8 | 78.75 |  |  | 144 | 144 |  | 92.25 | 226.75 | 1447 |  | 20 | 675 | 62 | 444.5 | 116 | 325 | 809 | 59 | 24
Schedule Unfinished hours | 1684.37 | 73.88 | 169.55 | 31.53 | 0 | 243.67 | 24 | 0 | 24 | 1.26 | 45 | 189.13 | 34.81 | 0 | 0 | 196 | 0 | 34.81 | 11.53 | 37.62 | 0 | 6.49 | 98.31 | 35.84 | 14.36 | 0 | 77.95 | 6.53 | 35.99 | 6.89 | 222.8 | 62.42 | 0 | 0
PlanView Remaining hours | 3115.3 | 135.93 | 224.98 | 106.5 | 63.97 | 466.98 | 13.5 | 7.48 |  |  | 20.47 | 56.97 | 84.98 | 0 | 16.97 | 21.23 | 0 | 0 | 155.98 | 157.97 |  | 31.75 | 144.97 | 310.98 | 0 | 4.98 | 182 | 61.98 | 141 | 17.75 | 671 | 14.98 | 0 | 0
Sch Unifinished - PV Remaining hours | -1513.93 | -62.05 | -55.43 | -74.97 | -63.97 | -223.31 | 10.5 | -7.48 | 24 | 1.26 | 24.53 | 132.16 | -50.17 | 0 | -16.97 | 174.77 | 0 | 34.81 | -144.45 | -120.35 | 0 | -25.26 | -46.66 | -275.14 | 14.36 | -4.98 | -104.05 | -55.45 | -105.01 | -10.86 | -448.2 | 47.44 | -59 | -24
◄▬Menu

## PARTrns
Proj. 1234 | PARs Status Details |  |  |  | as on | 2003-06-10
PAR Assignment & PlanView Allocation |  |  |  |  | PAR - Submission Details
Assigned to | Submited on Date | Approved on Date | Alloc. Hours | Team Status | PAR Key Ref No | Project Role | Work Entity | From Date | To Date | Alloc. Hours | Skills | Role Steward
Ashok Kumar | 2002-05-01 | 2002-05-01 | 500 | Up | Initial Alloc | Proj Planner | R10481--RESERVED PROJECT TEAM SKILLS | 2002-05-06 | 2003-04-22 | 500 | Project Planning and Tracking | DONNA ANDREWS
Carol Elam | 2002-05-01 | 2002-05-01 | 1000 | Up | Initial Alloc | Proj Manager | R10481--RESERVED PROJECT TEAM SKILLS | 2002-05-06 | 2003-04-22 | 1000 | Project Management
Ed Weidenbenner | 2002-05-01 | 2002-05-01 | 1000 | Up | Initial Alloc | Business Analyst | R10481--RESERVED PROJECT TEAM SKILLS | 2002-05-06 | 2003-04-22 | 1000 | ???Requirements Ananlysis, Acceptance criteria
Eric Gullixon | 2002-05-01 | 2002-05-01 | 1200 | Up | Initial Alloc | Systems Analyst | R10481--RESERVED PROJECT TEAM SKILLS | 2002-05-06 | 2003-04-22 | 1200 | Design/Development ( ? )
Jill Kastello | 2002-05-01 | 2002-05-01 | 120 | Up | Initial Alloc | Systems Analyst | R10481--RESERVED PROJECT TEAM SKILLS | 2002-05-06 | 2002-07-26 | 120 | Design/Development ( ? )
Michael Frey | 2002-05-01 | 2002-05-01 | 30 | Up | Initial Alloc | Systems Analyst | R10481--RESERVED PROJECT TEAM SKILLS | 2002-05-06 | 2003-04-04 | 30 | Design/Development ( ? )
Michelle Celeschi | 2002-05-01 | 2002-05-01 | 494 | Up | Initial Alloc | OSS(ASA) | R10481--RESERVED PROJECT TEAM SKILLS | 2002-05-06 | 2003-04-22 | 500 | Administrattive Support
Steve Hall | 2002-05-01 | 2002-05-01 | 750 | Up | Initial Alloc | Test Specialist | R10481--RESERVED PROJECT TEAM SKILLS | 2002-05-06 | 2003-04-22 | 750 | Testing Coordination
Note on M3: Primary Skill (other skills in comment attached to the cell)
Note on M4: 1. Level 3 -- MICROSOFT PROJECT - USE 2. Level 3 -- MEETING FACILITATION 3. Level 3 -- PLANVIEW - USE
Update Team status
Temp macro
◄▬Menu

## SRA_SDS_AIP
Auto- Increase Underwriting Product Order Abatement & Automated Issuance
Lead | Task Code | Task Name | Work in Hours | Duration in Days | Planned Start Date | Planned Finish date | Predecessor | Successors | Resources
| 22 | SRA / SDS | 1,226 h | 194.68 d | 2002-02-18 | 2002-11-07
ED | 23 | Determine Business Requirements | 10 h | 23 d | 2002-06-13 | 2002-07-15 |  | 24FS+6 d | Ed[0.03],Tina[0.03]
ED | 24 | Review Testable Business Requirements | 24 h | 1 d | 2002-07-23 | 2002-07-24 | 23FS+6 d | 61,26FS+5 d,25FS+1 d | Ed[0.26],Carol[0.5],Ashok[0.4],Eric[0.4],Murthy,Jill[0.4],Lakshmi,Michael[0.4],Steve[0.4],Tina,Amarnath,Michelle[0.4]
ED | 25 | Review Business Requirements | 8 h | 1 d | 2002-07-25 | 2002-07-25 | 24FS+1 d | 27,29FS+1 d,34FS+1 d,51FS+1 d | Ed,Carol[0.5],Tina,Eric[0.26]
ED | 26 | MS: Business Req approved | 0 h | 0 d | 2002-07-30 | 2002-07-30 | 24FS+5 d | 91
Tina | 27 | Create New ECHO Screen Layout | 5 h | 3 d | 2002-07-26 | 2002-07-30 | 25 |  | Tina[0.22]
| 28 | Domain Specs | 13 h | 47.01 d | 2002-07-26 | 2002-09-30
Jill | 29 | DOMAIN - review existing territory validation | 3 h | 1 d | 2002-07-26 | 2002-07-29 | 25FS+1 d | 30 | Jill[0.39]
Jill | 30 | DOMAIN - review existing IRG validation | 3 h | 5 d | 2002-07-29 | 2002-08-05 | 29 | 31SS | Jill[0.08]
Jill | 32 | DOMAIN - review existing driver's license validation | 3 h | 5 d | 2002-07-29 | 2002-08-05 | 30SS | 37 | Jill[0.08]
Jill | 33 | Create SRA 4/SDS 3.1 identifying impacted reusable service areas | 4 h | 1 d | 2002-09-27 | 2002-09-30 | 37 | 69 | Jill[0.26],Ed[0.4],Tina[0.4]
| 34 | AUTO Specs | 45 h | 128.68 d | 2002-02-18 | 2002-08-09
Eric | 35 | AUTO - review existing territory validation | 15 h | 5 d | 2002-07-26 | 2002-08-02 | 25FS+1 d | 35,37,40FS+10 d | Eric[0.39]
Eric | 36 | AUTO - review existing IRG validation | 15 h | 5 d | 2002-08-02 | 2002-08-09 | 34 |  | Eric[0.39]
Eric | 38 | AUTO - review existing driver's license validation | 15 h | 5 d | 2002-02-18 | 2002-02-22 |  | 69 | Eric[0.39]
Jill | 39 | Determine Validation Components for ECHO & AUI | 48 h | 40.01 d | 2002-08-05 | 2002-09-27 | 34,31 | 32,54 | Eric[0.03],Ty,Mary,Tina,Jill[0.03],Michael[0.03]
| 41 | ECHO Specs | 721 h | 45 d | 2002-07-26 | 2002-09-26
| 42 | ECHO - design territory validation | 237 h | 30 d | 2002-08-16 | 2002-09-26 |  | 57
Tina | 42a | ECHO - New Territory Info Screen | 79 h | 10 d | 2002-08-16 | 2002-08-30 | 34FS+10 d | 41,44SS | Tina[0.13],Lakshmi[0.19],Murthy[0.35],Amarnath[0.35]
Tina | 42b | ECHO - New Territory Info Program | 79 h | 10 d | 2002-08-30 | 2002-09-12 | 40 | 42 | Tina[0.13],Lakshmi[0.19],Murthy[0.35],Amarnath[0.35]
Tina | 42c | ECHO - New Territory Info Interfaces | 79 h | 10 d | 2002-09-12 | 2002-09-26 | 41 |  | Tina[0.13],Lakshmi[0.19],Murthy[0.35],Amarnath[0.35]
| 43 | ECHO - design IRG validation | 237 h | 30 d | 2002-08-16 | 2002-09-26
Tina | 43a | ECHO - New IRG Info Screen | 79 h | 10 d | 2002-08-16 | 2002-08-30 | 40SS | 45,48SS | Tina[0.13],Lakshmi[0.19],Murthy[0.35],Amarnath[0.35]
Tina | 43b | ECHO - New IRG Info Program | 79 h | 10 d | 2002-08-30 | 2002-09-12 | 44 | 46 | Tina[0.13],Lakshmi[0.19],Murthy[0.35],Amarnath[0.35]
Tina | 43c | ECHO - New IRG Info Interfaces | 79 h | 10 d | 2002-09-12 | 2002-09-26 | 45 | 57 | Tina[0.13],Lakshmi[0.19],Murthy[0.35],Amarnath[0.35]
| 45 | ECHO - design driver's license validation | 237 h | 30 d | 2002-08-16 | 2002-09-26
Tina | 45a | ECHO - New Driver's Info Screen | 79 h | 10 d | 2002-08-16 | 2002-08-30 | 44SS | 49 | Tina[0.13],Lakshmi[0.19],Murthy[0.35],Amarnath[0.35]
Tina | 45b | ECHO - New Driver's Info Program | 79 h | 10 d | 2002-08-30 | 2002-09-12 | 48 | 50 | Tina[0.13],Lakshmi[0.19],Murthy[0.35],Amarnath[0.35]
Tina | 45c | ECHO - New Driver's Info Interfaces | 79 h | 10 d | 2002-09-12 | 2002-09-26 | 49 | 57 | Tina[0.13],Lakshmi[0.19],Murthy[0.35],Amarnath[0.35]
Tina | 46 | ECHO - Design Auto App AUI Request Screen | 5 h | 3 d | 2002-07-26 | 2002-07-31 | 25FS+1 d | 52SS
Tina | 47 | ECHO - Design ECHO Residence Address Screen | 5 h | 3 d | 2002-07-26 | 2002-07-31 | 51SS | 69
| 48 | AUI Specs | 75 h | 30 d | 2002-09-27 | 2002-11-07
MiChael | 50 | AUI - design address standardization | 25 h | 10 d | 2002-09-27 | 2002-10-11 | 37 | 55 | Michael[0.32]
MiChael | 52 | AUI - design driver's license validation | 25 h | 10 d | 2002-10-11 | 2002-10-24 | 54 | 56 | Michael[0.32]
MiChael | 54 | AUI - design VIN validation | 25 h | 10 d | 2002-10-24 | 2002-11-07 | 55 |  | Michael[0.32]
Jill | 55 | Logical Interface Designs (one per each reusable service modified or created) - SDS 3.1 | 25 h | 5 d | 2002-09-26 | 2002-10-03 | 46,50,39 | 58 | Jill[0.13],Ed[0.13],Tina[0.13],Analyst
Jill | 56 | Logical Interface Design Walkthrough complete (one for each reusable service modified or created) | 2 h | 1 d | 2002-10-03 | 2002-10-04 | 57 | 59 | Analyst[0.26]
Jill | 57 | Reusable Service Catalog entries are made | 2 h | 1 d | 2002-10-04 | 2002-10-07 | 58 | 69 | Analyst[0.26]
| 58 | Testing Strategy and Test Plans | 213 h | 74 d | 2002-07-24 | 2002-10-31
Steve | 59 | Create Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 50 h | 10 d | 2002-07-24 | 2002-08-06 | 24 | 62 | Steve[0.65]
Steve | 60 | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 13 h | 5 d | 2002-08-06 | 2002-08-13 | 61 | 63 | Steve[0.03],Carol[0.5],Ashok[0.4],Ed,Murthy,Eric[0.4],Jill[0.4],Lakshmi,Michael[0.4],Tina,Amarnath,Ty,Mary
Steve | 61 | Create Defect Tracking Strategy | 40 h | 10 d | 2002-08-13 | 2002-08-27 | 62 | 64 | Steve[0.52]
Steve | 62 | Review Defect Tracking Strategy | 10 h | 5 d | 2002-08-27 | 2002-09-03 | 63 |  | Steve[0.01],Carol[0.5],Ashok[0.4],Ed,Murthy,Eric[0.4],Jill[0.4],Lakshmi,Michael[0.4],Tina,Amarnath,Ty,Mary
Steve | 63 | Create Implementation Test Plan | 40 h | 10 d | 2002-10-11 | 2002-10-24 | 69 | 66 | Steve[0.52]
Steve | 64 | Review Implementation Test Plan | 10 h | 5 d | 2002-10-24 | 2002-10-31 | 65 |  | Steve[0.01],Carol[0.5],Ashok[0.4],Ed,Murthy,Eric[0.4],Jill[0.4],Lakshmi,Michael[0.4],Tina,Amarnath,Ty,Mary
Steve | 65 | Create Acceptance Test Plan | 40 h | 10 d | 2002-10-11 | 2002-10-24 | 69 | 68 | Steve[0.52]
Steve | 66 | Review Acceptance Test Plan | 10 h | 5 d | 2002-10-24 | 2002-10-31 | 67 |  | Steve[0.01],Carol[0.5],Ashok[0.4],Ed,Murthy,Eric[0.4],Jill[0.4],Lakshmi,Michael[0.4],Tina,Amarnath,Ty,Mary
ED | 67 | Update Delivery Specs Doc | 20 h | 4 d | 2002-10-07 | 2002-10-11 | 59,36,52,32 | 65,67,70
ED | 68 | Review SDS Doc | 15 h | 1 d | 2002-10-11 | 2002-10-14 | 69 | 71
Carol | 69 | SDS Doc Authorized | 0 h | 0 d | 2002-10-14 | 2002-10-14 | 70 | 74,75
| 70 | AIP | 209 h | 114 d | 2002-07-30 | 2003-01-01
| 71 | AIP 1 - Assess Existing Technology Architecture | 36 h | 8 d | 2002-10-14 | 2002-10-23
Ty | 72 | Identify Architectural Constraints - AIP 1.1 | 20 h | 5 d | 2002-10-14 | 2002-10-21 | 71 | 76 | Mary[0.52]
Ty | 73 | Inventory Development Tools Standards and Procedures - AIP 1.3 | 4 h | 1 d | 2002-10-14 | 2002-10-15 | 71 | 77 | Mary[0.52]
Ty | 74 | Identify Existing Network Topology - AIP 1.2 | 4 h | 1 d | 2002-10-21 | 2002-10-21 | 74 | 77 | Mary[0.52]
Ty | 75 | Inventory Existing Hardware and System Software - AIP 1.4 | 4 h | 1 d | 2002-10-21 | 2002-10-22 | 75,76 | 78 | Mary[0.52]
Ty | 76 | Assemble Architecture Assessment - AIP 1.5 | 4 h | 1 d | 2002-10-22 | 2002-10-23 | 77 | 80,83 | Mary[0.52]
| 77 | AIP 2 - Design Technology Architecture | 140 h | 40 d | 2002-10-23 | 2002-12-17
Ty | 78 | Design Network - AIP 2.1 | 10 h | 10 d | 2002-10-23 | 2002-11-06 | 78 | 81,82 | Mary[0.13]
Ty | 79 | Define Operating Systems - AIP 2.2 | 10 h | 10 d | 2002-11-06 | 2002-11-20 | 80 |  | Mary[0.13]
Ty | 80 | Define Hardware Configuration - AIP 2.3 | 20 h | 10 d | 2002-11-06 | 2002-11-20 | 80 | 84 | Mary[0.26]
Ty | 81 | Define Data Distribution - AIP 2.4 | 20 h | 10 d | 2002-10-23 | 2002-11-06 | 78 | 84,85 | Mary[0.26]
Ty | 82 | Define Middleware Req. - AIP 2.5 | 20 h | 10 d | 2002-11-20 | 2002-12-03 | 82,83 |  | Mary[0.26]
Ty | 83 | Define Application Service Distribution - AIP 2.6 | 20 h | 10 d | 2002-11-06 | 2002-11-20 | 83 | 86 | Mary[0.26]
Ty | 84 | Define Security Infrastructure - AIP 2.7 | 20 h | 10 d | 2002-11-20 | 2002-12-03 | 85 | 87 | Mary[0.26]
Ty | 85 | Define System Topology - AIP 2.8 | 20 h | 10 d | 2002-12-03 | 2002-12-17 | 86 | 88 | Mary[0.26]
Ty | 86 | MS: Technology Architecture Documentation complete | 0 h | 0 d | 2002-12-17 | 2002-12-17 | 87 | 94 | Mary[0.13]
| 87 | AIP 4 - Validate Technology Architecture | 33 h | 114 d | 2002-07-30 | 2003-01-01
| 88 | Engineer for Performance | 12 h | 6 d | 2002-07-30 | 2002-08-07
Ty | 89 | Submit initial IIA questionnaire | 2 h | 1 d | 2002-07-30 | 2002-07-31 | 26 | 92 | Mary[0.26]
Ty | 90 | Infrastructure Impact Assessment - Level 2 review (if necessary) | 10 h | 5 d | 2002-07-31 | 2002-08-07 | 91 |  | Mary[0.26]
| 91 | SFTA Review | 21 h | 11 d | 2002-12-17 | 2003-01-01
Ty | 92 | Assemble information for SFTA review | 10 h | 5 d | 2002-12-17 | 2002-12-24 | 88 | 95 | Mary[0.26]
Ty | 93 | Submit SFTA Design Review | 1 h | 1 d | 2002-12-24 | 2002-12-25 | 94 | 96 | Mary[0.13]
Ty | 94 | SFTA Review process | 10 h | 5 d | 2002-12-25 | 2003-01-01 | 95 | 97 | Mary[0.26]
Ty | 95 | MS: Authorized SFTA documentation | 0 h | 0 d | 2003-01-01 | 2003-01-01 | 96 |  | Mary[0.26]
◄▬Menu

## TaskSum
| Proj. 1234 | Leadwise Tasks Summary as on |  |  |  |  | 2003-06-10
Sr. No. | Lead Name | Total | Finished | WIP | DueOn Finish | DueOn Start | Total Hours | Compl Hours | Compl %ge
1 | Amar | 69 | 65 | 1 | 0 | 0 | 2021 | 2009.5 | 99.43%
2 | Ashok | 11 | 5 | 6 | 0 | 0 | 4589 | 3710.95 | 80.87%
3 | Bill | 14 | 14 | 0 | 0 | 0 | 316 | 316 | 100%
4 | Brian | 2 | 2 | 0 | 0 | 0 | 60 | 60 | 100%
5 | Carol | 13 | 9 | 0 | 0 | 0 | 198 | 138 | 69.7%
6 | David | 3 | 3 | 0 | 0 | 0 | 35 | 35 | 100%
7 | Durnan | 11 | 8 | 1 | 0 | 1 | 175 | 140 | 80%
8 | ED | 33 | 22 | 1 | 0 | 1 | 486 | 311 | 63.99%
9 | Eric | 3 | 3 | 0 | 0 | 0 | 45 | 45 | 100%
10 | Jill | 4 | 4 | 0 | 0 | 0 | 13 | 13 | 100%
11 | John | 9 | 7 | 0 | 0 | 0 | 149 | 129 | 86.58%
12 | Lynn | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0%
13 | Murthy | 29 | 29 | 0 | 0 | 0 | 961 | 961 | 100%
14 | SteveH | 29 | 22 | 3 | 0 | 2 | 821 | 716 | 87.21%
15 | Sushit | 3 | 3 | 0 | 0 | 0 | 31 | 31 | 100%
16 | Ty | 30 | 28 | 0 | 0 | 0 | 294 | 288 | 97.96%
17 | Vance | 8 | 2 | 0 | 0 | 2 | 90 | 30 | 33.33%
18 | Witter | 22 | 20 | 0 | 0 | 0 | 495 | 475 | 95.96%
| Total | 303 | 250 | 12 | 0 | 6 | 10779 | 9408.45 | 87.28%
◄▬Menu

## ResUses
Proj. 1234 |  | Tasks uses details for Resourcewise EVA as on |  |  |  |  | 2003-06-10
Task Group | Resource Name | Task Name | %Work Completed | BaseLine Work hrs | Current Work hrs | Duration in Days | Start Date | Finish Date | Indent Level No
G0101 | Amar | Team Weekly Meetings | 100% | 51 h | 51 h | 341.99 d | 2002-05-06 08:00 | 2002-05-14 11:00 | 1.1.2.4 | 5
G0102 | Amar | Design of New screen(83) | 100% | 2.11 h | 2.11 h | 3 d | 2002-07-16 14:30 | 2002-07-16 16:36 | 1.2.1.10.9.1 | 6
G0102 | Amar | Analysis of Flow of Data(84) | 100% | 2 h | 2 h | 32 d | 2002-07-19 13:45 | 2002-07-19 15:45 | 1.2.1.10.9.2 | 6
G0102 | Amar | Design of New screen(77) | 100% | 18 h | 18 h | 5 d | 2002-07-16 14:30 | 2002-07-23 13:15 | 1.2.1.10.8.1 | 6
G0102 | Amar | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-24 15:00 | 1.2.1.2 | 6
G0102 | Amar | Understand existing ECHO APPS System | 100% | 120 h | 120 h | 50 d | 2002-06-13 11:30 | 2002-08-20 16:00 | 1.2.1.10.1 | 6
G0102 | Amar | Analysing the requirements(59) | 100% | 2.03 h | 2.03 h | 10 d | 2002-09-03 08:00 | 2002-09-03 10:01 | 1.2.1.10.3.1 | 6
G0102 | Amar | Review Defect Tracking Strategy | 100% | 1.07 h | 1.07 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Amar | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-16 09:50 | 1.2.2.2 | 6
G0102 | Amar | Design the Highlevel Specs-2(61) | 100% | 2 h | 2 h | 9.1 d | 2002-09-16 14:30 | 2002-09-16 16:30 | 1.2.1.10.3.3 | 6
G0102 | Amar | Analysis of Flow of Data(78) | 100% | 23.85 h | 23.85 h | 42 d | 2002-07-23 13:15 | 2002-09-18 09:45 | 1.2.1.10.8.2 | 6
G0102 | Amar | Analysing the requirements(51) | 100% | 25 h | 25 h | 38 d | 2002-08-02 10:30 | 2002-09-24 09:00 | 1.2.1.10.5.1 | 6
G0102 | Amar | Analysing the requirements(73) | 100% | 18 h | 18 h | 15 d | 2002-09-16 08:00 | 2002-09-25 12:00 | 1.2.1.10.6.1 | 6
G0102 | Amar | Design the Highlevel Specs(52) | 100% | 20 h | 20 h | 9 d | 2002-09-20 09:30 | 2002-09-26 08:35 | 1.2.1.10.5.2 | 6
G0102 | Amar | Review of Highlevel Specs(62) | 100% | 1 h | 1 h | 1 d | 2002-09-27 13:00 | 2002-09-27 14:00 | 1.2.1.10.3.4 | 6
G0102 | Amar | Analysing the requirements(69) | 100% | 36 h | 36 h | 46 d | 2002-07-29 16:45 | 2002-09-30 13:15 | 1.2.1.10.2.1 | 6
G0102 | Amar | Analysis of Validations(79) | 100% | 32 h | 32 h | 20 d | 2002-08-06 09:45 | 2002-10-07 08:26 | 1.2.1.10.8.3 | 6
G0102 | Amar | Review of Highlevel Specs(53) | 100% | 2 h | 2 h | 1 d | 2002-10-04 10:20 | 2002-10-07 10:05 | 1.2.1.10.5.3 | 6
G0102 | Amar | Design the Highlevel Specs(70) | 100% | 28 h | 28 h | 10 d | 2002-09-30 13:15 | 2002-10-14 09:45 | 1.2.1.10.2.2 | 6
G0102 | Amar | Design the Highlevel Specs-2(86) | 100% | 4 h | 4 h | 10 d | 2002-10-15 15:45 | 2002-10-16 10:45 | 1.2.1.10.9.4 | 6
G0102 | Amar | Review of Highlevel Specs(71) | 100% | 2 h | 2 h | 4 d | 2002-10-14 09:45 | 2002-10-18 08:45 | 1.2.1.10.2.3 | 6
G0102 | Amar | Design the Highlevel Specs(74) | 100% | 14 h | 14 h | 10 d | 2002-10-04 13:15 | 2002-10-18 09:45 | 1.2.1.10.6.2 | 6
G0102 | Amar | Review of Highlevel Specs(75) | 100% | 2 h | 2 h | 4 d | 2002-10-18 09:45 | 2002-10-24 08:45 | 1.2.1.10.6.3 | 6
G0102 | Amar | Review of Highlevel Specs(87) | 100% | 2 h | 2 h | 1 d | 2002-10-29 13:15 | 2002-10-29 15:15 | 1.2.1.10.9.5 | 6
G0102 | Amar | Design the Highlevel Specs(80) | 100% | 28 h | 28 h | 8 d | 2002-10-24 08:45 | 2002-11-04 15:45 | 1.2.1.10.8.4 | 6
G0102 | Amar | Review of Highlevel Specs(81) | 100% | 12 h | 12 h | 8 d | 2002-10-24 08:45 | 2002-11-04 15:45 | 1.2.1.10.8.5 | 6
G0102 | Amar | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-05 16:30 | 1.2.1.13 | 6
G0102 | Amar | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 1.2.1.5 | 6
G0103 | Amar | NECHO VIN Validation - Analysis (TSD3.2) | 100% | 10 h | 10 h | 2 d | 2002-11-04 08:00 | 2002-11-05 16:30 | 1.3.5.1 | 7
G0103 | Amar | NECHO VIN Validation - Analysis (TSD8.3) | 100% | 15 h | 15 h | 2 d | 2002-11-05 16:30 | 2002-11-07 16:00 | 1.3.5.2 | 7
G0103 | Amar | NECHO VIN Validation - Coding | 100% | 15 h | 15 h | 2 d | 2002-11-07 16:00 | 2002-11-11 15:30 | 1.3.5.3 | 7
G0103 | Amar | NECHO -DLV - Unit Testing | 100% | 20 h | 20 h | 9 d | 2002-11-15 14:30 | 2002-12-02 11:15 | 1.3.4.4 | 7
G0103 | Amar | NECHO VIN Validation - Unit Testing | 100% | 10 h | 10 h | 23 d | 2002-11-11 15:30 | 2002-12-16 08:45 | 1.3.5.4 | 7
G0103 | Amar | Necho Pkg-1 Prep for pilot issuance | 100% | 10 h | 10 h | 2 d | 2003-01-03 14:15 | 2003-01-07 13:45 | 1.3.9.1 | 7
G0105 | Amar | Auto Apps - Main Program - TSD 3.2 | 100% | 40 h | 40 h | 17 d | 2002-11-13 08:00 | 2002-12-09 11:45 | 1.5.2.4.8 | 9
G0105 | Amar | Residence Address screen - TSD 3.2 | 100% | 20 h | 20 h | 27 d | 2002-11-13 15:00 | 2002-12-23 16:15 | 1.5.2.4.9 | 9
G0105 | Amar | Territory Validation (Options screen) - TSD 3.2 | 100% | 30 h | 30 h | 19 d | 2002-11-25 13:00 | 2002-12-23 16:15 | 1.5.2.4.11 | 9
G0105 | Amar | AUI Request Driver Information Screen - TSD 3.2 | 100% | 50 h | 50 h | 20 d | 2002-11-25 13:00 | 2002-12-24 16:00 | 1.5.2.4.10 | 9
G0105 | Amar | Pf Key format /Branching Program (PCS5F) - TSD 3.2 | 100% | 20 h | 20 h | 20 d | 2002-11-25 13:00 | 2002-12-24 16:00 | 1.5.2.4.12 | 9
G0105 | Amar | NECHO - all Remaining Changes - Review TSD 3.2 Docs | 100% | 2 h | 2 h | 18 d | 2002-12-27 15:30 | 2003-01-22 10:00 | 1.5.2.4.13 | 9
G0105 | Amar | Territory Validation (Options screen) - TSD 8.3 | 100% | 30 h | 30 h | 20 d | 2002-12-27 15:30 | 2003-01-24 09:30 | 1.5.2.4.20 | 9
G0105 | Amar | Pf Key format /Branching Program (PCS5F) - TSD 8.3 | 100% | 20 h | 20 h | 20 d | 2002-12-27 15:30 | 2003-01-24 09:30 | 1.5.2.4.21 | 9
G0105 | Amar | Residence Address screen - TSD 8.3 | 100% | 30 h | 30 h | 20 d | 2002-12-27 15:30 | 2003-01-24 09:30 | 1.5.2.4.23 | 9
G0105 | Amar | Perform Integration Testing for NECHO Changes - pkg-2 | 100% | 30 h | 30 h | 61 d | 2003-01-20 10:30 | 2003-01-27 16:59 | 1.5.2.5.1 | 9
G0105 | Amar | AUI Request Driver Information Screen - TSD 8.3 | 100% | 60 h | 60 h | 24 d | 2002-12-27 15:30 | 2003-01-30 08:30 | 1.5.2.4.24 | 9
G0105 | Amar | Auto Apps - Main Program - TSD 8.3 | 100% | 40 h | 40 h | 20 d | 2002-12-27 15:30 | 2003-01-31 08:15 | 1.5.2.4.22 | 9
G0105 | Amar | NECHO - all Remaining Changes - Review TSD 8.3 Docs | 100% | 2 h | 2 h | 4 d | 2003-01-31 08:15 | 2003-02-05 16:15 | 1.5.2.4.25 | 9
G0105 | Amar | Auto Apps - Main Program - Coding | 100% | 60 h | 60 h | 8 d | 2003-02-03 08:00 | 2003-02-12 15:00 | 1.5.2.6.13 | 9
G0105 | Amar | Residence Address screen - Coding | 100% | 40 h | 40 h | 10 d | 2003-02-12 15:00 | 2003-02-26 11:30 | 1.5.2.6.15 | 9
G0105 | Amar | Residence Address screen - UT/IT | 100% | 40 h | 40 h | 10 d | 2003-02-12 15:00 | 2003-02-26 11:30 | 1.5.2.6.16 | 9
G0105 | Amar | AUI Request Driver Information Screen - Coding | 100% | 80 h | 80 h | 15 d | 2003-02-26 11:30 | 2003-03-18 16:45 | 1.5.2.6.17 | 9
G0105 | Amar | Territory Validation (Options screen) - Coding | 100% | 60 h | 60 h | 8 d | 2003-03-14 08:00 | 2003-03-25 15:00 | 1.5.2.6.19 | 9
G0105 | Amar | Pf Key format /Branching Program (PCS5F) - Coding | 100% | 20 h | 20 h | 11 d | 2003-03-14 08:00 | 2003-03-28 14:15 | 1.5.2.6.21 | 9
G0105 | Amar | Territory Validation (Options screen) - UT/IT | 100% | 30 h | 30 h | 15 d | 2003-03-14 08:00 | 2003-04-03 13:15 | 1.5.2.6.20 | 9
G0105 | Amar | Driver Info warning Screen - Analysis TSD 3.2, TSD 8.3 | 100% | 0 h | 24 h | 3 d | 2003-04-01 08:00 | 2003-04-03 16:15 | 1.5.2.4.26 | 9
G0105 | Amar | Driver Info warning Screen -Coding, UT/IT | 100% | 0 h | 32 h | 6 d | 2003-04-03 16:15 | 2003-04-11 14:45 | 1.5.2.6.23 | 9
G0105 | Amar | Necho RSC Entry for Terr valid & Address Std | 25% | 2 h | 2 h | 146 d | 2002-11-25 13:00 | 2003-06-13 16:30 | 1.5.2.4.1 | 9
G0105 | Amar | Necho Pkg-3 Prep for pilot issuance | 0% | 10 h | 10 h | 8 d | 2003-07-10 08:15 | 2003-07-21 15:15 | 1.5.6.1 | 9
G0106 | Amar | Transition to Service | 0% | 6.53 h | 6.53 h | 20 d | 2003-08-25 08:00 | 2003-09-19 11:00 | 1.6.4 | 10
G0101 | Ashok | Prepare & Review Project Charter | 100% | 8.14 h | 8.14 h | 35 d | 2002-05-21 08:00 | 2002-07-05 16:15 | 1.1.3.1 | 5
G0101 | Ashok | Facilitation management Processes | 100% | 2 h | 2 h | 55 d | 2002-07-05 16:15 | 2002-07-19 13:10 | 1.1.3.4 | 5
G0101 | Ashok | Project Schedule Development -1 | 100% | 48 h | 48 h | 60 d | 2002-05-28 08:00 | 2002-08-16 09:00 | 1.1.3.8 | 5
G0101 | Ashok | Prepare & review Project Plan | 100% | 6 h | 6 h | 64 d | 2002-07-05 16:15 | 2002-10-01 16:15 | 1.1.3.5 | 5
G0101 | Ashok | Project Schedule Development -2 | 100% | 48 h | 48 h | 43 d | 2002-09-18 16:15 | 2002-11-15 13:30 | 1.1.3.10 | 5
G0101 | Ashok | Team Weekly Meetings | 80% | 51 h | 75.76 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0101 | Ashok | Project Schedule / PlanView Maintenance, and Status Reporting | 78% | 417 h | 450 h | 267 d | 2002-08-15 08:00 | 2003-08-15 14:15 | 1.1.2.5 | 5
G0102 | Ashok | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-25 09:00 | 1.2.1.2 | 6
G0102 | Ashok | Review Defect Tracking Strategy | 100% | 0.43 h | 0.43 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Ashok | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-16 09:50 | 1.2.2.2 | 6
G0102 | Ashok | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0106 | Ashok | Project Closure Tasks | 0% | 10 h | 10 h | 5 d | 2003-09-19 11:00 | 2003-09-24 12:00 | 1.6.5 | 10
G0101 | Bill | Team Weekly Meetings | 100% | 0 h | 20 h | 341.99 d | 2002-09-16 15:36 | 2002-09-19 10:36 | 1.1.2.4 | 5
G0104 | Bill | DLV - Host - Physical Design Interface | 100% | 20 h | 20 h | 4 d | 2002-11-18 14:15 | 2002-11-22 13:15 | 1.4.4.2.3 | 8
G0104 | Bill | DLV - Host - Physical Design Interface Walkthrough | 100% | 3 h | 3 h | 2 d | 2002-11-26 08:00 | 2002-11-26 11:00 | 1.4.4.2.4 | 8
G0104 | Bill | DLV - Host - Develop Design Specs | 100% | 30 h | 30 h | 25 d | 2002-11-04 16:45 | 2002-12-11 09:30 | 1.4.4.2.2 | 8
G0104 | Bill | DLV - Host - Design Specs Walkthrough | 100% | 3 h | 3 h | 1 d | 2002-12-12 08:00 | 2002-12-12 16:45 | 1.4.4.2.5 | 8
G0104 | Bill | DLV - Host - Code/Gen IMS transaction | 100% | 50 h | 50 h | 6 d | 2002-12-12 16:45 | 2002-12-20 15:15 | 1.4.4.2.6 | 8
G0104 | Bill | DLV - Host - Code Wrapper | 100% | 50 h | 50 h | 6 d | 2002-12-12 16:45 | 2002-12-20 15:15 | 1.4.4.2.7 | 8
G0104 | Bill | DLV - Host - Code Walkthrough | 100% | 3 h | 3 h | 3 d | 2002-12-17 16:00 | 2002-12-20 15:15 | 1.4.4.2.8 | 8
G0104 | Bill | DLV - Host - Unit test IMS transaction | 100% | 50 h | 50 h | 16 d | 2002-12-20 15:15 | 2003-01-14 10:15 | 1.4.4.2.9 | 8
G0104 | Bill | DLV - Host - Unit test Wrapper | 100% | 50 h | 50 h | 16 d | 2002-12-20 15:15 | 2003-01-14 10:15 | 1.4.4.2.10 | 8
G0104 | Bill | DLV - Host - Review Test Results | 100% | 3 h | 3 h | 3 d | 2003-01-14 10:15 | 2003-01-15 14:52 | 1.4.4.2.11 | 8
G0104 | Bill | DLV - Host - AUI/DLV Security -NT | 100% | 20 h | 20 h | 11 d | 2002-12-31 13:45 | 2003-01-17 10:45 | 1.4.4.2.13 | 8
G0104 | Bill | DLV - Mid Tier - RSC Entry | 100% | 2 h | 2 h | 36 d | 2002-11-29 08:00 | 2003-01-17 16:00 | 1.4.4.1.1 | 8
G0104 | Bill | DLV - Host RSC Entry | 100% | 4 h | 4 h | 11 d | 2003-01-06 08:00 | 2003-01-20 14:15 | 1.4.4.2.1 | 8
G0104 | Bill | AUI-DLV Mid Tier / Host Int Test | 100% | 25 h | 25 h | 14 d | 2003-01-17 10:45 | 2003-02-05 16:15 | 1.4.4.5.2 | 8
G0104 | Bill | DLV - Host - Mid Tier /Host Integration Test Reveiew | 100% | 2 h | 2 h | 2 d | 2003-02-05 16:15 | 2003-02-07 15:45 | 1.4.4.2.14 | 8
G0104 | Bill | AUI-DLV Web / Mid Tier / Host System Testing (Initial) | 100% | 20 h | 20 h | 15 d | 2003-02-05 16:15 | 2003-02-10 11:15 | 1.4.4.5.3 | 8
G0104 | Bill | Implementation testing execution pkg-2 | 39% | 0 h | 5 h | 31 d | 2003-05-02 08:00 | 2003-05-02 14:00 | 1.4.4.6.3 | 8
G0106 | Bill | Transition to Service | 0% | 6.53 h | 6.53 h | 20 d | 2003-08-25 08:00 | 2003-09-19 11:00 | 1.6.4 | 10
G0105 | Brian | Host Addr Std/ terr-analysis | 100% | 20 h | 20 h | 30 d | 2002-11-12 16:45 | 2002-12-27 08:15 | 1.5.2.3.1 | 9
G0105 | Brian | Perform Integration Testing for NECHO Changes - pkg-2 | 100% | 20 h | 20 h | 61 d | 2003-01-20 10:30 | 2003-01-24 14:59 | 1.5.2.5.1 | 9
G0105 | Brian | Host Addr Std/ terr-Coding | 100% | 40 h | 40 h | 104.13 d | 2002-12-27 08:15 | 2003-05-16 16:15 | 1.5.2.3.2 | 9
G0101 | Carol | Prepare & Review Project Charter | 100% | 9.98 h | 9.98 h | 35 d | 2002-05-21 08:00 | 2002-05-30 15:21 | 1.1.3.1 | 5
G0101 | Carol | Project Schedule Development -1 | 100% | 20 h | 20 h | 60 d | 2002-05-28 08:00 | 2002-06-18 14:00 | 1.1.3.8 | 5
G0101 | Carol | Prepare & review Project Plan | 100% | 15 h | 15 h | 64 d | 2002-07-05 16:15 | 2002-07-23 14:00 | 1.1.3.5 | 5
G0101 | Carol | Facilitation management Processes | 100% | 14.02 h | 14.02 h | 55 d | 2002-07-12 13:15 | 2002-09-19 09:30 | 1.1.3.4 | 5
G0101 | Carol | Project Schedule Development -2 | 100% | 20 h | 20 h | 43 d | 2002-09-18 16:15 | 2002-10-10 13:15 | 1.1.3.10 | 5
G0101 | Carol | Create Initial SPIP Participant Charts | 100% | 20 h | 20 h | 86 d | 2002-09-06 08:00 | 2003-01-06 10:30 | 1.1.4.1 | 5
G0101 | Carol | Project Management Activities | 84% | 699 h | 750 h | 342 d | 2002-05-06 08:00 | 2003-08-15 10:33 | 1.1.2.1 | 5
G0101 | Carol | Team Weekly Meetings | 80% | 60 h | 88.98 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0101 | Carol | Authorize final SPIP for transition | 0% | 20 h | 20 h | 10 d | 2003-09-11 13:30 | 2003-09-25 10:00 | 1.1.4.2 | 5
G0102 | Carol | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-24 17:00 | 1.2.1.2 | 6
G0102 | Carol | Review Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-26 11:30 | 2002-07-26 16:30 | 1.2.1.3 | 6
G0102 | Carol | Review Defect Tracking Strategy | 100% | 0.53 h | 0.53 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Carol | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-16 09:50 | 1.2.2.2 | 6
G0102 | Carol | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-05 16:32 | 1.2.1.13 | 6
G0106 | Carol | Project Closure Tasks | 0% | 20 h | 20 h | 5 d | 2003-09-19 11:00 | 2003-09-26 09:45 | 1.6.5 | 10
G0101 | Charles | IIA Team (Performance Impact Accessment) | 52% | 50 h | 50 h | 230 d | 2002-10-07 08:00 | 2002-10-15 10:00 | 1.1.5.1 | 5
G0101 | Daniel | IIA Team (Performance Impact Accessment) | 100% | 25 h | 25 h | 230 d | 2002-10-07 08:00 | 2002-10-10 09:00 | 1.1.5.1 | 5
G0101 | Dave | IIA Team (Performance Impact Accessment) | 52% | 50 h | 50 h | 230 d | 2002-10-07 08:00 | 2002-10-15 10:00 | 1.1.5.1 | 5
G0104 | David | DLV - Host - Security Analyst Setup | 100% | 10 h | 10 h | 5 d | 2003-01-10 13:00 | 2003-01-17 10:45 | 1.4.4.2.12 | 8
G0104 | David | Build Test Ids/Rules | 100% | 10 h | 10 h | 26 d | 2002-12-19 14:45 | 2003-01-24 16:15 | 1.4.2.2 | 8
G0104 | David | SDS 5.2 Specify Security and Control Requirements | 100% | 15 h | 15 h | 36 d | 2003-01-13 08:00 | 2003-02-28 16:00 | 1.4.2.1 | 8
G0106 | David | Transition to Service | 0% | 1.26 h | 1.26 h | 20 d | 2003-08-25 08:00 | 2003-08-25 09:15 | 1.6.4 | 10
G0105 | Durnan | MQ Q/A High Level Review (req’d objects id’d) | 100% | 20 h | 20 h | 17 d | 2002-10-28 08:00 | 2002-11-19 11:45 | 1.5.2.2.1.1 | 9
G0105 | Durnan | MQ design Infra Diagram (message flow) | 100% | 30 h | 30 h | 14 d | 2002-11-04 15:30 | 2002-11-22 11:00 | 1.5.2.2.1.2 | 9
G0105 | Durnan | MQ Q/A Detail Level Review (design Walkthrough) | 100% | 5 h | 5 h | 5 d | 2002-11-15 13:15 | 2002-11-22 11:00 | 1.5.2.2.1.3 | 9
G0105 | Durnan | MQ Objects on Dev Host (coding) | 100% | 10 h | 10 h | 7 d | 2002-12-30 14:00 | 2003-01-08 11:15 | 1.5.2.2.2.1 | 9
G0105 | Durnan | MQ Create Host Test Cases | 100% | 10 h | 10 h | 5 d | 2003-01-08 11:15 | 2003-01-15 10:00 | 1.5.2.2.2.2 | 9
G0105 | Durnan | MQ Execute & Doc Host Test Cases | 100% | 10 h | 10 h | 5 d | 2003-01-15 10:00 | 2003-01-22 08:45 | 1.5.2.2.2.3 | 9
G0105 | Durnan | Perform Integration Testing for NECHO Changes - pkg-2 | 100% | 20 h | 20 h | 61 d | 2003-01-20 10:30 | 2003-01-24 14:59 | 1.5.2.5.1 | 9
G0105 | Durnan | MQ Q/A App Code walkthrough | 100% | 20 h | 20 h | 9 d | 2003-03-26 08:00 | 2003-04-07 14:45 | 1.5.2.2.3.2 | 9
G0105 | Durnan | MQ Support NECHO Unit Testing | 100% | 20 h | 20 h | 35 d | 2003-02-24 10:45 | 2003-04-11 10:00 | 1.5.2.2.3.1 | 9
G0105 | Durnan | MQ Integration Testing | 75% | 20 h | 20 h | 49 d | 2003-04-09 08:00 | 2003-06-13 11:45 | 1.5.2.2.3.3 | 9
G0105 | Durnan | MQ Q/A Transition to MQService Agreement | 0% | 10 h | 10 h | 5 d | 2003-06-09 08:00 | 2003-06-13 15:45 | 1.5.2.4.27 | 9
G0105 | Durnan | MQ Pilot/Issuance | 0% | 20 h | 20 h | 10 d | 2003-07-18 15:30 | 2003-08-01 12:00 | 1.5.6.4 | 9
G0105 | Durnan | Pkg-3-Post implemetation questions | 0% | 10 h | 10 h | 20 d | 2003-08-25 08:00 | 2003-08-26 10:00 | 1.5.6.5 | 9
G0101 | Ed | Prepare & Review Project Charter | 100% | 5.99 h | 5.99 h | 35 d | 2002-05-21 08:00 | 2002-05-31 16:49 | 1.1.3.1 | 5
G0101 | Ed | Project Schedule Development -1 | 100% | 6 h | 6 h | 60 d | 2002-06-10 08:00 | 2002-06-21 17:00 | 1.1.3.8 | 5
G0101 | Ed | Facilitation management Processes | 100% | 2 h | 2 h | 55 d | 2002-07-12 13:15 | 2002-07-19 13:12 | 1.1.3.4 | 5
G0101 | Ed | Prepare & review Project Plan | 100% | 2 h | 2 h | 64 d | 2002-07-12 13:15 | 2002-07-19 13:15 | 1.1.3.5 | 5
G0101 | Ed | Project Schedule Development -2 | 100% | 6 h | 6 h | 43 d | 2002-09-18 16:15 | 2002-10-02 10:15 | 1.1.3.10 | 5
G0101 | Ed | Team Weekly Meetings | 80% | 50 h | 74.28 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0102 | Ed | Determine Business Requirements | 100% | 5 h | 5 h | 24 d | 2002-06-13 11:30 | 2002-07-16 14:30 | 1.2.1.1 | 6
G0102 | Ed | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-25 11:45 | 1.2.1.2 | 6
G0102 | Ed | Review Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-26 11:30 | 2002-07-26 14:30 | 1.2.1.3 | 6
G0102 | Ed | Create SRA 4/SDS 3.1 identifying impacted reusable service areas | 100% | 1 h | 1 h | 18 d | 2002-08-30 14:00 | 2002-08-30 16:30 | 1.2.1.7.4 | 6
G0102 | Ed | Review Defect Tracking Strategy | 100% | 1.07 h | 1.07 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Ed | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-16 09:50 | 1.2.2.2 | 6
G0102 | Ed | Update Delivery Specs Doc | 100% | 10 h | 10 h | 1 d | 2002-11-04 15:45 | 2002-11-05 15:30 | 1.2.1.12 | 6
G0102 | Ed | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0102 | Ed | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 1.2.1.5 | 6
G0103 | Ed | Pkg-1 Draft Communication | 100% | 10 h | 10 h | 2 d | 2002-10-25 08:00 | 2002-10-28 16:30 | 1.3.8.1 | 7
G0103 | Ed | Pkg-1 Communication Review by Proj Team | 100% | 5 h | 5 h | 14 d | 2002-10-29 08:00 | 2002-11-15 13:30 | 1.3.8.2 | 7
G0103 | Ed | Pkg-1 UPD Walkthrough with SPIP group | 100% | 5 h | 5 h | 8 d | 2002-11-18 08:00 | 2002-11-29 15:00 | 1.3.8.3 | 7
G0103 | Ed | Create Acceptance Test Cases - Pkg-1 | 100% | 1.14 h | 1.14 h | 2 d | 2002-12-06 16:30 | 2002-12-10 16:00 | 1.3.7.3 | 7
G0103 | Ed | AUI Acceptance Testing - Pkg-1 | 100% | 8 h | 8 h | 4 d | 2002-12-17 16:15 | 2002-12-23 15:15 | 1.3.7.4 | 7
G0103 | Ed | Pkg-1 Publish Communication | 100% | 5 h | 5 h | 5 d | 2002-12-27 08:30 | 2003-01-02 16:15 | 1.3.8.8 | 7
G0103 | Ed | NECHO Acceptance Testing - Pkg-1 | 100% | 8.55 h | 8.55 h | 21 d | 2002-12-09 10:00 | 2003-01-07 13:45 | 1.3.7.5 | 7
G0103 | Ed | Pkg 1-Post implementation questions | 100% | 25 h | 15 h | 11 d | 2003-01-31 08:00 | 2003-02-14 14:15 | 1.3.9.4 | 7
G0104 | Ed | AUI-DLV Acceptance Test Cases developed | 100% | 20 h | 20 h | 4 d | 2003-02-11 08:15 | 2003-02-14 16:15 | 1.4.4.5.4 | 8
G0104 | Ed | Pkg-2 Draft Communication | 100% | 10 h | 10 h | 1 d | 2003-02-17 08:00 | 2003-02-17 16:45 | 1.4.4.8.1 | 8
G0104 | Ed | Pkg-2 Communication Review by Proj Team | 100% | 5 h | 5 h | 5 d | 2003-02-17 16:45 | 2003-02-24 15:30 | 1.4.4.8.2 | 8
G0104 | Ed | Pkg-2 UPD Walkthrough with SPIP group | 100% | 5 h | 5 h | 4 d | 2003-02-24 15:30 | 2003-02-28 14:30 | 1.4.4.8.3 | 8
G0104 | Ed | AUI-DLV Acceptance Testing | 100% | 30 h | 30 h | 28.19 d | 2003-02-26 11:30 | 2003-04-04 15:00 | 1.4.4.5.6 | 8
G0104 | Ed | Pkg-2 Publish Communication | 0% | 5 h | 5 h | 1 d | 2003-06-23 08:00 | 2003-06-23 16:45 | 1.4.4.8.6 | 8
G0104 | Ed | Pkg 2-Post implemetation questions | 0% | 25 h | 25 h | 20 d | 2003-07-04 09:00 | 2003-07-31 12:00 | 1.4.4.9.5 | 8
G0105 | Ed | SAT -Perform System/Acceptance Testing pkg-3 | 100% | 50 h | 50 h | 36.68 d | 2003-04-14 10:59 | 2003-06-02 16:15 | 1.5.4.3 | 9
G0105 | Ed | SAT - Create FIT Test Cases | 0% | 40 h | 40 h | 10 d | 2003-06-02 16:15 | 2003-06-16 13:45 | 1.5.4.7.2 | 9
G0105 | Ed | SAT - Perform FIT Testing - Pkg-3 | 0% | 50 h | 50 h | 18 d | 2003-06-16 13:45 | 2003-07-10 08:15 | 1.5.4.7.3 | 9
G0105 | Ed | Pkg-3 Draft Communication | 50% | 10 h | 10 h | 46 d | 2003-05-12 08:00 | 2003-07-11 13:30 | 1.5.5.1 | 9
G0105 | Ed | Pkg-3 Communication Review by Proj Team | 0% | 5 h | 5 h | 5 d | 2003-07-11 13:30 | 2003-07-18 11:15 | 1.5.5.2 | 9
G0105 | Ed | Pkg-3 UPD Walkthrough with SPIP group | 0% | 5 h | 5 h | 5 d | 2003-07-18 11:15 | 2003-07-25 10:00 | 1.5.5.3 | 9
G0105 | Ed | Pkg-3 Publish Communication | 0% | 5 h | 5 h | 5 d | 2003-08-11 10:30 | 2003-08-18 09:15 | 1.5.5.8 | 9
G0105 | Ed | Pkg-3-Post implemetation questions | 0% | 25 h | 25 h | 20 d | 2003-08-25 08:00 | 2003-09-19 11:00 | 1.5.6.5 | 9
G0101 | Eric | Prepare & Review Project Charter | 100% | 5.99 h | 5.99 h | 35 d | 2002-05-21 08:00 | 2002-05-31 16:49 | 1.1.3.1 | 5
G0101 | Eric | Project Schedule Development -1 | 100% | 6 h | 6 h | 60 d | 2002-06-10 08:00 | 2002-06-21 17:00 | 1.1.3.8 | 5
G0101 | Eric | Facilitation management Processes | 100% | 2 h | 2 h | 55 d | 2002-07-12 13:15 | 2002-07-19 13:12 | 1.1.3.4 | 5
G0101 | Eric | Prepare & review Project Plan | 100% | 2 h | 2 h | 64 d | 2002-07-12 13:15 | 2002-07-19 13:15 | 1.1.3.5 | 5
G0101 | Eric | Project Schedule Development -2 | 100% | 6 h | 6 h | 43 d | 2002-09-18 16:15 | 2002-10-02 10:15 | 1.1.3.10 | 5
G0101 | Eric | Team Weekly Meetings | 80% | 51 h | 75.76 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0102 | Eric | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-25 09:00 | 1.2.1.2 | 6
G0102 | Eric | Review Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-26 11:30 | 2002-07-29 11:15 | 1.2.1.3 | 6
G0102 | Eric | AUTO - review existing territory validation | 100% | 15 h | 15 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 1.2.1.8.1 | 6
G0102 | Eric | AUTO - review existing IRG validation | 100% | 15 h | 15 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 1.2.1.8.2 | 6
G0102 | Eric | AUTO - review existing driver's license validation | 100% | 15 h | 15 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 1.2.1.8.3 | 6
G0102 | Eric | Review Defect Tracking Strategy | 100% | 0.43 h | 0.43 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Eric | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-16 09:50 | 1.2.2.2 | 6
G0102 | Eric | Determine Validation Components for ECHO & AUI | 100% | 8 h | 8 h | 18 d | 2002-08-30 14:00 | 2002-09-25 08:30 | 1.2.1.9 | 6
G0102 | Eric | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0102 | Eric | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 1.2.1.5 | 6
G0104 | EricH | DLV - Mid Tier - Logical Design Interface Walkthrough | 100% | 3 h | 3 h | 4 d | 2002-11-19 08:00 | 2002-11-19 11:00 | 1.4.4.1.3 | 8
G0104 | EricH | DLV - Host - Physical Design Interface Walkthrough | 100% | 3 h | 3 h | 2 d | 2002-11-26 08:00 | 2002-11-29 16:30 | 1.4.4.2.4 | 8
G0104 | EricH | DLV - Host - Design Specs Walkthrough | 100% | 3 h | 3 h | 1 d | 2002-12-12 08:00 | 2002-12-12 16:45 | 1.4.4.2.5 | 8
G0104 | EricH | DLV - Host - Code Walkthrough | 100% | 3 h | 3 h | 3 d | 2002-12-17 16:00 | 2002-12-18 10:00 | 1.4.4.2.8 | 8
G0104 | EricH | DLV - Host - Review Test Results | 100% | 3 h | 3 h | 3 d | 2003-01-14 10:15 | 2003-01-17 09:30 | 1.4.4.2.11 | 8
G0104 | EricH | DLV - Host - Mid Tier /Host Integration Test Reveiew | 100% | 2 h | 2 h | 2 d | 2003-02-05 16:15 | 2003-02-06 09:15 | 1.4.4.2.14 | 8
G0101 | Gilbert | IIA Team (Performance Impact Accessment) | 100% | 25 h | 25 h | 230 d | 2002-10-07 08:00 | 2002-10-10 09:00 | 1.1.5.1 | 5
G0101 | Harry | IIA Team (Performance Impact Accessment) | 2% | 200 h | 200 h | 230 d | 2002-10-07 08:00 | 2003-08-18 15:30 | 1.1.5.1 | 5
G0104 | Jeff | DLV - Mid Tier - Logical Design Interface Walkthrough | 100% | 3 h | 3 h | 4 d | 2002-11-19 08:00 | 2002-11-19 11:00 | 1.4.4.1.3 | 8
G0104 | Jeff | DLV - Mid Tier - Code Walk Through | 100% | 3 h | 3 h | 14 d | 2002-11-29 08:00 | 2002-12-20 10:28 | 1.4.4.1.5 | 8
G0104 | Jeff | DLV - Mid Tier - Unit Testing | 100% | 3 h | 3 h | 16 d | 2002-11-29 08:00 | 2002-12-20 16:15 | 1.4.4.1.7 | 8
G0104 | Jeff | DLV - Host - Mid Tier /Host Integration Test Reveiew | 100% | 2 h | 2 h | 2 d | 2003-02-05 16:15 | 2003-02-06 09:15 | 1.4.4.2.14 | 8
G0101 | Jill | Prepare & Review Project Charter | 100% | 5.99 h | 5.99 h | 35 d | 2002-05-21 08:00 | 2002-06-07 16:43 | 1.1.3.1 | 5
G0101 | Jill | Project Schedule Development -1 | 100% | 6 h | 6 h | 60 d | 2002-06-03 08:00 | 2002-06-21 17:00 | 1.1.3.8 | 5
G0101 | Jill | Facilitation management Processes | 100% | 2 h | 2 h | 55 d | 2002-07-12 13:15 | 2002-07-19 13:12 | 1.1.3.4 | 5
G0101 | Jill | Prepare & review Project Plan | 100% | 2 h | 2 h | 64 d | 2002-07-12 13:15 | 2002-07-19 13:15 | 1.1.3.5 | 5
G0101 | Jill | Project Schedule Development -2 | 100% | 6 h | 6 h | 43 d | 2002-09-18 16:15 | 2002-10-09 16:15 | 1.1.3.10 | 5
G0101 | Jill | Team Weekly Meetings | 80% | 51 h | 75.76 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0102 | Jill | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-25 09:00 | 1.2.1.2 | 6
G0102 | Jill | DOMAIN - review existing territory validation | 100% | 3 h | 3 h | 24 d | 2002-07-30 11:00 | 2002-08-30 14:00 | 1.2.1.7.1 | 6
G0102 | Jill | DOMAIN - review existing IRG validation | 100% | 3 h | 3 h | 23 d | 2002-07-31 10:45 | 2002-08-30 14:00 | 1.2.1.7.2 | 6
G0102 | Jill | DOMAIN - review existing driver's license validation | 100% | 3 h | 3 h | 23 d | 2002-07-31 10:45 | 2002-08-30 14:00 | 1.2.1.7.3 | 6
G0102 | Jill | Review Defect Tracking Strategy | 100% | 0.43 h | 0.43 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Jill | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-16 09:50 | 1.2.2.2 | 6
G0102 | Jill | Create SRA 4/SDS 3.1 identifying impacted reusable service areas | 100% | 2 h | 2 h | 18 d | 2002-08-30 14:00 | 2002-09-25 08:30 | 1.2.1.7.4 | 6
G0102 | Jill | Determine Validation Components for ECHO & AUI | 100% | 8 h | 8 h | 18 d | 2002-08-30 14:00 | 2002-09-25 08:30 | 1.2.1.9 | 6
G0102 | Jill | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0102 | Jill | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 1.2.1.5 | 6
G0101 | John | Team Weekly Meetings | 100% | 40 h | 20 h | 341.99 d | 2002-05-06 08:00 | 2002-05-08 12:00 | 1.1.2.4 | 5
G0102 | John | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-05 16:30 | 1.2.1.13 | 6
G0102 | John | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 1.2.1.5 | 6
G0104 | John | DLV - Mid Tier - Logical Design Interface | 100% | 24 h | 24 h | 5 d | 2002-11-04 15:30 | 2002-11-18 14:15 | 1.4.4.1.2 | 8
G0104 | John | DLV - Mid Tier - Logical Design Interface Walkthrough | 100% | 3 h | 3 h | 4 d | 2002-11-19 08:00 | 2002-11-22 16:00 | 1.4.4.1.3 | 8
G0104 | John | DLV - Mid Tier - RSC Entry | 100% | 2 h | 2 h | 36 d | 2002-11-29 08:00 | 2002-11-29 10:00 | 1.4.4.1.1 | 8
G0104 | John | DLV - Mid Tier - Coding | 100% | 60 h | 60 h | 18 d | 2002-11-22 16:00 | 2002-12-20 10:30 | 1.4.4.1.4 | 8
G0104 | John | DLV - Mid Tier - Code Walk Through | 100% | 3 h | 3 h | 14 d | 2002-11-29 08:00 | 2002-12-20 10:30 | 1.4.4.1.5 | 8
G0104 | John | DLV - Mid Tier - Unit Test Review | 100% | 20 h | 20 h | 16 d | 2002-11-29 08:00 | 2002-12-20 16:15 | 1.4.4.1.6 | 8
G0104 | John | DLV - Mid Tier - Unit Testing | 100% | 3 h | 3 h | 16 d | 2002-11-29 08:00 | 2002-12-20 16:15 | 1.4.4.1.7 | 8
G0104 | John | AUI-DLV Mid Tier / Host Int Test | 100% | 25 h | 25 h | 14 d | 2003-01-17 10:45 | 2003-01-30 08:01 | 1.4.4.5.2 | 8
G0104 | John | DLV - Host - Mid Tier /Host Integration Test Reveiew | 100% | 2 h | 2 h | 2 d | 2003-02-05 16:15 | 2003-02-06 09:15 | 1.4.4.2.14 | 8
G0104 | John | AUI-DLV Web / Mid Tier / Host System Testing (Initial) | 100% | 20 h | 20 h | 15 d | 2003-02-05 16:15 | 2003-02-10 11:15 | 1.4.4.5.3 | 8
G0104 | John | Implementation testing execution pkg-2 | 39% | 0 h | 5 h | 31 d | 2003-05-02 08:00 | 2003-05-02 14:00 | 1.4.4.6.3 | 8
G0104 | John | Mid Tier-Host Prep cowide issuance | 0% | 20 h | 20 h | 10 d | 2003-06-13 13:45 | 2003-06-27 10:15 | 1.4.4.9.1 | 8
G0106 | John | Transition to Service | 0% | 6.53 h | 6.53 h | 20 d | 2003-08-25 08:00 | 2003-09-19 11:00 | 1.6.4 | 10
G0101 | Lakshmi | Prepare & Review Project Charter | 100% | 5.99 h | 5.99 h | 35 d | 2002-05-21 08:00 | 2002-06-07 16:43 | 1.1.3.1 | 5
G0101 | Lakshmi | Project Schedule Development -1 | 100% | 6 h | 6 h | 60 d | 2002-06-03 08:00 | 2002-06-21 17:00 | 1.1.3.8 | 5
G0101 | Lakshmi | Facilitation management Processes | 100% | 2 h | 2 h | 55 d | 2002-07-12 13:15 | 2002-07-19 13:12 | 1.1.3.4 | 5
G0101 | Lakshmi | Prepare & review Project Plan | 100% | 2 h | 2 h | 64 d | 2002-07-12 13:15 | 2002-07-19 13:15 | 1.1.3.5 | 5
G0101 | Lakshmi | Project Schedule Development -2 | 100% | 6 h | 6 h | 43 d | 2002-09-18 16:15 | 2002-10-09 16:15 | 1.1.3.10 | 5
G0101 | Lakshmi | Team Weekly Meetings | 79% | 51 h | 77.91 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0102 | Lakshmi | Design of New screen(77) | 100% | 2 h | 2 h | 5 d | 2002-07-16 14:30 | 2002-07-16 16:30 | 1.2.1.10.8.1 | 6
G0102 | Lakshmi | Design of New screen(83) | 100% | 2.11 h | 2.11 h | 3 d | 2002-07-16 14:30 | 2002-07-16 16:36 | 1.2.1.10.9.1 | 6
G0102 | Lakshmi | Analysis of Flow of Data(84) | 100% | 4 h | 4 h | 32 d | 2002-07-19 13:45 | 2002-07-22 08:45 | 1.2.1.10.9.2 | 6
G0102 | Lakshmi | Analysis of Flow of Data(78) | 100% | 1.15 h | 1.15 h | 42 d | 2002-07-23 13:15 | 2002-07-23 14:24 | 1.2.1.10.8.2 | 6
G0102 | Lakshmi | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-24 15:00 | 1.2.1.2 | 6
G0102 | Lakshmi | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 0.85 h | 0.85 h | 31 d | 2002-08-26 08:00 | 2002-08-27 14:22 | 1.2.2.2 | 6
G0102 | Lakshmi | Review Defect Tracking Strategy | 100% | 1.07 h | 1.07 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Lakshmi | Design the Highlevel Specs-2(61) | 100% | 5 h | 5 h | 9.1 d | 2002-09-16 14:30 | 2002-09-17 10:30 | 1.2.1.10.3.3 | 6
G0102 | Lakshmi | Design the Highlevel Specs(52) | 100% | 13 h | 13 h | 9 d | 2002-09-20 09:30 | 2002-09-25 09:35 | 1.2.1.10.5.2 | 6
G0102 | Lakshmi | Review of Highlevel Specs(62) | 100% | 2 h | 2 h | 1 d | 2002-09-27 13:00 | 2002-09-27 15:00 | 1.2.1.10.3.4 | 6
G0102 | Lakshmi | Design the Highlevel Specs-2(66) | 100% | 14 h | 14 h | 10 d | 2002-09-27 11:56 | 2002-10-01 09:56 | 1.2.1.10.4.3 | 6
G0102 | Lakshmi | Design the Highlevel Specs(48) | 100% | 8 h | 8 h | 10 d | 2002-09-30 13:15 | 2002-10-01 13:15 | 1.2.1.10.7.2 | 6
G0102 | Lakshmi | Design the Highlevel Specs(70) | 100% | 12 h | 12 h | 10 d | 2002-09-30 13:15 | 2002-10-02 08:15 | 1.2.1.10.2.2 | 6
G0102 | Lakshmi | Analysing the requirements(73) | 100% | 2 h | 2 h | 15 d | 2002-09-16 08:00 | 2002-10-04 13:15 | 1.2.1.10.6.1 | 6
G0102 | Lakshmi | Design the Highlevel Specs(74) | 100% | 3 h | 3 h | 10 d | 2002-10-04 13:15 | 2002-10-04 16:15 | 1.2.1.10.6.2 | 6
G0102 | Lakshmi | Review of Highlevel Specs(53) | 100% | 2 h | 2 h | 1 d | 2002-10-04 10:20 | 2002-10-07 10:05 | 1.2.1.10.5.3 | 6
G0102 | Lakshmi | Review of Highlevel Specs(71) | 100% | 3 h | 3 h | 4 d | 2002-10-14 09:45 | 2002-10-14 13:45 | 1.2.1.10.2.3 | 6
G0102 | Lakshmi | Review of Highlevel Specs(49) | 100% | 3 h | 3 h | 1 d | 2002-10-14 09:45 | 2002-10-15 09:30 | 1.2.1.10.7.3 | 6
G0102 | Lakshmi | Review of Highlevel Specs(67) | 100% | 3 h | 3 h | 2 d | 2002-10-11 09:26 | 2002-10-15 15:45 | 1.2.1.10.4.4 | 6
G0102 | Lakshmi | Design the Highlevel Specs-2(86) | 100% | 4 h | 4 h | 10 d | 2002-10-15 15:45 | 2002-10-16 10:45 | 1.2.1.10.9.4 | 6
G0102 | Lakshmi | Review of Highlevel Specs(75) | 100% | 3 h | 3 h | 4 d | 2002-10-18 09:45 | 2002-10-18 13:45 | 1.2.1.10.6.3 | 6
G0102 | Lakshmi | Design the Highlevel Specs(80) | 100% | 0 h | 0 h | 8 d | 2002-10-24 08:45 | 2002-10-24 08:45 | 1.2.1.10.8.4 | 6
G0102 | Lakshmi | Review of Highlevel Specs(81) | 100% | 0 h | 0 h | 8 d | 2002-10-24 08:45 | 2002-10-24 08:45 | 1.2.1.10.8.5 | 6
G0102 | Lakshmi | Review of Highlevel Specs(87) | 100% | 2 h | 2 h | 1 d | 2002-10-29 13:15 | 2002-10-29 15:15 | 1.2.1.10.9.5 | 6
G0102 | Lakshmi | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-09-04 14:47 | 2002-11-06 14:02 | 1.2.1.5 | 6
G0102 | Lakshmi | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0105 | Lakshmi | NECHO - all Remaining Changes - Review TSD 3.2 Docs | 100% | 2 h | 2 h | 18 d | 2002-12-27 15:30 | 2003-01-22 10:00 | 1.5.2.4.13 | 9
G0105 | Lakshmi | NECHO - all Remaining Changes - Review TSD 8.3 Docs | 100% | 2 h | 2 h | 4 d | 2003-01-31 08:15 | 2003-02-05 16:15 | 1.5.2.4.25 | 9
G0105 | Lakshmi | AUI Request Vehicle Information Screen - UT/IT | 100% | 80 h | 80 h | 10 d | 2003-02-03 08:00 | 2003-02-14 14:30 | 1.5.2.6.2 | 9
G0105 | Lakshmi | Incoming Interface - UT/IT | 100% | 30 h | 30 h | 4 d | 2003-03-07 09:45 | 2003-03-13 08:45 | 1.5.2.6.6 | 9
G0105 | Lakshmi | Build Auto App Program - UT/IT | 100% | 40 h | 40 h | 19 d | 2003-03-13 08:45 | 2003-04-08 12:00 | 1.5.2.6.8 | 9
G0105 | Lakshmi | Warning Screen - UT/IT | 100% | 30 h | 30 h | 13 d | 2003-03-24 08:00 | 2003-04-09 13:45 | 1.5.2.6.10 | 9
G0105 | Lakshmi | Outgoing Interface - UT/IT | 100% | 30 h | 30 h | 5 d | 2003-04-03 08:15 | 2003-04-09 16:00 | 1.5.2.6.12 | 9
G0103 | Lynn | Create Acceptance Test Cases - Pkg-1 | 100% | 8.86 h | 8.86 h | 2 d | 2002-12-06 16:30 | 2002-12-10 16:00 | 1.3.7.3 | 7
G0103 | Lynn | NECHO Acceptance Testing - Pkg-1 | 100% | 16.34 h | 16.34 h | 21 d | 2002-12-09 10:00 | 2002-12-11 10:20 | 1.3.7.5 | 7
G0103 | Lynn | AUI Acceptance Testing - Pkg-1 | 100% | 16 h | 16 h | 4 d | 2002-12-17 16:15 | 2002-12-19 16:15 | 1.3.7.4 | 7
G0101 | Mary | Team Weekly Meetings | 100% | 26 h | 29.84 h | 341.99 d | 2002-05-06 08:00 | 2002-12-02 08:16 | 1.1.2.4 | 5
G0102 | Mary | Identify Architectural Constraints - AIP 1.1 | 100% | 20 h | 20 h | 5 d | 2002-07-19 08:00 | 2002-07-25 15:45 | 1.2.3.1.1 | 6
G0102 | Mary | Inventory Development Tools Standards and Procedures - AIP 1.3 | 100% | 4 h | 4 h | 1 d | 2002-07-25 15:45 | 2002-07-26 15:30 | 1.2.3.1.2 | 6
G0102 | Mary | Identify Existing Network Topology - AIP 1.2 | 100% | 4 h | 4 h | 1 d | 2002-07-26 15:30 | 2002-07-29 15:15 | 1.2.3.1.3 | 6
G0102 | Mary | Inventory Existing Hardware and System Software - AIP 1.4 | 100% | 4 h | 4 h | 1 d | 2002-07-29 15:15 | 2002-07-30 15:00 | 1.2.3.1.4 | 6
G0102 | Mary | Assemble Architecture Assessment - AIP 1.5 | 100% | 4 h | 4 h | 1 d | 2002-07-30 15:00 | 2002-07-31 14:45 | 1.2.3.1.5 | 6
G0102 | Mary | Determine Validation Components for ECHO & AUI | 100% | 8 h | 8 h | 18 d | 2002-08-30 14:00 | 2002-09-02 14:00 | 1.2.1.9 | 6
G0102 | Mary | Review Defect Tracking Strategy | 100% | 1.07 h | 1.07 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Mary | Define Operating Systems - AIP 2.2 | 100% | 5 h | 5 h | 10 d | 2002-08-26 15:00 | 2002-09-09 11:30 | 1.2.3.2.2 | 6
G0102 | Mary | Submit initial IIA questionnaire | 100% | 2 h | 2 h | 1 d | 2002-09-10 11:15 | 2002-09-11 11:00 | 1.2.3.4.1.1 | 6
G0102 | Mary | Design Network - AIP 2.1 | 100% | 5 h | 5 h | 10 d | 2002-08-14 08:15 | 2002-09-16 08:57 | 1.2.3.2.1 | 6
G0102 | Mary | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-16 09:50 | 1.2.2.2 | 6
G0102 | Mary | Infrastructure Impact Assessment - Level 2 review (if necessary) | 100% | 5 h | 5 h | 5 d | 2002-09-11 11:00 | 2002-09-18 09:45 | 1.2.3.4.1.2 | 6
G0102 | Mary | Define Data Distribution - AIP 2.4 | 100% | 10 h | 10 h | 10 d | 2002-09-09 11:30 | 2002-09-25 08:30 | 1.2.3.2.4 | 6
G0102 | Mary | Define Hardware Configuration - AIP 2.3 | 100% | 10 h | 10 h | 13 d | 2002-09-09 10:12 | 2002-09-25 15:57 | 1.2.3.2.3 | 6
G0102 | Mary | Define Middleware Req. - AIP 2.5 | 100% | 10 h | 10 h | 5 d | 2002-09-19 08:12 | 2002-09-25 15:57 | 1.2.3.2.5 | 6
G0102 | Mary | Submit SFTA Design Review | 100% | 1 h | 1 h | 1 d | 2002-09-25 15:57 | 2002-09-26 15:42 | 1.2.3.4.2.2 | 6
G0102 | Mary | Assemble information for SFTA review | 100% | 5 h | 5 h | 14 d | 2002-09-10 11:15 | 2002-09-27 16:45 | 1.2.3.4.2.1 | 6
G0102 | Mary | Define Application Service Distribution - AIP 2.6 | 100% | 10 h | 10 h | 10 d | 2002-09-19 09:30 | 2002-10-02 16:00 | 1.2.3.2.6 | 6
G0102 | Mary | SFTA Review process | 100% | 5 h | 5 h | 8 d | 2002-09-26 15:42 | 2002-10-08 13:42 | 1.2.3.4.2.3 | 6
G0102 | Mary | MS: Authorized SFTA documentation | 100% | 0 h | 0 h | 0 d | 2002-10-08 13:42 | 2002-10-08 13:42 | 1.2.3.4.3 | 6
G0102 | Mary | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0102 | Mary | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 1.2.1.5 | 6
G0102 | Mary | Define Security Infrastructure - AIP 2.7 | 100% | 10 h | 10 h | 41 d | 2002-10-02 16:00 | 2002-11-29 13:45 | 1.2.3.2.7 | 6
G0102 | Mary | Define System Topology - AIP 2.8 | 100% | 10 h | 10 h | 5 d | 2002-11-08 08:15 | 2002-12-04 13:00 | 1.2.3.2.8 | 6
G0102 | Mary | MS: Technology Architecture Documentation complete | 100% | 0 h | 0 h | 0 d | 2002-12-04 13:00 | 2002-12-04 13:00 | 1.2.3.3 | 6
G0103 | Mary | Pkg-1 - Review AUI Tech System Design - TSD 9.2 | 100% | 0 h | 0 h | 3 d | 2002-12-17 14:45 | 2002-12-17 14:45 | 1.3.6.1 | 7
G0103 | Mary | Pkg-1 - Review Consolidated Tech Doc - TPD 7.1 | 100% | 2.16 h | 2.16 h | 2 d | 2002-12-18 14:30 | 2002-12-20 14:00 | 1.3.6.3 | 7
G0104 | Mary | AUI - DLV - Review Technical System Design - TSD 9.2 | 100% | 1.5 h | 1.5 h | 8 d | 2002-12-24 15:45 | 2003-01-06 13:45 | 1.4.4.7.1 | 8
G0104 | Mary | Pkg-2 - Review AUI Technical System Design - TSD 9.2 | 100% | 2.38 h | 2.38 h | 8 d | 2002-12-24 15:45 | 2003-01-06 13:45 | 1.4.4.7.2 | 8
G0105 | Mary | NECHO - all Remaining Changes - Review TSD 3.2 Docs | 100% | 2 h | 2 h | 18 d | 2002-12-27 15:30 | 2002-12-30 08:30 | 1.5.2.4.13 | 9
G0105 | Mary | Pkg-3 - Review NECHO Technical System Design TSD 9.2 | 100% | 2.38 h | 2.38 h | 39 d | 2003-04-04 16:00 | 2003-05-30 10:23 | 1.5.3.1 | 9
G0105 | Mary | Pkg-3 - Review Consolidated Technical Documentation TPD 7.1 | 100% | 1.98 h | 1.98 h | 29 d | 2003-04-04 16:00 | 2003-05-30 10:23 | 1.5.3.2 | 9
G0106 | Mary | Update design documents (AIP 2.6) to reflect implemented system | 0% | 1.44 h | 1.44 h | 1 d | 2003-08-25 08:00 | 2003-08-25 16:45 | 1.6.1 | 10
G0106 | Mary | Transition design documents to local architect | 0% | 1.36 h | 1.36 h | 2 d | 2003-08-25 08:00 | 2003-08-26 16:30 | 1.6.2 | 10
G0101 | Michelle | Prepare & Review Project Charter | 100% | 1 h | 1 h | 35 d | 2002-05-21 08:00 | 2002-05-24 16:55 | 1.1.3.1 | 5
G0101 | Michelle | Facilitation management Processes | 100% | 1 h | 1 h | 55 d | 2002-07-05 16:15 | 2002-07-12 13:12 | 1.1.3.4 | 5
G0101 | Michelle | Prepare & review Project Plan | 100% | 1 h | 1 h | 64 d | 2002-07-05 16:15 | 2002-07-12 13:15 | 1.1.3.5 | 5
G0101 | Michelle | SSS activities | 85% | 349 h | 350 h | 342 d | 2002-05-06 08:00 | 2003-08-15 10:30 | 1.1.2.3 | 5
G0101 | Michelle | Team Weekly Meetings | 80% | 51 h | 75.76 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0102 | Michelle | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-25 09:00 | 1.2.1.2 | 6
G0102 | Michelle | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0106 | Michelle | Project Closure Tasks | 0% | 10 h | 10 h | 5 d | 2003-09-19 11:00 | 2003-09-24 12:00 | 1.6.5 | 10
G0101 | Murthy | Prepare & Review Project Charter | 100% | 5.99 h | 5.99 h | 35 d | 2002-05-21 08:00 | 2002-06-07 16:43 | 1.1.3.1 | 5
G0101 | Murthy | Project Schedule Development -1 | 100% | 6 h | 6 h | 60 d | 2002-06-03 08:00 | 2002-06-21 17:00 | 1.1.3.8 | 5
G0101 | Murthy | Facilitation management Processes | 100% | 2 h | 2 h | 55 d | 2002-07-12 13:15 | 2002-07-19 13:12 | 1.1.3.4 | 5
G0101 | Murthy | Prepare & review Project Plan | 100% | 2 h | 2 h | 64 d | 2002-07-12 13:15 | 2002-07-19 13:15 | 1.1.3.5 | 5
G0101 | Murthy | Project Schedule Development -2 | 100% | 6 h | 6 h | 43 d | 2002-09-18 16:15 | 2002-10-09 16:15 | 1.1.3.10 | 5
G0101 | Murthy | Team Weekly Meetings | 80% | 51 h | 76.79 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0102 | Murthy | Design of New screen(83) | 100% | 15.79 h | 15.79 h | 3 d | 2002-07-16 14:30 | 2002-07-19 13:45 | 1.2.1.10.9.1 | 6
G0102 | Murthy | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-24 15:00 | 1.2.1.2 | 6
G0102 | Murthy | Understand existing ECHO APPS System | 100% | 120 h | 120 h | 50 d | 2002-06-13 11:30 | 2002-08-16 17:00 | 1.2.1.10.1 | 6
G0102 | Murthy | Review Defect Tracking Strategy | 100% | 1.07 h | 1.07 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Murthy | Analysing the requirements(64) | 100% | 34 h | 34 h | 20 d | 2002-08-05 09:30 | 2002-09-13 13:30 | 1.2.1.10.4.1 | 6
G0102 | Murthy | Analysis of Flow of Data(84) | 100% | 60 h | 60 h | 32 d | 2002-07-19 13:45 | 2002-09-16 13:45 | 1.2.1.10.9.2 | 6
G0102 | Murthy | Analysing the requirements(59) | 100% | 22.97 h | 22.97 h | 10 d | 2002-09-03 08:00 | 2002-09-16 14:30 | 1.2.1.10.3.1 | 6
G0102 | Murthy | Design the Highlevel Specs-1(85) | 100% | 8 h | 8 h | 24 d | 2002-08-02 10:15 | 2002-09-18 16:15 | 1.2.1.10.9.3 | 6
G0102 | Murthy | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-20 08:15 | 1.2.2.2 | 6
G0102 | Murthy | Design the Highlevel Specs-1(60) | 100% | 8 h | 8 h | 4 d | 2002-09-16 14:30 | 2002-09-20 13:30 | 1.2.1.10.3.2 | 6
G0102 | Murthy | Design the Highlevel Specs-1(65) | 100% | 12 h | 12 h | 11 d | 2002-08-13 08:00 | 2002-09-27 11:56 | 1.2.1.10.4.2 | 6
G0102 | Murthy | Design the Highlevel Specs-2(61) | 100% | 6 h | 6 h | 9.1 d | 2002-09-16 14:30 | 2002-09-27 12:00 | 1.2.1.10.3.3 | 6
G0102 | Murthy | Review of Highlevel Specs(62) | 100% | 2 h | 2 h | 1 d | 2002-09-27 13:00 | 2002-09-27 14:56 | 1.2.1.10.3.4 | 6
G0102 | Murthy | Design the Highlevel Specs(52) | 100% | 20 h | 20 h | 9 d | 2002-09-20 09:30 | 2002-10-04 10:20 | 1.2.1.10.5.2 | 6
G0102 | Murthy | Review of Highlevel Specs(53) | 100% | 2 h | 2 h | 1 d | 2002-10-04 10:20 | 2002-10-04 13:16 | 1.2.1.10.5.3 | 6
G0102 | Murthy | Design the Highlevel Specs-2(66) | 100% | 12 h | 12 h | 10 d | 2002-09-27 11:56 | 2002-10-11 09:26 | 1.2.1.10.4.3 | 6
G0102 | Murthy | Analysing the requirements(47) | 100% | 48 h | 48 h | 24 d | 2002-09-10 08:00 | 2002-10-11 10:00 | 1.2.1.10.7.1 | 6
G0102 | Murthy | Review of Highlevel Specs(67) | 100% | 2 h | 2 h | 2 d | 2002-10-11 09:26 | 2002-10-11 11:22 | 1.2.1.10.4.4 | 6
G0102 | Murthy | Design the Highlevel Specs(48) | 100% | 52 h | 52 h | 10 d | 2002-09-30 13:15 | 2002-10-14 09:45 | 1.2.1.10.7.2 | 6
G0102 | Murthy | Review of Highlevel Specs(49) | 100% | 2 h | 2 h | 1 d | 2002-10-14 09:45 | 2002-10-14 11:41 | 1.2.1.10.7.3 | 6
G0102 | Murthy | Design the Highlevel Specs-2(86) | 100% | 16 h | 16 h | 10 d | 2002-10-15 15:45 | 2002-10-29 13:15 | 1.2.1.10.9.4 | 6
G0102 | Murthy | Review of Highlevel Specs(87) | 100% | 4 h | 4 h | 1 d | 2002-10-29 13:15 | 2002-10-30 13:00 | 1.2.1.10.9.5 | 6
G0102 | Murthy | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-05 10:00 | 2002-11-01 15:47 | 1.2.1.5 | 6
G0102 | Murthy | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0103 | Murthy | NECHO -DLV - Design Low level Specs (TSD3.2) | 100% | 20 h | 20 h | 3 d | 2002-11-04 08:00 | 2002-11-06 16:15 | 1.3.4.1 | 7
G0103 | Murthy | NECHO -DLV - Design Test Cases (TSD8.3) | 100% | 40 h | 40 h | 6 d | 2002-11-06 16:15 | 2002-11-14 14:45 | 1.3.4.2 | 7
G0103 | Murthy | NECHO - DLV - Coding | 100% | 30 h | 30 h | 6 d | 2002-11-14 14:45 | 2002-11-22 13:15 | 1.3.4.3 | 7
G0103 | Murthy | NECHO -DLV - Unit Testing | 100% | 9 h | 9 h | 9 d | 2002-11-15 14:30 | 2002-12-02 11:15 | 1.3.4.4 | 7
G0103 | Murthy | NECHO DLV - RSC Entry | 100% | 2 h | 2 h | 1 d | 2003-01-27 08:00 | 2003-01-27 16:45 | 1.3.4.5 | 7
G0105 | Murthy | AUI Request Vehicle Information Screen - TSD 3.2 | 100% | 50 h | 50 h | 12 d | 2002-11-25 13:00 | 2002-12-13 09:00 | 1.5.2.4.2 | 9
G0105 | Murthy | MQ - Interface module - TSD 3.2 | 100% | 30 h | 30 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 1.5.2.4.3 | 9
G0105 | Murthy | Incoming Interface - TSD 3.2 | 100% | 20 h | 20 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 1.5.2.4.4 | 9
G0105 | Murthy | Build Auto App Program - TSD 3.2 | 100% | 20 h | 20 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 1.5.2.4.6 | 9
G0105 | Murthy | Warning Screen - TSD 3.2 | 100% | 20 h | 20 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 1.5.2.4.7 | 9
G0105 | Murthy | Outgoing Interface - TSD 3.2 | 100% | 20 h | 20 h | 16 d | 2002-12-03 11:00 | 2002-12-24 16:00 | 1.5.2.4.5 | 9
G0105 | Murthy | Build Auto App Program - TSD 8.3 | 100% | 20 h | 20 h | 11 d | 2002-12-27 08:00 | 2003-01-10 14:15 | 1.5.2.4.18 | 9
G0105 | Murthy | Warning Screen - TSD 8.3 | 100% | 20 h | 20 h | 15 d | 2002-12-27 15:30 | 2003-01-17 10:45 | 1.5.2.4.19 | 9
G0105 | Murthy | NECHO - all Remaining Changes - Review TSD 3.2 Docs | 100% | 2 h | 2 h | 18 d | 2002-12-27 15:30 | 2003-01-22 10:00 | 1.5.2.4.13 | 9
G0105 | Murthy | AUI Request Vehicle Information Screen - TSD 8.3 | 100% | 60 h | 60 h | 18 d | 2002-12-27 15:30 | 2003-01-22 10:00 | 1.5.2.4.14 | 9
G0105 | Murthy | Outgoing Interface - TSD 8.3 | 100% | 20 h | 20 h | 21 d | 2002-12-27 15:30 | 2003-01-27 09:15 | 1.5.2.4.17 | 9
G0105 | Murthy | Perform Integration Testing for NECHO Changes - pkg-2 | 100% | 30 h | 30 h | 61 d | 2003-01-20 10:30 | 2003-01-27 16:59 | 1.5.2.5.1 | 9
G0105 | Murthy | MQ - Interface module - TSD 8.3 | 100% | 30 h | 30 h | 24 d | 2002-12-27 15:30 | 2003-01-30 08:30 | 1.5.2.4.15 | 9
G0105 | Murthy | Incoming Interface - TSD 8.3 | 100% | 20 h | 20 h | 24 d | 2002-12-27 15:30 | 2003-01-30 08:30 | 1.5.2.4.16 | 9
G0105 | Murthy | NECHO - all Remaining Changes - Review TSD 8.3 Docs | 100% | 2 h | 2 h | 4 d | 2003-01-31 08:15 | 2003-02-05 16:15 | 1.5.2.4.25 | 9
G0105 | Murthy | AUI Request Vehicle Information Screen - Coding | 100% | 80 h | 80 h | 10 d | 2003-02-03 08:00 | 2003-02-14 14:30 | 1.5.2.6.1 | 9
G0105 | Murthy | Incoming Interface - Coding | 100% | 30 h | 30 h | 4 d | 2003-03-07 09:45 | 2003-03-13 08:45 | 1.5.2.6.5 | 9
G0105 | Murthy | Pf Key format /Branching Program (PCS5F) - UT/IT | 100% | 20 h | 20 h | 4 d | 2003-03-28 14:15 | 2003-04-02 09:15 | 1.5.2.6.22 | 9
G0105 | Murthy | MQ - Interface module - Coding | 100% | 50 h | 50 h | 38 d | 2003-02-14 14:30 | 2003-04-08 12:00 | 1.5.2.6.3 | 9
G0105 | Murthy | MQ - Interface module - UT/IT | 100% | 40 h | 40 h | 38 d | 2003-02-14 14:30 | 2003-04-08 12:00 | 1.5.2.6.4 | 9
G0105 | Murthy | Build Auto App Program - Coding | 100% | 40 h | 40 h | 19 d | 2003-03-13 08:45 | 2003-04-08 12:00 | 1.5.2.6.7 | 9
G0105 | Murthy | Warning Screen - Coding | 100% | 30 h | 30 h | 13 d | 2003-03-24 08:00 | 2003-04-09 13:45 | 1.5.2.6.9 | 9
G0105 | Murthy | Outgoing Interface - Coding | 100% | 30 h | 30 h | 5 d | 2003-04-03 08:15 | 2003-04-09 16:00 | 1.5.2.6.11 | 9
G0104 | PerTeam | Setup Perf. Testing Pkg-2 | 100% | 5 h | 9.36 h | 28 d | 2003-03-05 11:45 | 2003-04-11 13:45 | 1.4.4.6.1 | 8
G0104 | PerTeam | Execute Perf. Testing Pkg-2 | 75% | 40 h | 40 h | 45 d | 2003-04-15 08:00 | 2003-06-13 13:45 | 1.4.4.6.2 | 8
G0101 | Sherrill | IIA Team (Performance Impact Accessment) | 100% | 25 h | 25 h | 230 d | 2002-10-07 08:00 | 2002-10-10 09:00 | 1.1.5.1 | 5
G0101 | SteveH | Prepare & Review Project Charter | 100% | 5.99 h | 5.99 h | 35 d | 2002-05-21 08:00 | 2002-06-07 16:43 | 1.1.3.1 | 5
G0101 | SteveH | Facilitation management Processes | 100% | 2 h | 2 h | 55 d | 2002-07-12 13:15 | 2002-07-19 13:12 | 1.1.3.4 | 5
G0101 | SteveH | Prepare & review Project Plan | 100% | 2 h | 2 h | 64 d | 2002-07-12 13:15 | 2002-07-19 13:15 | 1.1.3.5 | 5
G0101 | SteveH | Team Weekly Meetings | 80% | 51 h | 75.76 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0102 | SteveH | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-25 09:00 | 1.2.1.2 | 6
G0102 | SteveH | Create Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 50 h | 50 h | 32 d | 2002-07-25 11:45 | 2002-09-06 11:45 | 1.2.2.1 | 6
G0102 | SteveH | Create Defect Tracking Strategy | 100% | 40 h | 40 h | 10 d | 2002-08-26 08:00 | 2002-09-06 14:30 | 1.2.2.3 | 6
G0102 | SteveH | Review Defect Tracking Strategy | 100% | 0.28 h | 0.28 h | 5 d | 2002-09-06 14:30 | 2002-09-13 13:15 | 1.2.2.4 | 6
G0102 | SteveH | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-16 11:32 | 1.2.2.2 | 6
G0102 | SteveH | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0102 | SteveH | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 1.2.1.5 | 6
G0103 | SteveH | Establish Test Environment Needs - Pkg-1 | 100% | 10 h | 10 h | 2 d | 2002-11-13 16:45 | 2002-11-15 16:15 | 1.3.7.1 | 7
G0103 | SteveH | Establish Test Environment - Pkg-1 | 100% | 20 h | 20 h | 5 d | 2002-11-11 08:30 | 2002-11-15 16:15 | 1.3.7.2 | 7
G0103 | SteveH | NECHO Acceptance Testing - Pkg-1 | 100% | 5.11 h | 5.11 h | 21 d | 2002-12-09 10:00 | 2002-12-10 15:46 | 1.3.7.5 | 7
G0103 | SteveH | AUI Acceptance Testing - Pkg-1 | 100% | 5 h | 5 h | 4 d | 2002-12-17 16:15 | 2002-12-19 11:45 | 1.3.7.4 | 7
G0103 | SteveH | Create Acceptance Test Summary Report - Pkg-1 | 100% | 10 h | 10 h | 9 d | 2002-12-23 16:15 | 2003-01-06 14:00 | 1.3.7.7 | 7
G0103 | SteveH | Review / Authorize Acceptance Test Summary Report - Pkg-1 | 100% | 20 h | 20 h | 5 d | 2003-01-06 14:00 | 2003-01-13 11:45 | 1.3.7.8 | 7
G0104 | SteveH | Establish Test Environment needs | 100% | 10 h | 10 h | 3 d | 2002-12-23 16:15 | 2002-12-27 15:30 | 1.4.3.1 | 8
G0104 | SteveH | Determine FIT Test Environment Needs | 100% | 20 h | 20 h | 9 d | 2002-12-23 16:15 | 2003-01-06 14:00 | 1.4.3.4 | 8
G0104 | SteveH | Set-up AUI Integration/System Test Environment | 100% | 20 h | 20 h | 18 d | 2002-12-23 16:15 | 2003-01-17 10:45 | 1.4.3.2 | 8
G0104 | SteveH | Set-up NECHO Integration/System Test Environment | 100% | 20 h | 20 h | 18 d | 2002-12-23 16:15 | 2003-01-17 10:45 | 1.4.3.3 | 8
G0104 | SteveH | AUI - Create AUI System Test Plan | 100% | 20 h | 20 h | 10 d | 2003-01-06 08:00 | 2003-01-17 14:30 | 1.4.4.5.1 | 8
G0104 | SteveH | AUI-DLV Mid Tier / Host Int Test | 100% | 10 h | 10 h | 14 d | 2003-01-17 10:45 | 2003-01-24 16:06 | 1.4.4.5.2 | 8
G0104 | SteveH | AUI-DLV Web / Mid Tier / Host System Testing (Initial) | 100% | 10 h | 10 h | 15 d | 2003-02-05 16:15 | 2003-02-11 08:15 | 1.4.4.5.3 | 8
G0104 | SteveH | Setup Perf. Testing Pkg-2 | 100% | 15 h | 10.64 h | 28 d | 2003-03-05 11:45 | 2003-04-11 13:45 | 1.4.4.6.1 | 8
G0104 | SteveH | Implementation testing execution pkg-2 | 20% | 0 h | 5 h | 31 d | 2003-05-02 08:00 | 2003-05-05 09:41 | 1.4.4.6.3 | 8
G0104 | SteveH | Set-up FIT Test Environment | 100% | 20 h | 20 h | 91.87 d | 2003-01-21 08:00 | 2003-05-23 17:00 | 1.4.3.5 | 8
G0104 | SteveH | Execute Perf. Testing Pkg-2 | 75% | 10 h | 10 h | 45 d | 2003-04-15 08:00 | 2003-06-13 13:45 | 1.4.4.6.2 | 8
G0105 | SteveH | SAT - Create System/Acceptance Test Plan | 100% | 20 h | 20 h | 10 d | 2003-02-05 16:15 | 2003-02-19 13:45 | 1.5.4.1 | 9
G0105 | SteveH | SAT - Create NECHO System/Acceptance Test Plan | 100% | 20 h | 20 h | 34 d | 2003-01-06 14:00 | 2003-02-20 13:30 | 1.5.4.7.1 | 9
G0105 | SteveH | SAT - Create System/Acceptance Test Cases | 100% | 40 h | 40 h | 31 d | 2003-02-21 08:00 | 2003-04-04 08:15 | 1.5.4.2 | 9
G0105 | SteveH | Perform Integration Testing for NECHO Changes - pkg-2 | 100% | 10 h | 10 h | 61 d | 2003-01-20 10:30 | 2003-04-15 10:44 | 1.5.2.5.1 | 9
G0105 | SteveH | SAT - Create System/Acceptance Test Summary Report | 0% | 10 h | 10 h | 2 d | 2003-06-02 16:15 | 2003-06-04 15:45 | 1.5.4.4 | 9
G0105 | SteveH | SAT - Authorize System/Acceptance Test Summary Report | 0% | 10 h | 10 h | 5 d | 2003-06-04 15:45 | 2003-06-11 14:30 | 1.5.4.5 | 9
G0105 | SteveH | SAT - Create FIT Test Summary Report | 0% | 10 h | 10 h | 10 d | 2003-07-10 08:15 | 2003-07-23 14:45 | 1.5.4.7.4 | 9
G0105 | SteveH | SAT - Authorize FIT Test Summary Report | 0% | 10 h | 10 h | 5 d | 2003-07-23 14:45 | 2003-07-30 13:30 | 1.5.4.7.5 | 9
G0105 | Sushit | SRA 4.2 Establish Security and Control, Requirements | 100% | 6 h | 6 h | 23 d | 2002-11-01 08:00 | 2002-12-05 10:15 | 1.5.2.1.1 | 9
G0105 | Sushit | SDS 5.2 Specify Security and Control Requirements | 100% | 15 h | 15 h | 26 d | 2002-12-19 08:00 | 2003-01-24 09:30 | 1.5.2.1.2 | 9
G0105 | Sushit | Build Test Ids/Rules | 100% | 10 h | 10 h | 31 d | 2002-12-27 08:00 | 2003-02-07 08:15 | 1.5.2.1.3 | 9
G0106 | Sushit | Transition to Service | 0% | 6.53 h | 6.53 h | 20 d | 2003-08-25 08:00 | 2003-09-19 11:00 | 1.6.4 | 10
G0101 | Tina | Prepare & Review Project Charter | 100% | 5.99 h | 5.99 h | 35 d | 2002-05-21 08:00 | 2002-06-07 16:43 | 1.1.3.1 | 5
G0101 | Tina | Project Schedule Development -1 | 100% | 6 h | 6 h | 60 d | 2002-05-28 08:00 | 2002-06-14 17:00 | 1.1.3.8 | 5
G0101 | Tina | Facilitation management Processes | 100% | 2 h | 2 h | 55 d | 2002-07-12 13:15 | 2002-07-19 13:12 | 1.1.3.4 | 5
G0101 | Tina | Prepare & review Project Plan | 100% | 2 h | 2 h | 64 d | 2002-07-12 13:15 | 2002-07-19 13:15 | 1.1.3.5 | 5
G0101 | Tina | Project Schedule Development -2 | 100% | 6 h | 6 h | 43 d | 2002-09-18 16:15 | 2002-10-07 11:15 | 1.1.3.10 | 5
G0101 | Tina | Team Weekly Meetings | 80% | 51 h | 76.79 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0102 | Tina | Determine Business Requirements | 100% | 5 h | 5 h | 24 d | 2002-06-13 11:30 | 2002-07-16 14:30 | 1.2.1.1 | 6
G0102 | Tina | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-24 15:00 | 1.2.1.2 | 6
G0102 | Tina | Review Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-26 11:30 | 2002-07-26 14:30 | 1.2.1.3 | 6
G0102 | Tina | Create New ECHO Screen Layout | 100% | 5 h | 5 h | 3 d | 2002-07-29 11:15 | 2002-08-01 10:30 | 1.2.1.6 | 6
G0102 | Tina | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 0.84 h | 0.84 h | 31 d | 2002-08-19 08:00 | 2002-08-19 08:56 | 1.2.2.2 | 6
G0102 | Tina | Create SRA 4/SDS 3.1 identifying impacted reusable service areas | 100% | 1 h | 1 h | 18 d | 2002-08-30 14:00 | 2002-08-30 16:30 | 1.2.1.7.4 | 6
G0102 | Tina | Determine Validation Components for ECHO & AUI | 100% | 8 h | 8 h | 18 d | 2002-08-30 14:00 | 2002-09-02 14:00 | 1.2.1.9 | 6
G0102 | Tina | Review Defect Tracking Strategy | 100% | 1.07 h | 1.07 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Tina | Design the Highlevel Specs-2(61) | 100% | 2 h | 2 h | 9.1 d | 2002-09-16 14:30 | 2002-09-16 16:30 | 1.2.1.10.3.3 | 6
G0102 | Tina | Design the Highlevel Specs(52) | 100% | 5 h | 5 h | 9 d | 2002-09-20 09:30 | 2002-09-24 09:35 | 1.2.1.10.5.2 | 6
G0102 | Tina | Review of Highlevel Specs(62) | 100% | 3 h | 3 h | 1 d | 2002-09-27 13:00 | 2002-09-30 11:45 | 1.2.1.10.3.4 | 6
G0102 | Tina | Design the Highlevel Specs-2(66) | 100% | 8 h | 8 h | 10 d | 2002-09-27 11:56 | 2002-09-30 11:56 | 1.2.1.10.4.3 | 6
G0102 | Tina | Design the Highlevel Specs(70) | 100% | 4 h | 4 h | 10 d | 2002-09-30 13:15 | 2002-10-01 08:15 | 1.2.1.10.2.2 | 6
G0102 | Tina | Design the Highlevel Specs(48) | 100% | 4 h | 4 h | 10 d | 2002-09-30 13:15 | 2002-10-01 08:15 | 1.2.1.10.7.2 | 6
G0102 | Tina | Design the Highlevel Specs(74) | 100% | 3 h | 3 h | 10 d | 2002-10-04 13:15 | 2002-10-04 16:15 | 1.2.1.10.6.2 | 6
G0102 | Tina | Review of Highlevel Specs(53) | 100% | 2 h | 2 h | 1 d | 2002-10-04 10:20 | 2002-10-07 10:05 | 1.2.1.10.5.3 | 6
G0102 | Tina | Review of Highlevel Specs(71) | 100% | 3 h | 3 h | 4 d | 2002-10-14 09:45 | 2002-10-14 13:45 | 1.2.1.10.2.3 | 6
G0102 | Tina | Review of Highlevel Specs(49) | 100% | 3 h | 3 h | 1 d | 2002-10-14 09:45 | 2002-10-15 09:30 | 1.2.1.10.7.3 | 6
G0102 | Tina | Review of Highlevel Specs(67) | 100% | 3 h | 3 h | 2 d | 2002-10-11 09:26 | 2002-10-15 15:45 | 1.2.1.10.4.4 | 6
G0102 | Tina | Design the Highlevel Specs-2(86) | 100% | 4 h | 4 h | 10 d | 2002-10-15 15:45 | 2002-10-16 10:45 | 1.2.1.10.9.4 | 6
G0102 | Tina | Review of Highlevel Specs(75) | 100% | 3 h | 3 h | 4 d | 2002-10-18 09:45 | 2002-10-18 13:45 | 1.2.1.10.6.3 | 6
G0102 | Tina | Design the Highlevel Specs(80) | 100% | 4 h | 4 h | 8 d | 2002-10-24 08:45 | 2002-10-24 13:45 | 1.2.1.10.8.4 | 6
G0102 | Tina | Review of Highlevel Specs(81) | 100% | 4 h | 4 h | 8 d | 2002-10-24 08:45 | 2002-10-24 13:45 | 1.2.1.10.8.5 | 6
G0102 | Tina | Review of Highlevel Specs(87) | 100% | 2 h | 2 h | 1 d | 2002-10-29 13:15 | 2002-10-29 15:15 | 1.2.1.10.9.5 | 6
G0102 | Tina | Update Delivery Specs Doc | 100% | 10 h | 10 h | 1 d | 2002-11-04 15:45 | 2002-11-05 15:30 | 1.2.1.12 | 6
G0102 | Tina | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0102 | Tina | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-19 08:00 | 2002-11-08 14:59 | 1.2.1.5 | 6
G0105 | Tina | NECHO - all Remaining Changes - Review TSD 3.2 Docs | 100% | 2 h | 2 h | 18 d | 2002-12-27 15:30 | 2003-01-22 10:00 | 1.5.2.4.13 | 9
G0105 | Tina | Perform Integration Testing for NECHO Changes - pkg-2 | 100% | 10 h | 10 h | 61 d | 2003-01-20 10:30 | 2003-01-23 11:59 | 1.5.2.5.1 | 9
G0105 | Tina | NECHO - all Remaining Changes - Review TSD 8.3 Docs | 100% | 2 h | 2 h | 4 d | 2003-01-31 08:15 | 2003-02-05 16:15 | 1.5.2.4.25 | 9
G0105 | Tina | Auto Apps - Main Program - UT/IT | 100% | 60 h | 60 h | 8 d | 2003-02-03 08:00 | 2003-02-12 15:00 | 1.5.2.6.14 | 9
G0105 | Tina | Territory Validation (Options screen) - UT/IT | 100% | 30 h | 30 h | 15 d | 2003-03-14 08:00 | 2003-03-19 15:00 | 1.5.2.6.20 | 9
G0105 | Tina | AUI Request Driver Information Screen - UT/IT | 100% | 80 h | 80 h | 23 d | 2003-02-26 11:30 | 2003-03-28 14:45 | 1.5.2.6.18 | 9
G0105 | Tina | Pf Key format /Branching Program (PCS5F) - UT/IT | 100% | 20 h | 20 h | 4 d | 2003-03-28 14:15 | 2003-04-03 13:15 | 1.5.2.6.22 | 9
G0101 | Ty | Team Weekly Meetings | 100% | 26 h | 29.84 h | 341.99 d | 2002-05-06 08:00 | 2002-12-02 08:16 | 1.1.2.4 | 5
G0102 | Ty | Determine Validation Components for ECHO & AUI | 100% | 8 h | 8 h | 18 d | 2002-08-30 14:00 | 2002-09-02 14:00 | 1.2.1.9 | 6
G0102 | Ty | Define Operating Systems - AIP 2.2 | 100% | 5 h | 5 h | 10 d | 2002-08-26 15:00 | 2002-09-04 14:22 | 1.2.3.2.2 | 6
G0102 | Ty | Review Defect Tracking Strategy | 100% | 1.07 h | 1.07 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Ty | Submit initial IIA questionnaire | 100% | 2 h | 2 h | 1 d | 2002-09-10 11:15 | 2002-09-10 14:15 | 1.2.3.4.1.1 | 6
G0102 | Ty | Assemble information for SFTA review | 100% | 5 h | 5 h | 14 d | 2002-09-10 11:15 | 2002-09-11 08:15 | 1.2.3.4.2.1 | 6
G0102 | Ty | Design Network - AIP 2.1 | 100% | 5 h | 5 h | 10 d | 2002-08-14 08:15 | 2002-09-11 10:49 | 1.2.3.2.1 | 6
G0102 | Ty | Infrastructure Impact Assessment - Level 2 review (if necessary) | 100% | 5 h | 5 h | 5 d | 2002-09-11 11:00 | 2002-09-11 17:00 | 1.2.3.4.1.2 | 6
G0102 | Ty | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-16 09:50 | 1.2.2.2 | 6
G0102 | Ty | Define Hardware Configuration - AIP 2.3 | 100% | 10 h | 10 h | 13 d | 2002-09-09 10:12 | 2002-09-17 14:51 | 1.2.3.2.3 | 6
G0102 | Ty | Define Data Distribution - AIP 2.4 | 100% | 10 h | 10 h | 10 d | 2002-09-09 11:30 | 2002-09-19 15:39 | 1.2.3.2.4 | 6
G0102 | Ty | Define Middleware Req. - AIP 2.5 | 100% | 10 h | 10 h | 5 d | 2002-09-19 08:12 | 2002-09-25 15:57 | 1.2.3.2.5 | 6
G0102 | Ty | Submit SFTA Design Review | 100% | 1 h | 1 h | 1 d | 2002-09-25 15:57 | 2002-09-25 16:57 | 1.2.3.4.2.2 | 6
G0102 | Ty | SFTA Review process | 100% | 5 h | 5 h | 8 d | 2002-09-26 15:42 | 2002-09-27 11:42 | 1.2.3.4.2.3 | 6
G0102 | Ty | Define Application Service Distribution - AIP 2.6 | 100% | 10 h | 10 h | 10 d | 2002-09-19 09:30 | 2002-09-27 14:09 | 1.2.3.2.6 | 6
G0102 | Ty | Define Security Infrastructure - AIP 2.7 | 100% | 10 h | 10 h | 41 d | 2002-10-02 16:00 | 2002-10-11 10:39 | 1.2.3.2.7 | 6
G0102 | Ty | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0102 | Ty | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 1.2.1.5 | 6
G0102 | Ty | Define System Topology - AIP 2.8 | 100% | 10 h | 10 h | 5 d | 2002-11-08 08:15 | 2002-12-04 13:00 | 1.2.3.2.8 | 6
G0103 | Ty | Pkg-1 - Review NECHO Tech System Design - TSD 9.2 | 100% | 10 h | 10 h | 5 d | 2002-11-22 13:15 | 2002-12-03 11:00 | 1.3.6.2 | 7
G0103 | Ty | Pkg-1 - Review Consolidated Tech Doc - TPD 7.1 | 100% | 0.84 h | 0.84 h | 2 d | 2002-12-18 14:30 | 2002-12-18 16:38 | 1.3.6.3 | 7
G0103 | Ty | Pkg-1 - Review AUI Tech System Design - TSD 9.2 | 100% | 3 h | 3 h | 3 d | 2002-12-17 14:45 | 2002-12-20 14:00 | 1.3.6.1 | 7
G0104 | Ty | Pkg-2 - Review AUI Technical System Design - TSD 9.2 | 100% | 0.62 h | 0.62 h | 8 d | 2002-12-24 15:45 | 2002-12-26 09:07 | 1.4.4.7.2 | 8
G0104 | Ty | AUI - DLV - Review Technical System Design - TSD 9.2 | 100% | 1.5 h | 1.5 h | 8 d | 2002-12-24 15:45 | 2003-01-06 13:45 | 1.4.4.7.1 | 8
G0105 | Ty | NECHO - all Remaining Changes - Review TSD 3.2 Docs | 100% | 2 h | 2 h | 18 d | 2002-12-27 15:30 | 2002-12-30 08:30 | 1.5.2.4.13 | 9
G0105 | Ty | Pkg-3 - Review NECHO Technical System Design TSD 9.2 | 100% | 0.62 h | 0.62 h | 39 d | 2003-04-04 16:00 | 2003-04-07 09:22 | 1.5.3.1 | 9
G0105 | Ty | Pkg-3 - Review Consolidated Technical Documentation TPD 7.1 | 100% | 1.02 h | 1.02 h | 29 d | 2003-04-04 16:00 | 2003-05-30 10:23 | 1.5.3.2 | 9
G0106 | Ty | Update design documents (AIP 2.6) to reflect implemented system | 0% | 0.56 h | 0.56 h | 1 d | 2003-08-25 08:00 | 2003-08-25 16:45 | 1.6.1 | 10
G0106 | Ty | Transition design documents to local architect | 0% | 2.64 h | 2.64 h | 2 d | 2003-08-25 08:00 | 2003-08-26 16:30 | 1.6.2 | 10
G0101 | Vance | Project Coordination Activities | 80% | 964 h | 964 h | 281 d | 2002-07-26 08:00 | 2003-08-15 09:45 | 1.1.2.2 | 5
G0104 | Vance | Create Pkg-2 SFQ Solutions | 100% | 10 h | 10 h | 37 d | 2003-03-21 08:00 | 2003-05-09 15:45 | 1.4.4.8.7 | 8
G0104 | Vance | Populate pkg-2 SFQ Solutions | 0% | 10 h | 10 h | 5 d | 2003-05-23 13:15 | 2003-05-30 11:00 | 1.4.4.8.9 | 8
G0105 | Vance | Create Pkg-3 SFQ Solutions | 0% | 10 h | 10 h | 10 d | 2003-06-16 13:45 | 2003-06-30 10:15 | 1.5.5.9 | 9
G0105 | Vance | Populate pkg-3 SFQ Solutions | 0% | 10 h | 10 h | 5 d | 2003-07-11 16:45 | 2003-07-18 15:30 | 1.5.5.11 | 9
G0101 | Witter | Prepare & Review Project Charter | 100% | 5.99 h | 5.99 h | 35 d | 2002-05-21 08:00 | 2002-06-07 16:43 | 1.1.3.1 | 5
G0101 | Witter | Project Schedule Development -1 | 100% | 6 h | 6 h | 60 d | 2002-05-28 08:00 | 2002-06-14 17:00 | 1.1.3.8 | 5
G0101 | Witter | Facilitation management Processes | 100% | 2 h | 2 h | 55 d | 2002-07-12 13:15 | 2002-07-19 13:12 | 1.1.3.4 | 5
G0101 | Witter | Prepare & review Project Plan | 100% | 2 h | 2 h | 64 d | 2002-07-12 13:15 | 2002-07-19 13:15 | 1.1.3.5 | 5
G0101 | Witter | Project Schedule Development -2 | 100% | 6 h | 6 h | 43 d | 2002-09-18 16:15 | 2002-10-07 11:15 | 1.1.3.10 | 5
G0101 | Witter | Team Weekly Meetings | 80% | 51 h | 75.76 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4 | 5
G0102 | Witter | Review Testable Business Requirements | 100% | 2 h | 2 h | 1 d | 2002-07-24 13:00 | 2002-07-25 09:00 | 1.2.1.2 | 6
G0102 | Witter | Review Defect Tracking Strategy | 100% | 0.43 h | 0.43 h | 5 d | 2002-09-06 14:30 | 2002-09-06 15:34 | 1.2.2.4 | 6
G0102 | Witter | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 1 h | 0.85 h | 31 d | 2002-08-09 08:00 | 2002-09-16 09:50 | 1.2.2.2 | 6
G0102 | Witter | Determine Validation Components for ECHO & AUI | 100% | 8 h | 8 h | 18 d | 2002-08-30 14:00 | 2002-09-25 08:30 | 1.2.1.9 | 6
G0102 | Witter | AUI - design address Std | 100% | 25 h | 25 h | 10 d | 2002-09-13 10:30 | 2002-09-26 17:00 | 1.2.1.11.1 | 6
G0102 | Witter | AUI - design driver's license validation | 100% | 25 h | 25 h | 16 d | 2002-09-27 08:00 | 2002-10-18 12:00 | 1.2.1.11.2 | 6
G0102 | Witter | AUI - design VIN validation | 100% | 25 h | 25 h | 16 d | 2002-09-27 08:00 | 2002-10-18 12:00 | 1.2.1.11.3 | 6
G0102 | Witter | Review SDS Doc | 100% | 1 h | 1 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13 | 6
G0102 | Witter | Technical discussion meetings | 100% | 40 h | 40 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 1.2.1.5 | 6
G0103 | Witter | AUI Address Std - Analysis & Design | 100% | 10 h | 10 h | 3 d | 2002-10-21 08:00 | 2002-10-23 16:15 | 1.3.2.2 | 7
G0103 | Witter | AUI Address Std - Coding | 100% | 40 h | 40 h | 9 d | 2002-10-23 16:15 | 2002-11-05 14:00 | 1.3.2.3 | 7
G0103 | Witter | AUI Address Std - RSC Entry | 100% | 2 h | 2 h | 5 d | 2002-11-22 09:45 | 2002-12-03 08:30 | 1.3.2.1 | 7
G0103 | Witter | AUI Address Std - Unit Test Cases/Testing | 100% | 20 h | 20 h | 5 d | 2002-11-22 09:45 | 2002-12-03 08:30 | 1.3.2.4 | 7
G0103 | Witter | AUI Address Std - Integration Testing | 100% | 13 h | 13 h | 4 d | 2002-12-03 08:30 | 2002-12-06 16:30 | 1.3.2.5 | 7
G0103 | Witter | AUI VIN Validation - Analysis & Design | 100% | 10 h | 10 h | 2 d | 2002-12-05 08:00 | 2002-12-06 16:30 | 1.3.3.1 | 7
G0103 | Witter | AUI VIN Validation - Coding | 100% | 10 h | 10 h | 7 d | 2002-12-06 16:30 | 2002-12-17 14:45 | 1.3.3.2 | 7
G0103 | Witter | AUI VIN Validation - Unit Test cases/Testing | 100% | 8 h | 8 h | 6 d | 2002-12-10 08:45 | 2002-12-17 16:15 | 1.3.3.3 | 7
G0104 | Witter | AUI -Chgs for NECHO - Analysis & design | 100% | 10 h | 10 h | 4 d | 2002-11-18 13:00 | 2002-11-22 11:00 | 1.4.4.4.1 | 8
G0104 | Witter | AUI - DLV - Analysis & Design | 100% | 20 h | 20 h | 5 d | 2002-11-18 13:00 | 2002-11-25 10:45 | 1.4.4.3.1 | 8
G0104 | Witter | AUI -Chgs for NECHO - Coding | 100% | 20 h | 20 h | 16 d | 2002-11-22 11:00 | 2002-12-17 16:00 | 1.4.4.4.2 | 8
G0104 | Witter | AUI -Chgs for NECHO - Unit Testing | 100% | 10 h | 10 h | 6 d | 2002-12-17 16:00 | 2002-12-26 14:30 | 1.4.4.4.3 | 8
G0104 | Witter | AUI - DLV - Coding | 100% | 80 h | 80 h | 20 d | 2003-01-06 11:45 | 2003-01-31 15:45 | 1.4.4.3.2 | 8
G0104 | Witter | AUI - DLV - Unit Testing | 100% | 50 h | 50 h | 20 d | 2003-01-06 11:45 | 2003-01-31 15:45 | 1.4.4.3.3 | 8
G0104 | Witter | AUI - DLV - RSC Entry | 100% | 2 h | 2 h | 5 d | 2003-01-27 08:30 | 2003-01-31 16:15 | 1.4.4.3.4 | 8
G0104 | Witter | AUI-DLV Web / Mid Tier / Host System Testing (Initial) | 100% | 30 h | 30 h | 15 d | 2003-02-05 16:15 | 2003-02-26 11:30 | 1.4.4.5.3 | 8
G0104 | Witter | Implementation testing execution pkg-2 | 2% | 0 h | 5 h | 31 d | 2003-05-02 08:00 | 2003-06-13 08:15 | 1.4.4.6.3 | 8
G0104 | Witter | AUI Pkg-2 Prep for cowide issaunce | 0% | 20 h | 20 h | 5 d | 2003-06-27 10:15 | 2003-07-04 09:00 | 1.4.4.9.3 | 8
G0106 | Witter | Transition to Service | 0% | 2.61 h | 2.61 h | 20 d | 2003-08-25 08:00 | 2003-09-19 11:00 | 1.6.4 | 10
G0101 |  | MS: Project Activated | 100% | 0 h | 0 h | 0 d | 2002-05-06 08:00 | 2002-05-06 08:00 | 1.1.1
G0101 |  | Prepare & Review Project Charter | 100% | 67 h | 67 h | 35 d | 2002-05-21 08:00 | 2002-07-05 16:15 | 1.1.3.1
G0101 |  | MS: Project Charter Reviewed | 100% | 0 h | 0 h | 0 d | 2002-07-05 16:15 | 2002-07-05 16:15 | 1.1.3.2
G0102 |  | Determine Business Requirements | 100% | 10 h | 10 h | 24 d | 2002-06-13 11:30 | 2002-07-16 14:30 | 1.2.1.1
G0102 |  | Design of New screen(83) | 100% | 20 h | 20 h | 3 d | 2002-07-16 14:30 | 2002-07-19 13:45 | 1.2.1.10.9.1
G0102 |  | Design of New screen(77) | 100% | 20 h | 20 h | 5 d | 2002-07-16 14:30 | 2002-07-23 13:15 | 1.2.1.10.8.1
G0102 |  | Review Testable Business Requirements | 100% | 24 h | 24 h | 1 d | 2002-07-24 13:00 | 2002-07-25 11:45 | 1.2.1.2
G0102 |  | Identify Architectural Constraints - AIP 1.1 | 100% | 20 h | 20 h | 5 d | 2002-07-19 08:00 | 2002-07-25 15:45 | 1.2.3.1.1
G0102 |  | Inventory Development Tools Standards and Procedures - AIP 1.3 | 100% | 4 h | 4 h | 1 d | 2002-07-25 15:45 | 2002-07-26 15:30 | 1.2.3.1.2
G0102 |  | Review Business Requirements | 100% | 8 h | 8 h | 1 d | 2002-07-26 11:30 | 2002-07-29 11:15 | 1.2.1.3
G0102 |  | Identify Existing Network Topology - AIP 1.2 | 100% | 4 h | 4 h | 1 d | 2002-07-26 15:30 | 2002-07-29 15:15 | 1.2.3.1.3
G0102 |  | Inventory Existing Hardware and System Software - AIP 1.4 | 100% | 4 h | 4 h | 1 d | 2002-07-29 15:15 | 2002-07-30 15:00 | 1.2.3.1.4
G0102 |  | R10481 - AIP 1 - Assess Existing Technology Architecture | 100% | 36 h | 36 h | 9 d | 2002-07-19 08:00 | 2002-07-31 14:45 | 1.2.3.1
G0102 |  | Assemble Architecture Assessment - AIP 1.5 | 100% | 4 h | 4 h | 1 d | 2002-07-30 15:00 | 2002-07-31 14:45 | 1.2.3.1.5
G0102 |  | MS: Business Req approved | 100% | 0 h | 0 h | 0 d | 2002-08-01 10:30 | 2002-08-01 10:30 | 1.2.1.4
G0102 |  | Create New ECHO Screen Layout | 100% | 5 h | 5 h | 3 d | 2002-07-29 11:15 | 2002-08-01 10:30 | 1.2.1.6
G0101 |  | Project Schedule Development -1 | 100% | 110 h | 110 h | 60 d | 2002-05-28 08:00 | 2002-08-16 09:00 | 1.1.3.8
G0101 |  | MS: Performance Measurement Baseline - 1 Established | 100% | 0 h | 0 h | 0 d | 2002-08-16 09:00 | 2002-08-16 09:00 | 1.1.3.9
G0102 |  | Understand existing ECHO APPS System | 100% | 240 h | 240 h | 50 d | 2002-06-13 11:30 | 2002-08-20 16:00 | 1.2.1.10.1
G0102 |  | R10481 - AUTO Specs | 100% | 45 h | 45 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 1.2.1.8
G0102 |  | AUTO - review existing territory validation | 100% | 15 h | 15 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 1.2.1.8.1
G0102 |  | AUTO - review existing IRG validation | 100% | 15 h | 15 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 1.2.1.8.2
G0102 |  | AUTO - review existing driver's license validation | 100% | 15 h | 15 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 1.2.1.8.3
G0101 |  | MS: Project Charter Authorized | 100% | 0 h | 0 h | 0 d | 2002-08-30 08:00 | 2002-08-30 08:00 | 1.1.3.3
G0102 |  | DOMAIN - review existing territory validation | 100% | 3 h | 3 h | 24 d | 2002-07-30 11:00 | 2002-08-30 14:00 | 1.2.1.7.1
G0102 |  | DOMAIN - review existing IRG validation | 100% | 3 h | 3 h | 23 d | 2002-07-31 10:45 | 2002-08-30 14:00 | 1.2.1.7.2
G0102 |  | DOMAIN - review existing driver's license validation | 100% | 3 h | 3 h | 23 d | 2002-07-31 10:45 | 2002-08-30 14:00 | 1.2.1.7.3
G0102 |  | Create Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 50 h | 50 h | 32 d | 2002-07-25 11:45 | 2002-09-06 11:45 | 1.2.2.1
G0102 |  | Create Defect Tracking Strategy | 100% | 40 h | 40 h | 10 d | 2002-08-26 08:00 | 2002-09-06 14:30 | 1.2.2.3
G0102 |  | Define Operating Systems - AIP 2.2 | 100% | 10 h | 10 h | 10 d | 2002-08-26 15:00 | 2002-09-09 11:30 | 1.2.3.2.2
G0102 |  | Submit initial IIA questionnaire | 100% | 4 h | 4 h | 1 d | 2002-09-10 11:15 | 2002-09-11 11:00 | 1.2.3.4.1.1
G0102 |  | Review Defect Tracking Strategy | 100% | 10 h | 10 h | 5 d | 2002-09-06 14:30 | 2002-09-13 13:15 | 1.2.2.4
G0102 |  | Analysing the requirements(64) | 100% | 34 h | 34 h | 20 d | 2002-08-05 09:30 | 2002-09-13 13:30 | 1.2.1.10.4.1
G0102 |  | Design Network - AIP 2.1 | 100% | 10 h | 10 h | 10 d | 2002-08-14 08:15 | 2002-09-16 08:57 | 1.2.3.2.1
G0102 |  | Analysis of Flow of Data(84) | 100% | 66 h | 66 h | 32 d | 2002-07-19 13:45 | 2002-09-16 13:45 | 1.2.1.10.9.2
G0102 |  | Analysing the requirements(59) | 100% | 25 h | 25 h | 10 d | 2002-09-03 08:00 | 2002-09-16 14:30 | 1.2.1.10.3.1
G0102 |  | Analysis of Flow of Data(78) | 100% | 25 h | 25 h | 42 d | 2002-07-23 13:15 | 2002-09-18 09:45 | 1.2.1.10.8.2
G0102 |  | R10481 - Engineer for Performance | 100% | 14 h | 14 h | 6 d | 2002-09-10 11:15 | 2002-09-18 09:45 | 1.2.3.4.1
G0102 |  | Infrastructure Impact Assessment - Level 2 review (if necessary) | 100% | 10 h | 10 h | 5 d | 2002-09-11 11:00 | 2002-09-18 09:45 | 1.2.3.4.1.2
G0102 |  | Design the Highlevel Specs-1(85) | 100% | 8 h | 8 h | 24 d | 2002-08-02 10:15 | 2002-09-18 16:15 | 1.2.1.10.9.3
G0101 |  | Facilitation management Processes | 100% | 33 h | 33 h | 55 d | 2002-07-05 16:15 | 2002-09-19 09:30 | 1.1.3.4
G0102 |  | R10481 - Testing Strategy and Test Plans | 100% | 211 h | 111 h | 41.87 d | 2002-07-25 11:45 | 2002-09-20 08:15 | 1.2.2
G0102 |  | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 11 h | 11 h | 31 d | 2002-08-09 08:00 | 2002-09-20 08:15 | 1.2.2.2
G0102 |  | Design the Highlevel Specs-1(60) | 100% | 8 h | 8 h | 4 d | 2002-09-16 14:30 | 2002-09-20 13:30 | 1.2.1.10.3.2
G0102 |  | Analysing the requirements(51) | 100% | 25 h | 25 h | 38 d | 2002-08-02 10:30 | 2002-09-24 09:00 | 1.2.1.10.5.1
G0102 |  | R10481 - Domain Specs | 100% | 13 h | 13 h | 42 d | 2002-07-30 11:00 | 2002-09-25 08:30 | 1.2.1.7
G0102 |  | Create SRA 4/SDS 3.1 identifying impacted reusable service areas | 100% | 4 h | 4 h | 18 d | 2002-08-30 14:00 | 2002-09-25 08:30 | 1.2.1.7.4
G0102 |  | Determine Validation Components for ECHO & AUI | 100% | 48 h | 48 h | 18 d | 2002-08-30 14:00 | 2002-09-25 08:30 | 1.2.1.9
G0102 |  | Define Data Distribution - AIP 2.4 | 100% | 20 h | 20 h | 10 d | 2002-09-09 11:30 | 2002-09-25 08:30 | 1.2.3.2.4
G0102 |  | Define Hardware Configuration - AIP 2.3 | 100% | 20 h | 20 h | 13 d | 2002-09-09 10:12 | 2002-09-25 15:57 | 1.2.3.2.3
G0102 |  | Define Middleware Req. - AIP 2.5 | 100% | 20 h | 20 h | 5 d | 2002-09-19 08:12 | 2002-09-25 15:57 | 1.2.3.2.5
G0102 |  | Submit SFTA Design Review | 100% | 2 h | 2 h | 1 d | 2002-09-25 15:57 | 2002-09-26 15:42 | 1.2.3.4.2.2
G0102 |  | AUI - design address Std | 100% | 25 h | 25 h | 10 d | 2002-09-13 10:30 | 2002-09-26 17:00 | 1.2.1.11.1
G0102 |  | Design the Highlevel Specs-1(65) | 100% | 12 h | 12 h | 11 d | 2002-08-13 08:00 | 2002-09-27 11:56 | 1.2.1.10.4.2
G0102 |  | Design the Highlevel Specs-2(61) | 100% | 15 h | 15 h | 9.1 d | 2002-09-16 14:30 | 2002-09-27 12:00 | 1.2.1.10.3.3
G0102 |  | Assemble information for SFTA review | 100% | 10 h | 10 h | 14 d | 2002-09-10 11:15 | 2002-09-27 16:45 | 1.2.3.4.2.1
G0102 |  | R10481 - VIN Validation | 100% | 56 h | 56 h | 20.1 d | 2002-09-03 08:00 | 2002-09-30 11:45 | 1.2.1.10.3
G0102 |  | Review of Highlevel Specs(62) | 100% | 8 h | 8 h | 1 d | 2002-09-27 13:00 | 2002-09-30 11:45 | 1.2.1.10.3.4
G0102 |  | Analysing the requirements(69) | 100% | 36 h | 36 h | 46 d | 2002-07-29 16:45 | 2002-09-30 13:15 | 1.2.1.10.2.1
G0101 |  | Prepare & review Project Plan | 100% | 38 h | 38 h | 64 d | 2002-07-05 16:15 | 2002-10-01 16:15 | 1.1.3.5
G0101 |  | MS: Project Plan Reviewed | 100% | 0 h | 0 h | 0 d | 2002-10-01 16:15 | 2002-10-01 16:15 | 1.1.3.6
G0102 |  | Define Application Service Distribution - AIP 2.6 | 100% | 20 h | 20 h | 10 d | 2002-09-19 09:30 | 2002-10-02 16:00 | 1.2.3.2.6
G0102 |  | Design the Highlevel Specs(52) | 100% | 58 h | 58 h | 9 d | 2002-09-20 09:30 | 2002-10-04 10:20 | 1.2.1.10.5.2
G0102 |  | Analysing the requirements(73) | 100% | 20 h | 20 h | 15 d | 2002-09-16 08:00 | 2002-10-04 13:15 | 1.2.1.10.6.1
G0101 |  | MS: Project Plan Authorized | 100% | 0 h | 0 h | 0 d | 2002-10-04 15:30 | 2002-10-04 15:30 | 1.1.3.7
G0102 |  | Analysis of Validations(79) | 100% | 32 h | 32 h | 20 d | 2002-08-06 09:45 | 2002-10-07 08:26 | 1.2.1.10.8.3
G0102 |  | R10481 - Driver's Licence Validation | 100% | 91 h | 91 h | 47.43 d | 2002-08-02 10:30 | 2002-10-07 10:05 | 1.2.1.10.5
G0102 |  | Review of Highlevel Specs(53) | 100% | 8 h | 8 h | 1 d | 2002-10-04 10:20 | 2002-10-07 10:05 | 1.2.1.10.5.3
G0102 |  | R10481 - AIP 4 - Validate Technology Architecture | 100% | 36 h | 36 h | 20.83 d | 2002-09-10 11:15 | 2002-10-08 13:42 | 1.2.3.4
G0102 |  | R10481 - SFTA Review | 100% | 22 h | 22 h | 20.83 d | 2002-09-10 11:15 | 2002-10-08 13:42 | 1.2.3.4.2
G0102 |  | SFTA Review process | 100% | 10 h | 10 h | 8 d | 2002-09-26 15:42 | 2002-10-08 13:42 | 1.2.3.4.2.3
G0102 |  | MS: Authorized SFTA documentation | 100% | 0 h | 0 h | 0 d | 2002-10-08 13:42 | 2002-10-08 13:42 | 1.2.3.4.3
G0102 |  | Design the Highlevel Specs-2(66) | 100% | 34 h | 34 h | 10 d | 2002-09-27 11:56 | 2002-10-11 09:26 | 1.2.1.10.4.3
G0102 |  | Analysing the requirements(47) | 100% | 48 h | 48 h | 24 d | 2002-09-10 08:00 | 2002-10-11 10:00 | 1.2.1.10.7.1
G0102 |  | Design the Highlevel Specs(70) | 100% | 44 h | 44 h | 10 d | 2002-09-30 13:15 | 2002-10-14 09:45 | 1.2.1.10.2.2
G0102 |  | Design the Highlevel Specs(48) | 100% | 64 h | 64 h | 10 d | 2002-09-30 13:15 | 2002-10-14 09:45 | 1.2.1.10.7.2
G0102 |  | R10481 - Teritory Validation | 100% | 120 h | 120 h | 26 d | 2002-09-10 08:00 | 2002-10-15 09:30 | 1.2.1.10.7
G0102 |  | Review of Highlevel Specs(49) | 100% | 8 h | 8 h | 1 d | 2002-10-14 09:45 | 2002-10-15 09:30 | 1.2.1.10.7.3
G0102 |  | R10481 - MQseries/EUI Interface. | 100% | 88 h | 88 h | 53.32 d | 2002-08-05 09:30 | 2002-10-15 15:45 | 1.2.1.10.4
G0102 |  | Review of Highlevel Specs(67) | 100% | 8 h | 8 h | 2 d | 2002-10-11 09:26 | 2002-10-15 15:45 | 1.2.1.10.4.4
G0102 |  | R10481 - Address Standradisation- Auto Main Screen | 100% | 88 h | 88 h | 60 d | 2002-07-29 16:45 | 2002-10-18 08:45 | 1.2.1.10.2
G0102 |  | Review of Highlevel Specs(71) | 100% | 8 h | 8 h | 4 d | 2002-10-14 09:45 | 2002-10-18 08:45 | 1.2.1.10.2.3
G0102 |  | Design the Highlevel Specs(74) | 100% | 20 h | 20 h | 10 d | 2002-10-04 13:15 | 2002-10-18 09:45 | 1.2.1.10.6.2
G0102 |  | R10481 - AUI Specs | 100% | 75 h | 75 h | 26 d | 2002-09-13 10:30 | 2002-10-18 12:00 | 1.2.1.11
G0102 |  | AUI - design driver's license validation | 100% | 25 h | 25 h | 16 d | 2002-09-27 08:00 | 2002-10-18 12:00 | 1.2.1.11.2
G0102 |  | AUI - design VIN validation | 100% | 25 h | 25 h | 16 d | 2002-09-27 08:00 | 2002-10-18 12:00 | 1.2.1.11.3
G0103 |  | MS: Pkg -1 work started | 100% | 0 h | 0 h | 0 d | 2002-10-21 08:00 | 2002-10-21 08:00 | 1.3.1
G0103 |  | AUI Address Std - Analysis & Design | 100% | 10 h | 10 h | 3 d | 2002-10-21 08:00 | 2002-10-23 16:15 | 1.3.2.2
G0102 |  | R10481 - Address Standradisation- Residence Address Scrn | 100% | 48 h | 48 h | 29 d | 2002-09-16 08:00 | 2002-10-24 08:45 | 1.2.1.10.6
G0102 |  | Review of Highlevel Specs(75) | 100% | 8 h | 8 h | 4 d | 2002-10-18 09:45 | 2002-10-24 08:45 | 1.2.1.10.6.3
G0104 |  | MS: Pkg -2 work started | 100% | 0 h | 0 h | 0 d | 2002-10-28 08:00 | 2002-10-28 08:00 | 1.4.1
G0105 |  | MS: Pkg -3 work started | 100% | 0 h | 0 h | 0 d | 2002-10-28 08:00 | 2002-10-28 08:00 | 1.5.1
G0103 |  | Pkg-1 Draft Communication | 100% | 10 h | 10 h | 2 d | 2002-10-25 08:00 | 2002-10-28 16:30 | 1.3.8.1
G0102 |  | Design the Highlevel Specs-2(86) | 100% | 28 h | 28 h | 10 d | 2002-10-15 15:45 | 2002-10-29 13:15 | 1.2.1.10.9.4
G0102 |  | R10481 - AUI request Screen | 100% | 132 h | 132 h | 78.26 d | 2002-07-16 14:30 | 2002-10-30 13:00 | 1.2.1.10.9
G0102 |  | Review of Highlevel Specs(87) | 100% | 10 h | 10 h | 1 d | 2002-10-29 13:15 | 2002-10-30 13:00 | 1.2.1.10.9.5
G0102 |  | R10481 - ECHO Specs | 100% | 1,076 h | 988 h | 105.71 d | 2002-06-13 11:30 | 2002-11-04 15:45 | 1.2.1.10
G0102 |  | R10481 - AUI Driver Information Screen | 100% | 125 h | 125 h | 81.71 d | 2002-07-16 14:30 | 2002-11-04 15:45 | 1.2.1.10.8
G0102 |  | Design the Highlevel Specs(80) | 100% | 32 h | 32 h | 8 d | 2002-10-24 08:45 | 2002-11-04 15:45 | 1.2.1.10.8.4
G0102 |  | Review of Highlevel Specs(81) | 100% | 16 h | 16 h | 8 d | 2002-10-24 08:45 | 2002-11-04 15:45 | 1.2.1.10.8.5
G0102 |  | MS: ECHO Specs completed | 100% | 0 h | 0 h | 0 d | 2002-11-04 15:45 | 2002-11-04 15:45 | 1.2.1.10.10
G0103 |  | AUI Address Std - Coding | 100% | 40 h | 40 h | 9 d | 2002-10-23 16:15 | 2002-11-05 14:00 | 1.3.2.3
G0102 |  | Update Delivery Specs Doc | 100% | 20 h | 20 h | 1 d | 2002-11-04 15:45 | 2002-11-05 15:30 | 1.2.1.12
G0103 |  | NECHO VIN Validation - Analysis (TSD3.2) | 100% | 10 h | 10 h | 2 d | 2002-11-04 08:00 | 2002-11-05 16:30 | 1.3.5.1
G0102 |  | Review SDS Doc | 100% | 15 h | 15 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 1.2.1.13
G0103 |  | NECHO -DLV - Design Low level Specs (TSD3.2) | 100% | 20 h | 20 h | 3 d | 2002-11-04 08:00 | 2002-11-06 16:15 | 1.3.4.1
G0103 |  | NECHO VIN Validation - Analysis (TSD8.3) | 100% | 15 h | 15 h | 2 d | 2002-11-05 16:30 | 2002-11-07 16:00 | 1.3.5.2
G0102 |  | Technical discussion meetings | 100% | 480 h | 480 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 1.2.1.5
G0103 |  | NECHO VIN Validation - Coding | 100% | 15 h | 15 h | 2 d | 2002-11-07 16:00 | 2002-11-11 15:30 | 1.3.5.3
G0103 |  | NECHO -DLV - Design Test Cases (TSD8.3) | 100% | 40 h | 40 h | 6 d | 2002-11-06 16:15 | 2002-11-14 14:45 | 1.3.4.2
G0101 |  | Project Schedule Development -2 | 100% | 110 h | 110 h | 43 d | 2002-09-18 16:15 | 2002-11-15 13:30 | 1.1.3.10
G0103 |  | Pkg-1 Communication Review by Proj Team | 100% | 5 h | 5 h | 14 d | 2002-10-29 08:00 | 2002-11-15 13:30 | 1.3.8.2
G0103 |  | Establish Test Environment Needs - Pkg-1 | 100% | 10 h | 10 h | 2 d | 2002-11-13 16:45 | 2002-11-15 16:15 | 1.3.7.1
G0103 |  | Establish Test Environment - Pkg-1 | 100% | 20 h | 20 h | 5 d | 2002-11-11 08:30 | 2002-11-15 16:15 | 1.3.7.2
G0104 |  | DLV - Mid Tier - Logical Design Interface | 100% | 24 h | 24 h | 5 d | 2002-11-04 15:30 | 2002-11-18 14:15 | 1.4.4.1.2
G0105 |  | MQ Q/A High Level Review (req’d objects id’d) | 100% | 20 h | 20 h | 17 d | 2002-10-28 08:00 | 2002-11-19 11:45 | 1.5.2.2.1.1
G0102 |  | R10481 - SRA / SDS | 100% | 1,848 h | 1,731 h | 119.29 d | 2002-06-13 11:30 | 2002-11-22 08:00 | 1.2.1
G0102 |  | MS: SDS Doc Authorized | 100% | 0 h | 0 h | 0 d | 2002-11-22 08:00 | 2002-11-22 08:00 | 1.2.1.14
G0104 |  | AUI -Chgs for NECHO - Analysis & design | 100% | 10 h | 10 h | 4 d | 2002-11-18 13:00 | 2002-11-22 11:00 | 1.4.4.4.1
G0105 |  | R10481 - TSD 3.2 phase doc | 100% | 55 h | 55 h | 20 d | 2002-10-28 08:00 | 2002-11-22 11:00 | 1.5.2.2.1
G0105 |  | MQ design Infra Diagram (message flow) | 100% | 30 h | 30 h | 14 d | 2002-11-04 15:30 | 2002-11-22 11:00 | 1.5.2.2.1.2
G0105 |  | MQ Q/A Detail Level Review (design Walkthrough) | 100% | 5 h | 5 h | 5 d | 2002-11-15 13:15 | 2002-11-22 11:00 | 1.5.2.2.1.3
G0103 |  | NECHO - DLV - Coding | 100% | 30 h | 30 h | 6 d | 2002-11-14 14:45 | 2002-11-22 13:15 | 1.3.4.3
G0104 |  | DLV - Host - Physical Design Interface | 100% | 20 h | 20 h | 4 d | 2002-11-18 14:15 | 2002-11-22 13:15 | 1.4.4.2.3
G0104 |  | DLV - Mid Tier - Logical Design Interface Walkthrough | 100% | 9 h | 9 h | 4 d | 2002-11-19 08:00 | 2002-11-22 16:00 | 1.4.4.1.3
G0104 |  | AUI - DLV - Analysis & Design | 100% | 20 h | 20 h | 5 d | 2002-11-18 13:00 | 2002-11-25 10:45 | 1.4.4.3.1
G0102 |  | Define Security Infrastructure - AIP 2.7 | 100% | 20 h | 20 h | 41 d | 2002-10-02 16:00 | 2002-11-29 13:45 | 1.2.3.2.7
G0103 |  | Pkg-1 UPD Walkthrough with SPIP group | 100% | 5 h | 5 h | 8 d | 2002-11-18 08:00 | 2002-11-29 15:00 | 1.3.8.3
G0104 |  | DLV - Host - Physical Design Interface Walkthrough | 100% | 6 h | 6 h | 2 d | 2002-11-26 08:00 | 2002-11-29 16:30 | 1.4.4.2.4
G0103 |  | NECHO -DLV - Unit Testing | 100% | 29 h | 29 h | 9 d | 2002-11-15 14:30 | 2002-12-02 11:15 | 1.3.4.4
G0103 |  | AUI Address Std - RSC Entry | 100% | 2 h | 2 h | 5 d | 2002-11-22 09:45 | 2002-12-03 08:30 | 1.3.2.1
G0103 |  | AUI Address Std - Unit Test Cases/Testing | 100% | 20 h | 20 h | 5 d | 2002-11-22 09:45 | 2002-12-03 08:30 | 1.3.2.4
G0103 |  | Pkg-1 - Review NECHO Tech System Design - TSD 9.2 | 100% | 10 h | 10 h | 5 d | 2002-11-22 13:15 | 2002-12-03 11:00 | 1.3.6.2
G0102 |  | R10481 - Reqs Analysis and Solution Def/Specs | 100% | 2,271 h | 2,054 h | 126 d | 2002-06-13 11:30 | 2002-12-04 13:00 | 1.2
G0102 |  | R10481 - AIP | 100% | 212 h | 212 h | 99.61 d | 2002-07-19 08:00 | 2002-12-04 13:00 | 1.2.3
G0102 |  | R10481 - AIP 2 - Design Technology Architecture | 100% | 140 h | 140 h | 81 d | 2002-08-14 08:15 | 2002-12-04 13:00 | 1.2.3.2
G0102 |  | Define System Topology - AIP 2.8 | 100% | 20 h | 20 h | 5 d | 2002-11-08 08:15 | 2002-12-04 13:00 | 1.2.3.2.8
G0102 |  | MS: Technology Architecture Documentation complete | 100% | 0 h | 0 h | 0 d | 2002-12-04 13:00 | 2002-12-04 13:00 | 1.2.3.3
G0105 |  | SRA 4.2 Establish Security and Control, Requirements | 100% | 6 h | 6 h | 23 d | 2002-11-01 08:00 | 2002-12-05 10:15 | 1.5.2.1.1
G0103 |  | R10481 - AUI Address Std (TSD/TPD/UPD) | 100% | 85 h | 85 h | 34 d | 2002-10-21 08:00 | 2002-12-06 16:30 | 1.3.2
G0103 |  | AUI Address Std - Integration Testing | 100% | 13 h | 13 h | 4 d | 2002-12-03 08:30 | 2002-12-06 16:30 | 1.3.2.5
G0103 |  | AUI VIN Validation - Analysis & Design | 100% | 10 h | 10 h | 2 d | 2002-12-05 08:00 | 2002-12-06 16:30 | 1.3.3.1
G0105 |  | Auto Apps - Main Program - TSD 3.2 | 100% | 40 h | 40 h | 17 d | 2002-11-13 08:00 | 2002-12-09 11:45 | 1.5.2.4.8
G0103 |  | Create Acceptance Test Cases - Pkg-1 | 100% | 10 h | 10 h | 2 d | 2002-12-06 16:30 | 2002-12-10 16:00 | 1.3.7.3
G0104 |  | DLV - Host - Develop Design Specs | 100% | 30 h | 30 h | 25 d | 2002-11-04 16:45 | 2002-12-11 09:30 | 1.4.4.2.2
G0104 |  | DLV - Host - Design Specs Walkthrough | 100% | 6 h | 6 h | 1 d | 2002-12-12 08:00 | 2002-12-12 16:45 | 1.4.4.2.5
G0105 |  | AUI Request Vehicle Information Screen - TSD 3.2 | 100% | 50 h | 50 h | 12 d | 2002-11-25 13:00 | 2002-12-13 09:00 | 1.5.2.4.2
G0101 |  | R10481 - Project Charter, Plan & Schedule | 100% | 358 h | 358 h | 151.74 d | 2002-05-21 08:00 | 2002-12-16 08:00 | 1.1.3
G0101 |  | MS: Performance Measurement Baseline - 2 Established | 100% | 0 h | 0 h | 0 d | 2002-12-16 08:00 | 2002-12-16 08:00 | 1.1.3.11
G0103 |  | R10481 - NECHO VIN Validation (TSD/TPD/UPD) | 100% | 50 h | 50 h | 29 d | 2002-11-04 08:00 | 2002-12-16 08:45 | 1.3.5
G0103 |  | NECHO VIN Validation - Unit Testing | 100% | 10 h | 10 h | 23 d | 2002-11-11 15:30 | 2002-12-16 08:45 | 1.3.5.4
G0103 |  | AUI VIN Validation - Coding | 100% | 10 h | 10 h | 7 d | 2002-12-06 16:30 | 2002-12-17 14:45 | 1.3.3.2
G0104 |  | AUI -Chgs for NECHO - Coding | 100% | 20 h | 20 h | 16 d | 2002-11-22 11:00 | 2002-12-17 16:00 | 1.4.4.4.2
G0103 |  | R10481 - AUI VIN Validation (TSD/TPD/UPD) | 100% | 28 h | 28 h | 9.19 d | 2002-12-05 08:00 | 2002-12-17 16:15 | 1.3.3
G0103 |  | AUI VIN Validation - Unit Test cases/Testing | 100% | 8 h | 8 h | 6 d | 2002-12-10 08:45 | 2002-12-17 16:15 | 1.3.3.3
G0104 |  | DLV - Mid Tier - Coding | 100% | 60 h | 60 h | 18 d | 2002-11-22 16:00 | 2002-12-20 10:30 | 1.4.4.1.4
G0104 |  | DLV - Mid Tier - Code Walk Through | 100% | 6 h | 6 h | 14 d | 2002-11-28 15:00 | 2002-12-20 10:30 | 1.4.4.1.5
G0103 |  | R10481 - Pkg-1 Consolidated Tech Doc | 100% | 16 h | 16 h | 18.68 d | 2002-11-22 13:15 | 2002-12-20 14:00 | 1.3.6
G0103 |  | Pkg-1 - Review AUI Tech System Design - TSD 9.2 | 100% | 3 h | 3 h | 3 d | 2002-12-17 14:45 | 2002-12-20 14:00 | 1.3.6.1
G0103 |  | Pkg-1 - Review Consolidated Tech Doc - TPD 7.1 | 100% | 3 h | 3 h | 2 d | 2002-12-18 14:30 | 2002-12-20 14:00 | 1.3.6.3
G0104 |  | DLV - Host - Code/Gen IMS transaction | 100% | 50 h | 50 h | 6 d | 2002-12-12 16:45 | 2002-12-20 15:15 | 1.4.4.2.6
G0104 |  | DLV - Host - Code Wrapper | 100% | 50 h | 50 h | 6 d | 2002-12-12 16:45 | 2002-12-20 15:15 | 1.4.4.2.7
G0104 |  | DLV - Host - Code Walkthrough | 100% | 6 h | 6 h | 3 d | 2002-12-17 16:00 | 2002-12-20 15:15 | 1.4.4.2.8
G0104 |  | DLV - Mid Tier - Unit Test Review | 100% | 20 h | 20 h | 16 d | 2002-11-28 15:00 | 2002-12-20 16:15 | 1.4.4.1.6
G0104 |  | DLV - Mid Tier - Unit Testing | 100% | 6 h | 6 h | 16 d | 2002-11-28 15:00 | 2002-12-20 16:15 | 1.4.4.1.7
G0103 |  | AUI Acceptance Testing - Pkg-1 | 100% | 29 h | 29 h | 4 d | 2002-12-17 16:15 | 2002-12-23 15:15 | 1.3.7.4
G0105 |  | MQ - Interface module - TSD 3.2 | 100% | 30 h | 30 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 1.5.2.4.3
G0105 |  | Incoming Interface - TSD 3.2 | 100% | 20 h | 20 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 1.5.2.4.4
G0105 |  | Build Auto App Program - TSD 3.2 | 100% | 20 h | 20 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 1.5.2.4.6
G0105 |  | Warning Screen - TSD 3.2 | 100% | 20 h | 20 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 1.5.2.4.7
G0105 |  | Residence Address screen - TSD 3.2 | 100% | 20 h | 20 h | 27 d | 2002-11-13 15:00 | 2002-12-23 16:15 | 1.5.2.4.9
G0105 |  | Territory Validation (Options screen) - TSD 3.2 | 100% | 30 h | 30 h | 19 d | 2002-11-25 13:00 | 2002-12-23 16:15 | 1.5.2.4.11
G0105 |  | Outgoing Interface - TSD 3.2 | 100% | 20 h | 20 h | 16 d | 2002-12-03 11:00 | 2002-12-24 16:00 | 1.5.2.4.5
G0105 |  | AUI Request Driver Information Screen - TSD 3.2 | 100% | 50 h | 50 h | 20 d | 2002-11-25 13:00 | 2002-12-24 16:00 | 1.5.2.4.10
G0105 |  | Pf Key format /Branching Program (PCS5F) - TSD 3.2 | 100% | 20 h | 20 h | 20 d | 2002-11-25 13:00 | 2002-12-24 16:00 | 1.5.2.4.12
G0104 |  | AUI -Chgs for NECHO - Unit Testing | 100% | 10 h | 10 h | 6 d | 2002-12-17 16:00 | 2002-12-26 14:30 | 1.4.4.4.3
G0105 |  | Host Addr Std/ terr-analysis | 100% | 20 h | 20 h | 30 d | 2002-11-12 16:45 | 2002-12-27 08:15 | 1.5.2.3.1
G0104 |  | Establish Test Environment needs | 100% | 10 h | 10 h | 3 d | 2002-12-23 16:15 | 2002-12-27 15:30 | 1.4.3.1
G0103 |  | MS: Pkg-1 Create Agency pilot communications | 100% | 0 h | 0 h | 0 d | 2002-12-30 15:15 | 2002-12-30 15:15 | 1.3.8.4
G0103 |  | Pkg-1 Publish Communication | 100% | 5 h | 5 h | 5 d | 2002-12-27 08:30 | 2003-01-02 16:15 | 1.3.8.8
G0101 |  | Create Initial SPIP Participant Charts | 100% | 20 h | 20 h | 86 d | 2002-09-06 08:00 | 2003-01-06 10:30 | 1.1.4.1
G0104 |  | R10481 - Pkg-2 Consolidated Tech Doc | 100% | 6 h | 6 h | 8 d | 2002-12-24 15:45 | 2003-01-06 13:45 | 1.4.4.7
G0104 |  | AUI - DLV - Review Technical System Design - TSD 9.2 | 100% | 3 h | 3 h | 8 d | 2002-12-24 15:45 | 2003-01-06 13:45 | 1.4.4.7.1
G0104 |  | Pkg-2 - Review AUI Technical System Design - TSD 9.2 | 100% | 3 h | 3 h | 8 d | 2002-12-24 15:45 | 2003-01-06 13:45 | 1.4.4.7.2
G0103 |  | Create Acceptance Test Summary Report - Pkg-1 | 100% | 10 h | 10 h | 9 d | 2002-12-23 16:15 | 2003-01-06 14:00 | 1.3.7.7
G0103 |  | MS: Pkg-1 Publish Agency pilot communications | 100% | 0 h | 0 h | 0 d | 2003-01-06 14:00 | 2003-01-06 14:00 | 1.3.8.5
G0104 |  | Determine FIT Test Environment Needs | 100% | 20 h | 20 h | 9 d | 2002-12-23 16:15 | 2003-01-06 14:00 | 1.4.3.4
G0103 |  | NECHO Acceptance Testing - Pkg-1 | 100% | 30 h | 30 h | 21 d | 2002-12-09 10:00 | 2003-01-07 13:45 | 1.3.7.5
G0103 |  | MS: Pkg-1 Create Agency cowide communications | 100% | 0 h | 0 h | 0 d | 2003-01-07 13:45 | 2003-01-07 13:45 | 1.3.8.6
G0103 |  | Necho Pkg-1 Prep for pilot issuance | 100% | 10 h | 10 h | 2 d | 2003-01-03 14:15 | 2003-01-07 13:45 | 1.3.9.1
G0103 |  | MS: Pkg-1 Pilot Necho | 100% | 0 h | 0 h | 0 d | 2003-01-07 13:45 | 2003-01-07 13:45 | 1.3.9.2
G0105 |  | MQ Objects on Dev Host (coding) | 100% | 10 h | 10 h | 7 d | 2002-12-30 14:00 | 2003-01-08 11:15 | 1.5.2.2.2.1
G0103 |  | MS: Pkg-1 SAT Completed | 100% | 0 h | 0 h | 0 d | 2003-01-08 13:30 | 2003-01-08 13:30 | 1.3.7.6
G0105 |  | Build Auto App Program - TSD 8.3 | 100% | 20 h | 20 h | 11 d | 2002-12-27 08:00 | 2003-01-10 14:15 | 1.5.2.4.18
G0103 |  | R10481 - Pkg -1 Systems Acceptance Test (SAT) | 100% | 174 h | 129 h | 43.77 d | 2002-11-11 08:30 | 2003-01-13 11:45 | 1.3.7
G0103 |  | Review / Authorize Acceptance Test Summary Report - Pkg-1 | 100% | 20 h | 20 h | 5 d | 2003-01-06 14:00 | 2003-01-13 11:45 | 1.3.7.8
G0104 |  | DLV - Host - Unit test IMS transaction | 100% | 50 h | 50 h | 16 d | 2002-12-20 15:15 | 2003-01-14 10:15 | 1.4.4.2.9
G0104 |  | DLV - Host - Unit test Wrapper | 100% | 50 h | 50 h | 16 d | 2002-12-20 15:15 | 2003-01-14 10:15 | 1.4.4.2.10
G0103 |  | R10481 - Pkg -1 Communication | 100% | 25 h | 25 h | 56.19 d | 2002-10-25 08:00 | 2003-01-14 11:30 | 1.3.8
G0103 |  | MS: Pkg-1 Publish Agency cowide communications | 100% | 0 h | 0 h | 0 d | 2003-01-14 11:30 | 2003-01-14 11:30 | 1.3.8.7
G0105 |  | MQ Create Host Test Cases | 100% | 10 h | 10 h | 5 d | 2003-01-08 11:15 | 2003-01-15 10:00 | 1.5.2.2.2.2
G0104 |  | DLV - Host - Review Test Results | 100% | 6 h | 6 h | 3 d | 2003-01-14 10:15 | 2003-01-17 09:30 | 1.4.4.2.11
G0104 |  | Set-up AUI Integration/System Test Environment | 100% | 20 h | 20 h | 18 d | 2002-12-23 16:15 | 2003-01-17 10:45 | 1.4.3.2
G0104 |  | Set-up NECHO Integration/System Test Environment | 100% | 20 h | 20 h | 18 d | 2002-12-23 16:15 | 2003-01-17 10:45 | 1.4.3.3
G0104 |  | DLV - Host - Security Analyst Setup | 100% | 10 h | 10 h | 5 d | 2003-01-10 13:00 | 2003-01-17 10:45 | 1.4.4.2.12
G0104 |  | DLV - Host - AUI/DLV Security -NT | 100% | 20 h | 20 h | 11 d | 2002-12-31 13:45 | 2003-01-17 10:45 | 1.4.4.2.13
G0105 |  | Warning Screen - TSD 8.3 | 100% | 20 h | 20 h | 15 d | 2002-12-27 15:30 | 2003-01-17 10:45 | 1.5.2.4.19
G0104 |  | AUI - Create AUI System Test Plan | 100% | 20 h | 20 h | 10 d | 2003-01-06 08:00 | 2003-01-17 14:30 | 1.4.4.5.1
G0104 |  | R10481 - DLV - Mid Tier(TSD/TPD/UPD) | 100% | 129 h | 129 h | 52.71 d | 2002-11-04 15:30 | 2003-01-17 16:00 | 1.4.4.1
G0104 |  | DLV - Mid Tier - RSC Entry | 100% | 4 h | 4 h | 36 d | 2002-11-28 08:00 | 2003-01-17 16:00 | 1.4.4.1.1
G0104 |  | DLV - Host RSC Entry | 100% | 4 h | 4 h | 11 d | 2003-01-06 08:00 | 2003-01-20 14:15 | 1.4.4.2.1
G0105 |  | R10481 - TSD 8.3 phase doc | 100% | 30 h | 30 h | 17 d | 2002-12-30 14:00 | 2003-01-22 08:45 | 1.5.2.2.2
G0105 |  | MQ Execute & Doc Host Test Cases | 100% | 10 h | 10 h | 5 d | 2003-01-15 10:00 | 2003-01-22 08:45 | 1.5.2.2.2.3
G0105 |  | NECHO - all Remaining Changes - Review TSD 3.2 Docs | 100% | 12 h | 12 h | 18 d | 2002-12-27 15:30 | 2003-01-22 10:00 | 1.5.2.4.13
G0105 |  | AUI Request Vehicle Information Screen - TSD 8.3 | 100% | 60 h | 60 h | 18 d | 2002-12-27 15:30 | 2003-01-22 10:00 | 1.5.2.4.14
G0105 |  | SDS 5.2 Specify Security and Control Requirements | 100% | 15 h | 15 h | 26 d | 2002-12-19 08:00 | 2003-01-24 09:30 | 1.5.2.1.2
G0105 |  | Territory Validation (Options screen) - TSD 8.3 | 100% | 30 h | 30 h | 20 d | 2002-12-27 15:30 | 2003-01-24 09:30 | 1.5.2.4.20
G0105 |  | Pf Key format /Branching Program (PCS5F) - TSD 8.3 | 100% | 20 h | 20 h | 20 d | 2002-12-27 15:30 | 2003-01-24 09:30 | 1.5.2.4.21
G0105 |  | Residence Address screen - TSD 8.3 | 100% | 30 h | 30 h | 20 d | 2002-12-27 15:30 | 2003-01-24 09:30 | 1.5.2.4.23
G0104 |  | Build Test Ids/Rules | 100% | 10 h | 10 h | 26 d | 2002-12-19 14:45 | 2003-01-24 16:15 | 1.4.2.2
G0105 |  | Outgoing Interface - TSD 8.3 | 100% | 20 h | 20 h | 21 d | 2002-12-27 15:30 | 2003-01-27 09:15 | 1.5.2.4.17
G0103 |  | R10481 - NECHO DLV (TSD/TPD/UPD) | 100% | 121 h | 121 h | 59.84 d | 2002-11-04 08:00 | 2003-01-27 16:45 | 1.3.4
G0103 |  | NECHO DLV - RSC Entry | 100% | 2 h | 2 h | 1 d | 2003-01-27 08:00 | 2003-01-27 16:45 | 1.3.4.5
G0103 |  | MS: NECHO Pkg-1 cowide Issuance | 100% | 0 h | 0 h | 0 d | 2003-01-28 09:00 | 2003-01-28 09:00 | 1.3.9.3
G0105 |  | MQ - Interface module - TSD 8.3 | 100% | 30 h | 30 h | 24 d | 2002-12-27 15:30 | 2003-01-30 08:30 | 1.5.2.4.15
G0105 |  | Incoming Interface - TSD 8.3 | 100% | 20 h | 20 h | 24 d | 2002-12-27 15:30 | 2003-01-30 08:30 | 1.5.2.4.16
G0105 |  | AUI Request Driver Information Screen - TSD 8.3 | 100% | 60 h | 60 h | 24 d | 2002-12-27 15:30 | 2003-01-30 08:30 | 1.5.2.4.24
G0105 |  | Auto Apps - Main Program - TSD 8.3 | 100% | 40 h | 40 h | 20 d | 2002-12-27 15:30 | 2003-01-31 08:15 | 1.5.2.4.22
G0104 |  | AUI - DLV - Coding | 100% | 80 h | 80 h | 20 d | 2003-01-06 11:45 | 2003-01-31 15:45 | 1.4.4.3.2
G0104 |  | AUI - DLV - Unit Testing | 100% | 50 h | 50 h | 20 d | 2003-01-06 11:45 | 2003-01-31 15:45 | 1.4.4.3.3
G0104 |  | Create production ids/rules | 100% | 10 h | 10 h | 20 d | 2003-01-06 13:15 | 2003-01-31 16:15 | 1.4.2.3
G0104 |  | R10481 - AUI - DLV (TSD/TPD/UPD) | 100% | 152 h | 152 h | 53.06 d | 2002-11-18 13:00 | 2003-01-31 16:15 | 1.4.4.3
G0104 |  | AUI - DLV - RSC Entry | 100% | 2 h | 2 h | 5 d | 2003-01-27 08:30 | 2003-01-31 16:15 | 1.4.4.3.4
G0104 |  | AUI-DLV Mid Tier / Host Int Test | 100% | 60 h | 60 h | 14 d | 2003-01-17 10:45 | 2003-02-05 16:15 | 1.4.4.5.2
G0105 |  | NECHO - all Remaining Changes - Review TSD 8.3 Docs | 100% | 8 h | 8 h | 4 d | 2003-01-31 08:15 | 2003-02-05 16:15 | 1.5.2.4.25
G0105 |  | R10481 - Security Support - Sushit | 100% | 31 h | 31 h | 69.19 d | 2002-11-01 08:00 | 2003-02-07 08:15 | 1.5.2.1
G0105 |  | Build Test Ids/Rules | 100% | 10 h | 10 h | 31 d | 2002-12-27 08:00 | 2003-02-07 08:15 | 1.5.2.1.3
G0104 |  | R10481 - DLV - Host - (TSD/TPD/UPD) | 100% | 316 h | 316 h | 68 d | 2002-11-04 16:45 | 2003-02-07 15:45 | 1.4.4.2
G0104 |  | DLV - Host - Mid Tier /Host Integration Test Reveiew | 100% | 8 h | 8 h | 2 d | 2003-02-05 16:15 | 2003-02-07 15:45 | 1.4.4.2.14
G0105 |  | Auto Apps - Main Program - Coding | 100% | 60 h | 60 h | 8 d | 2003-02-03 08:00 | 2003-02-12 15:00 | 1.5.2.6.13
G0105 |  | Auto Apps - Main Program - UT/IT | 100% | 60 h | 60 h | 8 d | 2003-02-03 08:00 | 2003-02-12 15:00 | 1.5.2.6.14
G0103 |  | R10481 - Pkg -1 Design/Build/Test/Implement | 100% | 554 h | 479 h | 84.29 d | 2002-10-21 08:00 | 2003-02-14 14:15 | 1.3
G0103 |  | R10481 - Pkg -1 Implementation | 100% | 55 h | 25 h | 30.97 d | 2003-01-03 14:15 | 2003-02-14 14:15 | 1.3.9
G0103 |  | Pkg 1-Post implementation questions | 100% | 25 h | 15 h | 11 d | 2003-01-31 08:00 | 2003-02-14 14:15 | 1.3.9.4
G0103 |  | MS: Pkg-1 Implemented | 100% | 0 h | 0 h | 0 d | 2003-02-14 14:15 | 2003-02-14 14:15 | 1.3.9.5
G0105 |  | AUI Request Vehicle Information Screen - Coding | 100% | 80 h | 80 h | 10 d | 2003-02-03 08:00 | 2003-02-14 14:30 | 1.5.2.6.1
G0105 |  | AUI Request Vehicle Information Screen - UT/IT | 100% | 80 h | 80 h | 10 d | 2003-02-03 08:00 | 2003-02-14 14:30 | 1.5.2.6.2
G0104 |  | AUI-DLV Acceptance Test Cases developed | 100% | 20 h | 20 h | 4 d | 2003-02-11 08:15 | 2003-02-14 16:15 | 1.4.4.5.4
G0104 |  | Pkg-2 Draft Communication | 100% | 10 h | 10 h | 1 d | 2003-02-17 08:00 | 2003-02-17 16:45 | 1.4.4.8.1
G0105 |  | SAT - Create System/Acceptance Test Plan | 100% | 20 h | 20 h | 10 d | 2003-02-05 16:15 | 2003-02-19 13:45 | 1.5.4.1
G0105 |  | SAT - Create NECHO System/Acceptance Test Plan | 100% | 20 h | 20 h | 34 d | 2003-01-06 14:00 | 2003-02-20 13:30 | 1.5.4.7.1
G0104 |  | Pkg-2 Communication Review by Proj Team | 100% | 5 h | 5 h | 5 d | 2003-02-17 16:45 | 2003-02-24 15:30 | 1.4.4.8.2
G0104 |  | AUI-DLV Web / Mid Tier / Host System Testing (Initial) | 100% | 80 h | 80 h | 15 d | 2003-02-05 16:15 | 2003-02-26 11:30 | 1.4.4.5.3
G0105 |  | Residence Address screen - Coding | 100% | 40 h | 40 h | 10 d | 2003-02-12 15:00 | 2003-02-26 11:30 | 1.5.2.6.15
G0105 |  | Residence Address screen - UT/IT | 100% | 40 h | 40 h | 10 d | 2003-02-12 15:00 | 2003-02-26 11:30 | 1.5.2.6.16
G0104 |  | Pkg-2 UPD Walkthrough with SPIP group | 100% | 5 h | 5 h | 4 d | 2003-02-24 15:30 | 2003-02-28 14:30 | 1.4.4.8.3
G0104 |  | R10481 - Security Support - David | 100% | 25 h | 35 h | 51.77 d | 2002-12-19 14:45 | 2003-02-28 16:00 | 1.4.2
G0104 |  | SDS 5.2 Specify Security and Control Requirements | 100% | 15 h | 15 h | 36 d | 2003-01-13 08:00 | 2003-02-28 16:00 | 1.4.2.1
G0105 |  | Incoming Interface - Coding | 100% | 30 h | 30 h | 4 d | 2003-03-07 09:45 | 2003-03-13 08:45 | 1.5.2.6.5
G0105 |  | Incoming Interface - UT/IT | 100% | 30 h | 30 h | 4 d | 2003-03-07 09:45 | 2003-03-13 08:45 | 1.5.2.6.6
G0105 |  | AUI Request Driver Information Screen - Coding | 100% | 80 h | 80 h | 15 d | 2003-02-26 11:30 | 2003-03-18 16:45 | 1.5.2.6.17
G0105 |  | Territory Validation (Options screen) - Coding | 100% | 60 h | 60 h | 8 d | 2003-03-14 08:00 | 2003-03-25 15:00 | 1.5.2.6.19
G0105 |  | Pf Key format /Branching Program (PCS5F) - Coding | 100% | 20 h | 20 h | 11 d | 2003-03-14 08:00 | 2003-03-28 14:15 | 1.5.2.6.21
G0105 |  | AUI Request Driver Information Screen - UT/IT | 100% | 80 h | 80 h | 23 d | 2003-02-26 11:30 | 2003-03-28 14:45 | 1.5.2.6.18
G0104 |  | R10481 - AUI -Chgs for NECHO (TSD/TPD/UPD) | 100% | 40 h | 115 h | 94.35 d | 2002-11-18 13:00 | 2003-03-28 16:15 | 1.4.4.4
G0104 |  | MVR Message Chnages - Coding/UT | 100% | 0 h | 75 h | 14 d | 2003-03-11 10:45 | 2003-03-28 16:15 | 1.4.4.4.4
G0105 |  | Territory Validation (Options screen) - UT/IT | 100% | 60 h | 60 h | 15 d | 2003-03-14 08:00 | 2003-04-03 13:15 | 1.5.2.6.20
G0105 |  | Pf Key format /Branching Program (PCS5F) - UT/IT | 100% | 40 h | 40 h | 4 d | 2003-03-28 14:15 | 2003-04-03 13:15 | 1.5.2.6.22
G0105 |  | Driver Info warning Screen - Analysis TSD 3.2, TSD 8.3 | 100% | 0 h | 24 h | 3 d | 2003-04-01 08:00 | 2003-04-03 16:15 | 1.5.2.4.26
G0105 |  | SAT - Create System/Acceptance Test Cases | 100% | 40 h | 40 h | 31 d | 2003-02-21 08:00 | 2003-04-04 08:15 | 1.5.4.2
G0104 |  | R10481 - AUI -DLV Int Testing | 100% | 210 h | 230 h | 66.84 d | 2003-01-06 08:00 | 2003-04-04 15:00 | 1.4.4.5
G0104 |  | AUI-DLV Web / Mid Tier / Host System Testing (Additional) | 100% | 0 h | 20 h | 5 d | 2003-03-28 16:15 | 2003-04-04 15:00 | 1.4.4.5.5
G0104 |  | AUI-DLV Acceptance Testing | 100% | 30 h | 30 h | 28.19 d | 2003-02-26 11:30 | 2003-04-04 15:00 | 1.4.4.5.6
G0105 |  | MQ Q/A App Code walkthrough | 100% | 20 h | 20 h | 9 d | 2003-03-26 08:00 | 2003-04-07 14:45 | 1.5.2.2.3.2
G0105 |  | MQ - Interface module - Coding | 100% | 50 h | 50 h | 38 d | 2003-02-14 14:30 | 2003-04-08 12:00 | 1.5.2.6.3
G0105 |  | MQ - Interface module - UT/IT | 100% | 40 h | 40 h | 38 d | 2003-02-14 14:30 | 2003-04-08 12:00 | 1.5.2.6.4
G0105 |  | Build Auto App Program - Coding | 100% | 40 h | 40 h | 19 d | 2003-03-13 08:45 | 2003-04-08 12:00 | 1.5.2.6.7
G0105 |  | Build Auto App Program - UT/IT | 100% | 40 h | 40 h | 19 d | 2003-03-13 08:45 | 2003-04-08 12:00 | 1.5.2.6.8
G0105 |  | Warning Screen - Coding | 100% | 30 h | 30 h | 13 d | 2003-03-24 08:00 | 2003-04-09 13:45 | 1.5.2.6.9
G0105 |  | Warning Screen - UT/IT | 100% | 30 h | 30 h | 13 d | 2003-03-24 08:00 | 2003-04-09 13:45 | 1.5.2.6.10
G0105 |  | Outgoing Interface - Coding | 100% | 30 h | 30 h | 5 d | 2003-04-03 08:15 | 2003-04-09 16:00 | 1.5.2.6.11
G0105 |  | Outgoing Interface - UT/IT | 100% | 30 h | 30 h | 5 d | 2003-04-03 08:15 | 2003-04-09 16:00 | 1.5.2.6.12
G0105 |  | MQ Support NECHO Unit Testing | 100% | 20 h | 20 h | 35 d | 2003-02-24 10:45 | 2003-04-11 10:00 | 1.5.2.2.3.1
G0104 |  | Setup Perf. Testing Pkg-2 | 100% | 20 h | 20 h | 28 d | 2003-03-05 11:45 | 2003-04-11 13:45 | 1.4.4.6.1
G0105 |  | R10481 - NECHO - all Remaining Changes -(TPD) | 100% | 1,050 h | 1,082 h | 51.32 d | 2003-02-03 08:00 | 2003-04-11 14:45 | 1.5.2.6
G0105 |  | Driver Info warning Screen -Coding, UT/IT | 100% | 0 h | 32 h | 6 d | 2003-04-03 16:15 | 2003-04-11 14:45 | 1.5.2.6.23
G0105 |  | MS: NECHO - all Remaining Changes -Coding/UT/IT completed | 100% | 0 h | 0 h | 0 d | 2003-04-11 14:45 | 2003-04-11 14:45 | 1.5.2.6.24
G0105 |  | R10481 - Pkg-3 NECHO Integration Testing | 100% | 120 h | 120 h | 63 d | 2003-01-20 10:30 | 2003-04-15 10:44 | 1.5.2.5
G0105 |  | Perform Integration Testing for NECHO Changes - pkg-2 | 100% | 120 h | 120 h | 61 d | 2003-01-20 10:30 | 2003-04-15 10:44 | 1.5.2.5.1
G0104 |  | Create Pkg-2 SFQ Solutions | 100% | 10 h | 10 h | 37 d | 2003-03-21 08:00 | 2003-05-09 15:45 | 1.4.4.8.7
G0105 |  | R10481 - Host Addr Std/Terr | 100% | 60 h | 60 h | 134.13 d | 2002-11-12 16:45 | 2003-05-16 16:15 | 1.5.2.3
G0105 |  | Host Addr Std/ terr-Coding | 100% | 40 h | 40 h | 104.13 d | 2002-12-27 08:15 | 2003-05-16 16:15 | 1.5.2.3.2
G0104 |  | MS: ISC Review Pkg-2 SFQ Solutions | 0% | 0 h | 0 h | 0 d | 2003-05-23 13:15 | 2003-05-23 13:15 | 1.4.4.8.8
G0104 |  | R10481 - Test Environment Setup | 100% | 90 h | 90 h | 111.58 d | 2002-12-23 16:15 | 2003-05-24 16:15 | 1.4.3
G0104 |  | Set-up FIT Test Environment | 100% | 20 h | 20 h | 91.87 d | 2003-01-21 08:00 | 2003-05-24 16:15 | 1.4.3.5
G0105 |  | Setup Performance Test Environment -pkg3 | 100% | 0 h | 20 h | 15.48 d | 2003-05-05 08:00 | 2003-05-24 16:15 | 1.5.4.6.1
G0105 |  | R10481 - Pkg-3 Consolidated Tech Doc | 100% | 6 h | 6 h | 40.69 d | 2003-04-04 16:00 | 2003-05-30 10:23 | 1.5.3
G0105 |  | Pkg-3 - Review NECHO Technical System Design TSD 9.2 | 100% | 3 h | 3 h | 39 d | 2003-04-04 16:00 | 2003-05-30 10:23 | 1.5.3.1
G0105 |  | Pkg-3 - Review Consolidated Technical Documentation TPD 7.1 | 100% | 3 h | 3 h | 29 d | 2003-04-04 16:00 | 2003-05-30 10:23 | 1.5.3.2
G0104 |  | Populate pkg-2 SFQ Solutions | 0% | 10 h | 10 h | 5 d | 2003-05-23 13:15 | 2003-05-30 11:00 | 1.4.4.8.9
G0105 |  | SAT -Perform System/Acceptance Testing pkg-3 | 100% | 50 h | 50 h | 36.68 d | 2003-04-14 10:59 | 2003-06-02 16:15 | 1.5.4.3
G0105 |  | SAT - Create System/Acceptance Test Summary Report | 0% | 10 h | 10 h | 2 d | 2003-06-02 16:15 | 2003-06-04 15:45 | 1.5.4.4
G0105 |  | SAT - Authorize System/Acceptance Test Summary Report | 0% | 10 h | 10 h | 5 d | 2003-06-04 15:45 | 2003-06-11 14:30 | 1.5.4.5
G0104 |  | Implementation testing execution pkg-2 | 25% | 0 h | 20 h | 31 d | 2003-05-02 08:00 | 2003-06-13 08:15 | 1.4.4.6.3
G0105 |  | R10481 - MQSeries | 97% | 145 h | 145 h | 166.68 d | 2002-10-28 08:00 | 2003-06-13 11:45 | 1.5.2.2
G0105 |  | R10481 - MQ Regional Office MVS Dev Environment | 92% | 60 h | 60 h | 81.68 d | 2003-02-24 10:45 | 2003-06-13 11:45 | 1.5.2.2.3
G0105 |  | MQ Integration Testing | 75% | 20 h | 20 h | 49 d | 2003-04-09 08:00 | 2003-06-13 11:45 | 1.5.2.2.3.3
G0105 |  | R10481 - Pkg-3 Perf Testing | 46% | 0 h | 70 h | 30.48 d | 2003-05-05 08:00 | 2003-06-13 13:15 | 1.5.4.6
G0105 |  | Execute Performance Testing - pk3 | 25% | 0 h | 50 h | 15 d | 2003-05-26 08:00 | 2003-06-13 13:15 | 1.5.4.6.2
G0104 |  | R10481 - Performance Testing Pkg-2 | 69% | 70 h | 90 h | 74.45 d | 2003-03-05 11:45 | 2003-06-13 13:45 | 1.4.4.6
G0104 |  | Execute Perf. Testing Pkg-2 | 75% | 50 h | 50 h | 45 d | 2003-04-15 08:00 | 2003-06-13 13:45 | 1.4.4.6.2
G0105 |  | MQ Q/A Transition to MQService Agreement | 0% | 10 h | 10 h | 5 d | 2003-06-09 08:00 | 2003-06-13 15:45 | 1.5.2.4.27
G0105 |  | R10481 - NECHO - all Remaining Changes (TSD/TPD/UPD) | 99% | 2,108 h | 2,164 h | 167.16 d | 2002-10-28 08:00 | 2003-06-13 16:30 | 1.5.2
G0105 |  | R10481 - NECHO - all Remaining Changes -(TSD) | 98% | 702 h | 726 h | 154.77 d | 2002-11-13 08:00 | 2003-06-13 16:30 | 1.5.2.4
G0105 |  | Necho RSC Entry for Terr valid & Address Std | 25% | 2 h | 2 h | 146 d | 2002-11-25 13:00 | 2003-06-13 16:30 | 1.5.2.4.1
G0105 |  | SAT - Create FIT Test Cases | 0% | 40 h | 40 h | 10 d | 2003-06-02 16:15 | 2003-06-16 13:45 | 1.5.4.7.2
G0104 |  | MS: Pkg-2 Create Agency cowide communications | 0% | 0 h | 0 h | 0 d | 2003-06-20 11:30 | 2003-06-20 11:30 | 1.4.4.8.4
G0104 |  | Pkg-2 Publish Communication | 0% | 5 h | 5 h | 1 d | 2003-06-23 08:00 | 2003-06-23 16:45 | 1.4.4.8.6
G0104 |  | R10481 - Pkg -2 Communication | 67% | 45 h | 45 h | 97.32 d | 2003-02-17 08:00 | 2003-06-27 10:15 | 1.4.4.8
G0104 |  | MS: Pkg-2 Publish Agency cowide communications | 0% | 0 h | 0 h | 0 d | 2003-06-27 10:15 | 2003-06-27 10:15 | 1.4.4.8.5
G0104 |  | Mid Tier-Host Prep cowide issuance | 0% | 20 h | 20 h | 10 d | 2003-06-13 13:45 | 2003-06-27 10:15 | 1.4.4.9.1
G0104 |  | MS: Mid Tier-Host cowide issuance | 0% | 0 h | 0 h | 0 d | 2003-06-27 10:15 | 2003-06-27 10:15 | 1.4.4.9.2
G0105 |  | Create Pkg-3 SFQ Solutions | 0% | 10 h | 10 h | 10 d | 2003-06-16 13:45 | 2003-06-30 10:15 | 1.5.5.9
G0104 |  | AUI Pkg-2 Prep for cowide issaunce | 0% | 20 h | 20 h | 5 d | 2003-06-27 10:15 | 2003-07-04 09:00 | 1.4.4.9.3
G0104 |  | MS: AUI Pkg-2 cowide Issuance | 0% | 0 h | 0 h | 0 d | 2003-07-04 09:00 | 2003-07-04 09:00 | 1.4.4.9.4
G0105 |  | SAT - Perform FIT Testing - Pkg-3 | 0% | 50 h | 50 h | 18 d | 2003-06-16 13:45 | 2003-07-10 08:15 | 1.5.4.7.3
G0105 |  | Pkg-3 Draft Communication | 50% | 10 h | 10 h | 46 d | 2003-05-12 08:00 | 2003-07-11 13:30 | 1.5.5.1
G0105 |  | MS: Pkg-3 Create Agency pilot communications | 0% | 0 h | 0 h | 0 d | 2003-07-11 16:45 | 2003-07-11 16:45 | 1.5.5.4
G0105 |  | MS: ISC Review Pkg-3 SFQ Solutions | 0% | 0 h | 0 h | 0 d | 2003-07-11 16:45 | 2003-07-11 16:45 | 1.5.5.10
G0105 |  | Pkg-3 Communication Review by Proj Team | 0% | 5 h | 5 h | 5 d | 2003-07-11 13:30 | 2003-07-18 11:15 | 1.5.5.2
G0105 |  | MS: Pkg-3 Publish Agency pilot communications | 0% | 0 h | 0 h | 0 d | 2003-07-18 15:30 | 2003-07-18 15:30 | 1.5.5.5
G0105 |  | Populate pkg-3 SFQ Solutions | 0% | 10 h | 10 h | 5 d | 2003-07-11 16:45 | 2003-07-18 15:30 | 1.5.5.11
G0105 |  | Necho Pkg-3 Prep for pilot issuance | 0% | 10 h | 10 h | 8 d | 2003-07-10 08:15 | 2003-07-21 15:15 | 1.5.6.1
G0105 |  | SAT - Create FIT Test Summary Report | 0% | 10 h | 10 h | 10 d | 2003-07-10 08:15 | 2003-07-23 14:45 | 1.5.4.7.4
G0105 |  | Pkg-3 UPD Walkthrough with SPIP group | 0% | 5 h | 5 h | 5 d | 2003-07-18 11:15 | 2003-07-25 10:00 | 1.5.5.3
G0105 |  | R10481 - Pkg-3 Systems Acceptance Test (SAT) | 49% | 260 h | 330 h | 151.68 d | 2003-01-06 14:00 | 2003-07-30 13:30 | 1.5.4
G0105 |  | R10481 - Pkg-3 FIT Test (SAT) | 15% | 130 h | 130 h | 151.68 d | 2003-01-06 14:00 | 2003-07-30 13:30 | 1.5.4.7
G0105 |  | SAT - Authorize FIT Test Summary Report | 0% | 10 h | 10 h | 5 d | 2003-07-23 14:45 | 2003-07-30 13:30 | 1.5.4.7.5
G0104 |  | R10481 - Pkg -2 Design/Build/Test/Implement | 92% | 1,273 h | 1,273 h | 201.81 d | 2002-10-28 08:00 | 2003-07-31 12:00 | 1.4
G0104 |  | R10481 - AUI - DLV | 91% | 1,148 h | 1,148 h | 195.81 d | 2002-11-04 15:30 | 2003-07-31 12:00 | 1.4.4
G0104 |  | R10481 - Pkg -2 Implementation | 0% | 65 h | 65 h | 35 d | 2003-06-13 13:45 | 2003-07-31 12:00 | 1.4.4.9
G0104 |  | Pkg 2-Post implemetation questions | 0% | 25 h | 25 h | 20 d | 2003-07-04 09:00 | 2003-07-31 12:00 | 1.4.4.9.5
G0104 |  | MS: Pkg-2 Completed | 0% | 0 h | 0 h | 0 d | 2003-07-31 12:00 | 2003-07-31 12:00 | 1.4.4.9.6
G0105 |  | MS: Pkg-3 Pilot Necho | 0% | 0 h | 0 h | 0 d | 2003-08-01 12:00 | 2003-08-01 12:00 | 1.5.6.2
G0105 |  | MQ Pilot/Issuance | 0% | 20 h | 20 h | 10 d | 2003-07-18 15:30 | 2003-08-01 12:00 | 1.5.6.4
G0105 |  | MS: Pkg-3 Create Agency cowide communications | 0% | 0 h | 0 h | 0 d | 2003-08-04 11:45 | 2003-08-04 11:45 | 1.5.5.6
G0105 |  | MS: Pkg-3 Publish Agency cowide communications | 0% | 0 h | 0 h | 0 d | 2003-08-11 10:30 | 2003-08-11 10:30 | 1.5.5.7
G0101 |  | Project Coordination Activities | 80% | 964 h | 964 h | 281 d | 2002-07-26 08:00 | 2003-08-15 09:45 | 1.1.2.2
G0101 |  | SSS activities | 85% | 349 h | 350 h | 342 d | 2002-05-06 08:00 | 2003-08-15 10:30 | 1.1.2.3
G0101 |  | Project Management Activities | 84% | 699 h | 750 h | 342 d | 2002-05-06 08:00 | 2003-08-15 10:33 | 1.1.2.1
G0101 |  | Team Weekly Meetings | 83% | 712 h | 1,000 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 1.1.2.4
G0101 |  | R10481 - Project Admin & Cordination | 82% | 3,514 h | 3,514 h | 342.35 d | 2002-05-06 08:00 | 2003-08-15 14:15 | 1.1.2
G0101 |  | Project Schedule / PlanView Maintenance, and Status Reporting | 78% | 417 h | 450 h | 267 d | 2002-08-15 08:00 | 2003-08-15 14:15 | 1.1.2.5
G0105 |  | R10481 - Pkg-3 Communication | 11% | 45 h | 45 h | 72.42 d | 2003-05-12 08:00 | 2003-08-18 09:15 | 1.5.5
G0105 |  | Pkg-3 Publish Communication | 0% | 5 h | 5 h | 5 d | 2003-08-11 10:30 | 2003-08-18 09:15 | 1.5.5.8
G0101 |  | R10481 - IIA | 35% | 0 h | 375 h | 230 d | 2002-10-07 08:00 | 2003-08-18 15:30 | 1.1.5
G0101 |  | IIA Team (Performance Impact Accessment) | 35% | 375 h | 375 h | 230 d | 2002-10-07 08:00 | 2003-08-18 15:30 | 1.1.5.1
G0105 |  | MS: NECHO Pkg-3 cowide Issuance | 0% | 0 h | 0 h | 0 d | 2003-08-22 17:00 | 2003-08-22 17:00 | 1.5.6.3
G0106 |  | Update design documents (AIP 2.6) to reflect implemented system | 0% | 2 h | 2 h | 1 d | 2003-08-25 08:00 | 2003-08-25 16:45 | 1.6.1
G0106 |  | Transition design documents to local architect | 0% | 4 h | 4 h | 2 d | 2003-08-25 08:00 | 2003-08-26 16:30 | 1.6.2
G0106 |  | MS: Lessons Learned doc | 0% | 0 h | 0 h | 0 d | 2003-09-12 13:15 | 2003-09-12 13:15 | 1.6.3
G0105 |  | R10481 - Pkg -3 Design/Build/Test/Implement | 89% | 2,484 h | 2,610 h | 238.84 d | 2002-10-28 08:00 | 2003-09-19 11:00 | 1.5
G0105 |  | R10481 - Pkg-3 Implementation | 0% | 65 h | 65 h | 53 d | 2003-07-10 08:15 | 2003-09-19 11:00 | 1.5.6
G0105 |  | Pkg-3-Post implemetation questions | 0% | 35 h | 35 h | 20 d | 2003-08-25 08:00 | 2003-09-19 11:00 | 1.5.6.5
G0105 |  | MS: Pkg-3 Completed | 0% | 0 h | 0 h | 0 d | 2003-09-19 11:00 | 2003-09-19 11:00 | 1.5.6.6
G0106 |  | Transition to Service | 0% | 30 h | 30 h | 20 d | 2003-08-25 08:00 | 2003-09-19 11:00 | 1.6.4
G0101 |  | R10481 - Planning/Admin/Meetings/Coordination | 79% | 4,287 h | 4,287.01 h | 371.87 d | 2002-05-06 08:00 | 2003-09-25 10:00 | 1.1
G0101 |  | R10481 - SP/IP | 50% | 40 h | 40 h | 280 d | 2002-09-06 08:00 | 2003-09-25 10:00 | 1.1.4
G0101 |  | Authorize final SPIP for transition | 0% | 20 h | 20 h | 10 d | 2003-09-11 13:30 | 2003-09-25 10:00 | 1.1.4.2
G0100 |  | R10481 - Auto Necho - Auto Apps Efficiency | 87% | 10,709.01 h | 10,779.01 h | 372.87 d | 2002-05-06 08:00 | 2003-09-26 09:45 | 1
G0106 |  | R10481 - Transition | 0% | 86 h | 76 h | 25 d | 2003-08-25 08:00 | 2003-09-26 09:45 | 1.6
G0106 |  | Project Closure Tasks | 0% | 40 h | 40 h | 5 d | 2003-09-19 11:00 | 2003-09-26 09:45 | 1.6.5
G0106 |  | MS: Project Completed | 0% | 0 h | 0 h | 0 d | 2003-09-26 09:45 | 2003-09-26 09:45 | 1.6.6
◄▬Menu

## ActHist
|  | Proj. 1234 | Monthly Actual Hours History
Sr.No. | Name as in PV | Name as in OL | Total Used Hours | 2003-06-01 | 2003-05-01 | 2003-04-01 | 2003-03-01 | 2003-02-01 | 2003-01-01 | 2002-12-01 | 2002-11-01 | 2002-10-01 | 2002-09-01 | 2002-08-01 | 2002-07-01 | 2002-06-01 | 2002-05-01 | 2002-04-01
1 | Awan Zafar | Zafar Awan | 46 | 6 | 5 | 5 | 6 | 9 | 7 | 8
2 | Baugh Sally | Sally Baugh | 23.5 |  | 4.5 | 11 | 4 | 4
3 | Bommisetti Amarnath | Amarnath Bommisetti | 1747 |  | 56 | 140 | 191 | 177 | 193 | 156 | 134 | 151 | 161 | 168 | 220
4 | Brown Brian [GS03] | Brian Brown | 100 |  | 0.5 | 3 |  |  |  | 64.5 | 32
5 | Celeschi Michelle | Michelle Celeschi | 224.75 |  | 8 | 9.25 | 17.25 | 17.5 | 18.5 | 18.5 | 23.5 | 17 | 9.5 | 18.5 | 16 | 17 | 30.25 | 4
6 | Dejaynes Vance | Vance Dejaynes | 325 | 3.5 | 13.5 | 11.5 | 16 | 24.5 | 38.5 | 35.5 | 45 | 40.5 | 53.5 | 32.5 | 10.5
7 | Dobrinich Tina L | Tina L Dobrinich | 438.5 |  | 36 | 122 | 47.5 | 20 | 31.5 | 36.5 | 29 | 26 | 29 | 15.5 | 24 | 11.5 | 10
8 | Durnan Steve | Steve Durnan | 164.5 | 4 | 9 | 24.5 | 30 | 30.5 | 31 | 14 | 21.5
9 | Elam Carol | Carol Elam | 546.5 | 2 | 29 | 26.5 | 21.5 | 18 | 48 | 48 | 58 | 46.5 | 46.5 | 39.5 | 67.5 | 39.5 | 56
10 | Frey Michael | Michael Frey | 271 | 10 | 70 | 91 | 11.5 | 8 | 12 | 10 | 8 | 7 | 6 | 12 | 11 | 8.5 | 6
11 | Gullixon Eric | Eric Gullixon | 117.5 |  | 3 | 2 | 5 | 8 | 5 | 2.5 | 1 | 7 | 19 | 13 | 33 | 11 | 8
12 | Hall Steve | Steve Hall | 625 |  | 78 | 112 | 49 | 57 | 69 | 75 | 56 | 9 | 24 | 43 | 30 | 19 | 4
13 | Hartness Ty | Ty Hartness | 115.5 | 2.25 |  | 2.75 | 0.75 | 2 | 5.5 | 3.25 | 12.75 | 10.25 | 28.5 | 17 | 24 | 6.5
14 | Isaacson John | John Isaacson | 40.5 |  |  |  | 3 | 0.5 | 7 | 5.5 | 4 | 4.5 | 3.5 | 12.5
15 | Kumar Ashok | Ashok Kumar | 514 |  | 27 | 33 | 31 | 31 | 44 | 38 | 41 | 54 | 37 | 41 | 44 | 49 | 44
16 | Lade Daniel | Daniel Lade | 47.5 |  | 20.75 | 10.25 |  | 0.5 | 4 | 1 | 4 | 7
17 | Lee Mary Kasley | Mary Kasley Lee | 92.25 |  |  | 0.75 | 0.5 | 0.75 | 0.25 | 4.25 | 11.75 | 11 | 22 | 20 | 15.75 | 5.25
18 | Leslie Sherrill | Sherrill Leslie | 20 |  | 5 | 5 |  |  | 1 | 2 |  | 7
19 | Ma Harry | Harry Ma | 78.75 | 2 | 4.75 | 9.25 | 5.5 | 8 | 16.25 | 10 | 18 | 5
20 | Malone Bill | Bill Malone | 193.5 |  | 20 | 17 | 17 | 15 | 37.5 | 53.5 | 27.25 | 6.25
21 | McKinney Brian | Brian McKinney | 21.5 | 1 | 15 | 5.5
22 | Miller Kim | Kim Miller | 46 |  | 37 | 5 | 2 |  |  | 2
23 | Mohandass Duzianthan | Duzianthan Mohandass | 8 |  | 6 | 2
24 | Murthy J | J Murthy | 1445 |  | 19 | 115 | 174 | 171 | 179 | 166 | 125 | 117 | 139 | 69 | 132 | 33 | 6
25 | Nutt John | John Nutt | 142 |  | 5 | 22 | 6 | 4 | 4 | 26 | 72 | 3
26 | Paige Charles | Charles Paige | 56.5 |  | 2.75 | 10.5 | 0.5 | 3.35 | 5.65 | 5.75 | 10.25 | 17.75
27 | Ramachandran Santosh [H6Z5] | Santosh Ramachandran | 6 |  | 6
28 | Reddy Lakshmi Narayana | Lakshmi Narayana Reddy | 144 |  | 15 | 69 | 10 | 7 | 2 |  |  | 5 | 14 |  | 9 | 7 | 6
29 | Rogers Charlie | Charlie Rogers | 9 |  | 9
30 | Saenz Gilbert | Gilbert Saenz | 8 |  |  | 1 |  | 1 | 1 | 3 |  | 2
31 | Saha Sushit | Sushit Saha | 56 |  |  | 3 | 8 | 10 | 15 | 6 | 11 | 3
32 | Sanders Dave | Dave Sanders | 10.75 |  |  | 1 |  | 0.25 |  | 3 | 2.25 | 4.25
33 | Scott Gary | Gary Scott | 3 | 2 | 1
34 | Shanmugam Kasi | Kasi Shanmugam | 46 |  | 28.5 | 9.5 |  | 8
35 | Stern David | David Stern | 75 | 4 | 6 | 1 | 9 | 13 | 32 | 6 | 4
36 | Weidenbenner Ed | Ed Weidenbenner | 495 | 4 | 19 | 38 | 32 | 27 | 37 | 41 | 39 | 39 | 42 | 47 | 60 | 43 | 27
37 | Witter Steve | Steve Witter | 802 | 10 | 61 | 110 | 109 | 125 | 102 | 82 | 3 | 116 | 48 | 28 | 8
38 | Woodman Andrew | Andrew Woodman | 18 |  | 10.5 | 2 | 5.5
39 | zzz$? |  | 9123 | 50.75 | 630.75 | 1030.25 | 812.5 | 800.85 | 946.65 | 926.75 | 793.25 | 716 | 682.5 | 576.5 | 704.75 | 250.25 | 197.25 | 4
◄▬Menu

## WKSch
Proj. 1234 |  |  | Weekly Allocation as per schedule
| Week No --> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
Resource Name ¦ V | Week Start ---------> | time axis 2002-05-06 to 2003-04-21
Carol | 477.39 | 15.07 | 15.07 | 20.19 | 25.04 | 21.47 | 21.47 | 23.07 | 27.91 | 24.19 | 16.19 | 15.07 | 19.07 | 15.07 | 16.07 | 15.07 | 15.07 | 15.6 | 15.07 | 15.07 | 15.07 | 19.39 | 21.47 | 21.47 | 17.95 | 16.14 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 15.07 | 5.65
Michelle | 211.44 | 7.94 | 7.94 | 8.94 | 7.94 | 7.94 | 7.94 | 9.94 | 7.94 | 7.94 | 7.94 | 7.94 | 9.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 7.94 | 2.98
Ashok | 358.43 | 9.35 | 9.35 | 11.03 | 18.06 | 19.71 | 19.71 | 20.64 | 20.71 | 19.64 | 9.46 | 9.35 | 11.35 | 9.35 | 10.35 | 9.35 | 9.35 | 9.78 | 9.35 | 9.35 | 9.35 | 14.93 | 17.61 | 17.61 | 17.61 | 18.47 | 17.61 | 10.49 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 0.38
Ed | 67.19 | 1 | 1 | 3.67 | 4.32 | 1 | 4.45 | 5.12 | 6.12 | 2.12 | 2.12 | 1.06 | 5 | 1 | 2 | 1 | 1 | 2.07 | 1 | 2 | 1 | 4.64 | 7.72 | 1.64 | 1 | 3.14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 51 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Eric | 107.54 | 16.01 | 1.01 | 3.68 | 4.33 | 1.01 | 4.01 | 4.01 | 5.01 | 1.01 | 1.01 | 1.01 | 5.11 | 16.5 | 17.82 | 2.66 | 2.66 | 3.09 | 2.66 | 1.01 | 1.01 | 3.17 | 4.21 | 1.65 | 1.01 | 1.87 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 0.38
Murthy | 297.7 | 1.01 | 1.01 | 2.73 | 3.16 | 5.14 | 3.01 | 3.01 | 5.01 | 1.01 | 1.01 | 1.01 | 3.01 | 1.01 | 2.01 | 5.21 | 42.95 | 43.76 | 42.94 | 42.81 | 42.94 | 32.11 | 3.01 | 3.01 | 1.66 | 3.15 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 0.38
Jill | 76.56 | 1.01 | 1.01 | 2.73 | 3.16 | 5.14 | 3.01 | 3.01 | 5.01 | 1.01 | 1.01 | 1.01 | 3.11 | 8.95 | 4.37 | 2.66 | 2.66 | 3.09 | 2.66 | 3.01 | 1.01 | 3.85 | 6.53 | 3.01 | 1.66 | 1.87 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 0.38
Lakshmi | 188.92 | 1.01 | 1.01 | 2.73 | 3.16 | 5.14 | 3.01 | 3.01 | 5.01 | 1.01 | 1.01 | 1.01 | 3.01 | 1.01 | 2.01 | 3.34 | 24.24 | 25.28 | 24.09 | 24.09 | 24.09 | 18.81 | 3.01 | 3.01 | 1.66 | 3.15 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 0.38
Michael | 135.58 | 1.01 | 1.01 | 2.73 | 4.87 | 5.28 | 3.16 | 1.01 | 5.01 | 1.01 | 1.01 | 1.01 | 3.01 | 1.01 | 3.41 | 2.66 | 14.36 | 15.99 | 15.57 | 13.92 | 13.92 | 14.33 | 3.41 | 2.99 | 1.01 | 1.87 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 0.38
Steve | 210.12 | 1.01 | 1.01 | 2.73 | 3.16 | 3.14 | 1.01 | 1.01 | 5.01 | 1.01 | 1.01 | 1.01 | 18.17 | 26.82 | 10.72 | 15.41 | 21.66 | 6.51 | 1.08 | 1.01 | 1.01 | 1.01 | 1.01 | 7.47 | 42.3 | 33.39 | 1.44 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 0.38
Tina | 170.62 | 1.01 | 1.01 | 2.73 | 4.87 | 5.28 | 3.6 | 2.13 | 6.13 | 2.13 | 2.13 | 1.08 | 6.73 | 4.29 | 10.01 | 2.57 | 16.57 | 17.49 | 16.57 | 17.5 | 16.57 | 15.13 | 6.93 | 2.99 | 1.01 | 3.15 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 0.38
Analyst | 14 | 2002-09-23: 10; 2002-09-30: 3.29; 2002-10-07: 0.71
Amarnath | 249.44 | 2002-07-22: 2; 2002-08-05: 1; 2002-08-12: 4.2; 2002-08-19: 41.94; 2002-08-26: 42.75; 2002-09-02: 41.93; 2002-09-09: 41.8; 2002-09-16: 41.93; 2002-09-23: 29.75; 2002-10-21: 2.14
Ty | 116.2 | 2002-08-05: 9; 2002-08-12: 9.94; 2002-08-19: 11.35; 2002-08-26: 19.68; 2002-09-02: 19.1; 2002-09-09: 15.48; 2002-09-16: 15; 2002-09-23: 7.74; 2002-09-30: 6.77; 2002-10-21: 2.14
Mary | 117.23 | 2002-07-15: 4.13; 2002-07-22: 20.65; 2002-07-29: 11.23; 2002-08-05: 9; 2002-08-12: 3.61; 2002-08-19: 4.13; 2002-08-26: 7.67; 2002-09-02: 6.66; 2002-09-09: 25.65; 2002-09-16: 16.16; 2002-09-23: 3.94; 2002-09-30: 2.26; 2002-10-21: 2.14
Totals --> | 2798.36 | 2002-05-06: 55.43; 2002-05-13: 40.43; 2002-05-20: 63.89; 2002-05-27: 82.07; 2002-06-03: 80.25; 2002-06-10: 74.38; 2002-06-17: 75.96; 2002-06-24: 98.87; 2002-07-01: 62.08; 2002-07-08: 43.9; 2002-07-15: 44.69; 2002-07-22: 110.16; 2002-07-29: 104.18; 2002-08-05: 105.71; 2002-08-12: 85.62; 2002-08-19: 215.88; 2002-08-26: 220.7; 2002-09-02: 206.62; 2002-09-09: 220.64; 2002-09-16: 207; 2002-09-23: 186.74; 2002-09-30: 95.17; 2002-10-07: 73.5; 2002-10-14: 94.81; 2002-10-21: 100.56; 2002-10-28: 49.12
Amarnath | 0 | 2002-05-13: 249.42
Analyst | 0 | 2002-05-13: 14
Ashok | 580.13 | 2002-05-13: 4.28
Carol | 878 | 2002-05-13: 6.6
Ed | 71.98 | 2002-05-13: 19.21
Eric | 72.98 | 2002-05-13: 59.28
Jill | 72.98 | 2002-05-13: 28.28
Lakshmi | 72.98 | 2002-05-13: 140.64
Mary | 26 | 2002-05-13: 136.21
Michelle | 403 | 2002-05-13: 2
Murthy | 72.98 | 2002-05-13: 249.42
Steve | 60.98 | 2002-05-13: 173.83
Tina | 72.98 | 2002-05-13: 122.34
Ty | 26 | 2002-05-13: 100.21
Unassigned | 0 | 2002-05-13: 145
Vance | 964 | 2002-05-13: 0
Witter | 72.98 | 2002-05-13: 87.28
◄▬Menu

## ResEVA
Proj. 1234 | Resourcewise Earned Value Analysis
Resource Name | Baseline Work Hrs | Schedule Work Hrs | %Work Complete | Earned hrs | Actaul Hrs | CPI (Earned/Actual) | Remarks
Amar | 1294.59 | 1350.44 | 98.61% | 1276.56 | 1747 | 73.07%
Ashok | 594.57 | 652.18 | 0.81173 | 482.63 | 514 | 93.9%
Bill | 341.53 | 366.53 | 98.09% | 335 | 193.5 | 173.1%
Brian | 80 | 80 | 100% | 80 | 100 | 80%
Carol | 904.53 | 984.36 | 81.89% | 740.69 | 547.5 | 135.3%
Charles | 50 | 50 | 52% | 26 | 56.5 | 46.02%
Daniel | 25 | 25 | 100% | 25 | 47.5 | 52.63%
Dave | 50 | 50 | 52% | 26 | 10.75 | 241.9%
David | 36.26 | 36.26 | 96.53% | 35 | 75 | 46.67%
Durnan | 205 | 205 | 78.05% | 160 | 171.5 | 93.29%
Ed | 492.75 | 506.88 | 64.49% | 317.75 | 499 | 63.68%
Eric | 172.42 | 197.03 | 94.08% | 162.22 | 117.5 | 138.1%
EricH | 17 | 17 | 100% | 17
Gilbert | 25 | 25 | 100% | 25 | 8 | 312.5%
Harry | 200 | 200 | 2% | 4 | 78.75 | 5.079%
Jeff | 11 | 11 | 100% | 11
Jill | 136.42 | 161.03 | 92.52% | 126.22
John | 269.53 | 254.53 | 90.16% | 243 | 144 | 168.8%
Lakshmi | 420.17 | 447.08 | 97.45% | 409.46 | 144 | 284.3%
Lynn | 41.2 | 41.2 | 100% | 41.2 |  | 0%
Mary | 216.27 | 219.96 | 98.71% | 213.47 | 92.25 | 231.4%
Michelle | 416 | 441.76 | 82.56% | 343.45 | 226.75 | 151.5%
Murthy | 1349.82 | 1375.46 | 99.24% | 1339.62 | 1447 | 92.58%
PerTeam | 45 | 49.36 | 77.78% | 35
Sherrill | 25 | 25 | 100% | 25 | 20 | 125%
SteveH | 550.38 | 575.63 | 90.42% | 497.68 | 675 | 73.73%
Sushit | 37.53 | 37.53 | 82.6% | 31 | 62 | 50%
Tina | 409.9 | 435.69 | 97.51% | 399.7 | 444.5 | 89.92%
Ty | 187.87 | 191.56 | 98.3% | 184.67 | 116 | 159.2%
Vance | 1004 | 1004 | 77.81% | 781.2 | 325 | 240.4%
Witter | 558.03 | 587.64 | 0.9412 | 525.22 | 809 | 64.92%
◄▬Menu

## EVASetup
| Proj. 1234 | Earned Value Analysis
| Project No: | Proj. 1234 | Y | Steps to follow for Initial Setup.
| Project Name: | Auto Necho - Auto Apps Efficiency |  | 1. Read comments to various cells to know more about what value to enter.
| Initial Budget: | 10000 |  | 2. Fill in Project No, Name, Initial budget, Start, End dates, Analysis Period, and Groups Tab Name and Group Description in the format given on left hand side..
| Start date: | 2002-05-06
| End date: | 2003-09-15 |  | 3. Click on
| Analysis Period: | Monthly
| Total # of Groups: | 6
| Total # of Periods: | 17
WBS | Group Tab Name | EVA Group Description |  | It will create a tab for each group you have entered.
1.1 | Planning | Planning/Admin/meetings/Coordination |  | Follow steps 1 to 3 if you need to update setup.
1.2 | SRASDS | Reqs Analysis and Solution Def/Specs
1.3 | PKG1 | Pkg -1 Design/Build/Test/Implemen |  | In case setup updates require deletion of some group tabs, these tabs will be renamed as deleted I.e. not physically deleted. You can physically delete these tabs mannually.
1.4 | PKG2 | Pkg -1 Design/Build/Test/Implemen
1.5 | PKG3 | Pkg -1 Design/Build/Test/Implemen
1.4 | TRA | Transition
Definitions:
BCWS: Budgeted Cost of Work Scheduled (as per Baseline Values)
BCWP: Budgeted Cost of Work Performed (Progress or Earned Value)
ACWP: Actual Cost of Work Performed (Actual or Burnt Value)
SPI: Schedule Performance Index = BCWP / BCWS
CPI: Cost Performance Index = BCWP / ACWP
EAT: Estimate cost at completion = ACWP +[(BAC-BCWP)/CPI
ETC: Estimate cost to complete = (BAC - BCWP)/CPI
(BAC is the cummulative value of BCWS at completion)
Note on A20: This column should contain first three chars of WBS column of MS Project Schedule. WBS has values like 1.1.2.4, 1.4.2 etc. These are all level 1 Summary Tasks. Level 0 Summary level tasks is the first top level summary tasks of MS Project Schedule. All other tasks are below this task. Basically these values represent the group codes corresponding to EVA groups.
Note on B20: Give one word name to appear as tab name for the sheet added for an EVA group. Use only chars A to Z and numbers 0 to 9. Do not use special chars like - + , & $ ! @ # % ^ * ( ) _ { } [ ] \ " ' / ? > < .
Process Setup
◄▬Menu

## Sheet1
Earned Value Analisys
Period ▬►

## EVAProject
| Proj. 1234 | Auto Necho - Auto Apps Efficiency | [9 empty] | EVA for Whole project |  |  | Budgeted Hours | 1078
| Start date: |  | 2002-05-06 |  | Period: | Monthly | 17 | 28 |  |  |  |  | SPI = | 90.23% | Earned Hours
| End date: |  | 2003-09-15 |  | Group: | [5 empty] | CPI |  | CPI = | 103.4% | Actual Hours
[5 empty] | 10919.95 | 8661.1 | 8373 |  |  | 9598.71 |  |  | EAC = | 10556.7124
Sr No | As on Date | For The Period |  |  | Cummulative
Sr No |  | BCWS | BCWP | ACWP | BCWS | BCWP | ACWP | SPI | CPI
1 | 2002-05-31 | 268.78 | 260 | 197 | 268.78 | 260 | 197 | 0.96733 | 1.3198 | 268.78
2 | 2002-06-30 | 360.4 | 414 | 251 | 629.18 | 674 | 448 | 1.0712 | 1.5045 | 360.4
3 | 2002-07-31 | 648.54 | 662 | 705 | 1277.72 | 1336 | 1153 | 1.0456 | 1.1587 | 648.54
4 | 2002-08-31 | 888.33 | 329 | 577 | 2166.05 | 1665 | 1730 | 0.76868 | 0.96243 | 888.33
5 | 2002-09-30 | 1019.29 | 743 | 683 | 3185.34 | 2408 | 2413 | 0.75596 | 0.99793 | 1019.29
6 | 2002-10-31 | 1091.75 | 1220 | 712 | 4277.09 | 3628 | 3125 | 0.84824 | 1.161 | 1091.75
7 | 2002-11-30 | 787.64 | 688 | 798 | 5064.73 | 4316 | 3923 | 0.85217 | 1.1002 | 787.64
8 | 2002-12-31 | 1152.54 | 1114 | 927 | 6217.27 | 5430 | 4850 | 0.87337 | 1.1196 | 1152.54
9 | 2003-01-31 | 1149.12 | 925 | 947 | 7366.39 | 6355 | 5797 | 0.8627 | 1.0963 | 1149.12
10 | 2003-02-28 | 897.98 | 1003 | 799 | 8264.37 | 7358 | 6596 | 0.89033 | 1.1155 | 897.98
11 | 2003-03-31 | 981.75 | 689.1 | 801 | 9246.12 | 8047.1 | 7397 | 0.87032 | 1.0879 | 981.75
12 | 2003-04-30 | 352.59 | 614 | 976 | 9598.71 | 8661.1 | 8373 | 0.90232 | 1.0344 | 352.59
13 | 2003-05-31 | 341.38 | 0 | 0 | 9940.09 | 0 | 0 | 0 | 0 | 0
14 | 2003-06-30 | 328.61 | 0 | 0 | 10268.7 | 0 | 0 | 0 | 0 | 0
15 | 2003-07-31 | 257.89 | 0 | 0 | 10526.59 | 0 | 0 | 0 | 0 | 0
16 | 2003-08-31 | 270.38 | 0 | 0 | 10796.97 | 0 | 0 | 0 | 0 | 0
17 | 2003-09-30 | 122.98 | 0 | 0 | 10919.95 | 0 | 0 | 0 | 0 | 0
18 | 2003-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 2003-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 2003-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 2004-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 2004-02-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 2004-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 2004-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 2004-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 2004-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 2004-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 2004-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
As on Date = IF(G2="Weekly",[As on Date, row above]+7,IF(G2="Bi-Weekly",[As on Date, row above]+14,IF(G2="Monthly",DATE(YEAR([As on Date, row above]),MONTH([As on Date, row above])+2,1)-1,[As on Date, row above])))
Refresh
Upd BCWS
◄▬Menu

## EVAPlanning
| Proj. 1234 | Auto Necho - Auto Apps Efficiency | [9 empty] | EVA for Planning |  |  | Budgeted Hours | 1078
| Start date: |  | 2002-05-06 |  | Period: | Monthly | 17 | 28 |  |  |  |  | SPI = | 86.3% | Earned Hours
| End date: |  | 2003-09-15 |  | Group: | 1.1 |  |  |  |  | CPI |  | CPI = | 115% | Actual Hours
[5 empty] | 4286.97 | 2886 | 2509 |  |  | 3344.31 |  |  | EAC = | 3726.9604
Sr No | As on Date | For The Period |  |  | Cummulative
Sr No |  | BCWS | BCWP | ACWP | BCWS | BCWP | ACWP | SPI | CPI
1 | 2002-05-31 | 268.78 | 260 | 197 | 268.78 | 260 | 197 | 0.96733 | 1.3198 | 268.78
2 | 2002-06-30 | 225.22 | 253 | 147 | 494 | 513 | 344 | 1.0385 | 1.4913 | 225.22
3 | 2002-07-31 | 254.8 | 192 | 193 | 748.8 | 705 | 537 | 0.94151 | 1.3128 | 254.8
4 | 2002-08-31 | 299.77 | 195 | 249 | 1048.57 | 900 | 786 | 0.85831 | 1.145 | 299.77
5 | 2002-09-30 | 384.12 | 303 | 233 | 1432.69 | 1203 | 1019 | 0.83968 | 1.1806 | 384.12
6 | 2002-10-31 | 591.15 | 321 | 276 | 2023.84 | 1524 | 1295 | 0.75302 | 1.1768 | 591.15
7 | 2002-11-30 | 227.62 | 185 | 240 | 2251.46 | 1709 | 1535 | 0.75906 | 1.1134 | 227.62
8 | 2002-12-31 | 215.86 | 220 | 226 | 2467.32 | 1929 | 1761 | 0.78182 | 1.0954 | 215.86
9 | 2003-01-31 | 234.54 | 212 | 217 | 2701.86 | 2141 | 1978 | 0.79242 | 1.0824 | 234.54
10 | 2003-02-28 | 203.95 | 269 | 135 | 2905.81 | 2410 | 2113 | 0.82937 | 1.1406 | 203.95
11 | 2003-03-31 | 214.15 | 207 | 203 | 3119.96 | 2617 | 2316 | 0.83879 | 1.13 | 214.15
12 | 2003-04-30 | 224.35 | 269 | 193 | 3344.31 | 2886 | 2509 | 0.86296 | 1.1503 | 224.35
13 | 2003-05-31 | 224.35 |  |  | 3568.66 | 0 | 0 | 0 | 0 | 0
14 | 2003-06-30 | 214.15 |  |  | 3782.81 | 0 | 0 | 0 | 0 | 0
15 | 2003-07-31 | 234.54 |  |  | 4017.35 | 0 | 0 | 0 | 0 | 0
16 | 2003-08-31 | 205.97 |  |  | 4223.32 | 0 | 0 | 0 | 0 | 0
17 | 2003-09-30 | 63.65 |  |  | 4286.97 | 0 | 0 | 0 | 0 | 0
18 | 2003-10-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
19 | 2003-11-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
20 | 2003-12-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
21 | 2004-01-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
22 | 2004-02-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
23 | 2004-03-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
24 | 2004-04-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
25 | 2004-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
26 | 2004-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
27 | 2004-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
28 | 2004-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
As on Date = IF(G2="Weekly",[As on Date, row above]+7,IF(G2="Bi-Weekly",[As on Date, row above]+14,IF(G2="Monthly",DATE(YEAR([As on Date, row above]),MONTH([As on Date, row above])+2,1)-1,[As on Date, row above])))
Refresh
Upd BCWS

## EVASRASDS
| Proj. 1234 | Auto Necho - Auto Apps Efficiency | [9 empty] | EVA for SRASDS | [5 empty] | Budgeted Hours | 1078
| Start date: |  | 2002-05-06 |  | Period: | Monthly | 17 | 28 |  |  |  |  | SPI = | 90.44% |  |  |  | Earned Hours
| End date: |  | 2003-09-15 |  | Group: | 1.2 |  |  |  |  | CPI |  | CPI = | 109.6% |  |  |  | Actual Hours
[5 empty] | 2271 | 2054 | 1873.75 |  |  | 2271 |  |  | EAC = | 2071.707
Sr No | As on Date | For The Period |  |  | Cummulative
Sr No |  | BCWS | BCWP | ACWP | BCWS | BCWP | ACWP | SPI | CPI
1 | 2002-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2002-06-30 | 135.18 | 161 | 104 | 135.18 | 161 | 104 | 1.191 | 1.5481 | 135.18
3 | 2002-07-31 | 393.74 | 470 | 512 | 528.92 | 631 | 616 | 1.193 | 1.0244 | 393.74
4 | 2002-08-31 | 588.56 | 134 | 328 | 1117.48 | 765 | 944 | 0.68458 | 0.81038 | 588.56
5 | 2002-09-30 | 635.17 | 440 | 450 | 1752.65 | 1205 | 1394 | 0.68753 | 0.86442 | 635.17
6 | 2002-10-31 | 446.68 | 824 | 329.75 | 2199.33 | 2029 | 1723.75 | 0.92255 | 1.1771 | 446.68
7 | 2002-11-30 | 71.67 | 25 | 150 | 2271 | 2054 | 1873.75 | 0.90445 | 1.0962 | 71.67
8 | 2002-12-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
9 | 2003-01-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
10 | 2003-02-28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
11 | 2003-03-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
12 | 2003-04-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
13 | 2003-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
14 | 2003-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
15 | 2003-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
16 | 2003-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
17 | 2003-09-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
18 | 2003-10-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
19 | 2003-11-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
20 | 2003-12-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
21 | 2004-01-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
22 | 2004-02-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
23 | 2004-03-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
24 | 2004-04-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
25 | 2004-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
26 | 2004-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
27 | 2004-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
28 | 2004-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 135.18h | 393.74h | 588.56h | 635.17h | 446.68h | 71.67h
Formulas:
As on Date = IF(G2="Weekly",[As on Date, row above]+7,IF(G2="Bi-Weekly",[As on Date, row above]+14,IF(G2="Monthly",DATE(YEAR([As on Date, row above]),MONTH([As on Date, row above])+2,1)-1,[As on Date, row above])))
Refresh
Upd BCWS

## EVAPKG1
| Proj. 1234 | Auto Necho - Auto Apps Efficiency | [9 empty] | EVA for ECHO |  |  | Budgeted Hours | 1078
| Start date: |  | 2002-05-06 |  | Period: | Monthly | 17 | 28 |  |  |  |  | SPI = | 88.29% | Earned Hours
| End date: |  | 2003-09-15 |  | Group: | 1.3 |  |  |  |  | CPI |  | CPI = | 77.98% | Actual Hours
[5 empty] | 554 | 489.1 | 627.25 |  |  | 554 |  |  | EAC = | 710.4815
Sr No | As on Date | For The Period |  |  | Cummulative
Sr No |  | BCWS | BCWP | ACWP | BCWS | BCWP | ACWP | SPI | CPI
1 | 2002-05-31 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
2 | 2002-06-30 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
3 | 2002-07-31 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
4 | 2002-08-31 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
5 | 2002-09-30 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
6 | 2002-10-31 | 49.06 | 75 | 106.25 | 49.06 | 75 | 106.25 | 1.5287 | 0.70588 | 49.06
7 | 2002-11-30 | 238.76 | 192 | 254 | 287.82 | 267 | 360.25 | 0.92766 | 0.74115 | 238.76
8 | 2002-12-31 | 164.35 | 174 | 198 | 452.17 | 441 | 558.25 | 0.9753 | 0.78997 | 164.35
9 | 2003-01-31 | 71.83 | 30 | 48 | 524 | 471 | 606.25 | 0.89885 | 0.77691 | 71.83
10 | 2003-02-28 | 20.81 | 18 | 16 | 544.81 | 489 | 622.25 | 0.89756 | 0.78586 | 20.81
11 | 2003-03-31 | 9.19 | 0.1 | 5 | 554 | 489.1 | 627.25 | 0.88285 | 0.77975 | 9.19
12 | 2003-04-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
13 | 2003-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
14 | 2003-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
15 | 2003-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
16 | 2003-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
17 | 2003-09-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
18 | 2003-10-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
19 | 2003-11-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
20 | 2003-12-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
21 | 2004-01-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
22 | 2004-02-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
23 | 2004-03-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
24 | 2004-04-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
25 | 2004-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
26 | 2004-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
27 | 2004-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
28 | 2004-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
As on Date = IF(G2="Weekly",[As on Date, row above]+7,IF(G2="Bi-Weekly",[As on Date, row above]+14,IF(G2="Monthly",DATE(YEAR([As on Date, row above]),MONTH([As on Date, row above])+2,1)-1,[As on Date, row above])))
Refresh
Upd BCWS

## EVAPKG2
| Proj. 1234 | Auto Necho - Auto Apps Efficiency | [9 empty] | EVA for AUI |  |  | Budgeted Hours | 1078
| Start date: |  | 2002-05-06 |  | Period: | Monthly | 17 | 28 |  |  |  |  | SPI = | 95.38% | Earned Hours
| End date: |  | 2003-09-15 |  | Group: | 1.4 |  |  |  |  | CPI |  | CPI = | 86.59% | Actual Hours
[5 empty] | 1147.99 | 1033 | 1193 |  |  | 1082.99 |  |  | EAC = | 1325.8006
Sr No | As on Date | For The Period |  |  | Cummulative
Sr No |  | BCWS | BCWP | ACWP | BCWS | BCWP | ACWP | SPI | CPI
1 | 2002-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2 | 2002-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3 | 2002-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
4 | 2002-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
5 | 2002-09-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
6 | 2002-10-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
7 | 2002-11-30 | 133.41 | 138 | 154 | 133.41 | 138 | 154 | 1.0344 | 0.8961 | 133.41
8 | 2002-12-31 | 427.86 | 319 | 192 | 561.27 | 457 | 346 | 0.81422 | 1.3208 | 427.86
9 | 2003-01-31 | 268.3 | 324 | 257 | 829.57 | 781 | 603 | 0.94145 | 1.2952 | 268.3
10 | 2003-02-28 | 121.94 | 190 | 236 | 951.51 | 971 | 839 | 1.0205 | 1.1573 | 121.94
11 | 2003-03-31 | 123.79 | 27 | 117 | 1075.3 | 998 | 956 | 0.92811 | 1.0439 | 123.79
12 | 2003-04-30 | 7.69 | 35 | 237 | 1082.99 | 1033 | 1193 | 0.95384 | 0.86588 | 7.69
13 | 2003-05-31 | 46.45 |  |  | 1129.44 | 0 | 0 | 0 | 0 | 0
14 | 2003-06-30 | 18.55 |  |  | 1147.99 | 0 | 0 | 0 | 0 | 0
15 | 2003-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
16 | 2003-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
17 | 2003-09-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
18 | 2003-10-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
19 | 2003-11-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
20 | 2003-12-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
21 | 2004-01-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
22 | 2004-02-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
23 | 2004-03-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
24 | 2004-04-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
25 | 2004-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
26 | 2004-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
27 | 2004-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
28 | 2004-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
As on Date = IF(G2="Weekly",[As on Date, row above]+7,IF(G2="Bi-Weekly",[As on Date, row above]+14,IF(G2="Monthly",DATE(YEAR([As on Date, row above]),MONTH([As on Date, row above])+2,1)-1,[As on Date, row above])))
Refresh
Upd BCWS

## EVAPKG3
| Proj. 1234 | Auto Necho - Auto Apps Efficiency | [9 empty] | EVA for AUI |  |  | Budgeted Hours | 1078
| Start date: |  | 2002-05-06 |  | Period: | Monthly | 17 | 28 |  |  |  |  | SPI = | 93.91% | Earned Hours
| End date: |  | 2003-09-15 |  | Group: | 1.5 |  |  |  |  | CPI |  | CPI = | 101.3% | Actual Hours
[5 empty] | 2573.99 | 2199 | 2170 |  |  | 2341.55 |  |  | EAC = | 2540.0447
Sr No | As on Date | For The Period |  |  | Cummulative
Sr No |  | BCWS | BCWP | ACWP | BCWS | BCWP | ACWP | SPI | CPI
1 | 2002-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2 | 2002-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3 | 2002-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
4 | 2002-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
5 | 2002-09-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
6 | 2002-10-31 | 4.86 |  |  | 4.86 | 0 | 0 | 0 | 0 | 0
7 | 2002-11-30 | 116.18 | 148 | 0 | 121.04 | 148 | 0 | 0 | 0 | 116.18
8 | 2002-12-31 | 344.47 | 401 | 311 | 465.51 | 549 | 311 | 1.1794 | 1.7653 | 344.47
9 | 2003-01-31 | 574.45 | 359 | 425 | 1039.96 | 908 | 736 | 0.87311 | 1.2337 | 574.45
10 | 2003-02-28 | 551.28 | 526 | 412 | 1591.24 | 1434 | 1148 | 0.90118 | 1.2491 | 551.28
11 | 2003-03-31 | 634.62 | 455 | 476 | 2225.86 | 1889 | 1624 | 0.84866 | 1.1632 | 634.62
12 | 2003-04-30 | 120.55 | 310 | 546 | 2346.41 | 2199 | 2170 | 0.93718 | 1.0134 | 120.55
13 | 2003-05-31 | 70.58 |  |  | 2416.99 | 0 | 0 | 0 | 0 | 0
14 | 2003-06-30 | 95.91 |  |  | 2512.9 | 0 | 0 | 0 | 0 | 0
15 | 2003-07-31 | 23.35 |  |  | 2536.25 | 0 | 0 | 0 | 0 | 0
16 | 2003-08-31 | 30.16 |  |  | 2566.41 | 0 | 0 | 0 | 0 | 0
17 | 2003-09-30 | 7.58 |  |  | 2573.99 | 0 | 0 | 0 | 0 | 0
18 | 2003-10-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
19 | 2003-11-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
20 | 2003-12-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
21 | 2004-01-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
22 | 2004-02-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
23 | 2004-03-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
24 | 2004-04-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
25 | 2004-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
26 | 2004-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
27 | 2004-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
28 | 2004-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
As on Date = IF(G2="Weekly",[As on Date, row above]+7,IF(G2="Bi-Weekly",[As on Date, row above]+14,IF(G2="Monthly",DATE(YEAR([As on Date, row above]),MONTH([As on Date, row above])+2,1)-1,[As on Date, row above])))
Refresh
Upd BCWS

## EVATRA
| Proj. 1234 | Auto Necho - Auto Apps Efficiency | [9 empty] | EVA for TRA |  |  | Budgeted Hours | 1078
| Start date: |  | 2002-05-06 |  | Period: | Monthly | 17 | 28 |  |  |  |  | SPI = | #DIV/0! | Earned Hours
| End date: |  | 2003-09-15 |  | Group: | 1.4 |  |  |  |  | CPI |  | CPI = | 0% | Actual Hours
[5 empty] | 86 | 0 | 0 |  |  | 0 |  |  | EAC = | 0
Sr No | As on Date | For The Period |  |  | Cummulative
Sr No |  | BCWS | BCWP | ACWP | BCWS | BCWP | ACWP | SPI | CPI
1 | 2002-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2 | 2002-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3 | 2002-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
4 | 2002-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
5 | 2002-09-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
6 | 2002-10-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
7 | 2002-11-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
8 | 2002-12-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
9 | 2003-01-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
10 | 2003-02-28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
11 | 2003-03-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
12 | 2003-04-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
13 | 2003-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
14 | 2003-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
15 | 2003-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
16 | 2003-08-31 | 34.25 |  |  | 34.25 | 0 | 0 | 0 | 0 | 0
17 | 2003-09-30 | 51.75 |  |  | 86 | 0 | 0 | 0 | 0 | 0
18 | 2003-10-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
19 | 2003-11-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
20 | 2003-12-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
21 | 2004-01-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
22 | 2004-02-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
23 | 2004-03-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
24 | 2004-04-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
25 | 2004-05-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
26 | 2004-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
27 | 2004-07-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
28 | 2004-08-31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
As on Date = IF(G2="Weekly",[As on Date, row above]+7,IF(G2="Bi-Weekly",[As on Date, row above]+14,IF(G2="Monthly",DATE(YEAR([As on Date, row above]),MONTH([As on Date, row above])+2,1)-1,[As on Date, row above])))
Refresh
Upd BCWS

## PTE
Proj. 1234 Planning Tasks Estimations |  |  | Recurring Activity Description | Start date | Finish date | Weeks Duration | Burn Rate | Total Hours | Elapsed Time in %
|  |  | Project Manager's Activities | 2002-05-06 | 2003-07-15 | 62.1429 | 12 | 745.7143 | 2034%
Project Start date | 2002-05-06 |  | OSS / TSS activities | 2002-05-06 | 2003-07-15 | 62.1429 | 10 | 621.4286 | 2034%
Project End date | 2003-07-15 |  | Team Activities (Weekly Meetings) | 2002-05-06 | 2003-07-15 | 62.1429 | 12 | 745.7143 | 2034%
Weekly meetings Start date | 2002-05-06 |  | Project Coordinator Activities | 2002-07-26 | 2003-07-15 | 50.5714 | 12 | 606.8571 | 2477%
Weekly meetings End date | 2003-07-15 |  | Project Schedule / PlanView Maintenance, and Status Reporting | 2002-08-15 | 2003-07-15 | 47.7143 | 10 | 477.1429 | 2619%
Project Duration in Calender days | 435 | days
Project Duration in Calender Weeks | 62.1429 | weeks
Work days per week | 5 | days
Project Duration in Work days | 310.7143 | days
Core Team Size (Number of Persons) | 16 | Nos
No of weekly meetings | 62.1429 | Nos
Duration of a weekly meeting | 1 | hour
Total work hours spent per weekly meeting | 16 | Hours
Hours per work unit | 6 | Hours
Total work units spent per weekly meeting | 2.6667 | Units
Total time to spend on weekly meetings | 994.2857 | hours
Hours per person to attend weekly meeting | 62.1429 | hours
Total Hours required for Schedule creation | 80 | Hours
Total Hours required for Replanning | 50 | Hours
Hours spent per week on Project Status Reporting | 2 | hours
Total Hours spent on Project Status Reporting | 124.2857 | hours
Hours spent per week on PlanView Maintenance | 2 | hour
Total Hours spent on PlanView maintenance / Reporting | 124.2857 | hours
Hours spent per week on Project Schedule maintenance | 2 | hours
Total Hours spent on Project Schedule maintenance | 124.2857 | hours
Hours spent per week on Earned Value Analysis | 1 | hour
Total Hours spent on Earned Value Analysis | 62.1429 | hours
Total hours for Project Planner | 627.1429 | hours
Hours/week | 10.092 | hours
Elapsed Time % (from start to today) | 2034%
◄▬Menu

## PVWES
Proj. 1234 |  | PlanView Work Entity Structure
| Auto Necho - Auto Apps Efficiency | [7 empty] | Start date | Finish date
| Planning Admin, Meetings, Coord | [7 empty] | 2002-05-06 | 2003-04-22
| Reqs Analysis and Solution Def/Specs | [7 empty] | 2002-05-06 | 2002-10-31
| AUI (Design, Build, Test, and Transition) | [7 empty] | 2002-10-31 | 2003-04-22
| ECHO (Design, Build, Test, and Transition) | [7 empty] | 2002-10-31 | 2003-04-22
Resource Name | Current PlanView Allocation | Total Schedule Allocation | R10481 - Planning Admin, Meetings, Coord after 8/5/02 |  | R10481 - Reqs Analysis and Solution Def/Specs | R10481 - AUI (Design, Build, Test, and Transition) | R10481 - ECHO (Design, Build, Test, and Transition) | PlanView - Schedule Alloc Difference | Remarks |  | Already used as on 8/5/02
Ashok | 500 | 500 | 500 |  | 0 | 0 | 0 | 0 | Carol/Ashok/Michelle/Vance will have total allocation only to Planning, Admin, Meetings, Coord |  | 143
Carol | 1000 | 1000 | 1000 |  | 0 | 0 | 0 | 0 |  |  | 168
Michelle | 500 | 500 | 500 |  | 0 | 0 | 0 | 0 |  |  | 69
Vance | 980 | 980 | 980 |  | 0 | 0 | 0 | 0 |  |  | 0
Amarnath | 1700 | 1774 | 270 | 74 | 300 |  | 1130 | -74 | Allocation to remaining work entities will be done after planning for remaining phases is completed. 6000 hours are reserved for remaining schedule for Design/Build/Test/Transition. |  | 196
Ed | 1000 | 1075.21 | 210 | 75 | 170.21 |  | 620 | -75.21 |  |  | 135
Eric | 1200 | 1275.28 | 130 | 75 | 100.28 |  | 970 | -75.28 |  |  | 55
Jill | 120 | 220 | 75 | 75 | 70 |  |  | -100 |  |  | 0
Lakshmi | 300 | 378 | 100 | 78 | 185 |  | 15 | -78 |  |  | 22
Mary | 135 | 356 | 100 | 76 | 180 |  |  | -221 |  |  | 24
Michael | 500 | 674 | 100 | 74 | 100 |  | 400 | -174 |  |  | 26
Murthy | 1700 | 1776 | 230 | 76 | 300 |  | 1170 | -76 |  |  | 154
Steve | 750 | 826.83 | 130 | 77 | 214.83 |  | 405 | -76.83 |  |  | 53
Tina | 520 | 597 | 125 | 77 | 185 |  | 210 | -77 |  |  | 48
Ty | 135 | 325 | 105 | 75 | 145 |  |  | -190 |  |  | 30
Witter | 200 | 290 | 85 | 75 | 130 |  |  | -90 |  |  | 10
Total Alloc | 11240 | 12547.32 | 4640 |  | 2080.32 | 0 | 4920 | -1307.32 |  |  | 1133
◄▬Menu

## WEResAllocPlan
Proj. 1234PlanView Work Entity x Resource Allocation Hours Plan
Work-Entity |  |  | Start Date | Finish Date | Total | Amarnath Bommisetti | Ashok Kumar | Bill Malone | Brian Brown | Carol Elam | Charles Paige | Daniel Lade | Dave Sanders | David Stern | Steve Durnan | Ed Weidenbenner | Eric Gullixon | EricH | Gilbert Saenz | Harry Ma | Jeff | Jill | John Nutt | Lakshmi Narayana Reddy | Lynn C Flannelly | Mary Kasley Lee | Michelle Celeschi | J Murthy | PerTeam | Sherrill Leslie | Steve Hall | Sushit Saha | Tina L Dobrinich | Ty Hartness | Vance Dejaynes | Steve Witter | Brian [GS03] Brown | Chad McCue | John Isaacson | Kasi Shanmugam | Kim Miller | Michael Frey | Sally Baugh | Zafar Awan
Proj. 1234Auto Necho - Auto Apps Efficiency Status Tracking |  | Schedule |  |  | 10598.11 | 1294.44 | 652.18 | 361.53 | 80 | 984.36 | 50 | 25 | 50 | 36.26 | 205 | 506.88 | 197.03 | 17 | 25 | 200 | 11 | 161.03 | 249.53 | 447.08 | 41.2 | 219.96 | 441.76 | 1375.46 | 90 | 25 | 599.99 | 37.53 | 435.69 | 191.56 | 1004 | 582.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PARed |  |  | 11712.25 | 1827 | 730 | 300 | 0 | 1001 | 50 | 55 | 50 | 53 | 162 | 501 | 201.5 | 0 | 25 | 100 | 0 | 0 | 300 | 300 | 0 | 121 | 299.5 | 1700 | 0 | 25 | 765 | 115 | 543.5 | 133.75 | 980 | 769 | 164 | 0 | 36.5 | 120 | 50 | 84.5 | 100 | 50
| Planning/Admin/Meetings/Coordination | Schedule |  |  | 4287.05 | 51 | 637.9 | 20 |  | 957.98 | 50 | 25 | 50 |  |  | 96.27 | 97.75 |  | 25 | 200 |  | 97.75 | 20 | 99.9 |  | 29.84 | 428.76 | 98.78 |  | 25 | 85.75 |  | 98.78 | 29.84 | 964 | 97.75
|  | PARed |  |  | 5581.75 | 366 | 730 | 20 |  | 1001 | 50 | 55 | 50 |  |  | 205 | 168 |  | 25 | 100 |  |  | 111 | 76 |  | 59 | 279.5 | 524 |  | 25 | 283 | 41 | 234.5 | 53.75 | 920 | 67 | 17 |  | 36.5 |  |  | 84.5
| Reqs Analysis and Solution Def/Specs | Schedule |  |  | 2054.07 | 440.91 | 4.28 |  |  | 6.38 | [5 empty] | 62.92 | 99.28 |  |  |  |  | 63.28 | 41 | 133.18 |  | 174.92 | 3 | 491.68 |  |  | 134.13 |  | 132.91 | 138.92 |  | 127.28
|  | PARed |  |  | 1403.5 | 580 | [9 empty] | 90 | 18.5 | [6 empty] | 9 |  | 47 | 20 | 297 |  |  | 56 |  | 63 | 65 |  | 158
| Pkg -1 Design/Build/Test/Implement | Schedule |  |  | 479 | 80 | [9 empty] | 57.69 | [8 empty] | 41.2 | 2.16 |  | 101 |  |  | 70.11 |  |  | 13.84 |  | 113
|  | PARed |  |  | 712.25 | 156 |  | 7.25 | [5 empty] | 3 | 6 | 80 | 15 | [6 empty] | 1 |  |  |  | 175 |  |  | 95 |  | 42 | 5 | 20 | 107
| Pkg -2 Design/Build/Test/Implement | Schedule |  |  | 1148 |  |  | 335 | [5 empty] | 35 |  | 100 |  | 17 |  |  | 11 |  | 182 |  |  | 3.88 |  |  | 45 |  | 155 |  |  | 2.12 | 20 | 242
|  | PARed |  |  | 1595.75 |  |  | 265.75 | [5 empty] | 50 | 18.5 | 101 | [6 empty] | 182 |  |  | 15 |  |  |  |  | 176 | 24 |  | 5 | 20 | 422 | 96.5 |  |  | 120 | 50 |  |  | 50
| Pkg -3 Design/Build/Test/Implement | Schedule |  |  | 2554 | 716 |  |  | 80 | [5 empty] | 205 | 190 | [7 empty] | 214 |  | 6.36 |  | 684 | 45 |  | 155 | 31 | 204 | 3.64 | 20
|  | PARed |  |  | 2380 | 715 | [8 empty] | 137.5 | 25 | [7 empty] | 214 |  |  |  | 704 |  |  | 155 | 50 | 204 | 5 | 20 |  | 50.5 | [5 empty] | 100
| Transition | Schedule |  |  | 75.99 | 6.53 | 10 | 6.53 |  | 20 |  |  |  | 1.26 | [8 empty] | 6.53 |  |  | 2.8 | 10 |  |  |  |  | 6.53 |  | 3.2 |  | 2.61
|  | PARed |  |  | 39 | 10 |  | 7 | [14 empty] | 7 | [12 empty] | 15
Refresh
◄▬Menu

## RemHrs
Proj. 1234Remaining Hours : WorkEntity x Resource
Work Entity Description |  | Start | Finish | Total Hrs | Amarnath Bommisetti | Andrew Woodman | Ashok Kumar | Bill Malone | Brian [GS03] Brown | Brian McKinney | Carol Elam | Chad McCue | Charles Paige | Charlie Rogers | Daniel Lade | Dave Sanders | David Stern | Duzianthan Mohandass | Ed Weidenbenner | Eric Gullixon | Gary Scott | Gilbert Saenz | Harry Ma | J Murthy | John Isaacson | John Nutt | Kasi Shanmugam | Kim Miller | Lakshmi Narayana Reddy | Mary Kasley Lee | Michael Frey | Michelle Celeschi | Sally Baugh | Santosh [H6Z5] Ramachandran | Sherrill Leslie | Steve Durnan | Steve Hall | Steve Witter | Sushit Saha | Tina L Dobrinich | Ty Hartness | Vance Dejaynes | Zafar Awan
Proj. 1234Auto Necho - Auto Apps Efficiency Status Tracking |  |  |  | 3300.5 | 136 | 35.5 | 225 | 106.5 | 64 | 0 | 467 | 0 | 13.5 | 28.25 | 7.5 | 0 | 0 | 8 | 57 | 85 | 26 | 17 | 21.25 | 311 | 0 | 156 | 66 | 0 | 158 | 31.75 | 0 | 145 | 0 | 19 | 5 | 20.5 | 182 | 15 | 62 | 141 | 17.75 | 671 | 2
| Pkg -1 Design/Build/Test/Implement |  |  | 55.75 | 24 | [14 empty] | 6.5 | [8 empty] | 1 | [11 empty] | 4.25 | 20
| R10481 - Pkg -2 Design/Build/Test/Implement |  |  | 248.25 |  |  |  | 91.5 | [10 empty] | 27 | [6 empty] | 43 | 66 |  |  | 14.5 | [10 empty] | 4.25 |  | 2
| Pkg -3 Design/Build/Test/Implement |  |  | 322.75 |  | 35.5 |  |  | 50.5 | [8 empty] | 8 | 25 | [9 empty] | 126 | [6 empty] | 20.5 |  |  | 35 |  | 2.25 | 20
| Planning/Admin/Meetings/Coordination |  |  | 2636.75 | 102 |  | 225 | 8 | 13.5 |  | 467 |  | 13.5 | 28.25 | 7.5 |  |  |  | 5 | 78.5 | 26 | 17 | 21.25 | 311 |  | 108 |  |  | 31 | 17.25 |  | 145 |  | 19 | 5 |  | 182 |  | 27 | 141 | 7 | 631
| Reqs Analysis and Solution Def/Specs |  |  | 0
| Transition |  |  | 37 | 10 |  |  | 7 | [17 empty] | 5 | [11 empty] | 15
Refresh
◄▬Menu

## ActHrs
Proj. 1234 - Actual Used Hours : WorkEntity x Resource
Work Entity Description |  | Start | Finish | Total Hrs | Amarnath Bommisetti | Andrew Woodman | Ashok Kumar | Bill Malone | Brian [GS03] Brown | Brian McKinney | Carol Elam | Chad McCue | Charles Paige | Charlie Rogers | Daniel Lade | Dave Sanders | David Stern | Duzianthan Mohandass | Ed Weidenbenner | Eric Gullixon | Gary Scott | Gilbert Saenz | Harry Ma | J Murthy | John Isaacson | John Nutt | Kasi Shanmugam | Kim Miller | Lakshmi Narayana Reddy | Mary Kasley Lee | Michael Frey | Michelle Celeschi | Sally Baugh | Santosh [H6Z5] Ramachandran | Sherrill Leslie | Steve Durnan | Steve Hall | Steve Witter | Sushit Saha | Tina L Dobrinich | Ty Hartness | Vance Dejaynes | Zafar Awan
Proj. 1234Auto Necho - Auto Apps Efficiency Status Tracking |  |  |  | 9199 | 1747 | 22 | 505 | 193.5 | 100 | 23.5 | 534 | 0 | 56.5 | 12 | 47.5 | 10.75 | 75 | 8 | 495 | 116.5 | 4 | 8 | 78.75 | 1447 | 39.5 | 144 | 54 | 63 | 142 | 89.25 | 288 | 226.75 | 23.5 | 6 | 20 | 171.5 | 665 | 803 | 62 | 439 | 116 | 314.5 | 48
| Pkg -1 Design/Build/Test/Implement |  |  | 660.5 | 132 |  |  | 7.25 | [8 empty] | 3 |  | 81 | 8.5 |  |  |  | 176 | [11 empty] | 6 | 95 | 109 |  | 42 | 0.75
| R10481 - Pkg -2 Design/Build/Test/Implement |  |  | 1645.5 |  | 7.5 |  | 174.25 | 96.5 | [7 empty] | 72 | 6 | 74 | [6 empty] | 139 | 54 | 63 |  | 0.5 | 110 |  |  |  |  | 18.5 | 257 | 466 | 33 |  | 0.75 | 25.5 | 48
| Pkg -3 Design/Build/Test/Implement |  |  | 2253.25 | 771 | 14.5 | [11 empty] | 2 | 50 |  |  |  |  | 761 |  |  |  |  | 88 |  |  |  | 23.5 |  |  | 147 | 156 |  | 15 | 222.5 | 2.75
| Planning/Admin/Meetings/Coordination |  |  | 3236.25 | 264 |  | 505 | 12 | 3.5 | 23.5 | 534 |  | 56.5 | 12 | 47.5 | 10.75 |  |  | 200 | 89.5 | 4 | 8 | 78.75 | 213 | 39.5 | 3 |  |  | 45 | 41.75 | 178 | 226.75 |  | 6 | 20 |  | 101 | 70 | 14 | 93.5 | 46.75 | 289
| Reqs Analysis and Solution Def/Specs |  |  | 1401.5 | 580 | [13 empty] | 90 | 18.5 |  |  |  | 297 |  |  |  |  | 9 | 47 | [6 empty] | 56 | 158 |  | 81 | 65
| Transition |  |  | 2 | [21 empty] | 2
Refresh
◄▬Menu

## WEResHrs
Proj. 1234 - WorkEntity x Resource wise Schedule/Allocated/Used/Remaining hours
Work-Entity |  |  | Start | Finish | Total Hrs | Amarnath Bommisetti | Andrew Woodman | Ashok Kumar | Bill Malone | Brian [GS03] Brown | Brian McKinney | Carol Elam | Chad McCue | Charles Paige | Charlie Rogers | Daniel Lade | Dave Sanders | David Stern | Duzianthan Mohandass | Ed Weidenbenner | Eric Gullixon | Gary Scott | Gilbert Saenz | Harry Ma | J Murthy | John Isaacson | John Nutt | Kasi Shanmugam | Kim Miller | Lakshmi Narayana Reddy | Mary Kasley Lee | Michael Frey | Michelle Celeschi | Sally Baugh | Santosh [H6Z5] Ramachandran | Sherrill Leslie | Steve Durnan | Steve Hall | Steve Witter | Sushit Saha | Tina L Dobrinich | Ty Hartness | Vance Dejaynes | Zafar Awan
Proj. 1234Auto Necho - Auto Apps Efficiency Status Tracking |  | Schedule |  |  | 10197.88 | 1294.44 | 0 | 652.18 | 361.53 | 0 | 0 | 984.36 | 0 | 50 | 0 | 25 | 50 | 36.26 | 0 | 506.88 | 197.03 | 0 | 25 | 200 | 1375.46 | 0 | 249.53 | 0 | 0 | 447.08 | 219.96 | 0 | 441.76 | 0 | 0 | 25 | 205 | 599.99 | 582.64 | 37.53 | 435.69 | 191.56 | 1004 | 0
|  | PARed |  |  | 11712.25 | 1827 | 0 | 730 | 300 | 164 | 0 | 1001 | 0 | 50 | 0 | 55 | 50 | 53 | 0 | 501 | 201.5 | 0 | 25 | 100 | 1700 | 36.5 | 300 | 120 | 50 | 300 | 121 | 84.5 | 299.5 | 100 | 0 | 25 | 162 | 765 | 769 | 115 | 543.5 | 133.75 | 980 | 50
|  | Used |  |  | 9199 | 1747 | 22 | 505 | 193.5 | 100 | 23.5 | 534 | 0 | 56.5 | 12 | 47.5 | 10.75 | 75 | 8 | 495 | 116.5 | 4 | 8 | 78.75 | 1447 | 39.5 | 144 | 54 | 63 | 142 | 89.25 | 288 | 226.75 | 23.5 | 6 | 20 | 171.5 | 665 | 803 | 62 | 439 | 116 | 314.5 | 48
|  | Remaining |  |  | 3300.5 | 136 | 35.5 | 225 | 106.5 | 64 | 0 | 467 | 0 | 13.5 | 28.25 | 7.5 | 0 | 0 | 8 | 57 | 85 | 26 | 17 | 21.25 | 311 | 0 | 156 | 66 | 0 | 158 | 31.75 | 0 | 145 | 0 | 19 | 5 | 20.5 | 182 | 15 | 62 | 141 | 17.75 | 671 | 2
| Pkg -1 Design/Build/Test/Implement | Schedule |  |  | 437.8 | 80 | [13 empty] | 57.69 |  |  |  |  | 101 | [5 empty] | 2.16 | [6 empty] | 70.11 | 113 |  |  | 13.84
|  | PARed |  |  | 712.25 | 156 |  |  | 7.25 | [8 empty] | 3 |  | 80 | 15 |  |  |  | 175 |  |  |  |  | 1 | [6 empty] | 6 | 95 | 107 |  | 42 | 5 | 20
|  | Used |  |  | 660.5 | 132 |  |  | 7.25 | [8 empty] | 3 |  | 81 | 8.5 |  |  |  | 176 | [11 empty] | 6 | 95 | 109 |  | 42 | 0.75
|  | Remaining |  |  | 55.75 | 24 | [14 empty] | 6.5 | [8 empty] | 1 | [11 empty] | 4.25 | 20
| Pkg -2 Design/Build/Test/Implement | Schedule |  |  | 1075 |  |  |  | 335 | [8 empty] | 35 |  | 100 | [6 empty] | 182 |  |  |  | 3.88 | [6 empty] | 155 | 242 |  |  | 2.12 | 20
|  | PARed |  |  | 1595.75 |  |  |  | 265.75 | 96.5 | [7 empty] | 50 |  | 101 | [6 empty] | 182 | 120 | 50 |  | 15 | [5 empty] | 18.5 | 176 | 422 | 24 |  | 5 | 20 | 50
|  | Used |  |  | 1645.5 |  | 7.5 |  | 174.25 | 96.5 | [7 empty] | 72 | 6 | 74 | [6 empty] | 139 | 54 | 63 |  | 0.5 | 110 |  |  |  |  | 18.5 | 257 | 466 | 33 |  | 0.75 | 25.5 | 48
|  | Remaining |  |  | 248.25 |  |  |  | 91.5 | [10 empty] | 27 | [6 empty] | 43 | 66 |  |  | 14.5 | [10 empty] | 4.25 |  | 2
| Pkg -3 Design/Build/Test/Implement | Schedule |  |  | 2429 | 716 | [13 empty] | 190 |  |  |  |  | 684 |  |  |  |  | 214 | 6.36 | [5 empty] | 205 | 155 |  | 31 | 204 | 3.64 | 20
|  | PARed |  |  | 2380 | 715 |  |  |  | 50.5 | [9 empty] | 25 |  |  |  |  | 704 |  |  |  |  | 214 |  |  |  | 100 |  |  | 137.5 | 155 |  | 50 | 204 | 5 | 20
|  | Used |  |  | 2253.25 | 771 | 14.5 | [11 empty] | 2 | 50 |  |  |  |  | 761 |  |  |  |  | 88 |  |  |  | 23.5 |  |  | 147 | 156 |  | 15 | 222.5 | 2.75
|  | Remaining |  |  | 322.75 |  | 35.5 |  |  | 50.5 | [8 empty] | 8 | 25 | [9 empty] | 126 | [6 empty] | 20.5 |  |  | 35 |  | 2.25 | 20
| Planning/Admin/Meetings/Coordination | Schedule |  |  | 4189.3 | 51 |  | 637.9 | 20 |  |  | 957.98 |  | 50 |  | 25 | 50 |  |  | 96.27 | 97.75 |  | 25 | 200 | 98.78 |  | 20 |  |  | 99.9 | 29.84 |  | 428.76 |  |  | 25 |  | 85.75 | 97.75 |  | 98.78 | 29.84 | 964
|  | PARed |  |  | 5581.75 | 366 |  | 730 | 20 | 17 |  | 1001 |  | 50 |  | 55 | 50 |  |  | 205 | 168 |  | 25 | 100 | 524 | 36.5 | 111 |  |  | 76 | 59 | 84.5 | 279.5 |  |  | 25 |  | 283 | 67 | 41 | 234.5 | 53.75 | 920
|  | Used |  |  | 3236.25 | 264 |  | 505 | 12 | 3.5 | 23.5 | 534 |  | 56.5 | 12 | 47.5 | 10.75 |  |  | 200 | 89.5 | 4 | 8 | 78.75 | 213 | 39.5 | 3 |  |  | 45 | 41.75 | 178 | 226.75 |  | 6 | 20 |  | 101 | 70 | 14 | 93.5 | 46.75 | 289
|  | Remaining |  |  | 2636.75 | 102 |  | 225 | 8 | 13.5 |  | 467 |  | 13.5 | 28.25 | 7.5 |  |  |  | 5 | 78.5 | 26 | 17 | 21.25 | 311 |  | 108 |  |  | 31 | 17.25 |  | 145 |  | 19 | 5 |  | 182 |  | 27 | 141 | 7 | 631
| Reqs Analysis and Solution Def/Specs | Schedule |  |  | 1990.79 | 440.91 |  | 4.28 |  |  |  | 6.38 | [7 empty] | 62.92 | 99.28 |  |  |  | 491.68 |  | 41 |  |  | 133.18 | 174.92 |  | 3 |  |  |  |  | 134.13 | 127.28 |  | 132.91 | 138.92
|  | PARed |  |  | 1403.5 | 580 | [13 empty] | 90 | 18.5 |  |  |  | 297 |  |  |  |  | 9 | 47 |  | 20 |  |  |  |  | 56 | 158 |  | 63 | 65
|  | Used |  |  | 1401.5 | 580 | [13 empty] | 90 | 18.5 |  |  |  | 297 |  |  |  |  | 9 | 47 | [6 empty] | 56 | 158 |  | 81 | 65
|  | Remaining |  |  | 0
| Transition | Schedule |  |  | 75.99 | 6.53 |  | 10 | 6.53 |  |  | 20 | [5 empty] | 1.26 | [8 empty] | 6.53 |  |  |  | 2.8 |  | 10 | [5 empty] | 2.61 | 6.53 |  | 3.2
|  | PARed |  |  | 39 | 10 |  |  | 7 | [17 empty] | 7 | [11 empty] | 15
|  | Used |  |  | 2 | [21 empty] | 2
|  | Remaining |  |  | 37 | 10 |  |  | 7 | [17 empty] | 5 | [11 empty] | 15
◄▬Menu

## ResWEHrs
Proj. 1234 | Resouce x Work Entity wise allocation Dates, Used and Remaining hours
Name | Work Entity | Start | Finish | UsedHrs | RemHrs | TotAlloc
Amarnath Bommisetti | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-09-30 | 264 | 102
| Reqs Analysis and Solution Def/Specs | 2002-08-01 | 2003-03-14 | 580 | 0 | 580
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 | 2003-08-07 | 132 | 24 | 156
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 |  | 771 | 0 | 771
| Transition | 2003-04-21 | 2004-01-23 | 0 | 10 | 10
Andrew Woodman | Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 7.5 | 0 | 7.5
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 | 2003-07-31 | 14.5 | 35.5 | 50
Ashok Kumar | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-09-30 | 505 | 225 | 730
Bill Malone | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-07-10 | 12 | 8 | 20
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 |  | 7.25 | 0 | 7.25
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 | 2003-06-30 | 174.25 | 91.5 | 265.75
| Transition | 2003-04-21 | 2004-01-23 | 0 | 7 | 7
Brian [GS03] Brown | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-13 | 3.5 | 13.5 | 17
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 96.5 | 0 | 96.5
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 | 2003-09-30 | 0 | 50.5 | 50.5
Brian McKinney | Planning/Admin/Meetings/Coordination | 2002-04-29 |  | 23.5 | 0 | 23.5
Carol Elam | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-09-30 | 534 | 467 | 1001
Chad McCue | Pkg -1 Design/Build/Test/Implement | 2002-09-30 |  | 0 | 0 | 0
Charles Paige | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-10 | 56.5 | 13.5 | 70
Charlie Rogers | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-09-30 | 12 | 28.25 | 40.25
Daniel Lade | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-08-11 | 47.5 | 7.5 | 55
Dave Sanders | Planning/Admin/Meetings/Coordination | 2002-04-29 |  | 10.75 | 0 | 10.75
David Stern | Pkg -1 Design/Build/Test/Implement | 2002-09-30 |  | 3 | 0 | 3
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 72 | 0 | 72
Duzianthan Mohandass | Planning/Admin/Meetings/Coordination | 2002-04-29 |  | 0 | 0 | 0
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 6 | 0 | 6
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 | 2003-06-10 | 2 | 8 | 10
Ed Weidenbenner | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-09 | 200 | 5 | 205
| Reqs Analysis and Solution Def/Specs | 2002-08-01 | 2003-03-14 | 90 | 0 | 90
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 |  | 81 | 0 | 81
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 | 2003-09-30 | 74 | 27 | 101
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 | 2003-06-25 | 50 | 25 | 75
Eric Gullixon | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-23 | 89.5 | 78.5 | 168
| Reqs Analysis and Solution Def/Specs | 2002-08-01 | 2003-03-14 | 18.5 | 0 | 18.5
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 | 2003-08-05 | 8.5 | 6.5 | 15
Gary Scott | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-17 | 4 | 26 | 30
Gilbert Saenz | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-08-26 | 8 | 17 | 25
Harry Ma | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-09-30 | 78.75 | 21.25 | 100
J Murthy | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-09-15 | 213 | 311 | 524
| Reqs Analysis and Solution Def/Specs | 2002-08-01 | 2003-03-14 | 297 | 0 | 297
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 |  | 176 | 0 | 176
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 |  | 761 | 0 | 761
John Isaacson | Planning/Admin/Meetings/Coordination | 2002-04-29 |  | 39.5 | 0 | 39.5
John Nutt | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-09-15 | 3 | 108 | 111
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 | 2003-07-08 | 139 | 43 | 182
| Transition | 2003-04-21 | 2003-08-01 | 2 | 5 | 7
Kasi Shanmugam | Pkg -2 Design/Build/Test/Implement | 2002-10-21 | 2003-09-30 | 54 | 66 | 120
Kim Miller | Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 63 | 0 | 63
Lakshmi Narayana Reddy | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-12 | 45 | 31 | 76
| Reqs Analysis and Solution Def/Specs | 2002-08-01 | 2003-03-14 | 9 | 0 | 9
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 | 2003-06-09 | 0 | 1 | 1
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 | 2003-09-30 | 88 | 126 | 214
Mary Kasley Lee | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-11 | 41.75 | 17.25 | 59
| Reqs Analysis and Solution Def/Specs | 2002-08-01 | 2003-03-14 | 47 | 0 | 47
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 | 2003-06-10 | 0.5 | 14.5 | 15
| Transition | 2003-04-21 |  | 0 | 0 | 0
Michael Frey | Planning/Admin/Meetings/Coordination | 2002-04-29 |  | 178 | 0 | 178
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 110 | 0 | 110
Michelle Celeschi | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-09-30 | 226.75 | 145 | 371.75
Sally Baugh | Pkg -3 Design/Build/Test/Implement | 2002-12-02 |  | 23.5 | 0 | 23.5
Santosh [H6Z5] Ramachandran | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-11 | 6 | 19 | 25
Sherrill Leslie | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-24 | 20 | 5 | 25
Steve Durnan | Pkg -1 Design/Build/Test/Implement | 2002-09-30 |  | 6 | 0 | 6
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 18.5 | 0 | 18.5
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 | 2003-09-30 | 147 | 20.5 | 167.5
Steve Hall | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-07-11 | 101 | 182 | 283
| Reqs Analysis and Solution Def/Specs | 2002-08-01 | 2003-03-14 | 56 | 0 | 56
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 |  | 95 | 0 | 95
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 257 | 0 | 257
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 |  | 156 | 0 | 156
Steve Witter | Planning/Admin/Meetings/Coordination | 2002-04-29 |  | 70 | 0 | 70
| Reqs Analysis and Solution Def/Specs | 2002-08-01 | 2003-03-14 | 158 | 0 | 158
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 |  | 109 | 0 | 109
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 466 | 0 | 466
| Transition | 2003-04-21 | 2003-12-24 | 0 | 15 | 15
Sushit Saha | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-12 | 14 | 27 | 41
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 33 | 0 | 33
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 | 2003-09-30 | 15 | 35 | 50
Tina L Dobrinich | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-07-03 | 93.5 | 141 | 234.5
| Reqs Analysis and Solution Def/Specs | 2002-08-01 | 2003-03-14 | 81 | 0 | 81
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 |  | 42 | 0 | 42
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 |  | 222.5 | 0 | 222.5
Ty Hartness | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-06-09 | 46.75 | 7 | 53.75
| Reqs Analysis and Solution Def/Specs | 2002-08-01 | 2003-03-14 | 65 | 0 | 65
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 | 2003-06-09 | 0.75 | 4.25 | 5
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 | 2003-06-09 | 0.75 | 4.25 | 5
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 | 2003-06-09 | 2.75 | 2.25 | 5
| Transition | 2003-04-21 |  | 0 | 0 | 0
Vance Dejaynes | Planning/Admin/Meetings/Coordination | 2002-04-29 | 2003-10-02 | 289 | 631 | 920
| Pkg -1 Design/Build/Test/Implement | 2002-09-30 | 2003-08-15 | 0 | 20 | 20
| Pkg -2 Design/Build/Test/Implement | 2002-10-21 |  | 25.5 | 0 | 25.5
| Pkg -3 Design/Build/Test/Implement | 2002-12-02 | 2003-08-19 | 0 | 20 | 20
Zafar Awan | Pkg -2 Design/Build/Test/Implement | 2002-10-21 | 2003-06-30 | 48 | 2 | 50
UpFinishDTinTeam
Refresh
◄▬Menu

## WRMHrs
R10481 - AUTO-INCREASE UNDERWRITING PRODUCT ORDER
| 2002-04-01 | 2002-05-01 | 2002-06-01 | 2002-07-01 | 2002-08-01 | 2002-09-01 | 2002-10-01 | 2002-11-01 | 2002-12-01 | 2003-01-01 | 2003-02-01 | 2003-03-01 | 2003-04-01 | 2003-05-01 | 2003-06-01 | 2003-07-01 | 2003-08-01 | 2003-09-01 | 2003-10-01 | 2003-11-01 | 2003-12-01 | 2004-01-01 | Total
R10481 - Planning/Admin/Meetings/Coordination
Leslie Sherrill | [6 empty] | 7 |  | 2 | 1 |  |  | 5 | 5 | 5 | [7 empty] | 5
Nutt John | [8 empty] | 1 |  |  |  | 2 |  | 36.58 | 37.38 | 25.57 | 8.47 |  |  |  |  | 108
Paige Charles | [6 empty] | 17.75 | 10.25 | 5.75 | 5.65 | 3.35 | 0.5 | 10.5 | 2.75 | 13.5 | [7 empty] | 13.5
Dobrinich Tina L |  | 10 | 11.5 | 24 | 4.5 | 25 | 7 | 3 | 5 | 4 | 1 | 1 |  |  | 124 | 17 | [6 empty] | 141
Celeschi Michelle | 4 | 30.25 | 17 | 16 | 18.5 | 9.5 | 17 | 23.5 | 18.5 | 18.5 | 17.5 | 17.25 | 9.25 | 10 | 31 | 41.78 | 37.98 | 34.23 |  |  |  |  | 145
Scott Gary | [13 empty] | 2 | 26 | [7 empty] | 26
Hall Steve |  | 4 | 19 | 30 | 1 |  | 6 |  | 22 | 1 | 1 |  | 2 | 15 | 124 | 58 | [6 empty] | 182
Brown Brian [GS03] | [12 empty] | 3 | 0.5 | 13.5 | [7 empty] | 13.5
Murthy J |  | 6 | 33 | 132 | 16 | 3 | 6 | 2 | 3 | 3 | 2 | 2 | 1 | 4 | 83.58 | 104.9 | 87.78 | 34.73 |  |  |  |  | 311
Reddy Lakshmi Narayana |  | 6 | 7 | 9 |  | 7 | 3 |  |  |  | 5 | 10 |  |  | 31 | [7 empty] | 31
Ramachandran Santosh [H6Z5] | [13 empty] | 6 | 19 | [7 empty] | 19
Kumar Ashok |  | 44 | 49 | 44 | 41 | 37 | 54 | 41 | 38 | 44 | 31 | 31 | 33 | 27 | 55.53 | 65.75 | 54.88 | 48.82 |  |  |  |  | 224.98
Bommisetti Amarnath |  |  |  | 220 | 19 | 3 | 5 | 4 | 2 | 2 | 2 | 2 | 3 | 2 | 30.35 | 35.02 | 22.07 | 14.55 |  |  |  |  | 101.98
Elam Carol |  | 56 | 39.5 | 67.5 | 39.5 | 46.5 | 46.5 | 58 | 48 | 48 | 18 | 21.5 | 26.5 | 29.85 | 100 | 134.78 | 120.73 | 111.48 |  |  |  |  | 467
Lee Mary Kasley |  |  | 5.25 | 15.75 | 8.25 | 2 | 4.5 | 2.5 | 1.75 | 0.25 | 0.25 | 0.5 | 0.75 |  | 17.25 | [7 empty] | 17.25
Hartness Ty |  |  | 6.5 | 24 | 0.25 | 1.25 | 4.5 | 1.25 | 1 | 2.5 | 2 |  | 2.5 |  | 7 | [7 empty] | 7
Dejaynes Vance |  |  |  | 10.5 | 32.5 | 53.5 | 40.5 | 45 | 35.5 | 32.5 | 24.5 | 11.5 | 3.5 | 6.5 | 124 | 170.5 | 162.75 | 162.75 | 11 |  |  |  | 631
Gullixon Eric |  | 8 | 11 | 33 | 11.5 | 4 | 6.5 | 1 | 1 | 4 | 3.5 | 4 | 2 | 1 | 78.5 | [7 empty] | 78.5
Malone Bill | [8 empty] | 2 | 2.5 | 2 | 0.5 | 1 | 4 | 6.67 | 1.33 | [6 empty] | 8
Saha Sushit | [6 empty] | 3 | 8 | 1 | 1 | 1 |  |  |  | 27 | [7 empty] | 27
Weidenbenner Ed |  | 27 | 43 | 60 | 23 | 12 | 13 | 4 | 7 | 3 | 3 | 4 |  | 1 | 5 | [7 empty] | 5
Lade Daniel | [6 empty] | 7 | 4 | 1 | 4 | 0.5 |  | 10.25 | 20.75 | 3.87 | 2.85 | 0.77 | [5 empty] | 7.48
Saenz Gilbert | [6 empty] | 2 |  | 3 | 1 | 1 |  | 1 |  | 10.1 | 4.65 | 2.23 | [5 empty] | 16.98
Ma Harry | [6 empty] | 5 | 18 | 10 | 16.25 | 8 | 5.5 | 9.25 | 4.75 | 4.78 | 5.68 | 5.42 | 5.35 |  |  |  |  | 21.23
Rogers Charlie | [13 empty] | 12 | 8.27 | 8.62 | 6.15 | 5.22 |  |  |  |  | 28.25
Frey Michael |  | 6 | 8.5 | 11 | 12 | 6 | 7 | 8 | 10 | 12 | 8 | 11.5 | 61 | 19 | [8 empty] | 180
Isaacson John |  |  |  |  | 12.5 | 3.5 | 4.5 | 4 | 5.5 | 7 | 0.5 | 3 | [10 empty] | 40.5
Witter Steve |  |  |  | 8 | 9 | 19 | 5 |  |  | 4 |  | 27 | [10 empty] | 72
Sanders Dave | [6 empty] | 4.25 | 2.25 | 3 |  | 0.25 |  | 1 | [9 empty] | 10.75
McKinney Brian | [12 empty] | 5.5 | 17 | 1 | [7 empty] | 23.5
| 4 | 197.25 | 250.25 | 704.75 | 248.5 | 232.25 | 276 | 239.75 | 227 | 217.15 | 135.35 | 152.75 | 193 | 190.1 | 985.48 | 688.25 | 526.33 | 425.6 | 11 |  |  |  | 2636.67
R10481 - Reqs Analysis and Solution Def/Specs
Dobrinich Tina L |  |  |  |  | 11 | 4 | 15 | 19 | 7 | 10 | 6 | 12 | [10 empty] | 84
Bommisetti Amarnath |  |  |  |  | 149 | 158 | 102 | 44 | 127 | [13 empty] | 580
Weidenbenner Ed |  |  |  |  | 24 | 30 | 22 | 13 | 5 | [13 empty] | 94
Murthy J |  |  |  |  | 53 | 129 | 65 | 50 | [14 empty] | 297
Gullixon Eric |  |  |  |  | 1.5 | 15 | 0.5 |  | 1.5 | [13 empty] | 18.5
Hartness Ty |  |  |  |  | 16.75 | 27.25 | 5.75 | 11.5 | 1.5 | 2.25 | [12 empty] | 65
Hall Steve |  |  |  |  | 42 | 24 | [16 empty] | 66
Witter Steve |  |  |  |  | 19 | 29 | 111 | 3 | [14 empty] | 162
Lee Mary Kasley |  |  |  |  | 11.75 | 20 | 6.5 | 9.25 | 2.5 | [13 empty] | 50
Reddy Lakshmi Narayana | [5 empty] | 7 | 2 | [15 empty] | 9
[5 empty] | 328 | 443.25 | 329.75 | 149.75 | 144.5 | 12.25 | 6 | 12 | [10 empty] | 1425.5
R10481 - Pkg -1 Design/Build/Test/Implement
Reddy Lakshmi Narayana | [14 empty] | 1 | [7 empty] | 1
Bommisetti Amarnath | [6 empty] | 44 | 86 | 2 | [5 empty] | 14.38 | 8.78 | 0.83 | [5 empty] | 24
Hartness Ty | [8 empty] | 0.75 | [5 empty] | 4.25 | [7 empty] | 4.25
Dejaynes Vance | [14 empty] | 11.37 | 7.23 | 1.4 | [5 empty] | 20
Gullixon Eric | [9 empty] | 1 | 4.5 | 1 |  | 2 | 3.3 | 2.83 | 0.37 | [5 empty] | 6.5
Weidenbenner Ed | [6 empty] | 4 | 22 | 25 | 20 | 6 | 4 | [10 empty] | 81
Murthy J | [5 empty] | 7 | 46 | 73 | 39 |  |  |  | 8 | 3 | [8 empty] | 176
Malone Bill | [6 empty] | 6.25 | 1 | [14 empty] | 7.25
Hall Steve | [6 empty] | 2 | 56 | 34 | 3 | [12 empty] | 95
Durnan Steve | [7 empty] | 6 | [14 empty] | 6
Dobrinich Tina L | [6 empty] | 4 | 7 | 24.5 | 6.5 | [12 empty] | 42
Stern David | [7 empty] | 3 | [14 empty] | 3
Witter Steve | [8 empty] | 82 | 5 |  |  | 22 | [9 empty] | 109
[6 empty] | 7 | 106.25 | 254 | 207.25 | 35.5 | 10.5 | 5 | 30 | 5 | 34.3 | 18.85 | 2.6 | [5 empty] | 55.75
R10481 - Pkg -2 Design/Build/Test/Implement
Awan Zafar | [8 empty] | 8 | 7 | 9 | 6 | 5 | 7 | 2 | [7 empty] | 2
Nutt John | [6 empty] | 3 | 72 | 25 | 4 | 4 | 6 | 18 | 7 | 34.6 | 8.4 | [6 empty] | 43
Shanmugam Kasi | [10 empty] | 8 |  | 9.5 | 36.5 | 20.67 | 25.08 | 12.83 | 7.42 |  |  |  |  | 66
Lee Mary Kasley | [10 empty] | 0.5 |  |  |  | 14.5 | [7 empty] | 14.5
Hartness Ty | [9 empty] | 0.75 |  |  |  |  | 4.25 | [7 empty] | 4.25
Malone Bill | [7 empty] | 26.25 | 51.5 | 35 | 13 | 16.5 | 16 | 16 | 91.5 | [7 empty] | 91.5
Weidenbenner Ed | [8 empty] | 2 | 13 | 17 | 20 | 15 | 5 | 10.43 | 5.72 | 5.42 | 5.43 |  |  |  |  | 27
Witter Steve | [9 empty] | 93 | 125 | 82 | 88 | 68 | 10 | [7 empty] | 466
Miller Kim | [8 empty] | 2 |  |  | 2 | 5 | 54 | [8 empty] | 63
Hall Steve | [6 empty] | 1 |  | 15 | 52 | 39 | 21 | 68 | 61 | [8 empty] | 257
Saha Sushit | [7 empty] | 3 | 5 | 14 | 9 | 2 | [10 empty] | 33
Brown Brian [GS03] | [7 empty] | 32 | 64.5 | [13 empty] | 96.5
Durnan Steve | [7 empty] | 15.5 | 3 | [13 empty] | 18.5
Stern David | [7 empty] | 1 | 6 | 32 | 13 | 9 | 1 | 6 | 4 | [7 empty] | 72
Dejaynes Vance | [9 empty] | 6 |  | 4.5 | 8 | 7 | [8 empty] | 25.5
Woodman Andrew | [11 empty] | 5.5 | 2 | [9 empty] | 7.5
Mohandass Duzianthan | [12 empty] | 2 | 4 | [8 empty] | 6
Frey Michael | [12 empty] | 30 | 70 | 10 | [7 empty] | 110
[7 empty] | 4 | 149.75 | 182 | 256.75 | 237.5 | 174.5 | 267.5 | 341.5 | 177.95 | 39.2 | 18.25 | 12.85 |  |  |  |  | 248.25
R10481 - Pkg -3 Design/Build/Test/Implement
Woodman Andrew | [13 empty] | 14.5 | 17.52 | 17.98 | [6 empty] | 35.5
Brown Brian [GS03] | [14 empty] | 19.88 | 17.7 | 7.48 | 5.43 |  |  |  |  | 50.5
Reddy Lakshmi Narayana | [9 empty] | 2 | 2 |  | 69 | 15 | 32.52 | 42.63 | 32.58 | 18.27 |  |  |  |  | 126
Hartness Ty | [11 empty] | 0.75 | 0.25 | 0.5 | 2.25 | [7 empty] | 2.25
Dejaynes Vance | [14 empty] | 12.53 | 5.8 | 1.67 | [5 empty] | 20
Durnan Steve | [8 empty] | 11 | 31 | 30.5 | 30 | 24.5 | 16 | 4.13 | 5.68 | 5.42 | 5.27 |  |  |  |  | 20.5
Mohandass Duzianthan | [13 empty] | 2 | 8 | [7 empty] | 8
Saha Sushit | [11 empty] | 6 | 5 | 4 | 14.22 | 10.08 | 5.43 | 5.25 |  |  |  |  | 34.98
Weidenbenner Ed | [8 empty] | 2 | 1 | 1 | 4 | 23 | 17 | 25 | [7 empty] | 25
Dobrinich Tina L | [9 empty] | 11 | 13 | 34.5 | 122 | 42 | [8 empty] | 222.5
Murthy J | [8 empty] | 124 | 176 | 169 | 172 | 106 | 14 | [8 empty] | 761
Hall Steve | [8 empty] | 4 | 13 | 17 | 28 | 42 | 52 | [8 empty] | 156
Bommisetti Amarnath | [8 empty] | 25 | 191 | 175 | 189 | 137 | 54 | [8 empty] | 771
Baugh Sally | [10 empty] | 4 | 4 | 11 | 4.5 | [8 empty] | 23.5
[9 empty] | 166 | 425 | 411.5 | 468.25 | 539.75 | 235.5 | 136.05 | 99.88 | 52.58 | 34.22 |  |  |  |  | 322.73
R10481 - Transition
Nutt John | [12 empty] | 2 |  | 2.07 | 2.83 | 0.1 | [5 empty] | 5
Witter Steve | [19 empty] | 3.87 | 11.13 |  | 15
Bommisetti Amarnath | [19 empty] | 1.55 | 5.68 | 2.77 | 10
Malone Bill | [19 empty] | 2.2 | 2.83 | 1.97 | 7
[13 empty] | 2 |  | 2.07 | 2.83 | 0.1 |  |  | 7.62 | 19.65 | 4.73 | 37
| 4 | 197.25 | 250.25 | 704.75 | 576.5 | 682.5 | 716 | 793.25 | 926.75 | 946.65 | 800.85 | 812.5 | 1032.25 | 772.1 | 1335.85 | 849.02 | 599.87 | 472.67 | 11 | 7.62 | 19.65 | 4.73 | 3300.4
◄▬Menu

## RTR001
37782 | Resource Planned vs Actual Work | [5 empty] | Page: | 1
[R_TR_001]
NECHO Auto Apps Efficiency
|  |  | Planned |  | Actual |  | Hours
|  | Start |  | Finish | Start | Finish | Actual | Remain
Kumar Ashok
Planning/Admin/Meetings/Coordination |  | 37781 | 37894 |  | 37375 |  | 505 | 225
| SUBTOTAL | [5 empty] | 505 | 225
Brown Brian [GS03]
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 96.5 | 0
Pkg -3 Design/Build/Test/Implement |  | 37781 | 37894 |  | 37592 |  | 0 | 50.5
Planning/Admin/Meetings/Coordination |  | 37781 | 37785 |  | 37375 |  | 3.5 | 13.5
| SUBTOTAL | [5 empty] | 100 | 64
Bommisetti Amarnath
Planning/Admin/Meetings/Coordination |  | 37781 | 37894 |  | 37375 |  | 264 | 102
Reqs Analysis and Solution Def/Specs |  |  |  |  | 37469 | 37694 | 580 | 0
Pkg -1 Design/Build/Test/Implement |  | 37781 | 37840 |  | 37529 |  | 132 | 24
Pkg -3 Design/Build/Test/Implement |  |  |  |  | 37592 |  | 771 | 0
Transition |  | 37944 | 38009 |  | 37732 |  | 0 | 10
| SUBTOTAL | [5 empty] | 1747 | 136
Mohandass Duzianthan
Pkg -3 Design/Build/Test/Implement |  | 37781 | 37782 |  | 37592 |  | 2 | 8
Planning/Admin/Meetings/Coordination |  |  |  |  | 37375 |  | 0 | 0
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 6 | 0
| SUBTOTAL | [5 empty] | 8 | 8
Murthy J
Planning/Admin/Meetings/Coordination |  | 37781 | 37879 |  | 37375 |  | 213 | 311
Reqs Analysis and Solution Def/Specs |  |  |  |  | 37469 | 37694 | 297 | 0
Pkg -1 Design/Build/Test/Implement |  |  |  |  | 37529 |  | 176 | 0
Pkg -3 Design/Build/Test/Implement |  |  |  |  | 37592 |  | 761 | 0
| SUBTOTAL | [5 empty] | 1447 | 311
Ramachandran Santosh [H6Z5]
Planning/Admin/Meetings/Coordination |  | 37781 | 37783 |  | 37375 |  | 6 | 19
| SUBTOTAL | [5 empty] | 6 | 19
Reddy Lakshmi Narayana
Planning/Admin/Meetings/Coordination |  | 37781 | 37784 |  | 37375 |  | 45 | 31
Reqs Analysis and Solution Def/Specs |  |  |  |  | 37469 | 37694 | 9 | 0
Pkg -1 Design/Build/Test/Implement |  | 37781 | 37781 |  | 37529 |  | 0 | 1
Pkg -3 Design/Build/Test/Implement |  | 37781 | 37894 |  | 37592 |  | 88 | 126
| SUBTOTAL | [5 empty] | 142 | 158
Saha Sushit
Planning/Admin/Meetings/Coordination |  | 37781 | 37784 |  | 37375 |  | 14 | 27
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 33 | 0
Pkg -3 Design/Build/Test/Implement |  | 37781 | 37894 |  | 37592 |  | 15 | 35
| SUBTOTAL | [5 empty] | 62 | 62
Shanmugam Kasi
Pkg -2 Design/Build/Test/Implement |  | 37781 | 37894 |  | 37550 |  | 54 | 66
| SUBTOTAL | [5 empty] | 54 | 66
Lade Daniel
Planning/Admin/Meetings/Coordination |  | 37781 | 37844 |  | 37375 |  | 47.5 | 7.5
| SUBTOTAL | [5 empty] | 47.5 | 7.5
Ma Harry
Planning/Admin/Meetings/Coordination |  | 37781 | 37894 |  | 37375 |  | 78.75 | 21.25
| SUBTOTAL | [5 empty] | 78.75 | 21.25
Rogers Charlie
Planning/Admin/Meetings/Coordination |  | 37781 | 37894 |  | 37375 |  | 12 | 28.25
| SUBTOTAL | [5 empty] | 12 | 28.25
Saenz Gilbert
Planning/Admin/Meetings/Coordination |  | 37781 | 37859 |  | 37375 |  | 8 | 17
| SUBTOTAL | [5 empty] | 8 | 17
Sanders Dave
Planning/Admin/Meetings/Coordination |  |  |  |  | 37375 |  | 10.75 | 0
| SUBTOTAL | [5 empty] | 10.75 | 0
Scott Gary
Planning/Admin/Meetings/Coordination |  | 37781 | 37789 |  | 37375 |  | 4 | 26
| SUBTOTAL | [5 empty] | 4 | 26
Paige Charles
Planning/Admin/Meetings/Coordination |  | 37781 | 37782 |  | 37375 |  | 56.5 | 13.5
| SUBTOTAL | [5 empty] | 56.5 | 13.5
McKinney Brian
Planning/Admin/Meetings/Coordination |  |  |  |  | 37375 |  | 23.5 | 0
| SUBTOTAL | [5 empty] | 23.5 | 0
Woodman Andrew
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 7.5 | 0
Pkg -3 Design/Build/Test/Implement |  | 37781 | 37833 |  | 37592 |  | 14.5 | 35.5
| SUBTOTAL | [5 empty] | 22 | 35.5
Dobrinich Tina L
Planning/Admin/Meetings/Coordination |  | 37781 | 37805 |  | 37375 |  | 93.5 | 141
Reqs Analysis and Solution Def/Specs |  |  |  |  | 37469 | 37694 | 81 | 0
Pkg -1 Design/Build/Test/Implement |  |  |  |  | 37529 |  | 42 | 0
Pkg -3 Design/Build/Test/Implement |  |  |  |  | 37592 |  | 222.5 | 0
| SUBTOTAL | [5 empty] | 439 | 141
Frey Michael
Planning/Admin/Meetings/Coordination |  |  |  |  | 37375 |  | 178 | 0
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 110 | 0
| SUBTOTAL | [5 empty] | 288 | 0
Isaacson John
Planning/Admin/Meetings/Coordination |  |  |  |  | 37375 |  | 39.5 | 0
| SUBTOTAL | [5 empty] | 39.5 | 0
Witter Steve
Planning/Admin/Meetings/Coordination |  |  |  |  | 37375 |  | 70 | 0
Reqs Analysis and Solution Def/Specs |  |  |  |  | 37469 | 37694 | 158 | 0
Pkg -1 Design/Build/Test/Implement |  |  |  |  | 37529 |  | 109 | 0
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 466 | 0
Transition |  | 37944 | 37979 |  | 37732 |  | 0 | 15
| SUBTOTAL | [5 empty] | 803 | 15
Dejaynes Vance
Planning/Admin/Meetings/Coordination |  | 37781 | 37896 |  | 37375 |  | 289 | 631
Pkg -1 Design/Build/Test/Implement |  | 37781 | 37848 |  | 37529 |  | 0 | 20
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 25.5 | 0
Pkg -3 Design/Build/Test/Implement |  | 37781 | 37852 |  | 37592 |  | 0 | 20
| SUBTOTAL | [5 empty] | 314.5 | 671
Malone Bill
Pkg -1 Design/Build/Test/Implement |  |  |  |  | 37529 |  | 7.25 | 0
Pkg -2 Design/Build/Test/Implement |  | 37781 | 37802 |  | 37550 |  | 174.25 | 91.5
Planning/Admin/Meetings/Coordination |  | 37781 | 37812 |  | 37375 |  | 12 | 8
Transition |  | 37929 | 38009 |  | 37732 |  | 0 | 7
| SUBTOTAL | [5 empty] | 193.5 | 106.5
Nutt John
Pkg -2 Design/Build/Test/Implement |  | 37781 | 37810 |  | 37550 |  | 139 | 43
Transition |  | 37781 | 37834 |  | 37732 |  | 2 | 5
Planning/Admin/Meetings/Coordination |  | 37781 | 37879 |  | 37375 |  | 3 | 108
| SUBTOTAL | [5 empty] | 144 | 156
Awan Zafar
Pkg -2 Design/Build/Test/Implement |  | 37781 | 37802 |  | 37550 |  | 48 | 2
| SUBTOTAL | [5 empty] | 48 | 2
Baugh Sally
Pkg -3 Design/Build/Test/Implement |  |  |  |  | 37592 |  | 23.5 | 0
| SUBTOTAL | [5 empty] | 23.5 | 0
Durnan Steve
Pkg -1 Design/Build/Test/Implement |  |  |  |  | 37529 |  | 6 | 0
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 18.5 | 0
Pkg -3 Design/Build/Test/Implement |  | 37781 | 37894 |  | 37592 |  | 147 | 20.5
| SUBTOTAL | [5 empty] | 171.5 | 20.5
Leslie Sherrill
Planning/Admin/Meetings/Coordination |  | 37781 | 37796 |  | 37375 |  | 20 | 5
| SUBTOTAL | [5 empty] | 20 | 5
McCue Chad
Pkg -1 Design/Build/Test/Implement |  |  |  |  | 37529 |  | 0 | 0
| SUBTOTAL | [5 empty] | 0 | 0
Miller Kim
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 63 | 0
| SUBTOTAL | [5 empty] | 63 | 0
Stern David
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 72 | 0
Pkg -1 Design/Build/Test/Implement |  |  |  |  | 37529 |  | 3 | 0
| SUBTOTAL | [5 empty] | 75 | 0
Celeschi Michelle
Planning/Admin/Meetings/Coordination |  | 37781 | 37894 |  | 37375 |  | 226.75 | 145
| SUBTOTAL | [5 empty] | 226.75 | 145
Hall Steve
Planning/Admin/Meetings/Coordination |  | 37781 | 37813 |  | 37375 |  | 101 | 182
Reqs Analysis and Solution Def/Specs |  |  |  |  | 37469 | 37694 | 56 | 0
Pkg -1 Design/Build/Test/Implement |  |  |  |  | 37529 |  | 95 | 0
Pkg -2 Design/Build/Test/Implement |  |  |  |  | 37550 |  | 257 | 0
Pkg -3 Design/Build/Test/Implement |  |  |  |  | 37592 |  | 156 | 0
| SUBTOTAL | [5 empty] | 665 | 182
Elam Carol
Planning/Admin/Meetings/Coordination |  | 37781 | 37894 |  | 37375 |  | 534 | 467
| SUBTOTAL | [5 empty] | 534 | 467
Gullixon Eric
Planning/Admin/Meetings/Coordination |  | 37781 | 37795 |  | 37375 |  | 89.5 | 78.5
Reqs Analysis and Solution Def/Specs |  |  |  |  | 37469 | 37694 | 18.5 | 0
Pkg -1 Design/Build/Test/Implement |  | 37781 | 37838 |  | 37529 |  | 8.5 | 6.5
| SUBTOTAL | [5 empty] | 116.5 | 85
Hartness Ty
Planning/Admin/Meetings/Coordination |  | 37781 | 37781 |  | 37375 |  | 46.75 | 7
Reqs Analysis and Solution Def/Specs |  |  |  |  | 37469 | 37694 | 65 | 0
Pkg -1 Design/Build/Test/Implement |  | 37781 | 37781 |  | 37529 |  | 0.75 | 4.25
Pkg -2 Design/Build/Test/Implement |  | 37781 | 37781 |  | 37550 |  | 0.75 | 4.25
Pkg -3 Design/Build/Test/Implement |  | 37781 | 37781 |  | 37592 |  | 2.75 | 2.25
Transition |  |  |  |  | 37732 |  | 0 | 0
| SUBTOTAL | [5 empty] | 116 | 17.75
Lee Mary Kasley
Planning/Admin/Meetings/Coordination |  | 37781 | 37783 |  | 37375 |  | 41.75 | 17.25
Reqs Analysis and Solution Def/Specs |  |  |  |  | 37469 | 37694 | 47 | 0
Pkg -2 Design/Build/Test/Implement |  | 37781 | 37782 |  | 37550 |  | 0.5 | 14.5
Transition |  |  |  |  | 37732 |  | 0 | 0
| SUBTOTAL | [5 empty] | 89.25 | 31.75
Weidenbenner Ed
Planning/Admin/Meetings/Coordination |  | 37781 | 37781 |  | 37375 |  | 200 | 5
Reqs Analysis and Solution Def/Specs |  |  |  |  | 37469 | 37694 | 90 | 0
Pkg -1 Design/Build/Test/Implement |  |  |  |  | 37529 |  | 81 | 0
Pkg -2 Design/Build/Test/Implement |  | 37781 | 37894 |  | 37550 |  | 74 | 27
Pkg -3 Design/Build/Test/Implement |  | 37781 | 37797 |  | 37592 |  | 50 | 25
| SUBTOTAL | [5 empty] | 495 | 57
| TOTAL | [5 empty] | 9199 | 3300.5

## RDTCD1MM
Report Run Date: |  |  |  | Page: | 1
2003-06-10 |  | Releases w/actual hours.
Project Title
Actual
Hrs.
AUTO-INCREASE UNDERWRITING PRODUCT ORDER |  |  | 50.75
| Awan Zafar |  | 6
Bommisetti Amarnath
Brown Brian [GS03]
Celeschi Michelle
| Dejaynes Vance |  | 3.5
Dobrinich Tina L
| Durnan Steve |  | 4
| Elam Carol |  | 2
| Frey Michael |  | 10
Gullixon Eric
Hall Steve
| Hartness Ty |  | 2.25
Kumar Ashok
Lade Daniel
Lee Mary Kasley
Leslie Sherrill
| Ma Harry |  | 2
Malone Bill
| McKinney Brian |  | 1
Mohandass Duzianthan
Murthy J
Nutt John
Paige Charles
Ramachandran Santosh [H6Z5]
Reddy Lakshmi Narayana
Rogers Charlie
Saenz Gilbert
Saha Sushit
| Scott Gary |  | 2
Shanmugam Kasi
| Stern David |  | 4
| Weidenbenner Ed |  | 4
| Witter Steve |  | 10
Woodman Andrew

## RDTCD1
Report Run Date: |  |  |  |  | Page: | 1
2003-06-10 |  | Releases w/actual hours.
Project Title
|  |  | Remaining | Actual
|  |  | Hrs. | Hrs.
AUTO-INCREASE UNDERWRITING PRODUCT ORDER |  |  | 3299.98 | 9266.5
Upd Team | Awan Zafar |  | 1.98 | 48
Upd Team | Baugh Sally |  |  | 23.5
Upd Team | Bommisetti Amarnath |  | 135.93 | 1747
Upd Team | Brown Brian [GS03] |  | 63.97 | 100
Upd Team | Celeschi Michelle |  | 144.97 | 226.75
Upd Team | Dejaynes Vance |  | 671 | 325
Upd Team | Dobrinich Tina L |  | 141 | 444.5
Upd Team | Durnan Steve |  | 20.47 | 171.5
Upd Team | Elam Carol |  | 466.98 | 547.5
Upd Team | Frey Michael |  |  | 290
Upd Team | Gullixon Eric |  | 84.98 | 117.5
Upd Team | Hall Steve |  | 182 | 675
Upd Team | Hartness Ty |  | 17.75 | 116
Upd Team | Isaacson John |  |  | 40.5
Upd Team | Kumar Ashok |  | 224.98 | 514
Upd Team | Lade Daniel |  | 7.48 | 47.5
Upd Team | Lee Mary Kasley |  | 31.75 | 92.25
Upd Team | Leslie Sherrill |  | 4.98 | 20
Upd Team | Ma Harry |  | 21.23 | 78.75
Upd Team | Malone Bill |  | 106.5 | 193.5
Upd Team | McKinney Brian |  |  | 23.5
Upd Team | Miller Kim |  |  | 63
Upd Team | Mohandass Duzianthan |  | 8 | 8
Upd Team | Murthy J |  | 310.98 | 1447
Upd Team | Nutt John |  | 155.98 | 144
Upd Team | Paige Charles |  | 13.5 | 56.5
Upd Team | Ramachandran Santosh [H6Z5] |  | 19 | 6
Upd Team | Reddy Lakshmi Narayana |  | 157.97 | 144
Upd Team | Rogers Charlie |  | 28.23 | 12
Upd Team | Saenz Gilbert |  | 16.97 | 8
Upd Team | Saha Sushit |  | 61.98 | 62
Upd Team | Sanders Dave |  |  | 10.75
Upd Team | Scott Gary |  | 26 | 4
Upd Team | Shanmugam Kasi |  | 65.97 | 54
Upd Team | Stern David |  |  | 75
Upd Team | Weidenbenner Ed |  | 56.97 | 499
Upd Team | Witter Steve |  | 14.98 | 809
Upd Team | Woodman Andrew |  | 35.48 | 22

## PDTA10
37782 | Actual and Remaining Work with Resource (Time Phased) |  |  | 1
[P_DT_A10]
NECHO Auto Apps Efficiency
From: | Period: | Month
|  |  | 37347 | 37377 | 37408 | 37438 | 37469 | 37500 | 37530 | 37561 | 37591 | 37622 | 37653 | 37681 | 37712 | 37742 | 37773 | 37803 | 37834 | 37865 | 37895 | 37926 | 37956 | 37987 | Total
Description |  |  | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain | Remain
AUTO-INCREASE UNDERWRITING PRODUCT ORDER
Planning/Admin/Meetings/Coordination
Leslie Sherrill | [8 empty] | 7 |  | 2 | 1 |  |  | 5 | 5 | 5 | [7 empty] | 5
Nutt John | [10 empty] | 1 |  |  |  | 2 |  | 36.58 | 37.38 | 25.57 | 8.47 |  |  |  |  | 108
Paige Charles | [8 empty] | 17.75 | 10.25 | 5.75 | 5.65 | 3.35 | 0.5 | 10.5 | 2.75 | 13.5 | [7 empty] | 13.5
Dobrinich Tina L |  |  |  | 10 | 11.5 | 24 | 4.5 | 25 | 7 | 3 | 5 | 4 | 1 | 1 |  |  | 124 | 17 | [6 empty] | 141
Celeschi Michelle |  |  | 4 | 30.25 | 17 | 16 | 18.5 | 9.5 | 17 | 23.5 | 18.5 | 18.5 | 17.5 | 17.25 | 9.25 | 10 | 31 | 41.78 | 37.98 | 34.23 |  |  |  |  | 145
Scott Gary | [15 empty] | 2 | 26 | [7 empty] | 26
Hall Steve |  |  |  | 4 | 19 | 30 | 1 |  | 6 |  | 22 | 1 | 1 |  | 2 | 15 | 124 | 58 | [6 empty] | 182
Brown Brian [GS03] | [14 empty] | 3 | 0.5 | 13.5 | [7 empty] | 13.5
Murthy J |  |  |  | 6 | 33 | 132 | 16 | 3 | 6 | 2 | 3 | 3 | 2 | 2 | 1 | 4 | 83.58 | 104.9 | 87.78 | 34.73 |  |  |  |  | 311
Reddy Lakshmi Narayana |  |  |  | 6 | 7 | 9 |  | 7 | 3 |  |  |  | 5 | 10 |  |  | 31 | [7 empty] | 31
Ramachandran Santosh [H6Z5] | [15 empty] | 6 | 19 | [7 empty] | 19
Kumar Ashok |  |  |  | 44 | 49 | 44 | 41 | 37 | 54 | 41 | 38 | 44 | 31 | 31 | 33 | 27 | 55.53 | 65.75 | 54.88 | 48.82 |  |  |  |  | 224.98
Bommisetti Amarnath | [5 empty] | 220 | 19 | 3 | 5 | 4 | 2 | 2 | 2 | 2 | 3 | 2 | 30.35 | 35.02 | 22.07 | 14.55 |  |  |  |  | 101.98
Elam Carol |  |  |  | 56 | 39.5 | 67.5 | 39.5 | 46.5 | 46.5 | 58 | 48 | 48 | 18 | 21.5 | 26.5 | 29.85 | 100 | 134.78 | 120.73 | 111.48 |  |  |  |  | 467
Lee Mary Kasley |  |  |  |  | 5.25 | 15.75 | 8.25 | 2 | 4.5 | 2.5 | 1.75 | 0.25 | 0.25 | 0.5 | 0.75 |  | 17.25 | [7 empty] | 17.25
Hartness Ty |  |  |  |  | 6.5 | 24 | 0.25 | 1.25 | 4.5 | 1.25 | 1 | 2.5 | 2 |  | 2.5 |  | 7 | [7 empty] | 7
Dejaynes Vance | [5 empty] | 10.5 | 32.5 | 53.5 | 40.5 | 45 | 35.5 | 32.5 | 24.5 | 11.5 | 3.5 | 6.5 | 124 | 170.5 | 162.75 | 162.75 | 11 |  |  |  | 631
Gullixon Eric |  |  |  | 8 | 11 | 33 | 11.5 | 4 | 6.5 | 1 | 1 | 4 | 3.5 | 4 | 2 | 1 | 78.5 | [7 empty] | 78.5
Malone Bill | [10 empty] | 2 | 2.5 | 2 | 0.5 | 1 | 4 | 6.67 | 1.33 | [6 empty] | 8
Saha Sushit | [8 empty] | 3 | 8 | 1 | 1 | 1 |  |  |  | 27 | [7 empty] | 27
Weidenbenner Ed |  |  |  | 27 | 43 | 60 | 23 | 12 | 13 | 4 | 7 | 3 | 3 | 4 |  | 1 | 5 | [7 empty] | 5
Lade Daniel | [8 empty] | 7 | 4 | 1 | 4 | 0.5 |  | 10.25 | 20.75 | 3.87 | 2.85 | 0.77 | [5 empty] | 7.48
Saenz Gilbert | [8 empty] | 2 |  | 3 | 1 | 1 |  | 1 |  | 10.1 | 4.65 | 2.23 | [5 empty] | 16.98
Ma Harry | [8 empty] | 5 | 18 | 10 | 16.25 | 8 | 5.5 | 9.25 | 4.75 | 4.78 | 5.68 | 5.42 | 5.35 |  |  |  |  | 21.23
Rogers Charlie | [15 empty] | 12 | 8.27 | 8.62 | 6.15 | 5.22 |  |  |  |  | 28.25
Frey Michael |  |  |  | 6 | 8.5 | 11 | 12 | 6 | 7 | 8 | 10 | 12 | 8 | 11.5 | 61 | 19 | [8 empty] | 180
Isaacson John | [6 empty] | 12.5 | 3.5 | 4.5 | 4 | 5.5 | 7 | 0.5 | 3 | [10 empty] | 40.5
Witter Steve | [5 empty] | 8 | 9 | 19 | 5 |  |  | 4 |  | 27 | [10 empty] | 72
Sanders Dave | [8 empty] | 4.25 | 2.25 | 3 |  | 0.25 |  | 1 | [9 empty] | 10.75
McKinney Brian | [14 empty] | 5.5 | 17 | 1 | [7 empty] | 23.5
|  | Subtotal | 4 | 197.25 | 250.25 | 704.75 | 248.5 | 232.25 | 276 | 239.75 | 227 | 217.15 | 135.35 | 152.75 | 193 | 190.1 | 985.48 | 688.25 | 526.33 | 425.6 | 11 |  |  |  | 2636.67
Reqs Analysis and Solution Def/Specs
Dobrinich Tina L | [6 empty] | 11 | 4 | 15 | 19 | 7 | 10 | 6 | 12 | [10 empty] | 84
Bommisetti Amarnath | [6 empty] | 149 | 158 | 102 | 44 | 127 | [13 empty] | 580
Weidenbenner Ed | [6 empty] | 24 | 30 | 22 | 13 | 5 | [13 empty] | 94
Murthy J | [6 empty] | 53 | 129 | 65 | 50 | [14 empty] | 297
Gullixon Eric | [6 empty] | 1.5 | 15 | 0.5 |  | 1.5 | [13 empty] | 18.5
Hartness Ty | [6 empty] | 16.75 | 27.25 | 5.75 | 11.5 | 1.5 | 2.25 | [12 empty] | 65
Hall Steve | [6 empty] | 42 | 24 | [16 empty] | 66
Witter Steve | [6 empty] | 19 | 29 | 111 | 3 | [14 empty] | 162
Lee Mary Kasley | [6 empty] | 11.75 | 20 | 6.5 | 9.25 | 2.5 | [13 empty] | 50
Reddy Lakshmi Narayana | [7 empty] | 7 | 2 | [15 empty] | 9
|  | Subtotal |  |  |  |  | 328 | 443.25 | 329.75 | 149.75 | 144.5 | 12.25 | 6 | 12 | [10 empty] | 1425.5
Pkg -1 Design/Build/Test/Implement
Reddy Lakshmi Narayana | [16 empty] | 1 | [7 empty] | 1
Bommisetti Amarnath | [8 empty] | 44 | 86 | 2 | [5 empty] | 14.38 | 8.78 | 0.83 | [5 empty] | 24
Hartness Ty | [10 empty] | 0.75 | [5 empty] | 4.25 | [7 empty] | 4.25
Dejaynes Vance | [16 empty] | 11.37 | 7.23 | 1.4 | [5 empty] | 20
Gullixon Eric | [11 empty] | 1 | 4.5 | 1 |  | 2 | 3.3 | 2.83 | 0.37 | [5 empty] | 6.5
Weidenbenner Ed | [8 empty] | 4 | 22 | 25 | 20 | 6 | 4 | [10 empty] | 81
Murthy J | [7 empty] | 7 | 46 | 73 | 39 |  |  |  | 8 | 3 | [8 empty] | 176
Malone Bill | [8 empty] | 6.25 | 1 | [14 empty] | 7.25
Hall Steve | [8 empty] | 2 | 56 | 34 | 3 | [12 empty] | 95
Durnan Steve | [9 empty] | 6 | [14 empty] | 6
Dobrinich Tina L | [8 empty] | 4 | 7 | 24.5 | 6.5 | [12 empty] | 42
Stern David | [9 empty] | 3 | [14 empty] | 3
Witter Steve | [10 empty] | 82 | 5 |  |  | 22 | [9 empty] | 109
|  | Subtotal | [5 empty] | 7 | 106.25 | 254 | 207.25 | 35.5 | 10.5 | 5 | 30 | 5 | 34.3 | 18.85 | 2.6 | [5 empty] | 55.75
Pkg -2 Design/Build/Test/Implement
Awan Zafar | [10 empty] | 8 | 7 | 9 | 6 | 5 | 7 | 2 | [7 empty] | 2
Nutt John | [8 empty] | 3 | 72 | 25 | 4 | 4 | 6 | 18 | 7 | 34.6 | 8.4 | [6 empty] | 43
Shanmugam Kasi | [12 empty] | 8 |  | 9.5 | 36.5 | 20.67 | 25.08 | 12.83 | 7.42 |  |  |  |  | 66
Lee Mary Kasley | [12 empty] | 0.5 |  |  |  | 14.5 | [7 empty] | 14.5
Hartness Ty | [11 empty] | 0.75 |  |  |  |  | 4.25 | [7 empty] | 4.25
Malone Bill | [9 empty] | 26.25 | 51.5 | 35 | 13 | 16.5 | 16 | 16 | 91.5 | [7 empty] | 91.5
Weidenbenner Ed | [10 empty] | 2 | 13 | 17 | 20 | 15 | 5 | 10.43 | 5.72 | 5.42 | 5.43 |  |  |  |  | 27
Witter Steve | [11 empty] | 93 | 125 | 82 | 88 | 68 | 10 | [7 empty] | 466
Miller Kim | [10 empty] | 2 |  |  | 2 | 5 | 54 | [8 empty] | 63
Hall Steve | [8 empty] | 1 |  | 15 | 52 | 39 | 21 | 68 | 61 | [8 empty] | 257
Saha Sushit | [9 empty] | 3 | 5 | 14 | 9 | 2 | [10 empty] | 33
Brown Brian [GS03] | [9 empty] | 32 | 64.5 | [13 empty] | 96.5
Durnan Steve | [9 empty] | 15.5 | 3 | [13 empty] | 18.5
Stern David | [9 empty] | 1 | 6 | 32 | 13 | 9 | 1 | 6 | 4 | [7 empty] | 72
Dejaynes Vance | [11 empty] | 6 |  | 4.5 | 8 | 7 | [8 empty] | 25.5
Woodman Andrew | [13 empty] | 5.5 | 2 | [9 empty] | 7.5
Mohandass Duzianthan | [14 empty] | 2 | 4 | [8 empty] | 6
Frey Michael | [14 empty] | 30 | 70 | 10 | [7 empty] | 110
|  | Subtotal | [6 empty] | 4 | 149.75 | 182 | 256.75 | 237.5 | 174.5 | 267.5 | 341.5 | 177.95 | 39.2 | 18.25 | 12.85 |  |  |  |  | 248.25
Pkg -3 Design/Build/Test/Implement
Woodman Andrew | [15 empty] | 14.5 | 17.52 | 17.98 | [6 empty] | 35.5
Brown Brian [GS03] | [16 empty] | 19.88 | 17.7 | 7.48 | 5.43 |  |  |  |  | 50.5
Reddy Lakshmi Narayana | [11 empty] | 2 | 2 |  | 69 | 15 | 32.52 | 42.63 | 32.58 | 18.27 |  |  |  |  | 126
Hartness Ty | [13 empty] | 0.75 | 0.25 | 0.5 | 2.25 | [7 empty] | 2.25
Dejaynes Vance | [16 empty] | 12.53 | 5.8 | 1.67 | [5 empty] | 20
Durnan Steve | [10 empty] | 11 | 31 | 30.5 | 30 | 24.5 | 16 | 4.13 | 5.68 | 5.42 | 5.27 |  |  |  |  | 20.5
Mohandass Duzianthan | [15 empty] | 2 | 8 | [7 empty] | 8
Saha Sushit | [13 empty] | 6 | 5 | 4 | 14.22 | 10.08 | 5.43 | 5.25 |  |  |  |  | 34.98
Weidenbenner Ed | [10 empty] | 2 | 1 | 1 | 4 | 23 | 17 | 25 | [7 empty] | 25
Dobrinich Tina L | [11 empty] | 11 | 13 | 34.5 | 122 | 42 | [8 empty] | 222.5
Murthy J | [10 empty] | 124 | 176 | 169 | 172 | 106 | 14 | [8 empty] | 761
Hall Steve | [10 empty] | 4 | 13 | 17 | 28 | 42 | 52 | [8 empty] | 156
Bommisetti Amarnath | [10 empty] | 25 | 191 | 175 | 189 | 137 | 54 | [8 empty] | 771
Baugh Sally | [12 empty] | 4 | 4 | 11 | 4.5 | [8 empty] | 23.5
|  | Subtotal | [8 empty] | 166 | 425 | 411.5 | 468.25 | 539.75 | 235.5 | 136.05 | 99.88 | 52.58 | 34.22 |  |  |  |  | 322.73
Transition
Nutt John | [14 empty] | 2 |  | 2.07 | 2.83 | 0.1 | [5 empty] | 5
Witter Steve | [21 empty] | 3.87 | 11.13 |  | 15
Bommisetti Amarnath | [21 empty] | 1.55 | 5.68 | 2.77 | 10
Malone Bill | [21 empty] | 2.2 | 2.83 | 1.97 | 7
|  | Subtotal | [12 empty] | 2 |  | 2.07 | 2.83 | 0.1 |  |  | 7.62 | 19.65 | 4.73 | 37
|  | Project Total | 4 | 197.25 | 250.25 | 704.75 | 576.5 | 682.5 | 716 | 793.25 | 926.75 | 946.65 | 800.85 | 812.5 | 1032.25 | 772.1 | 1335.85 | 849.02 | 599.87 | 472.67 | 11 | 7.62 | 19.65 | 4.73 | 3300.4

## Scratch
Proj. 1234 | All Tasks List |  | as on | 2003-06-10 |  | 70 | 1901-01-09
Lead | Task Code | Task Name | % Work Completed | Work in Hours | Duration in Days | Planned Start Date | Planned Finish date | Compl Work Hrs | Successors | BaseLine Work | Earned Value | Summary Yes/No | Indent Level | Predecessor | Resources | Baseline Start date | Baseline Finish date | Datelast Updated
Amar | 83 | Design of New screen(83) | 100% | 20 h | 3 d | 2002-07-16 14:30 | 2002-07-19 13:45 | 20 | 81 | 20 h | 20 | No | 1.2.1.10.9.1 | 29 | Murthy[68%],Amar,Lakshmi | 2002-07-16 14:30 | 2003-08-28 09:44 | NA
Amar | 77 | Design of New screen(77) | 100% | 20 h | 5 d | 2002-07-16 14:30 | 2002-07-23 13:15 | 20 | 75 | 20 h | 20 | No | 1.2.1.10.8.1 | 29 | Amar[46%],Lakshmi | 2002-07-16 14:30 | 2003-09-12 15:00 | NA
Amar | 33 | Create New ECHO Screen Layout | 100% | 5 h | 3 d | 2002-07-29 11:15 | 2002-08-01 10:30 | 5 |  | 5 h | 5 | No | 1.2.1.6 | 31 | Tina[22%] | 2002-07-29 11:15 | 2002-05-06 08:00 | NA
Amar | 45 | Understand existing ECHO APPS System | 100% | 240 h | 50 d | 2002-06-13 11:30 | 2002-08-20 16:00 | 240 |  | 240 h | 240 | No | 1.2.1.10.1 | 29SS | Murthy[70%],Amar[70%] | 2002-06-13 11:30 | 2003-09-05 15:33 | NA
Amar | 56 | Analysing the requirements(64) | 100% | 34 h | 20 d | 2002-08-05 09:30 | 2002-09-13 13:30 | 34 | 58 | 34 h | 34 | No | 1.2.1.10.4.1 | 29 | Murthy[73%] | 2002-08-05 09:30 | 2003-04-21 16:15 | NA
Amar | 84 | Analysis of Flow of Data(84) | 100% | 66 h | 32 d | 2002-07-19 13:45 | 2002-09-16 13:45 | 66 | 82FF+2 d | 66 h | 66 | No | 1.2.1.10.9.2 | 80 | Murthy[77%],Amar,Lakshmi | 2002-07-19 13:45 | 2003-04-21 15:30 | NA
Amar | 51 | Analysing the requirements(59) | 100% | 25 h | 10 d | 2002-09-03 08:00 | 2002-09-16 14:30 | 25 | 53,54 | 25 h | 25 | No | 1.2.1.10.3.1 | 29 | Murthy[33%],Amar | 2002-08-01 08:00 | 2003-04-21 16:15 | NA
Amar | 78 | Analysis of Flow of Data(78) | 100% | 25 h | 42 d | 2002-07-23 13:15 | 2002-09-18 09:45 | 25 | 76 | 25 h | 25 | No | 1.2.1.10.8.2 | 74 | Amar[31%],Lakshmi | 2002-07-23 13:15 | 2003-04-21 16:15 | NA
Amar | 85 | Design the Highlevel Specs-1(85) | 100% | 8 h | 24 d | 2002-08-02 10:15 | 2002-09-18 16:15 | 8 | 83 | 8 h | 8 | No | 1.2.1.10.9.3 | 81FF+2 d | Murthy[34%] | 2002-08-02 10:15 | 2003-04-21 10:15 | NA
Amar | 52 | Design the Highlevel Specs-1(60) | 100% | 8 h | 4 d | 2002-09-16 14:30 | 2002-09-20 13:30 | 8 |  | 8 h | 8 | No | 1.2.1.10.3.2 | 52 | Murthy[26%] | 2002-08-14 14:30 | 2002-11-20 10:45 | NA
Amar | 61 | Analysing the requirements(51) | 100% | 25 h | 38 d | 2002-08-02 10:30 | 2002-09-24 09:00 | 25 | 63 | 25 h | 25 | No | 1.2.1.10.5.1 | 29 | Amar[32%] | 2002-08-02 10:30 | 2002-06-17 11:00 | NA
Amar | 57 | Design the Highlevel Specs-1(65) | 100% | 12 h | 11 d | 2002-08-13 08:00 | 2002-09-27 11:56 | 12 | 59 | 12 h | 12 | No | 1.2.1.10.4.2 | 57 | Murthy[52%] | 2002-08-13 08:00 | 2002-06-17 11:00 | NA
Amar | 53 | Design the Highlevel Specs-2(61) | 100% | 15 h | 9.1 d | 2002-09-16 14:30 | 2002-09-27 12:00 | 15 | 55 | 15 h | 15 | No | 1.2.1.10.3.3 | 52 | Murthy[9%],Amar,Lakshmi,Tina | 2002-09-02 13:45 | 2002-06-17 11:00 | NA
Amar | 54 | Review of Highlevel Specs(62) | 100% | 8 h | 1 d | 2002-09-27 13:00 | 2002-09-30 11:45 | 8 | 83 | 8 h | 8 | No | 1.2.1.10.3.4 | 54 | Murthy[103%],Amar,Lakshmi,Tina[39%] | 2002-09-13 11:15 | 2002-07-08 16:00 | NA
Amar | 47 | Analysing the requirements(69) | 100% | 36 h | 46 d | 2002-07-29 16:45 | 2002-09-30 13:15 | 36 | 49 | 36 h | 36 | No | 1.2.1.10.2.1 |  | Amar[52%] | 2002-07-29 16:45 | 2002-07-05 16:15 | NA
Amar | 62 | Design the Highlevel Specs(52) | 100% | 58 h | 9 d | 2002-09-20 09:30 | 2002-10-04 10:20 | 58 | 64 | 58 h | 58 | No | 1.2.1.10.5.2 | 62 | Murthy[29%],Amar,Lakshmi,Tina | 2002-08-16 08:00 | 2002-07-05 16:15 | NA
Amar | 69 | Analysing the requirements(73) | 100% | 20 h | 15 d | 2002-09-16 08:00 | 2002-10-04 13:15 | 20 | 67 | 20 h | 20 | No | 1.2.1.10.6.1 |  | Amar[30%],Lakshmi[2%] | 2002-07-29 16:45 | 2002-07-05 16:15 | NA
Amar | 79 | Analysis of Validations(79) | 100% | 32 h | 20 d | 2002-08-06 09:45 | 2002-10-07 08:26 | 32 | 77 | 32 h | 32 | No | 1.2.1.10.8.3 | 75 | Amar[46%] | 2002-08-06 09:45 | 2002-08-16 09:00 | NA
Amar | 63 | Review of Highlevel Specs(53) | 100% | 8 h | 1 d | 2002-10-04 10:20 | 2002-10-07 10:05 | 8 | 77 | 8 h | 8 | No | 1.2.1.10.5.3 | 63 | Murthy[103%],Lakshmi[26%],Tina[26%],Amar[26%] | 2002-09-09 13:30 | 2002-08-16 09:00 | NA
Amar | 58 | Design the Highlevel Specs-2(66) | 100% | 34 h | 10 d | 2002-09-27 11:56 | 2002-10-11 09:26 | 34 | 60 | 34 h | 34 | No | 1.2.1.10.4.3 | 58 | Murthy[15%],Lakshmi,Tina | 2002-08-15 16:15 | 2002-11-19 11:00 | NA
Amar | 73 | Analysing the requirements(47) | 100% | 48 h | 24 d | 2002-09-10 08:00 | 2002-10-11 10:00 | 48 |  | 48 h | 48 | No | 1.2.1.10.7.1 | 29 | Murthy[46%] | 2002-09-10 08:00 | 2002-11-20 10:45 | NA
Amar | 48 | Design the Highlevel Specs(70) | 100% | 44 h | 10 d | 2002-09-30 13:15 | 2002-10-14 09:45 | 44 | 50 | 44 h | 44 | No | 1.2.1.10.2.2 | 48 | Amar[36%],Lakshmi,Tina | 2002-09-09 08:00 | 2003-04-21 08:15 | NA
Amar | 74 | Design the Highlevel Specs(48) | 100% | 64 h | 10 d | 2002-09-30 13:15 | 2002-10-14 09:45 | 64 | 72 | 64 h | 64 | No | 1.2.1.10.7.2 |  | Murthy[134%],Lakshmi,Tina | 2002-09-23 14:30 | 2002-11-19 10:59 | NA
Amar | 75 | Review of Highlevel Specs(49) | 100% | 8 h | 1 d | 2002-10-14 09:45 | 2002-10-15 09:30 | 8 | 77 | 8 h | 8 | No | 1.2.1.10.7.3 | 71 | Murthy[103%],Lakshmi[39%],Tina[39%] | 2002-10-07 11:00 | 2003-04-21 08:15 | NA
Amar | 59 | Review of Highlevel Specs(67) | 100% | 8 h | 2 d | 2002-10-11 09:26 | 2002-10-15 15:45 | 8 | 83 | 8 h | 8 | No | 1.2.1.10.4.4 | 59 | Murthy[103%],Lakshmi[19%],Tina[19%] | 2002-09-09 15:45 | NA | NA
Amar | 49 | Review of Highlevel Specs(71) | 100% | 8 h | 4 d | 2002-10-14 09:45 | 2002-10-18 08:45 | 8 | 77 | 8 h | 8 | No | 1.2.1.10.2.3 | 49 | Amar[6%],Lakshmi,Tina | 2002-09-23 09:00 | 2003-08-18 15:30 | NA
Amar | 70 | Design the Highlevel Specs(74) | 100% | 20 h | 10 d | 2002-10-04 13:15 | 2002-10-18 09:45 | 20 | 68 | 20 h | 20 | No | 1.2.1.10.6.2 | 66 | Amar[18%],Lakshmi,Tina | 2002-08-28 09:30 | 2002-11-15 11:30 | NA
Amar | 71 | Review of Highlevel Specs(75) | 100% | 8 h | 4 d | 2002-10-18 09:45 | 2002-10-24 08:45 | 8 | 77 | 8 h | 8 | No | 1.2.1.10.6.3 | 67 | Amar[6%],Lakshmi,Tina | 2002-09-10 16:00 | 2002-10-30 10:00 | NA
Amar | 86 | Design the Highlevel Specs-2(86) | 100% | 28 h | 10 d | 2002-10-15 15:45 | 2002-10-29 13:15 | 28 | 84 | 28 h | 28 | No | 1.2.1.10.9.4 | 82,55,60 | Murthy[21%],Amar,Lakshmi,Tina | 2002-09-16 11:00 | 2002-07-16 14:30 | NA
Amar | 87 | Review of Highlevel Specs(87) | 100% | 10 h | 1 d | 2002-10-29 13:15 | 2002-10-30 13:00 | 10 | 85 | 10 h | 10 | No | 1.2.1.10.9.5 | 83 | Murthy[52%],Amar,Lakshmi,Tina | 2002-09-30 08:30 | 2002-07-25 11:45 | NA
Amar | 80 | Design the Highlevel Specs(80) | 100% | 32 h | 8 d | 2002-10-24 08:45 | 2002-11-04 15:45 | 32 | 78SS | 32 h | 32 | No | 1.2.1.10.8.4 | 76,64,68,50,72 | Amar[66%],Lakshmi[142%],Tina | 2002-10-08 10:45 | 2002-07-29 11:15 | NA
Amar | 81 | Review of Highlevel Specs(81) | 100% | 16 h | 8 d | 2002-10-24 08:45 | 2002-11-04 15:45 | 16 | 85 | 16 h | 16 | No | 1.2.1.10.8.5 | 77SS | Amar[19%],Lakshmi,Tina | 2002-10-08 10:45 | 2002-08-01 10:30 | NA
Amar | 88 | MS: ECHO Specs completed | 100% | 0 h | 0 d | 2002-11-04 15:45 | 2002-11-04 15:45 | 0 | 90 | 0 h | 0 | No | 1.2.1.10.10 | 78,84 |  | 2002-10-21 08:30 | 2002-10-30 10:00 | NA
Amar | 220 | NECHO VIN Validation - Analysis (TSD3.2) | 100% | 10 h | 2 d | 2002-11-04 08:00 | 2002-11-05 16:30 | 10 | 144 | 10 h | 10 | No | 1.3.5.1 | 137SS | Amar[65%] | 2002-11-04 08:00 | 2002-08-01 10:30 | NA
Amar | 221 | NECHO VIN Validation - Analysis (TSD8.3) | 100% | 15 h | 2 d | 2002-11-05 16:30 | 2002-11-07 16:00 | 15 | 145,154 | 15 h | 15 | No | 1.3.5.2 | 143 | Amar[97%] | 2002-11-05 16:30 | 2002-09-27 16:45 | NA
Amar | 222 | NECHO VIN Validation - Coding | 100% | 15 h | 2 d | 2002-11-07 16:00 | 2002-11-11 15:30 | 15 | 146,149 | 15 h | 15 | No | 1.3.5.3 | 144 | Amar[97%] | 2002-11-07 16:00 | 2002-07-31 10:45 | NA
Amar | 432 | Auto Apps - Main Program - TSD 3.2 | 100% | 40 h | 17 d | 2002-11-13 08:00 | 2002-12-09 11:45 | 40 | 318 | 40 h | 40 | No | 1.5.2.4.8 |  | Amar[30%] | 2002-11-13 08:00 | 2002-08-07 09:30 | NA
Amar | 223 | NECHO VIN Validation - Unit Testing | 100% | 10 h | 23 d | 2002-11-11 15:30 | 2002-12-16 08:45 | 10 | 156FS-5 d | 10 h | 10 | No | 1.3.5.4 | 145 | Amar[6%] | 2002-11-11 15:30 | 2002-08-07 09:30 | NA
Amar | 433 | Residence Address screen - TSD 3.2 | 100% | 20 h | 27 d | 2002-11-13 15:00 | 2002-12-23 16:15 | 20 |  | 20 h | 20 | No | 1.5.2.4.9 | 277FF | Amar[11%] | 2002-11-13 15:00 | 2002-09-27 16:45 | NA
Amar | 435 | Territory Validation (Options screen) - TSD 3.2 | 100% | 30 h | 19 d | 2002-11-25 13:00 | 2002-12-23 16:15 | 30 |  | 30 h | 30 | No | 1.5.2.4.11 | 277FF | Amar[24%] | 2002-11-25 13:00 | 2002-08-23 15:15 | NA
Amar | 434 | AUI Request Driver Information Screen - TSD 3.2 | 100% | 50 h | 20 d | 2002-11-25 13:00 | 2002-12-24 16:00 | 50 |  | 50 h | 50 | No | 1.5.2.4.10 | 277FF | Amar[32%] | 2002-11-25 13:00 | 2002-08-23 15:15 | NA
Amar | 436 | Pf Key format /Branching Program (PCS5F) - TSD 3.2 | 100% | 20 h | 20 d | 2002-11-25 13:00 | 2002-12-24 16:00 | 20 | 288FS+2 d | 20 h | 20 | No | 1.5.2.4.12 | 277FF | Amar[13%] | 2002-11-25 13:00 | 2002-08-23 15:15 | NA
Amar | 251 | Necho Pkg-1 Prep for pilot issuance | 100% | 10 h | 2 d | 2003-01-03 14:15 | 2003-01-07 13:45 | 10 | 171 | 10 h | 10 | No | 1.3.9.1 | 156FS+7 d | Amar[65%] | 2003-01-03 14:15 | 2002-08-23 15:15 | NA
Amar | 252 | MS: Pkg-1 Pilot Necho | 100% | 0 h | 0 d | 2003-01-07 13:45 | 2003-01-07 13:45 | 0 | 165FF-10 d,172FS+15 d | 0 h | 0 | No | 1.3.9.2 | 170 |  | 2003-01-20 10:30 | 2002-09-26 17:00 | NA
Amar | 437 | NECHO - all Remaining Changes - Review TSD 3.2 Docs | 100% | 12 h | 18 d | 2002-12-27 15:30 | 2003-01-22 10:00 | 12 | 289SS,182FS-3 d,290SS,291SS,292SS,293SS,294SS,295SS,296SS,297SS,298SS,299SS | 12 h | 12 | No | 1.5.2.4.13 | 287FS+2 d | Amar[2%],Murthy[2%],Tina[2%],Lakshmi[2%],Ty,Mary | 2002-12-27 15:30 | 2002-10-21 08:30 | NA
Amar | 444 | Territory Validation (Options screen) - TSD 8.3 | 100% | 30 h | 20 d | 2002-12-27 15:30 | 2003-01-24 09:30 | 30 | 334,335 | 30 h | 30 | No | 1.5.2.4.20 | 288SS | Amar[48%] | 2002-12-27 15:30 | 2002-07-12 15:00 | NA
Amar | 445 | Pf Key format /Branching Program (PCS5F) - TSD 8.3 | 100% | 20 h | 20 d | 2002-12-27 15:30 | 2003-01-24 09:30 | 20 | 334,335 | 20 h | 20 | No | 1.5.2.4.21 | 288SS | Amar[32%] | 2002-12-27 15:30 | 2002-09-27 | NA
Amar | 447 | Residence Address screen - TSD 8.3 | 100% | 30 h | 20 d | 2002-12-27 15:30 | 2003-01-24 09:30 | 30 | 334,335 | 30 h | 30 | No | 1.5.2.4.23 | 288SS | Amar[19%] | 2002-12-27 15:30 | 2002-08-09 14:30 | NA
Amar | 255 | MS: NECHO Pkg-1 cowide Issuance | 100% | 0 h | 0 d | 2003-01-28 09:00 | 2003-01-28 09:00 | 0 | 173,167FF-10 d | 0 h | 0 | No | 1.3.9.3 | 171FS+15 d |  | 2003-02-07 15:45 | 2002-09-20 14:30 | NA
Amar | 448 | AUI Request Driver Information Screen - TSD 8.3 | 100% | 60 h | 24 d | 2002-12-27 15:30 | 2003-01-30 08:30 | 60 | 300FS+1 d,334,335 | 60 h | 60 | No | 1.5.2.4.24 | 288SS | Amar[32%] | 2002-12-27 15:30 | 2002-09-27 | NA
Amar | 446 | Auto Apps - Main Program - TSD 8.3 | 100% | 40 h | 20 d | 2002-12-27 15:30 | 2003-01-31 08:15 | 40 | 334,335 | 40 h | 40 | No | 1.5.2.4.22 | 288SS | Amar[32%] | 2002-12-27 15:30 | 2002-09-16 11:00 | NA
Amar | 449 | NECHO - all Remaining Changes - Review TSD 8.3 Docs | 100% | 8 h | 4 d | 2003-01-31 08:15 | 2003-02-05 16:15 | 8 | 334,335 | 8 h | 8 | No | 1.5.2.4.25 | 299FS+1 d | Amar[26%],Murthy[26%],Tina[26%],Lakshmi[26%] | 2003-01-31 08:15 | 2002-08-14 14:30 | NA
Amar | 466 | Auto Apps - Main Program - Coding | 100% | 60 h | 8 d | 2003-02-03 08:00 | 2003-02-12 15:00 | 60 | 319FF | 60 h | 60 | No | 1.5.2.6.13 | 283 | Amar[97%] | 2003-02-03 08:00 | 2002-09-02 13:45 | NA
Amar | 467 | Auto Apps - Main Program - UT/IT | 100% | 60 h | 8 d | 2003-02-03 08:00 | 2003-02-12 15:00 | 60 | 320 | 60 h | 60 | No | 1.5.2.6.14 | 318FF | Tina[97%] | 2003-02-03 08:00 | 2002-09-13 11:15 | NA
Amar | 468 | Residence Address screen - Coding | 100% | 40 h | 10 d | 2003-02-12 15:00 | 2003-02-26 11:30 | 40 | 321FF | 40 h | 40 | No | 1.5.2.6.15 | 319 | Amar[52%] | 2003-02-12 15:00 | 2002-09-16 11:00 | NA
Amar | 469 | Residence Address screen - UT/IT | 100% | 40 h | 10 d | 2003-02-12 15:00 | 2003-02-26 11:30 | 40 | 322,324 | 40 h | 40 | No | 1.5.2.6.16 | 320FF | Amar[52%] | 2003-02-12 15:00 | 2002-09-11 13:18 | NA
Amar | 470 | AUI Request Driver Information Screen - Coding | 100% | 80 h | 15 d | 2003-02-26 11:30 | 2003-03-18 16:45 | 80 | 323FF | 80 h | 80 | No | 1.5.2.6.17 | 321 | Amar[103%] | 2003-02-26 11:30 | 2002-08-13 | NA
Amar | 472 | Territory Validation (Options screen) - Coding | 100% | 60 h | 8 d | 2003-03-14 08:00 | 2003-03-25 15:00 | 60 | 325FF,326SS | 60 h | 60 | No | 1.5.2.6.19 | 321 | Amar[97%] | 2003-03-12 09:00 | 2002-08-15 16:15 | NA
Amar | 474 | Pf Key format /Branching Program (PCS5F) - Coding | 100% | 20 h | 11 d | 2003-03-14 08:00 | 2003-03-28 14:15 | 20 | 327 | 20 h | 20 | No | 1.5.2.6.21 | 324SS | Amar[23%] | 2003-03-25 15:30 | 2002-09-09 15:45 | NA
Amar | 471 | AUI Request Driver Information Screen - UT/IT | 100% | 80 h | 23 d | 2003-02-26 11:30 | 2003-03-28 14:45 | 80 | 328FF | 80 h | 80 | No | 1.5.2.6.18 | 322FF | Tina[103%] | 2003-02-26 11:30 | 2002-09-11 13:18 | NA
Amar | 473 | Territory Validation (Options screen) - UT/IT | 100% | 60 h | 15 d | 2003-03-14 08:00 | 2003-04-03 13:15 | 60 |  | 60 h | 60 | No | 1.5.2.6.20 | 324FF | Amar[48%],Tina | 2003-03-12 09:00 | 2002-09-10 13:15 | NA
Amar | 475 | Pf Key format /Branching Program (PCS5F) - UT/IT | 100% | 40 h | 4 d | 2003-03-28 14:15 | 2003-04-03 13:15 | 40 |  | 40 h | 40 | No | 1.5.2.6.22 | 326 | Tina[65%],Murthy | 2003-03-25 15:30 | 2002-08-16 | NA
Amar | 449a | Driver Info warning Screen - Analysis TSD 3.2, TSD 8.3 | 100% | 24 h | 3 d | 2003-04-01 08:00 | 2003-04-03 16:15 | 24 | 328 | 0 h | 0 | No | 1.5.2.4.26 |  | Amar[103%] | NA | 2002-09-09 13:30 | NA
Amar | 471a | Driver Info warning Screen -Coding, UT/IT | 100% | 32 h | 6 d | 2003-04-03 16:15 | 2003-04-11 14:45 | 32 | 329 | 0 h | 0 | No | 1.5.2.6.23 | 301,323FF | Amar[103%] | NA | 2002-09-10 13:15 | NA
Amar | 476 | MS: NECHO - all Remaining Changes -Coding/UT/IT completed | 100% | 0 h | 0 d | 2003-04-11 14:45 | 2003-04-11 14:45 | 0 | 331FS-3 d,336 | 0 h | 0 | No | 1.5.2.6.24 | 317,328 |  | 2003-03-28 14:45 | 2002-09-16 15:00 | NA
Amar | 425 | Necho RSC Entry for Terr valid & Address Std | 25% | 2 h | 146 d | 2002-11-25 13:00 | 2003-06-13 16:30 | 0.5 |  | 2 h | 0.5 | No | 1.5.2.4.1 | 277SS | Amar[13%] | 2002-11-25 13:00 | 2002-08-28 09:30 | NA
Amar | 505 | Necho Pkg-3 Prep for pilot issuance | 0% | 10 h | 8 d | 2003-07-10 08:15 | 2003-07-21 15:15 | 0 | 362FS+9 d | 10 h | 0 | No | 1.5.6.1 | 345 | Amar[16%] | 2003-05-30 13:30 | 2002-09-10 16:00 | NA
Amar | 506 | MS: Pkg-3 Pilot Necho | 0% | 0 h | 0 d | 2003-08-01 12:00 | 2003-08-01 12:00 | 0 | 353FF-10 d,363FS+16 d,364FF | 0 h | 0 | No | 1.5.6.2 | 361FS+9 d |  | 2003-06-24 17:00 | 2002-09-16 15:00 | NA
Amar | 507 | MS: NECHO Pkg-3 cowide Issuance | 0% | 0 h | 0 d | 2003-08-22 17:00 | 2003-08-22 17:00 | 0 | 355FF-10 d,356FF-5 d,368,369,371,370FS+15 d,365 | 0 h | 0 | No | 1.5.6.3 | 362FS+16 d |  | 2003-07-15 13:15 | 2002-10-08 10:45 | NA
Ashok | 18 | Project Schedule Development -1 | 100% | 110 h | 60 d | 2002-05-28 08:00 | 2002-08-16 09:00 | 110 | 19 | 110 h | 110 | No | 1.1.3.8 | 15FF | Ashok[10%],Carol[16%],Ed[8%],Eric[8%],Murthy[5%],Jill[5%],Lakshmi[5%],Witter[5%],Tina[5%] | 2002-05-28 08:00 | 2002-09-23 14:30 | NA
Ashok | 19 | MS: Performance Measurement Baseline - 1 Established | 100% | 0 h | 0 d | 2002-08-16 09:00 | 2002-08-16 09:00 | 0 |  | 0 h | 0 | No | 1.1.3.9 | 18 |  | 2002-08-16 09:00 | 2002-10-07 11:00 | NA
Ashok | 32 | Technical discussion meetings | 100% | 480 h | 64 d | 2002-08-05 10:00 | 2002-11-08 17:00 | 480 |  | 480 h | 480 | No | 1.2.1.5 | 91FF,32FS+2 d | Ed[8%],Eric[8%],Murthy[10%],Jill[8%],Lakshmi[11%],Witter[8%],SteveH[8%],Tina[10%],Ty[8%],Mary[8%],Amar[8%],John[8%] | 2002-08-05 10:00 | 2002-10-08 10:45 | NA
Ashok | 20 | Project Schedule Development -2 | 100% | 110 h | 43 d | 2002-09-18 16:15 | 2002-11-15 13:30 | 110 | 21 | 110 h | 110 | No | 1.1.3.10 | 92FS-40 d | Ashok[17%],Carol[16%],Ed[8%],Eric[8%],Murthy[5%],Jill[5%],Lakshmi[5%],Witter[6%],Tina[6%] | 2002-10-09 10:30 | 2002-10-21 08:30 | NA
Ashok | 21 | MS: Performance Measurement Baseline - 2 Established | 100% | 0 h | 0 d | 2002-12-16 08:00 | 2002-12-16 08:00 | 0 |  | 0 h | 0 | No | 1.1.3.11 | 20 |  | 2002-11-19 11:00 | 2002-07-23 13:15 | NA
Ashok | 6 | Project Coordination Activities | 80% | 964 h | 281 d | 2002-07-26 08:00 | 2003-08-15 09:45 | 771.2 |  | 964 h | 771.2 | No | 1.1.2.2 |  | Vance[63%] | 2002-07-26 08:00 | 2002-08-06 09:45 | NA
Ashok | 7 | SSS activities | 85% | 350 h | 342 d | 2002-05-06 08:00 | 2003-08-15 10:30 | 297.5 |  | 349 h | 296.65 | No | 1.1.2.3 |  | Michelle[17%] | 2002-05-06 08:00 | 2002-08-16 16:30 | NA
Ashok | 5 | Project Management Activities | 84% | 750 h | 342 d | 2002-05-06 08:00 | 2003-08-15 10:33 | 630 |  | 699 h | 587.16 | No | 1.1.2.1 |  | Carol[35%] | 2002-05-06 08:00 | 2002-10-21 08:30 | NA
Ashok | 8 | Team Weekly Meetings | 83% | 1,000 h | 341.99 d | 2002-05-06 08:00 | 2003-08-15 10:38 | 830 |  | 712 h | 590.96 | No | 1.1.2.4 |  | Carol[4%],Michelle[3%],Ashok[3%],Ed[3%],Eric[3%],Murthy[3%],Jill[3%],Lakshmi[4%],Witter[3%],SteveH[3%],Tina[3%],Ty[3%],Mary[3%],Amar,John,Bill | 2002-05-06 08:00 | 2002-10-21 08:30 | NA
Ashok | 9 | Project Schedule / PlanView Maintenance, and Status Reporting | 78% | 450 h | 267 d | 2002-08-15 08:00 | 2003-08-15 14:15 | 351 |  | 417 h | 325.26 | No | 1.1.2.5 |  | Ashok[29%] | 2002-08-15 08:00 | 2002-10-01 08:15 | NA
Ashok | 24a | IIA Team (Performance Impact Accessment) | 35% | 375 h | 230 d | 2002-10-07 08:00 | 2003-08-18 15:30 | 131.25 |  | 375 h | 131.25 | No | 1.1.5.1 |  | Charles,Daniel,Sherrill,Dave,Harry[18%],Gilbert | 2002-10-07 08:00 | 2002-07-19 13:45 | NA
Bill | 325 | DLV - Host - Physical Design Interface | 100% | 20 h | 4 d | 2002-11-18 14:15 | 2002-11-22 13:15 | 20 | 200 | 20 h | 20 | No | 1.4.4.2.3 | 190 | Bill[65%] | 2002-11-18 14:15 | 2002-08-02 10:15 | NA
Bill | 326 | DLV - Host - Physical Design Interface Walkthrough | 100% | 6 h | 2 d | 2002-11-26 08:00 | 2002-11-29 16:30 | 6 | 198FF+2 d | 6 h | 6 | No | 1.4.4.2.4 | 199 | Bill,EricH[19%] | 2002-11-26 08:00 | 2002-08-07 09:29 | NA
Bill | 324 | DLV - Host - Develop Design Specs | 100% | 30 h | 25 d | 2002-11-04 16:45 | 2002-12-11 09:30 | 30 | 201,182 | 30 h | 30 | No | 1.4.4.2.2 | 200FF+2 d | Bill[19%] | 2002-11-04 16:45 | 2002-09-30 08:30 | NA
Bill | 327 | DLV - Host - Design Specs Walkthrough | 100% | 6 h | 1 d | 2002-12-12 08:00 | 2002-12-12 16:45 | 6 | 202,222 | 6 h | 6 | No | 1.4.4.2.5 | 198 | Bill[39%],EricH[39%] | 2002-12-12 08:00 | 2002-10-01 08:15 | NA
Bill | 328 | DLV - Host - Code/Gen IMS transaction | 100% | 50 h | 6 d | 2002-12-12 16:45 | 2002-12-20 15:15 | 50 | 203SS,204FF,197 | 50 h | 50 | No | 1.4.4.2.6 | 201 | Bill[108%] | 2002-12-12 16:45 | 2002-10-21 08:30 | NA
Bill | 329 | DLV - Host - Code Wrapper | 100% | 50 h | 6 d | 2002-12-12 16:45 | 2002-12-20 15:15 | 50 | 204FF | 50 h | 50 | No | 1.4.4.2.7 | 202SS | Bill[108%] | 2002-12-12 16:45 | 2002-10-17 13:15 | NA
Bill | 330 | DLV - Host - Code Walkthrough | 100% | 6 h | 3 d | 2002-12-17 16:00 | 2002-12-20 15:15 | 6 | 205,225,233 | 6 h | 6 | No | 1.4.4.2.8 | 202FF,203FF | Bill[13%],EricH | 2002-12-17 16:00 | 2002-09-20 09:15 | NA
Bill | 331 | DLV - Host - Unit test IMS transaction | 100% | 50 h | 16 d | 2002-12-20 15:15 | 2003-01-14 10:15 | 50 | 206SS,207 | 50 h | 50 | No | 1.4.4.2.9 | 204 | Bill[43%] | 2002-12-20 15:15 | 2002-10-03 15:45 | NA
Bill | 332 | DLV - Host - Unit test Wrapper | 100% | 50 h | 16 d | 2002-12-20 15:15 | 2003-01-14 10:15 | 50 | 207 | 50 h | 50 | No | 1.4.4.2.10 | 205SS | Bill[43%] | 2002-12-20 15:15 | 2002-10-17 13:15 | NA
Bill | 333 | DLV - Host - Review Test Results | 100% | 6 h | 3 d | 2003-01-14 10:15 | 2003-01-17 09:30 | 6 | 223 | 6 h | 6 | No | 1.4.4.2.11 | 206,205 | Bill[26%],EricH[13%] | 2003-01-13 10:30 | 2002-10-25 16:15 | NA
Bill | 334 | DLV - Host - Security Analyst Setup | 100% | 10 h | 5 d | 2003-01-10 13:00 | 2003-01-17 10:45 | 10 |  | 10 h | 10 | No | 1.4.4.2.12 | 223FF-16 d | David[26%] | 2003-01-07 11:30 | 2002-10-29 15:45 | NA
Bill | 335 | DLV - Host - AUI/DLV Security -NT | 100% | 20 h | 11 d | 2002-12-31 13:45 | 2003-01-17 10:45 | 20 |  | 20 h | 20 | No | 1.4.4.2.13 | 223FF-17 d | Bill[26%] | 2002-12-31 13:45 | 2002-10-29 15:45 | NA
Bill | 323 | DLV - Host RSC Entry | 100% | 4 h | 11 d | 2003-01-06 08:00 | 2003-01-20 14:15 | 4 |  | 4 h | 4 | No | 1.4.4.2.1 | 202 | Bill[7%] | 2002-12-20 15:15 | 2002-11-15 11:30 | NA
Bill | 336 | DLV - Host - Mid Tier /Host Integration Test Reveiew | 100% | 8 h | 2 d | 2003-02-05 16:15 | 2003-02-07 15:45 | 8 |  | 8 h | 8 | No | 1.4.4.2.14 | 223 | Bill[13%],John,EricH,Jeff | 2003-02-05 15:00 | 2002-08-09 09:00 | NA
Brian | 422 | Host Addr Std/ terr-analysis | 100% | 20 h | 30 d | 2002-11-12 16:45 | 2002-12-27 08:15 | 20 | 274 | 20 h | 20 | No | 1.5.2.3.1 | 253 | Brian[14%] | 2002-11-12 16:45 | 2002-08-26 08:00 | NA
Brian | 423 | Host Addr Std/ terr-Coding | 100% | 40 h | 104.13 d | 2002-12-27 08:15 | 2003-05-16 16:15 | 40 |  | 40 h | 40 | No | 1.5.2.3.2 | 273 | Brian[26%] | 2002-12-27 08:15 | 2002-09-06 14:30 | NA
Carol | 3 | MS: Project Activated | 100% | 0 h | 0 d | 2002-05-06 08:00 | 2002-05-06 08:00 | 0 | 11 | 0 h | 0 | No | 1.1.1 |  |  | 2002-05-06 08:00 | 2002-09-13 13:15 | NA
Carol | 11 | Prepare & Review Project Charter | 100% | 67 h | 35 d | 2002-05-21 08:00 | 2002-07-05 16:15 | 67 | 12,14,15,29FS-2 d | 67 h | 67 | No | 1.1.3.1 | 3 | Carol[16%],Ashok[3%],Michelle[3%],Ed[8%],Eric[8%],Murthy[5%],Jill[5%],Lakshmi[5%],Witter[5%],SteveH[5%],Tina[5%] | 2002-05-21 08:00 | 2002-11-07 08:30 | NA
Carol | 12 | MS: Project Charter Reviewed | 100% | 0 h | 0 d | 2002-07-05 16:15 | 2002-07-05 16:15 | 0 | 13 | 0 h | 0 | No | 1.1.3.2 | 11 |  | 2002-06-17 11:00 | 2002-07-31 14:45 | NA
Carol | 13 | MS: Project Charter Authorized | 100% | 0 h | 0 d | 2002-08-30 08:00 | 2002-08-30 08:00 | 0 | 23 | 0 h | 0 | No | 1.1.3.3 | 12 |  | 2002-06-17 11:00 | 2002-07-25 15:45 | NA
Carol | 14 | Facilitation management Processes | 100% | 33 h | 55 d | 2002-07-05 16:15 | 2002-09-19 09:30 | 33 |  | 33 h | 33 | No | 1.1.3.4 | 11 | Carol[4%],Ashok[3%],Michelle[3%],Ed[5%],Eric[5%],Murthy[5%],Jill[5%],Lakshmi[5%],Witter[5%],SteveH[5%],Tina[5%] | 2002-06-17 11:00 | 2002-07-26 15:30 | NA
Carol | 15 | Prepare & review Project Plan | 100% | 38 h | 64 d | 2002-07-05 16:15 | 2002-10-01 16:15 | 38 | 16,18FF | 38 h | 38 | No | 1.1.3.5 | 11 | Carol[16%],Ashok[2%],Michelle[3%],Ed[5%],Eric[5%],Murthy[5%],Jill[5%],Lakshmi[5%],Witter[5%],SteveH[5%],Tina[5%] | 2002-06-17 11:00 | 2002-07-29 15:15 | NA
Carol | 16 | MS: Project Plan Reviewed | 100% | 0 h | 0 d | 2002-10-01 16:15 | 2002-10-01 16:15 | 0 | 17FS+3 d | 0 h | 0 | No | 1.1.3.6 | 15 |  | 2002-07-05 16:15 | 2002-07-30 15:00 | NA
Carol | 17 | MS: Project Plan Authorized | 100% | 0 h | 0 d | 2002-10-04 15:30 | 2002-10-04 15:30 | 0 |  | 0 h | 0 | No | 1.1.3.7 | 16FS+3 d |  | 2002-07-05 16:15 | 2002-07-31 14:45 | NA
Carol | 98 | MS: SDS Doc Authorized | 100% | 0 h | 0 d | 2002-11-22 08:00 | 2002-11-22 08:00 | 0 | 20FS-40 d | 0 h | 0 | No | 1.2.1.14 | 91 |  | 2002-10-29 15:45 | 2002-11-07 08:30 | NA
Carol | 604 | MS: Lessons Learned doc | 0% | 0 h | 0 d | 2003-09-12 13:15 | 2003-09-12 13:15 | 0 |  | 0 h | 0 | No | 1.6.3 | 363FS+15 d |  | 2003-08-05 08:30 | 2002-09-11 10:21 | NA
Carol | 24 | Authorize final SPIP for transition | 0% | 20 h | 10 d | 2003-09-11 13:30 | 2003-09-25 10:00 | 0 |  | 20 h | 0 | No | 1.1.4.2 | 373FS-11 d | Carol[26%] | 2003-04-07 10:45 | 2002-09-24 16:51 | NA
Carol | 606 | Project Closure Tasks | 0% | 40 h | 5 d | 2003-09-19 11:00 | 2003-09-26 09:45 | 0 | 373 | 40 h | 0 | No | 1.6.5 | 371 | Carol[52%],Ashok[40%],Michelle[40%] | 2003-08-11 16:15 | 2002-09-24 16:51 | NA
Carol | 607 | MS: Project Completed | 0% | 0 h | 0 d | 2003-09-26 09:45 | 2003-09-26 09:45 | 0 | 24FS-11 d | 0 h | 0 | No | 1.6.6 | 372 |  | 2003-08-18 15:00 | 2002-09-26 17:00 | NA
David | 306 | Build Test Ids/Rules | 100% | 10 h | 26 d | 2002-12-19 14:45 | 2003-01-24 16:15 | 10 |  | 10 h | 10 | No | 1.4.2.2 |  | David[5%] | 2002-12-19 08:00 | 2002-10-10 14:30 | NA
David | 604a | Create production ids/rules | 100% | 10 h | 20 d | 2003-01-06 13:15 | 2003-01-31 16:15 | 10 |  | 10 h | 10 | No | 1.4.2.3 |  |  | 2003-01-06 13:15 | 2002-10-10 14:30 | NA
David | 305 | SDS 5.2 Specify Security and Control Requirements | 100% | 15 h | 36 d | 2003-01-13 08:00 | 2003-02-28 16:00 | 15 |  | 15 h | 15 | No | 1.4.2.1 |  | David[5%] | 2003-05-07 09:00 | 2002-10-24 11:00 | NA
Durnan | 410 | MQ Q/A High Level Review (req’d objects id’d) | 100% | 20 h | 17 d | 2002-10-28 08:00 | 2002-11-19 11:45 | 20 | 262SS+6 d | 20 h | 20 | No | 1.5.2.2.1.1 | 253 | Durnan[15%] | 2002-10-28 08:00 | 2002-11-07 08:30 | NA
Durnan | 411 | MQ design Infra Diagram (message flow) | 100% | 30 h | 14 d | 2002-11-04 15:30 | 2002-11-22 11:00 | 30 | 263FF | 30 h | 30 | No | 1.5.2.2.1.2 | 261SS+6 d | Durnan[28%] | 2002-11-04 15:30 | 2002-11-07 08:30 | NA
Durnan | 412 | MQ Q/A Detail Level Review (design Walkthrough) | 100% | 5 h | 5 d | 2002-11-15 13:15 | 2002-11-22 11:00 | 5 | 265FS+24 d | 5 h | 5 | No | 1.5.2.2.1.3 | 262FF | Durnan[13%] | 2002-11-15 13:15 | 2002-09-25 08:30 | NA
Durnan | 414 | MQ Objects on Dev Host (coding) | 100% | 10 h | 7 d | 2002-12-30 14:00 | 2003-01-08 11:15 | 10 | 266 | 10 h | 10 | No | 1.5.2.2.2.1 | 263FS+24 d | Durnan[18%] | 2002-12-30 14:00 | 2002-09-18 09:45 | NA
Durnan | 415 | MQ Create Host Test Cases | 100% | 10 h | 5 d | 2003-01-08 11:15 | 2003-01-15 10:00 | 10 | 267 | 10 h | 10 | No | 1.5.2.2.2.2 | 265 | Durnan[26%] | 2003-01-08 11:15 | 2002-09-11 11:00 | NA
Durnan | 416 | MQ Execute & Doc Host Test Cases | 100% | 10 h | 5 d | 2003-01-15 10:00 | 2003-01-22 08:45 | 10 | 269 | 10 h | 10 | No | 1.5.2.2.2.3 | 266 | Durnan[26%] | 2003-01-15 10:00 | 2002-09-18 09:45 | NA
Durnan | 420 | MQ Q/A App Code walkthrough | 100% | 20 h | 9 d | 2003-03-26 08:00 | 2003-04-07 14:45 | 20 |  | 20 h | 20 | No | 1.5.2.2.3.2 | 313FF-6 d | Durnan[43%] | 2003-03-17 08:15 | 2002-09-25 08:30 | NA
Durnan | 418 | MQ Support NECHO Unit Testing | 100% | 20 h | 35 d | 2003-02-24 10:45 | 2003-04-11 10:00 | 20 |  | 20 h | 20 | No | 1.5.2.2.3.1 | 267 | Durnan[14%] | 2003-02-24 10:45 | 2002-09-17 10:00 | NA
Durnan | 419 | MQ Integration Testing | 75% | 20 h | 49 d | 2003-04-09 08:00 | 2003-06-13 11:45 | 15 |  | 20 h | 15 | No | 1.5.2.2.3.3 | 313FF-5 d | Durnan[18%] | 2003-03-17 08:15 | 2002-09-18 09:45 | NA
Durnan | 450 | MQ Q/A Transition to MQService Agreement | 0% | 10 h | 5 d | 2003-06-09 08:00 | 2003-06-13 15:45 | 0 |  | 10 h | 0 | No | 1.5.2.4.27 | 304 | Durnan[26%] | 2003-03-28 14:45 | 2002-09-25 08:30 | NA
Durnan | 508 | MQ Pilot/Issuance | 0% | 20 h | 10 d | 2003-07-18 15:30 | 2003-08-01 12:00 | 0 |  | 20 h | 0 | No | 1.5.6.4 | 362FF | Durnan[26%] | 2003-06-11 10:30 | 2002-09-25 08:30 | NA
ED | 27 | Determine Business Requirements | 100% | 10 h | 24 d | 2002-06-13 11:30 | 2002-07-16 14:30 | 10 | 30FS+6 d,80,46SS,74,52,57,62,70 | 10 h | 10 | No | 1.2.1.1 | 11FS-2 d | Ed[3%],Tina[3%] | 2002-06-13 11:30 | 2003-03-12 09:00 | NA
ED | 28 | Review Testable Business Requirements | 100% | 24 h | 1 d | 2002-07-24 13:00 | 2002-07-25 11:45 | 24 | 94,32FS+5 d,31FS+1 d | 24 h | 24 | No | 1.2.1.2 | 29FS+6 d | Ed[26%],Carol[50%],Ashok[40%],Eric[40%],Murthy,Jill[40%],Lakshmi,Witter[40%],SteveH[40%],Tina,Amar,Michelle[40%] | 2002-07-24 13:00 | 2002-10-21 08:00 | NA
ED | 29 | Review Business Requirements | 100% | 8 h | 1 d | 2002-07-26 11:30 | 2002-07-29 11:15 | 8 | 34,41FS+1 d | 8 h | 8 | No | 1.2.1.3 | 30FS+1 d | Ed,Carol[50%],Tina,Eric[26%] | 2002-07-26 11:30 | 2002-12-06 16:30 | NA
ED | 30 | MS: Business Req approved | 100% | 0 h | 0 d | 2002-08-01 10:30 | 2002-08-01 10:30 | 0 | 33FS+2 d | 0 h | 0 | No | 1.2.1.4 | 30FS+5 d |  | 2002-08-01 10:30 | 2002-12-03 08:30 | NA
ED | 239 | Pkg-1 Draft Communication | 100% | 10 h | 2 d | 2002-10-25 08:00 | 2002-10-28 16:30 | 10 | 162 | 10 h | 10 | No | 1.3.8.1 | 125 | Ed[65%] | 2002-10-25 08:00 | 2002-10-23 16:15 | NA
ED | 96 | Update Delivery Specs Doc | 100% | 20 h | 1 d | 2002-11-04 15:45 | 2002-11-05 15:30 | 20 | 91 | 20 h | 20 | No | 1.2.1.12 | 43,39,85 | Ed[129%],Tina[129%] | 2002-10-22 08:15 | 2002-11-05 14:00 | NA
ED | 97 | Review SDS Doc | 100% | 15 h | 1 d | 2002-11-05 15:30 | 2002-11-06 15:15 | 15 | 33FF,92 | 15 h | 15 | No | 1.2.1.13 | 90 | Carol[97%],Michelle[13%],Ashok[13%],Ed[13%],Eric[13%],Murthy[13%],Jill[13%],Lakshmi[13%],Witter[13%],SteveH[13%],Tina[13%],Ty[13%],Mary[13%],Amar,John | 2002-10-25 16:15 | 2002-12-03 08:30 | NA
ED | 240 | Pkg-1 Communication Review by Proj Team | 100% | 5 h | 14 d | 2002-10-29 08:00 | 2002-11-15 13:30 | 5 | 163 | 5 h | 5 | No | 1.3.8.2 | 161 | Ed[5%] | 2002-10-29 08:00 | 2002-12-06 16:30 | NA
ED | 241 | Pkg-1 UPD Walkthrough with SPIP group | 100% | 5 h | 8 d | 2002-11-18 08:00 | 2002-11-29 15:00 | 5 |  | 5 h | 5 | No | 1.3.8.3 | 162 | Ed[13%] | 2002-11-18 08:00 | 2002-12-17 16:15 | NA
ED | 232 | Create Acceptance Test Cases - Pkg-1 | 100% | 10 h | 2 d | 2002-12-06 16:30 | 2002-12-10 16:00 | 10 |  | 10 h | 10 | No | 1.3.7.3 | 128,133,137,144 | Ed[7%],Lynn[57%] | 2002-12-06 16:30 | 2002-12-06 16:30 | NA
ED | 233 | AUI Acceptance Testing - Pkg-1 | 100% | 29 h | 4 d | 2002-12-17 16:15 | 2002-12-23 15:15 | 29 | 158,157 | 29 h | 29 | No | 1.3.7.4 | 131,135 | Ed[26%],Lynn,SteveH[40%] | 2002-12-17 16:15 | 2002-12-17 14:45 | NA
ED | 246 | Pkg-1 Publish Communication | 100% | 5 h | 5 d | 2002-12-27 08:30 | 2003-01-02 16:15 | 5 |  | 5 h | 5 | No | 1.3.8.8 |  | Ed[13%] | 2003-02-05 16:15 | 2002-12-17 16:15 | NA
ED | 234 | NECHO Acceptance Testing - Pkg-1 | 100% | 30 h | 21 d | 2002-12-09 10:00 | 2003-01-07 13:45 | 30 | 170FS+7 d,158FS-1 d,157 | 30 h | 30 | No | 1.3.7.5 | 146FS-5 d,140FS-5 d | Ed[11%],Lynn,SteveH[40%] | 2002-12-09 10:00 | 2003-01-02 15:45 | NA
ED | 235 | MS: Pkg-1 SAT Completed | 100% | 0 h | 0 d | 2003-01-08 13:30 | 2003-01-08 13:30 | 0 |  | 0 h | 0 | No | 1.3.7.6 | 155,156 |  | 2003-01-08 13:30 | 2002-11-06 16:15 | NA
ED | 256 | Pkg 1-Post implementation questions | 100% | 15 h | 11 d | 2003-01-31 08:00 | 2003-02-14 14:15 | 15 | 174 | 25 h | 25 | No | 1.3.9.4 | 172 | Ed[18%] | 2003-02-12 15:00 | 2002-11-14 14:45 | NA
ED | 257 | MS: Pkg-1 Implemented | 100% | 0 h | 0 d | 2003-02-14 14:15 | 2003-02-14 14:15 | 0 |  | 0 h | 0 | No | 1.3.9.5 | 173 |  | 2003-03-12 09:00 | 2002-11-22 13:15 | NA
ED | 350 | AUI-DLV Acceptance Test Cases developed | 100% | 20 h | 4 d | 2003-02-11 08:15 | 2003-02-14 16:15 | 20 |  | 20 h | 20 | No | 1.4.4.5.4 | 193,204,212 | Ed[65%] | 2002-12-20 15:15 | 2002-12-02 11:15 | NA
ED | 356 | Pkg-2 Draft Communication | 100% | 10 h | 1 d | 2003-02-17 08:00 | 2003-02-17 16:45 | 10 | 237 | 10 h | 10 | No | 1.4.4.8.1 | 176 | Ed[129%] | 2002-12-31 08:00 | 2003-01-02 15:45 | NA
ED | 357 | Pkg-2 Communication Review by Proj Team | 100% | 5 h | 5 d | 2003-02-17 16:45 | 2003-02-24 15:30 | 5 | 238 | 5 h | 5 | No | 1.4.4.8.2 | 236 | Ed[13%] | 2003-01-15 14:00 | 2002-12-16 08:45 | NA
ED | 358 | Pkg-2 UPD Walkthrough with SPIP group | 100% | 5 h | 4 d | 2003-02-24 15:30 | 2003-02-28 14:30 | 5 |  | 5 h | 5 | No | 1.4.4.8.3 | 237 | Ed[16%] | 2003-01-22 11:45 | 2002-11-05 16:30 | NA
ED | 351 | AUI-DLV Acceptance Testing | 100% | 30 h | 28.19 d | 2003-02-26 11:30 | 2003-04-04 15:00 | 30 | 246,242SS,229FS-25 d | 30 h | 30 | No | 1.4.4.5.6 | 224,226FF | Ed[18%] | 2003-02-26 10:15 | 2002-11-07 16:00 | NA
ED | 483 | SAT -Perform System/Acceptance Testing pkg-3 | 100% | 50 h | 36.68 d | 2003-04-14 10:59 | 2003-06-02 16:15 | 50 | 337,344,345 | 50 h | 50 | No | 1.5.4.3 | 304FS-1 d,329 | Ed[26%] | 2003-03-31 08:00 | 2002-11-11 15:30 | NA
ED | 488 | SAT - Create FIT Test Cases | 0% | 40 h | 10 d | 2003-06-02 16:15 | 2003-06-16 13:45 | 0 | 345 | 40 h | 0 | No | 1.5.4.7.2 | 336 | Ed[52%] | 2003-04-11 14:30 | 2002-12-16 08:45 | NA
ED | 361 | Pkg-2 Publish Communication | 0% | 5 h | 1 d | 2003-06-23 08:00 | 2003-06-23 16:45 | 0 |  | 5 h | 0 | No | 1.4.4.8.6 | 249FF-9 d | Ed[65%] | 2003-05-05 11:45 | 2002-12-20 14:00 | NA
ED | 489 | SAT - Perform FIT Testing - Pkg-3 | 0% | 50 h | 18 d | 2003-06-16 13:45 | 2003-07-10 08:15 | 0 | 346,361,357SS | 50 h | 0 | No | 1.5.4.7.3 | 336,186,344,341 | Ed[36%] | 2003-04-25 11:00 | 2002-12-20 14:00 | NA
ED | 493 | Pkg-3 Draft Communication | 50% | 10 h | 46 d | 2003-05-12 08:00 | 2003-07-11 13:30 | 5 | 350 | 10 h | 5 | No | 1.5.5.1 | 253 | Ed[26%] | 2003-04-07 08:00 | 2002-12-03 11:00 | NA
ED | 494 | Pkg-3 Communication Review by Proj Team | 0% | 5 h | 5 d | 2003-07-11 13:30 | 2003-07-18 11:15 | 0 | 351 | 5 h | 0 | No | 1.5.5.2 | 349 | Ed[13%] | 2003-04-14 15:30 | 2002-12-20 14:00 | NA
ED | 495 | Pkg-3 UPD Walkthrough with SPIP group | 0% | 5 h | 5 d | 2003-07-18 11:15 | 2003-07-25 10:00 | 0 |  | 5 h | 0 | No | 1.5.5.3 | 350 | Ed[13%] | 2003-04-21 14:15 | 2003-01-13 11:45 | NA
ED | 370 | Pkg 2-Post implemetation questions | 0% | 25 h | 20 d | 2003-07-04 09:00 | 2003-07-31 12:00 | 0 | 251 | 25 h | 0 | No | 1.4.4.9.5 | 249 | Ed[16%] | 2003-05-26 08:00 | 2002-11-15 16:15 | NA
ED | 371 | MS: Pkg-2 Completed | 0% | 0 h | 0 d | 2003-07-31 12:00 | 2003-07-31 12:00 | 0 |  | 0 h | 0 | No | 1.4.4.9.6 | 250 |  | 2003-06-20 11:00 | 2002-11-15 16:15 | NA
ED | 500 | Pkg-3 Publish Communication | 0% | 5 h | 5 d | 2003-08-11 10:30 | 2003-08-18 09:15 | 0 |  | 5 h | 0 | No | 1.5.5.8 | 363FF-5 d | Ed[13%] | 2003-07-01 15:45 | 2002-12-10 16:00 | NA
ED | 509 | Pkg-3-Post implemetation questions | 0% | 35 h | 20 d | 2003-08-25 08:00 | 2003-09-19 11:00 | 0 | 366 | 35 h | 0 | No | 1.5.6.5 | 363 | Ed[16%],Durnan | 2003-07-15 13:15 | 2002-12-23 15:15 | NA
ED | 510 | MS: Pkg-3 Completed | 0% | 0 h | 0 d | 2003-09-19 11:00 | 2003-09-19 11:00 | 0 |  | 0 h | 0 | No | 1.5.6.6 | 365 |  | 2003-08-11 16:15 | 2002-12-24 16:00 | NA
Eric | 40 | AUTO - review existing territory validation | 100% | 15 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 15 | 42FF,44,43FF | 15 h | 15 | No | 1.2.1.8.1 | 31FS+1 d | Eric[10%] | 2002-07-30 11:00 | 2003-01-08 13:30 | NA
Eric | 41 | AUTO - review existing IRG validation | 100% | 15 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 15 |  | 15 h | 15 | No | 1.2.1.8.2 | 41FF | Eric[10%] | 2002-07-30 11:00 | 2003-01-06 14:00 | NA
Eric | 42 | AUTO - review existing driver's license validation | 100% | 15 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 15 | 90 | 15 h | 15 | No | 1.2.1.8.3 | 41FF | Eric[10%] | 2002-07-30 11:00 | 2003-01-13 11:45 | NA
Jill | 35 | DOMAIN - review existing territory validation | 100% | 3 h | 24 d | 2002-07-30 11:00 | 2002-08-30 14:00 | 3 |  | 3 h | 3 | No | 1.2.1.7.1 |  | Jill[39%] | 2002-07-30 11:00 | 2003-02-12 15:00 | NA
Jill | 36 | DOMAIN - review existing IRG validation | 100% | 3 h | 23 d | 2002-07-31 10:45 | 2002-08-30 14:00 | 3 |  | 3 h | 3 | No | 1.2.1.7.2 |  | Jill[8%] | 2002-07-31 10:45 | 2002-10-28 16:30 | NA
Jill | 37 | DOMAIN - review existing driver's license validation | 100% | 3 h | 23 d | 2002-07-31 10:45 | 2002-08-30 14:00 | 3 | 44 | 3 h | 3 | No | 1.2.1.7.3 |  | Jill[8%] | 2002-07-31 10:45 | 2002-11-15 13:30 | NA
Jill | 38 | Create SRA 4/SDS 3.1 identifying impacted reusable service areas | 100% | 4 h | 18 d | 2002-08-30 14:00 | 2002-09-25 08:30 | 4 | 90 | 4 h | 4 | No | 1.2.1.7.4 | 44SS | Jill[2%],Ed[40%],Tina[40%] | 2002-09-27 08:00 | 2002-11-29 15:00 | NA
John | 316 | DLV - Mid Tier - Logical Design Interface | 100% | 24 h | 5 d | 2002-11-04 15:30 | 2002-11-18 14:15 | 24 | 191,199,222 | 24 h | 24 | No | 1.4.4.1.2 | 176FS+6 d | John[62%] | 2002-11-04 15:30 | 2002-12-30 15:15 | NA
John | 317 | DLV - Mid Tier - Logical Design Interface Walkthrough | 100% | 9 h | 4 d | 2002-11-19 08:00 | 2002-11-22 16:00 | 9 | 192,182 | 9 h | 9 | No | 1.4.4.1.3 | 190 | John[10%],EricH,Jeff | 2002-11-19 08:00 | 2003-01-06 14:00 | NA
John | 318 | DLV - Mid Tier - Coding | 100% | 60 h | 18 d | 2002-11-22 16:00 | 2002-12-20 10:30 | 60 | 189SS,193FF,194FF,195FF | 60 h | 60 | No | 1.4.4.1.4 | 191 | John[52%] | 2002-11-22 16:00 | 2003-01-20 10:30 | NA
John | 319 | DLV - Mid Tier - Code Walk Through | 100% | 6 h | 14 d | 2002-11-28 15:00 | 2002-12-20 10:30 | 6 | 225,233 | 6 h | 6 | No | 1.4.4.1.5 | 192FF | John[3%],Jeff[3%] | 2002-11-28 15:00 | 2003-01-27 09:15 | NA
John | 320 | DLV - Mid Tier - Unit Test Review | 100% | 20 h | 16 d | 2002-11-28 15:00 | 2002-12-20 16:15 | 20 |  | 20 h | 20 | No | 1.4.4.1.6 | 192FF | John[258%] | 2002-11-28 15:00 | 2003-02-12 15:00 | NA
John | 321 | DLV - Mid Tier - Unit Testing | 100% | 6 h | 16 d | 2002-11-28 15:00 | 2002-12-20 16:15 | 6 | 223 | 6 h | 6 | No | 1.4.4.1.7 | 192FF | John[3%],Jeff[3%] | 2002-11-28 15:00 | 2003-03-12 09:00 | NA
John | 315 | DLV - Mid Tier - RSC Entry | 100% | 4 h | 36 d | 2002-11-28 08:00 | 2003-01-17 16:00 | 4 |  | 4 h | 4 | No | 1.4.4.1.1 | 192SS | Bill[5%],John | 2002-11-28 08:00 | 2003-01-07 13:45 | NA
John | 366 | Mid Tier-Host Prep cowide issuance | 0% | 20 h | 10 d | 2003-06-13 13:45 | 2003-06-27 10:15 | 0 | 247 | 20 h | 0 | No | 1.4.4.9.1 | 227,230,231 | John[26%] | 2003-04-21 15:45 | 2003-01-20 10:30 | NA
John | 367 | MS: Mid Tier-Host cowide issuance | 0% | 0 h | 0 d | 2003-06-27 10:15 | 2003-06-27 10:15 | 0 | 248 | 0 h | 0 | No | 1.4.4.9.2 | 246 |  | 2003-05-12 08:00 | 2003-02-07 15:45 | NA
Lynn | 242 | MS: Pkg-1 Create Agency pilot communications | 100% | 0 h | 0 d | 2002-12-30 15:15 | 2002-12-30 15:15 | 0 |  | 0 h | 0 | No | 1.3.8.4 | 165FF-5 d |  | 2002-12-30 15:15 | 2003-03-12 09:00 | NA
Lynn | 243 | MS: Pkg-1 Publish Agency pilot communications | 100% | 0 h | 0 d | 2003-01-06 14:00 | 2003-01-06 14:00 | 0 | 164FF-5 d | 0 h | 0 | No | 1.3.8.5 | 171FF-10 d |  | 2003-01-06 14:00 | 2003-03-12 09:00 | NA
Lynn | 244 | MS: Pkg-1 Create Agency cowide communications | 100% | 0 h | 0 d | 2003-01-07 13:45 | 2003-01-07 13:45 | 0 |  | 0 h | 0 | No | 1.3.8.6 | 167FF-5 d |  | 2003-01-20 10:30 | 2003-06-20 11:00 | NA
Lynn | 245 | MS: Pkg-1 Publish Agency cowide communications | 100% | 0 h | 0 d | 2003-01-14 11:30 | 2003-01-14 11:30 | 0 | 166FF-5 d | 0 h | 0 | No | 1.3.8.7 | 172FF-10 d |  | 2003-01-27 09:15 | 2002-10-28 08:00 | NA
Lynn | 359 | MS: Pkg-2 Create Agency cowide communications | 0% | 0 h | 0 d | 2003-06-20 11:30 | 2003-06-20 11:30 | 0 |  | 0 h | 0 | No | 1.4.4.8.4 | 240FF-5 d |  | 2003-05-12 10:30 | 2003-05-14 16:30 | NA
Lynn | 360 | MS: Pkg-2 Publish Agency cowide communications | 0% | 0 h | 0 d | 2003-06-27 10:15 | 2003-06-27 10:15 | 0 | 239FF-5 d | 0 h | 0 | No | 1.4.4.8.5 | 249FF-5 d |  | 2003-05-19 09:15 | 2003-05-14 16:30 | NA
Lynn | 496 | MS: Pkg-3 Create Agency pilot communications | 0% | 0 h | 0 d | 2003-07-11 16:45 | 2003-07-11 16:45 | 0 |  | 0 h | 0 | No | 1.5.5.4 | 353FF-5 d |  | 2003-06-04 11:45 | 2003-03-03 10:45 | NA
Lynn | 497 | MS: Pkg-3 Publish Agency pilot communications | 0% | 0 h | 0 d | 2003-07-18 15:30 | 2003-07-18 15:30 | 0 | 352FF-5 d | 0 h | 0 | No | 1.5.5.5 | 362FF-10 d |  | 2003-06-11 10:30 | 2003-01-31 16:15 | NA
Lynn | 498 | MS: Pkg-3 Create Agency cowide communications | 0% | 0 h | 0 d | 2003-08-04 11:45 | 2003-08-04 11:45 | 0 |  | 0 h | 0 | No | 1.5.5.6 | 355FF-5 d |  | 2003-06-24 17:00 | 2003-04-21 16:15 | NA
Lynn | 499 | MS: Pkg-3 Publish Agency cowide communications | 0% | 0 h | 0 d | 2003-08-11 10:30 | 2003-08-11 10:30 | 0 | 354FF-5 d | 0 h | 0 | No | 1.5.5.7 | 363FF-10 d |  | 2003-07-01 15:45 | 2002-12-27 15:30 | NA
Murthy | 215 | NECHO -DLV - Design Low level Specs (TSD3.2) | 100% | 20 h | 3 d | 2002-11-04 08:00 | 2002-11-06 16:15 | 20 | 143SS,138,154 | 20 h | 20 | No | 1.3.4.1 | 125 | Murthy[86%] | 2002-11-04 08:00 | 2003-01-07 13:45 | NA
Murthy | 216 | NECHO -DLV - Design Test Cases (TSD8.3) | 100% | 40 h | 6 d | 2002-11-06 16:15 | 2002-11-14 14:45 | 40 | 139 | 40 h | 40 | No | 1.3.4.2 | 137 | Murthy[86%] | 2002-11-06 16:15 | 2003-01-07 13:45 | NA
Murthy | 217 | NECHO - DLV - Coding | 100% | 30 h | 6 d | 2002-11-14 14:45 | 2002-11-22 13:15 | 30 | 140SS+1 d,149 | 30 h | 30 | No | 1.3.4.3 | 138 | Murthy[65%] | 2002-11-14 14:45 | 2003-01-07 13:45 | NA
Murthy | 218 | NECHO -DLV - Unit Testing | 100% | 29 h | 9 d | 2002-11-15 14:30 | 2002-12-02 11:15 | 29 | 156FS-5 d,277SS+6 d,141 | 29 h | 29 | No | 1.3.4.4 | 139SS+1 d | Murthy[13%],Amar[29%] | 2002-11-15 14:30 | 2003-04-21 16:15 | NA
Murthy | 426 | AUI Request Vehicle Information Screen - TSD 3.2 | 100% | 50 h | 12 d | 2002-11-25 13:00 | 2002-12-13 09:00 | 50 | 278SS,279SS,280SS,281SS,282SS,284FF,285FF,286FF,287FF,276SS | 50 h | 50 | No | 1.5.2.4.2 | 140SS+6 d | Murthy[161%] | 2002-11-25 13:00 | 2003-06-20 11:00 | NA
Murthy | 427 | MQ - Interface module - TSD 3.2 | 100% | 30 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 30 |  | 30 h | 30 | No | 1.5.2.4.3 | 277SS | Murthy[32%] | 2002-12-03 11:00 | 2003-01-01 10:15 | NA
Murthy | 428 | Incoming Interface - TSD 3.2 | 100% | 20 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 20 |  | 20 h | 20 | No | 1.5.2.4.4 | 277SS | Murthy[22%] | 2002-12-03 11:00 | 2003-01-01 10:15 | NA
Murthy | 430 | Build Auto App Program - TSD 3.2 | 100% | 20 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 20 |  | 20 h | 20 | No | 1.5.2.4.6 | 277SS | Murthy[22%] | 2002-12-03 11:00 | 2002-11-18 14:15 | NA
Murthy | 431 | Warning Screen - TSD 3.2 | 100% | 20 h | 15 d | 2002-12-03 11:00 | 2002-12-23 16:15 | 20 |  | 20 h | 20 | No | 1.5.2.4.7 | 277SS | Murthy[22%] | 2002-12-03 11:00 | 2002-11-22 16:00 | NA
Murthy | 429 | Outgoing Interface - TSD 3.2 | 100% | 20 h | 16 d | 2002-12-03 11:00 | 2002-12-24 16:00 | 20 |  | 20 h | 20 | No | 1.5.2.4.5 | 277SS | Murthy[16%] | 2002-12-03 11:00 | 2002-12-20 10:30 | NA
Murthy | 442 | Build Auto App Program - TSD 8.3 | 100% | 20 h | 11 d | 2002-12-27 08:00 | 2003-01-10 14:15 | 20 | 334,335 | 20 h | 20 | No | 1.5.2.4.18 | 288SS | Murthy[23%] | 2002-12-27 08:00 | 2002-12-20 10:30 | NA
Murthy | 443 | Warning Screen - TSD 8.3 | 100% | 20 h | 15 d | 2002-12-27 15:30 | 2003-01-17 10:45 | 20 | 334,335 | 20 h | 20 | No | 1.5.2.4.19 | 288SS | Murthy[17%] | 2002-12-27 15:30 | 2002-12-20 16:15 | NA
Murthy | 438 | AUI Request Vehicle Information Screen - TSD 8.3 | 100% | 60 h | 18 d | 2002-12-27 15:30 | 2003-01-22 10:00 | 60 | 334,335,306 | 60 h | 60 | No | 1.5.2.4.14 | 288SS | Murthy[43%] | 2002-12-27 15:30 | 2002-12-20 16:15 | NA
Murthy | 441 | Outgoing Interface - TSD 8.3 | 100% | 20 h | 21 d | 2002-12-27 15:30 | 2003-01-27 09:15 | 20 | 334,335 | 20 h | 20 | No | 1.5.2.4.17 | 288SS | Murthy[22%] | 2002-12-27 15:30 | 2003-02-10 14:15 | NA
Murthy | 214 | NECHO DLV - RSC Entry | 100% | 2 h | 1 d | 2003-01-27 08:00 | 2003-01-27 16:45 | 2 |  | 2 h | 2 | No | 1.3.4.5 | 140 | Murthy[26%] | 2003-01-01 16:00 | 2002-12-30 14:00 | NA
Murthy | 439 | MQ - Interface module - TSD 8.3 | 100% | 30 h | 24 d | 2002-12-27 15:30 | 2003-01-30 08:30 | 30 | 334,335 | 30 h | 30 | No | 1.5.2.4.15 | 288SS | Murthy[16%] | 2002-12-27 15:30 | 2002-12-11 09:30 | NA
Murthy | 440 | Incoming Interface - TSD 8.3 | 100% | 20 h | 24 d | 2002-12-27 15:30 | 2003-01-30 08:30 | 20 | 334,335 | 20 h | 20 | No | 1.5.2.4.16 | 288SS | Murthy[11%] | 2002-12-27 15:30 | 2002-11-22 13:15 | NA
Murthy | 454 | AUI Request Vehicle Information Screen - Coding | 100% | 80 h | 10 d | 2003-02-03 08:00 | 2003-02-14 14:30 | 80 | 307FF | 80 h | 80 | No | 1.5.2.6.1 | 289 | Murthy[103%] | 2003-02-03 08:00 | 2002-11-29 16:30 | NA
Murthy | 455 | AUI Request Vehicle Information Screen - UT/IT | 100% | 80 h | 10 d | 2003-02-03 08:00 | 2003-02-14 14:30 | 80 | 308 | 80 h | 80 | No | 1.5.2.6.2 | 306FF | Lakshmi[103%] | 2003-02-03 08:00 | 2002-12-12 16:45 | NA
Murthy | 458 | Incoming Interface - Coding | 100% | 30 h | 4 d | 2003-03-07 09:45 | 2003-03-13 08:45 | 30 | 311FF | 30 h | 30 | No | 1.5.2.6.5 | 309FS-7 d | Murthy[97%] | 2003-03-04 10:30 | 2002-12-20 15:15 | NA
Murthy | 459 | Incoming Interface - UT/IT | 100% | 30 h | 4 d | 2003-03-07 09:45 | 2003-03-13 08:45 | 30 | 312,314,316 | 30 h | 30 | No | 1.5.2.6.6 | 310FF | Lakshmi[97%] | 2003-03-04 10:30 | 2002-12-20 15:15 | NA
Murthy | 456 | MQ - Interface module - Coding | 100% | 50 h | 38 d | 2003-02-14 14:30 | 2003-04-08 12:00 | 50 | 309FF | 50 h | 50 | No | 1.5.2.6.3 | 307 | Murthy[54%] | 2003-02-14 14:30 | 2002-12-20 15:15 | NA
Murthy | 457 | MQ - Interface module - UT/IT | 100% | 40 h | 38 d | 2003-02-14 14:30 | 2003-04-08 12:00 | 40 | 310FS-7 d | 40 h | 40 | No | 1.5.2.6.4 | 308FF | Murthy[43%] | 2003-02-14 14:30 | 2003-01-13 10:30 | NA
Murthy | 460 | Build Auto App Program - Coding | 100% | 40 h | 19 d | 2003-03-13 08:45 | 2003-04-08 12:00 | 40 | 313FF | 40 h | 40 | No | 1.5.2.6.7 | 311 | Murthy[129%] | 2003-03-10 09:30 | 2003-01-13 10:30 | NA
Murthy | 461 | Build Auto App Program - UT/IT | 100% | 40 h | 19 d | 2003-03-13 08:45 | 2003-04-08 12:00 | 40 | 271FF-5 d,270FF-6 d | 40 h | 40 | No | 1.5.2.6.8 | 312FF | Lakshmi[129%] | 2003-03-10 09:30 | 2003-01-16 09:45 | NA
Murthy | 462 | Warning Screen - Coding | 100% | 30 h | 13 d | 2003-03-24 08:00 | 2003-04-09 13:45 | 30 | 315FF | 30 h | 30 | No | 1.5.2.6.9 | 311 | Murthy[32%] | 2003-03-17 08:15 | 2003-01-14 10:15 | NA
Murthy | 463 | Warning Screen - UT/IT | 100% | 30 h | 13 d | 2003-03-24 08:00 | 2003-04-09 13:45 | 30 |  | 30 h | 30 | No | 1.5.2.6.10 | 314FF | Lakshmi[32%] | 2003-03-17 08:15 | 2003-01-14 10:15 | NA
Murthy | 464 | Outgoing Interface - Coding | 100% | 30 h | 5 d | 2003-04-03 08:15 | 2003-04-09 16:00 | 30 | 317FF | 30 h | 30 | No | 1.5.2.6.11 | 311 | Murthy[97%] | 2003-03-20 16:15 | 2003-02-10 14:15 | NA
Murthy | 465 | Outgoing Interface - UT/IT | 100% | 30 h | 5 d | 2003-04-03 08:15 | 2003-04-09 16:00 | 30 | 329 | 30 h | 30 | No | 1.5.2.6.12 | 316FF | Lakshmi[97%] | 2003-03-20 16:15 | 2003-01-08 13:15 | NA
SteveH | 100 | Create Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 50 h | 32 d | 2002-07-25 11:45 | 2002-09-06 11:45 | 50 |  | 50 h | 50 | No | 1.2.2.1 | 30 | SteveH[59%] | 2002-07-25 11:45 | 2002-11-25 10:45 | NA
SteveH | 102 | Create Defect Tracking Strategy | 100% | 40 h | 10 d | 2002-08-26 08:00 | 2002-09-06 14:30 | 40 | 97 | 40 h | 40 | No | 1.2.2.3 |  | SteveH[52%] | 2002-08-26 08:00 | 2002-12-24 15:45 | NA
SteveH | 103 | Review Defect Tracking Strategy | 100% | 10 h | 5 d | 2002-09-06 14:30 | 2002-09-13 13:15 | 10 |  | 10 h | 10 | No | 1.2.2.4 | 96 | SteveH[1%],Carol[50%],Ashok[40%],Ed,Murthy,Eric[40%],Jill[40%],Lakshmi,Witter[40%],Tina,Amar,Ty,Mary | 2002-09-06 14:30 | 2003-01-08 13:15 | NA
SteveH | 101 | Review Test Strategy (SRA 6.5) for AUI and ECHO enhancements | 100% | 11 h | 31 d | 2002-08-09 08:00 | 2002-09-20 08:15 | 11 |  | 11 h | 11 | No | 1.2.2.2 |  | SteveH[0%],Carol[0%],Ashok[0%],Ed[0%],Murthy[1%],Eric[0%],Jill[0%],Lakshmi[6%],Witter[0%],Tina[89%],Amar[0%],Ty[0%],Mary[0%] | 2002-08-09 09:00 | 2003-01-08 13:15 | NA
SteveH | 229 | Establish Test Environment Needs - Pkg-1 | 100% | 10 h | 2 d | 2002-11-13 16:45 | 2002-11-15 16:15 | 10 |  | 10 h | 10 | No | 1.3.7.1 |  | SteveH[65%] | 2002-11-13 16:45 | 2002-12-26 14:30 | NA
SteveH | 230 | Establish Test Environment - Pkg-1 | 100% | 20 h | 5 d | 2002-11-11 08:30 | 2002-11-15 16:15 | 20 |  | 20 h | 20 | No | 1.3.7.2 |  | SteveH[52%] | 2002-11-11 08:30 | 2002-11-22 11:00 | NA
SteveH | 308 | Establish Test Environment needs | 100% | 10 h | 3 d | 2002-12-23 16:15 | 2002-12-27 15:30 | 10 | 183SS,184SS,185SS,186 | 10 h | 10 | No | 1.4.3.1 | 191,198,212,288FS-3 d | SteveH[43%] | 2002-12-23 16:15 | 2002-12-17 16:00 | NA
SteveH | 236 | Create Acceptance Test Summary Report - Pkg-1 | 100% | 10 h | 9 d | 2002-12-23 16:15 | 2003-01-06 14:00 | 10 | 159 | 10 h | 10 | No | 1.3.7.7 | 155,156FS-1 d | SteveH[65%] | 2002-12-23 16:15 | 2002-12-26 14:30 | NA
SteveH | 311 | Determine FIT Test Environment Needs | 100% | 20 h | 9 d | 2002-12-23 16:15 | 2003-01-06 14:00 | 20 | 343 | 20 h | 20 | No | 1.4.3.4 | 182SS | SteveH[43%] | 2002-12-23 16:15 | NA | NA
SteveH | 237 | Review / Authorize Acceptance Test Summary Report - Pkg-1 | 100% | 20 h | 5 d | 2003-01-06 14:00 | 2003-01-13 11:45 | 20 |  | 20 h | 20 | No | 1.3.7.8 | 158 | SteveH[52%] | 2003-01-06 14:00 | 2003-03-05 09:00 | NA
SteveH | 309 | Set-up AUI Integration/System Test Environment | 100% | 20 h | 18 d | 2002-12-23 16:15 | 2003-01-17 10:45 | 20 | 223 | 20 h | 20 | No | 1.4.3.2 | 182SS | SteveH[26%] | 2002-12-23 16:15 | 2003-01-17 14:30 | NA
SteveH | 310 | Set-up NECHO Integration/System Test Environment | 100% | 20 h | 18 d | 2002-12-23 16:15 | 2003-01-17 10:45 | 20 | 304 | 20 h | 20 | No | 1.4.3.3 | 182SS | SteveH[26%] | 2002-12-23 16:15 | 2003-02-05 15:00 | NA
SteveH | 347 | AUI - Create AUI System Test Plan | 100% | 20 h | 10 d | 2003-01-06 08:00 | 2003-01-17 14:30 | 20 |  | 20 h | 20 | No | 1.4.4.5.1 | 212,190,201,217 | SteveH[26%] | 2003-01-06 08:00 | 2003-02-26 10:15 | NA
SteveH | 348 | AUI-DLV Mid Tier / Host Int Test | 100% | 60 h | 14 d | 2003-01-17 10:45 | 2003-02-05 16:15 | 60 | 209FF-17 d,208FF-16 d,210,224 | 60 h | 60 | No | 1.4.4.5.2 | 195,207,183,219 | Bill[23%],John[36%],SteveH[23%] | 2003-01-16 09:45 | 2003-01-13 10:30 | NA
SteveH | 481 | SAT - Create System/Acceptance Test Plan | 100% | 20 h | 10 d | 2003-02-05 16:15 | 2003-02-19 13:45 | 20 |  | 20 h | 20 | No | 1.5.4.1 | 289,290,291,292,293,294,295,296,297,298,299,300 | SteveH[26%] | 2003-02-05 16:15 | NA | NA
SteveH | 487 | SAT - Create NECHO System/Acceptance Test Plan | 100% | 20 h | 34 d | 2003-01-06 14:00 | 2003-02-20 13:30 | 20 |  | 20 h | 20 | No | 1.5.4.7.1 | 185 | SteveH[17%] | 2003-01-06 14:00 | 2003-03-05 09:00 | NA
SteveH | 349 | AUI-DLV Web / Mid Tier / Host System Testing (Initial) | 100% | 80 h | 15 d | 2003-02-05 16:15 | 2003-02-26 11:30 | 80 | 227 | 80 h | 80 | No | 1.4.4.5.3 | 223 | SteveH[40%],Witter[26%],John,Bill | 2003-02-05 15:00 | 2003-03-25 14:15 | NA
SteveH | 482 | SAT - Create System/Acceptance Test Cases | 100% | 40 h | 31 d | 2003-02-21 08:00 | 2003-04-04 08:15 | 40 |  | 40 h | 40 | No | 1.5.4.2 | 289,290,291,292,293,294,295,296,297,298,299,300 | SteveH[34%] | 2003-02-21 08:00 | 2003-03-11 16:45 | NA
SteveH | 351a | Setup Perf. Testing Pkg-2 | 100% | 20 h | 28 d | 2003-03-05 11:45 | 2003-04-11 13:45 | 20 | 230,231 | 20 h | 20 | No | 1.4.4.6.1 | 227FS-25 d | SteveH[6%],PerTeam[5%] | 2003-03-05 09:00 | 2003-03-25 14:15 | NA
SteveH | 452 | Perform Integration Testing for NECHO Changes - pkg-2 | 100% | 120 h | 61 d | 2003-01-20 10:30 | 2003-04-15 10:44 | 120 | 302,336FS-1 d | 120 h | 120 | No | 1.5.2.5.1 | 184 | SteveH[3%],Murthy,Tina,Amar,Durnan,Brian | 2003-01-20 10:30 | NA | NA
SteveH | 312 | Set-up FIT Test Environment | 100% | 20 h | 91.87 d | 2003-01-21 08:00 | 2003-05-24 16:15 | 20 | 345 | 20 h | 20 | No | 1.4.3.5 | 182 | SteveH[4%] | 2003-01-21 08:00 | 2003-01-07 13:30 | NA
SteveH | 491a | Setup Performance Test Environment -pkg3 | 100% | 20 h | 15.48 d | 2003-05-05 08:00 | 2003-05-24 16:15 | 20 | 341 | 0 h | 0 | No | 1.5.4.6.1 |  |  | NA | 2003-01-06 13:45 | NA
SteveH | 484 | SAT - Create System/Acceptance Test Summary Report | 0% | 10 h | 2 d | 2003-06-02 16:15 | 2003-06-04 15:45 | 0 | 338 | 10 h | 0 | No | 1.5.4.4 | 336 | SteveH[65%] | 2003-04-25 11:00 | 2003-01-07 13:30 | NA
SteveH | 485 | SAT - Authorize System/Acceptance Test Summary Report | 0% | 10 h | 5 d | 2003-06-04 15:45 | 2003-06-11 14:30 | 0 |  | 10 h | 0 | No | 1.5.4.5 | 337 | SteveH[26%] | 2003-04-30 10:15 | 2003-05-19 09:15 | NA
SteveH | 351c | Implementation testing execution pkg-2 | 25% | 20 h | 31 d | 2003-05-02 08:00 | 2003-06-13 08:15 | 5 | 246 | 0 h | 0 | No | 1.4.4.6.3 | 229 | SteveH[52%],Witter[6%],John,Bill | NA | 2003-01-15 14:00 | NA
SteveH | 491b | Execute Performance Testing - pk3 | 25% | 50 h | 15 d | 2003-05-26 08:00 | 2003-06-13 13:15 | 12.5 | 345 | 0 h | 0 | No | 1.5.4.6.2 | 340 |  | NA | 2003-01-22 11:45 | NA
SteveH | 351b | Execute Perf. Testing Pkg-2 | 75% | 50 h | 45 d | 2003-04-15 08:00 | 2003-06-13 13:45 | 37.5 | 246 | 50 h | 37.5 | No | 1.4.4.6.2 | 229 | SteveH[10%],PerTeam[40%] | 2003-03-11 16:45 | 2003-01-31 10:00 | NA
SteveH | 490 | SAT - Create FIT Test Summary Report | 0% | 10 h | 10 d | 2003-07-10 08:15 | 2003-07-23 14:45 | 0 | 347 | 10 h | 0 | No | 1.5.4.7.4 | 345 | SteveH[13%] | 2003-05-30 13:30 | 2003-05-12 10:30 | NA
SteveH | 491 | SAT - Authorize FIT Test Summary Report | 0% | 10 h | 5 d | 2003-07-23 14:45 | 2003-07-30 13:30 | 0 |  | 10 h | 0 | No | 1.5.4.7.5 | 346 | SteveH[26%] | 2003-06-13 10:00 | 2003-05-19 09:15 | NA
Sushit | 405 | SRA 4.2 Establish Security and Control, Requirements | 100% | 6 h | 23 d | 2002-11-01 08:00 | 2002-12-05 10:15 | 6 | 257,258 | 6 h | 6 | No | 1.5.2.1.1 | 253 | Sushit[3%] | 2002-11-01 08:00 | 2003-05-12 10:30 | NA
Sushit | 406 | SDS 5.2 Specify Security and Control Requirements | 100% | 15 h | 26 d | 2002-12-19 08:00 | 2003-01-24 09:30 | 15 |  | 15 h | 15 | No | 1.5.2.1.2 | 256 | Sushit[13%] | 2002-12-19 08:00 | 2003-03-11 16:45 | NA
Sushit | 407 | Build Test Ids/Rules | 100% | 10 h | 31 d | 2002-12-27 08:00 | 2003-02-07 08:15 | 10 |  | 10 h | 10 | No | 1.5.2.1.3 | 256 | Sushit[5%] | 2002-12-27 08:00 | 2003-03-25 14:15 | NA
Ty | 110 | Identify Architectural Constraints - AIP 1.1 | 100% | 20 h | 5 d | 2002-07-19 08:00 | 2002-07-25 15:45 | 20 | 101 | 20 h | 20 | No | 1.2.3.1.1 |  | Mary[52%] | 2002-07-19 08:00 | 2003-04-01 12:00 | NA
Ty | 111 | Inventory Development Tools Standards and Procedures - AIP 1.3 | 100% | 4 h | 1 d | 2002-07-25 15:45 | 2002-07-26 15:30 | 4 | 102 | 4 h | 4 | No | 1.2.3.1.2 | 100 | Mary[52%] | 2002-07-25 15:45 | 2003-06-20 11:00 | NA
Ty | 112 | Identify Existing Network Topology - AIP 1.2 | 100% | 4 h | 1 d | 2002-07-26 15:30 | 2002-07-29 15:15 | 4 | 103 | 4 h | 4 | No | 1.2.3.1.3 | 101 | Mary[52%] | 2002-07-26 15:30 | 2003-04-25 14:45 | NA
Ty | 113 | Inventory Existing Hardware and System Software - AIP 1.4 | 100% | 4 h | 1 d | 2002-07-29 15:15 | 2002-07-30 15:00 | 4 | 104 | 4 h | 4 | No | 1.2.3.1.4 | 102 | Mary[52%] | 2002-07-29 15:15 | 2003-05-12 08:00 | NA
Ty | 114 | Assemble Architecture Assessment - AIP 1.5 | 100% | 4 h | 1 d | 2002-07-30 15:00 | 2002-07-31 14:45 | 4 |  | 4 h | 4 | No | 1.2.3.1.5 | 103 | Mary[52%] | 2002-07-30 15:00 | 2003-05-20 15:45 | NA
Ty | 117 | Define Operating Systems - AIP 2.2 | 100% | 10 h | 10 d | 2002-08-26 15:00 | 2002-09-09 11:30 | 10 |  | 10 h | 10 | No | 1.2.3.2.2 | 106SS+9 d | Mary[6%],Ty[9%] | 2002-09-11 10:21 | 2003-05-26 08:00 | NA
Ty | 127 | Submit initial IIA questionnaire | 100% | 4 h | 1 d | 2002-09-10 11:15 | 2002-09-11 11:00 | 4 | 118 | 4 h | 4 | No | 1.2.3.4.1.1 | 106SS+20 d | Mary[26%],Ty | 2002-09-10 11:15 | 2003-06-20 11:00 | NA
Ty | 116 | Design Network - AIP 2.1 | 100% | 10 h | 10 d | 2002-08-14 08:15 | 2002-09-16 08:57 | 10 | 107SS+9 d,108FS-5 d,117SS+20 d,120SS+20 d | 10 h | 10 | No | 1.2.3.2.1 | 44SS+5 d | Mary[6%],Ty[9%] | 2002-08-14 08:15 | 2003-06-20 11:00 | NA
Ty | 128 | Infrastructure Impact Assessment - Level 2 review (if necessary) | 100% | 10 h | 5 d | 2002-09-11 11:00 | 2002-09-18 09:45 | 10 |  | 10 h | 10 | No | 1.2.3.4.1.2 | 117 | Mary[13%],Ty | 2002-09-11 11:00 | 2003-08-11 16:15 | NA
Ty | 43 | Determine Validation Components for ECHO & AUI | 100% | 48 h | 18 d | 2002-08-30 14:00 | 2002-09-25 08:30 | 48 | 39SS,87SS+10 d,106SS+5 d,109FF | 48 h | 48 | No | 1.2.1.9 | 41,38 | Eric[6%],Ty,Mary,Tina,Jill[6%],Witter[6%] | 2002-08-23 15:15 | 2002-10-28 08:00 | NA
Ty | 119 | Define Data Distribution - AIP 2.4 | 100% | 20 h | 10 d | 2002-09-09 11:30 | 2002-09-25 08:30 | 20 | 111FS-4 d,110FF | 20 h | 20 | No | 1.2.3.2.4 | 44FF | Mary[13%],Ty[19%] | 2002-09-13 10:30 | 2003-04-11 11:15 | NA
Ty | 118 | Define Hardware Configuration - AIP 2.3 | 100% | 20 h | 13 d | 2002-09-09 10:12 | 2002-09-25 15:57 | 20 |  | 20 h | 20 | No | 1.2.3.2.3 | 106FS-5 d | Mary[13%],Ty[19%] | 2002-09-11 10:21 | 2003-02-07 08:15 | NA
Ty | 120 | Define Middleware Req. - AIP 2.5 | 100% | 20 h | 5 d | 2002-09-19 08:12 | 2002-09-25 15:57 | 20 | 121SS+5 d | 20 h | 20 | No | 1.2.3.2.5 | 109FF | Mary[77%],Ty[52%] | 2002-09-27 08:00 | 2002-12-05 10:15 | NA
Ty | 131 | Submit SFTA Design Review | 100% | 2 h | 1 d | 2002-09-25 15:57 | 2002-09-26 15:42 | 2 | 122 | 2 h | 2 | No | 1.2.3.4.2.2 | 110SS+5 d | Mary[13%],Ty | 2002-09-17 10:00 | 2003-01-24 09:30 | NA
Ty | 130 | Assemble information for SFTA review | 100% | 10 h | 14 d | 2002-09-10 11:15 | 2002-09-27 16:45 | 10 |  | 10 h | 10 | No | 1.2.3.4.2.1 | 106SS+20 d | Mary[13%],Ty | 2002-09-10 11:15 | 2003-02-07 08:15 | NA
Ty | 121 | Define Application Service Distribution - AIP 2.6 | 100% | 20 h | 10 d | 2002-09-19 09:30 | 2002-10-02 16:00 | 20 | 112 | 20 h | 20 | No | 1.2.3.2.6 | 109FS-4 d | Mary[13%],Ty[19%] | 2002-09-27 08:00 | 2003-03-28 14:45 | NA
Ty | 132 | SFTA Review process | 100% | 10 h | 8 d | 2002-09-26 15:42 | 2002-10-08 13:42 | 10 | 123 | 10 h | 10 | No | 1.2.3.4.2.3 | 121 | Mary[8%],Ty | 2002-09-18 09:45 | 2002-11-22 11:00 | NA
Ty | 133 | MS: Authorized SFTA documentation | 100% | 0 h | 0 d | 2002-10-08 13:42 | 2002-10-08 13:42 | 0 |  | 0 h | 0 | No | 1.2.3.4.3 | 122 | Mary[26%] | 2002-09-25 08:30 | 2002-11-19 11:45 | NA
Ty | 122 | Define Security Infrastructure - AIP 2.7 | 100% | 20 h | 41 d | 2002-10-02 16:00 | 2002-11-29 13:45 | 20 | 113 | 20 h | 20 | No | 1.2.3.2.7 | 111 | Mary[13%],Ty[19%] | 2002-10-10 14:30 | 2002-11-22 11:00 | NA
Ty | 226 | Pkg-1 - Review NECHO Tech System Design - TSD 9.2 | 100% | 10 h | 5 d | 2002-11-22 13:15 | 2002-12-03 11:00 | 10 |  | 10 h | 10 | No | 1.3.6.2 | 139,145 | Ty[26%] | 2002-11-22 13:15 | 2002-11-22 11:00 | NA
Ty | 123 | Define System Topology - AIP 2.8 | 100% | 20 h | 5 d | 2002-11-08 08:15 | 2002-12-04 13:00 | 20 | 114 | 20 h | 20 | No | 1.2.3.2.8 | 112 | Mary[77%],Ty[52%] | 2002-10-24 11:00 | 2003-01-22 08:45 | NA
Ty | 124 | MS: Technology Architecture Documentation complete | 100% | 0 h | 0 d | 2002-12-04 13:00 | 2002-12-04 13:00 | 0 |  | 0 h | 0 | No | 1.2.3.3 | 113 | Mary[13%] | 2002-11-07 08:30 | 2003-01-08 11:15 | NA
Ty | 225 | Pkg-1 - Review AUI Tech System Design - TSD 9.2 | 100% | 3 h | 3 d | 2002-12-17 14:45 | 2002-12-20 14:00 | 3 | 150FF | 3 h | 3 | No | 1.3.6.1 | 129,134 | Ty[39%],Mary | 2002-12-17 14:45 | 2003-01-15 10:00 | NA
Ty | 227 | Pkg-1 - Review Consolidated Tech Doc - TPD 7.1 | 100% | 3 h | 2 d | 2002-12-18 14:30 | 2002-12-20 14:00 | 3 |  | 3 h | 3 | No | 1.3.6.3 | 148FF | Ty[39%],Mary[14%] | 2002-12-18 14:30 | 2003-01-22 08:45 | NA
Ty | 353 | AUI - DLV - Review Technical System Design - TSD 9.2 | 100% | 3 h | 8 d | 2002-12-24 15:45 | 2003-01-06 13:45 | 3 | 234SS | 3 h | 3 | No | 1.4.4.7.1 | 193,204 | Ty[2%],Mary[2%] | 2002-12-24 15:45 | 2003-03-28 14:45 | NA
Ty | 354 | Pkg-2 - Review AUI Technical System Design - TSD 9.2 | 100% | 3 h | 8 d | 2002-12-24 15:45 | 2003-01-06 13:45 | 3 |  | 3 h | 3 | No | 1.4.4.7.2 | 233SS | Ty[26%],Mary[31%] | 2003-01-06 13:45 | 2003-03-19 15:15 | NA
Ty | 478 | Pkg-3 - Review NECHO Technical System Design TSD 9.2 | 100% | 3 h | 39 d | 2003-04-04 16:00 | 2003-05-30 10:23 | 3 | 332FF | 3 h | 3 | No | 1.5.3.1 | 329FS-3 d | Ty[26%],Mary[31%] | 2003-03-28 14:45 | 2003-03-28 14:45 | NA
Ty | 479 | Pkg-3 - Review Consolidated Technical Documentation TPD 7.1 | 100% | 3 h | 29 d | 2003-04-04 16:00 | 2003-05-30 10:23 | 3 |  | 3 h | 3 | No | 1.5.3.2 | 331FF | Ty[13%],Mary[26%] | 2003-03-31 14:30 | 2003-03-28 14:45 | NA
Ty | 602 | Update design documents (AIP 2.6) to reflect implemented system | 0% | 2 h | 1 d | 2003-08-25 08:00 | 2003-08-25 16:45 | 0 |  | 2 h | 0 | No | 1.6.1 | 363 | Mary[19%],Ty[7%] | 2003-07-15 13:15 | 2003-03-14 10:00 | NA
Ty | 603 | Transition design documents to local architect | 0% | 4 h | 2 d | 2003-08-25 08:00 | 2003-08-26 16:30 | 0 |  | 4 h | 0 | No | 1.6.2 | 363 | Mary[9%],Ty[17%] | 2003-07-15 13:15 | 2002-12-27 08:15 | NA
Vance | 23 | Create Initial SPIP Participant Charts | 100% | 20 h | 86 d | 2002-09-06 08:00 | 2003-01-06 10:30 | 20 |  | 20 h | 20 | No | 1.1.4.1 | 13 | Carol[26%] | 2002-11-05 14:30 | 2003-03-14 10:00 | NA
Vance | 362 | Create Pkg-2 SFQ Solutions | 100% | 10 h | 37 d | 2003-03-21 08:00 | 2003-05-09 15:45 | 10 | 243FS+10 d | 10 h | 10 | No | 1.4.4.8.7 | 227SS | Vance[12%] | 2003-02-26 10:15 | 2003-04-11 11:15 | NA
Vance | 363 | MS: ISC Review Pkg-2 SFQ Solutions | 0% | 0 h | 0 d | 2003-05-23 13:15 | 2003-05-23 13:15 | 0 | 244 | 0 h | 0 | No | 1.4.4.8.8 | 242FS+10 d |  | 2003-03-25 14:15 | 2003-03-31 14:30 | NA
Vance | 364 | Populate pkg-2 SFQ Solutions | 0% | 10 h | 5 d | 2003-05-23 13:15 | 2003-05-30 11:00 | 0 |  | 10 h | 0 | No | 1.4.4.8.9 | 243 | Vance[26%] | 2003-03-25 14:15 | 2002-12-13 09:00 | NA
Vance | 501 | Create Pkg-3 SFQ Solutions | 0% | 10 h | 10 d | 2003-06-16 13:45 | 2003-06-30 10:15 | 0 | 358FS+10 d | 10 h | 0 | No | 1.5.5.9 | 345SS | Vance[13%] | 2003-04-25 11:00 | 2002-12-23 16:15 | NA
Vance | 502 | MS: ISC Review Pkg-3 SFQ Solutions | 0% | 0 h | 0 d | 2003-07-11 16:45 | 2003-07-11 16:45 | 0 | 359 | 0 h | 0 | No | 1.5.5.10 | 357FS+10 d |  | 2003-05-22 15:00 | 2002-12-23 16:15 | NA
Vance | 503 | Populate pkg-3 SFQ Solutions | 0% | 10 h | 5 d | 2003-07-11 16:45 | 2003-07-18 15:30 | 0 |  | 10 h | 0 | No | 1.5.5.11 | 358 | Vance[26%] | 2003-05-22 15:00 | 2002-12-24 16:00 | NA
Vance | 605 | Transition to Service | 0% | 30 h | 20 d | 2003-08-25 08:00 | 2003-09-19 11:00 | 0 | 372 | 30 h | 0 | No | 1.6.4 | 363 | David,Sushit[4%],Amar[4%],John[4%],Bill[4%],Witter[2%] | 2003-07-15 13:15 | 2002-12-23 16:15 | NA
Witter | 90 | AUI - design address Std | 100% | 25 h | 10 d | 2002-09-13 10:30 | 2002-09-26 17:00 | 25 | 88,89 | 25 h | 25 | No | 1.2.1.11.1 | 44SS+10 d | Witter[32%] | 2002-09-06 11:45 | 2002-12-23 16:15 | NA
Witter | 91 | AUI - design driver's license validation | 100% | 25 h | 16 d | 2002-09-27 08:00 | 2002-10-18 12:00 | 25 |  | 25 h | 25 | No | 1.2.1.11.2 | 87 | Witter[25%] | 2002-09-20 09:15 | 2002-12-09 11:45 | NA
Witter | 92 | AUI - design VIN validation | 100% | 25 h | 16 d | 2002-09-27 08:00 | 2002-10-18 12:00 | 25 |  | 25 h | 25 | No | 1.2.1.11.3 | 87 | Witter[20%] | 2002-10-03 15:45 | 2002-12-23 16:15 | NA
Witter | 205 | AUI Address Std - Analysis & Design | 100% | 10 h | 3 d | 2002-10-21 08:00 | 2002-10-23 16:15 | 10 | 129,154 | 10 h | 10 | No | 1.3.2.2 | 125 | Witter[43%] | 2002-10-21 08:00 | 2002-12-24 16:00 | NA
Witter | 206 | AUI Address Std - Coding | 100% | 40 h | 9 d | 2002-10-23 16:15 | 2002-11-05 14:00 | 40 | 130FS+13 d,148 | 40 h | 40 | No | 1.3.2.3 | 128 | Witter[57%] | 2002-10-23 16:15 | 2002-12-23 16:15 | NA
Witter | 343 | AUI -Chgs for NECHO - Analysis & design | 100% | 10 h | 4 d | 2002-11-18 13:00 | 2002-11-22 11:00 | 10 | 218,222 | 10 h | 10 | No | 1.4.4.4.1 | 176FS+16 d | Witter[32%] | 2002-11-18 13:00 | 2002-12-24 16:00 | NA
Witter | 339 | AUI - DLV - Analysis & Design | 100% | 20 h | 5 d | 2002-11-18 13:00 | 2002-11-25 10:45 | 20 | 222,182,225,213 | 20 h | 20 | No | 1.4.4.3.1 | 176 | Witter[52%] | 2002-11-18 13:00 | 2003-01-22 10:00 | NA
Witter | 204 | AUI Address Std - RSC Entry | 100% | 2 h | 5 d | 2002-11-22 09:45 | 2002-12-03 08:30 | 2 |  | 2 h | 2 | No | 1.3.2.1 | 130FF | Witter[5%] | 2002-11-22 09:45 | 2003-01-22 10:00 | NA
Witter | 207 | AUI Address Std - Unit Test Cases/Testing | 100% | 20 h | 5 d | 2002-11-22 09:45 | 2002-12-03 08:30 | 20 | 131,127FF | 20 h | 20 | No | 1.3.2.4 | 129FS+13 d | Witter[52%] | 2002-11-22 09:45 | 2003-01-30 08:30 | NA
Witter | 208 | AUI Address Std - Integration Testing | 100% | 13 h | 4 d | 2002-12-03 08:30 | 2002-12-06 16:30 | 13 | 133FS-2 d,155 | 13 h | 13 | No | 1.3.2.5 | 130 | Witter[42%] | 2002-12-03 08:30 | 2003-01-30 08:30 | NA
Witter | 210 | AUI VIN Validation - Analysis & Design | 100% | 10 h | 2 d | 2002-12-05 08:00 | 2002-12-06 16:30 | 10 | 134,154,135SS | 10 h | 10 | No | 1.3.3.1 | 131FS-2 d | Witter[65%] | 2002-12-05 08:00 | 2003-01-27 09:15 | NA
Witter | 211 | AUI VIN Validation - Coding | 100% | 10 h | 7 d | 2002-12-06 16:30 | 2002-12-17 14:45 | 10 | 148 | 10 h | 10 | No | 1.3.3.2 | 133 | Witter[18%] | 2002-12-06 16:30 | 2003-01-10 14:15 | NA
Witter | 344 | AUI -Chgs for NECHO - Coding | 100% | 20 h | 16 d | 2002-11-22 11:00 | 2002-12-17 16:00 | 20 | 219 | 20 h | 20 | No | 1.4.4.4.2 | 217 | Witter[16%] | 2002-11-22 11:00 | 2003-01-17 10:45 | NA
Witter | 212 | AUI VIN Validation - Unit Test cases/Testing | 100% | 8 h | 6 d | 2002-12-10 08:45 | 2002-12-17 16:15 | 8 | 155 | 8 h | 8 | No | 1.3.3.3 | 133SS | Witter[17%] | 2002-12-10 08:45 | 2003-01-24 09:30 | NA
Witter | 345 | AUI -Chgs for NECHO - Unit Testing | 100% | 10 h | 6 d | 2002-12-17 16:00 | 2002-12-26 14:30 | 10 | 223 | 10 h | 10 | No | 1.4.4.4.3 | 218 | Witter[22%] | 2002-12-17 16:00 | 2003-01-24 09:30 | NA
Witter | 340 | AUI - DLV - Coding | 100% | 80 h | 20 d | 2003-01-06 11:45 | 2003-01-31 15:45 | 80 | 214SS,215SS | 80 h | 80 | No | 1.4.4.3.2 | 212 | Witter[103%] | 2002-12-13 08:45 | 2003-01-31 08:15 | NA
Witter | 341 | AUI - DLV - Unit Testing | 100% | 50 h | 20 d | 2003-01-06 11:45 | 2003-01-31 15:45 | 50 |  | 50 h | 50 | No | 1.4.4.3.3 | 213SS | Witter[81%] | 2002-12-24 15:45 | 2003-01-24 09:30 | NA
Witter | 338 | AUI - DLV - RSC Entry | 100% | 2 h | 5 d | 2003-01-27 08:30 | 2003-01-31 16:15 | 2 |  | 2 h | 2 | No | 1.4.4.3.4 | 213SS | Witter[5%] | 2003-01-01 14:30 | 2003-01-30 08:30 | NA
Witter | 345a | MVR Message Chnages - Coding/UT | 100% | 75 h | 14 d | 2003-03-11 10:45 | 2003-03-28 16:15 | 75 | 226 | 0 h | 0 | No | 1.4.4.4.4 |  |  | NA | 2003-02-05 16:15 | NA
Witter | 350a | AUI-DLV Web / Mid Tier / Host System Testing (Additional) | 100% | 20 h | 5 d | 2003-03-28 16:15 | 2003-04-04 15:00 | 20 | 227FF | 0 h | 0 | No | 1.4.4.5.5 | 220 |  | NA | NA | NA
Witter | 368 | AUI Pkg-2 Prep for cowide issaunce | 0% | 20 h | 5 d | 2003-06-27 10:15 | 2003-07-04 09:00 | 0 | 249 | 20 h | 0 | No | 1.4.4.9.3 | 247 | Witter[52%] | 2003-05-14 08:00 | 2003-04-11 11:15 | NA
Witter | 369 | MS: AUI Pkg-2 cowide Issuance | 0% | 0 h | 0 d | 2003-07-04 09:00 | 2003-07-04 09:00 | 0 | 250,240FF-5 d,241FF-9 d | 0 h | 0 | No | 1.4.4.9.4 | 248 |  | 2003-05-26 08:00 | 2003-03-28 14:45 | NA
zzz$? | 109 | AIP 1 - Assess Existing Technology Architecture | 100% | 36 h | 9 d | 2002-07-19 08:00 | 2002-07-31 14:45 | 100% |  | 36 h | 36 | Yes | 1.2.3.1 |  |  | 2002-07-19 08:00 | 2003-03-28 14:45 | NA
zzz$? | 39 | AUTO Specs | 100% | 45 h | 19 d | 2002-07-30 11:00 | 2002-08-23 15:15 | 100% |  | 45 h | 45 | Yes | 1.2.1.8 |  |  | 2002-07-30 11:00 | 2003-03-28 14:45 | NA
zzz$? | 126 | Engineer for Performance | 100% | 14 h | 6 d | 2002-09-10 11:15 | 2002-09-18 09:45 | 100% |  | 14 h | 14 | Yes | 1.2.3.4.1 |  |  | 2002-09-10 11:15 | 2003-02-14 14:30 | NA
zzz$? | 99 | Testing Strategy and Test Plans | 100% | 111 h | 41.87 d | 2002-07-25 11:45 | 2002-09-20 08:15 | 100% |  | 211 h | 111 | Yes | 1.2.2 |  |  | 2002-07-25 11:45 | 2003-02-14 14:30 | NA
zzz$? | 34 | Domain Specs | 100% | 13 h | 42 d | 2002-07-30 11:00 | 2002-09-25 08:30 | 100% |  | 13 h | 13 | Yes | 1.2.1.7 |  |  | 2002-07-30 11:00 | 2003-03-04 10:30 | NA
zzz$? | 50 | VIN Validation | 100% | 56 h | 20.1 d | 2002-09-03 08:00 | 2002-09-30 11:45 | 100% |  | 56 h | 56 | Yes | 1.2.1.10.3 |  |  | 2002-08-01 08:00 | 2003-03-04 10:30 | NA
zzz$? | 60 | Driver's Licence Validation | 100% | 91 h | 47.43 d | 2002-08-02 10:30 | 2002-10-07 10:05 | 100% |  | 91 h | 91 | Yes | 1.2.1.10.5 |  |  | 2002-08-02 10:30 | 2003-03-10 09:30 | NA
zzz$? | 125 | AIP 4 - Validate Technology Architecture | 100% | 36 h | 20.83 d | 2002-09-10 11:15 | 2002-10-08 13:42 | 100% |  | 36 h | 36 | Yes | 1.2.3.4 |  |  | 2002-09-10 11:15 | 2003-03-10 09:30 | NA
zzz$? | 129 | SFTA Review | 100% | 22 h | 20.83 d | 2002-09-10 11:15 | 2002-10-08 13:42 | 100% |  | 22 h | 22 | Yes | 1.2.3.4.2 |  |  | 2002-09-10 11:15 | 2003-03-17 08:15 | NA
zzz$? | 72 | Teritory Validation | 100% | 120 h | 26 d | 2002-09-10 08:00 | 2002-10-15 09:30 | 100% |  | 120 h | 120 | Yes | 1.2.1.10.7 |  |  | 2002-09-10 08:00 | 2003-03-17 08:15 | NA
zzz$? | 55 | MQseries/EUI Interface. | 100% | 88 h | 53.32 d | 2002-08-05 09:30 | 2002-10-15 15:45 | 100% |  | 88 h | 88 | Yes | 1.2.1.10.4 |  |  | 2002-08-05 09:30 | 2003-03-20 16:15 | NA
zzz$? | 46 | Address Standradisation- Auto Main Screen | 100% | 88 h | 60 d | 2002-07-29 16:45 | 2002-10-18 08:45 | 100% |  | 88 h | 88 | Yes | 1.2.1.10.2 |  |  | 2002-07-29 16:45 | 2003-03-20 16:15 | NA
zzz$? | 89 | AUI Specs | 100% | 75 h | 26 d | 2002-09-13 10:30 | 2002-10-18 12:00 | 100% |  | 75 h | 75 | Yes | 1.2.1.11 |  |  | 2002-09-06 11:45 | 2003-03-26 15:15 | NA
zzz$? | 202 | MS: Pkg -1 work started | 100% | 0 h | 0 d | 2002-10-21 08:00 | 2002-10-21 08:00 | 100% | 128,137,161 | 0 h | 0 | No | 1.3.1 |  |  | 2002-10-21 08:00 | 2003-03-26 15:15 | NA
zzz$? | 68 | Address Standradisation- Residence Address Scrn | 100% | 48 h | 29 d | 2002-09-16 08:00 | 2002-10-24 08:45 | 100% |  | 48 h | 48 | Yes | 1.2.1.10.6 |  |  | 2002-07-29 16:45 | 2003-02-12 15:00 | NA
zzz$? | 302 | MS: Pkg -2 work started | 100% | 0 h | 0 d | 2002-10-28 08:00 | 2002-10-28 08:00 | 100% | 212,190FS+6 d,217FS+16 d,236 | 0 h | 0 | No | 1.4.1 |  |  | 2002-10-28 08:00 | 2003-02-12 15:00 | NA
zzz$? | 402 | MS: Pkg -3 work started | 100% | 0 h | 0 d | 2002-10-28 08:00 | 2002-10-28 08:00 | 100% | 256,261,273,349 | 0 h | 0 | No | 1.5.1 |  |  | 2002-10-28 08:00 | 2003-02-26 11:30 | NA
zzz$? | 82 | AUI request Screen | 100% | 132 h | 78.26 d | 2002-07-16 14:30 | 2002-10-30 13:00 | 100% |  | 132 h | 132 | Yes | 1.2.1.10.9 |  |  | 2002-07-16 14:30 | 2003-02-26 11:30 | NA
zzz$? | 44 | ECHO Specs | 100% | 988 h | 105.71 d | 2002-06-13 11:30 | 2002-11-04 15:45 | 100% |  | 1,076 h | 988 | Yes | 1.2.1.10 |  |  | 2002-06-13 11:30 | 2003-03-12 09:00 | NA
zzz$? | 76 | AUI Driver Information Screen | 100% | 125 h | 81.71 d | 2002-07-16 14:30 | 2002-11-04 15:45 | 100% |  | 125 h | 125 | Yes | 1.2.1.10.8 |  |  | 2002-07-16 14:30 | 2003-03-12 09:00 | NA
zzz$? | 26 | SRA / SDS | 100% | 1,731 h | 119.29 d | 2002-06-13 11:30 | 2002-11-22 08:00 | 100% |  | 1,848 h | 1731 | Yes | 1.2.1 |  |  | 2002-06-13 11:30 | 2003-03-25 15:30 | NA
zzz$? | 409 | TSD 3.2 phase doc | 100% | 55 h | 20 d | 2002-10-28 08:00 | 2002-11-22 11:00 | 100% |  | 55 h | 55 | Yes | 1.5.2.2.1 |  |  | 2002-10-28 08:00 | 2003-03-25 15:30 | NA
zzz$? | 25 | Reqs Analysis and Solution Def/Specs | 100% | 2,054 h | 126 d | 2002-06-13 11:30 | 2002-12-04 13:00 | 100% |  | 2,271 h | 2054 | Yes | 1.2 |  |  | 2002-06-13 11:30 | 2003-03-28 14:45 | NA
zzz$? | 108 | AIP | 100% | 212 h | 99.61 d | 2002-07-19 08:00 | 2002-12-04 13:00 | 100% |  | 212 h | 212 | Yes | 1.2.3 |  |  | 2002-07-19 08:00 | 2003-03-28 14:45 | NA
zzz$? | 115 | AIP 2 - Design Technology Architecture | 100% | 140 h | 81 d | 2002-08-14 08:15 | 2002-12-04 13:00 | 100% |  | 140 h | 140 | Yes | 1.2.3.2 |  |  | 2002-08-14 08:15 | NA | NA
zzz$? | 203 | AUI Address Std (TSD/TPD/UPD) | 100% | 85 h | 34 d | 2002-10-21 08:00 | 2002-12-06 16:30 | 100% |  | 85 h | 85 | Yes | 1.3.2 |  |  | 2002-10-21 08:00 | 2003-03-28 14:45 | NA
zzz$? | 10 | Project Charter, Plan & Schedule | 100% | 358 h | 151.74 d | 2002-05-21 08:00 | 2002-12-16 08:00 | 100% |  | 358 h | 358 | Yes | 1.1.3 |  |  | 2002-05-21 08:00 | 2003-04-01 14:15 | NA
zzz$? | 219 | NECHO VIN Validation (TSD/TPD/UPD) | 100% | 50 h | 29 d | 2002-11-04 08:00 | 2002-12-16 08:45 | 100% |  | 50 h | 50 | Yes | 1.3.5 |  |  | 2002-11-04 08:00 | 2003-03-31 14:30 | NA
zzz$? | 209 | AUI VIN Validation (TSD/TPD/UPD) | 100% | 28 h | 9.19 d | 2002-12-05 08:00 | 2002-12-17 16:15 | 100% |  | 28 h | 28 | Yes | 1.3.3 |  |  | 2002-12-05 08:00 | 2003-04-01 14:15 | NA
zzz$? | 224 | Pkg-1 Consolidated Tech Doc | 100% | 16 h | 18.68 d | 2002-11-22 13:15 | 2002-12-20 14:00 | 100% |  | 16 h | 16 | Yes | 1.3.6 |  |  | 2002-11-22 13:15 | 2003-06-20 08:45 | NA
zzz$? | 352 | Pkg-2 Consolidated Tech Doc | 100% | 6 h | 8 d | 2002-12-24 15:45 | 2003-01-06 13:45 | 100% |  | 6 h | 6 | Yes | 1.4.4.7 |  |  | 2002-12-24 15:45 | 2003-02-19 13:45 | NA
zzz$? | 228 | Pkg -1 Systems Acceptance Test (SAT) | 100% | 129 h | 43.77 d | 2002-11-11 08:30 | 2003-01-13 11:45 | 100% |  | 174 h | 129 | Yes | 1.3.7 |  |  | 2002-11-11 08:30 | 2003-03-13 13:15 | NA
zzz$? | 238 | Pkg -1 Communication | 100% | 25 h | 56.19 d | 2002-10-25 08:00 | 2003-01-14 11:30 | 100% |  | 25 h | 25 | Yes | 1.3.8 |  |  | 2002-10-25 08:00 | 2003-04-25 11:00 | NA
zzz$? | 314 | DLV - Mid Tier(TSD/TPD/UPD) | 100% | 129 h | 52.71 d | 2002-11-04 15:30 | 2003-01-17 16:00 | 100% |  | 129 h | 129 | Yes | 1.4.4.1 |  |  | 2002-11-04 15:30 | 2003-04-30 10:15 | NA
zzz$? | 413 | TSD 8.3 phase doc | 100% | 30 h | 17 d | 2002-12-30 14:00 | 2003-01-22 08:45 | 100% |  | 30 h | 30 | Yes | 1.5.2.2.2 |  |  | 2002-12-30 14:00 | 2003-05-07 09:00 | NA
zzz$? | 213 | NECHO DLV (TSD/TPD/UPD) | 100% | 121 h | 59.84 d | 2002-11-04 08:00 | 2003-01-27 16:45 | 100% |  | 121 h | 121 | Yes | 1.3.4 |  |  | 2002-11-04 08:00 | NA | NA
zzz$? | 337 | AUI - DLV (TSD/TPD/UPD) | 100% | 152 h | 53.06 d | 2002-11-18 13:00 | 2003-01-31 16:15 | 100% |  | 152 h | 152 | Yes | 1.4.4.3 |  |  | 2002-11-18 13:00 | NA | NA
zzz$? | 404 | Security Support - Sushit | 100% | 31 h | 69.19 d | 2002-11-01 08:00 | 2003-02-07 08:15 | 100% |  | 31 h | 31 | Yes | 1.5.2.1 |  |  | 2002-11-01 08:00 | NA | NA
zzz$? | 322 | DLV - Host - (TSD/TPD/UPD) | 100% | 316 h | 68 d | 2002-11-04 16:45 | 2003-02-07 15:45 | 100% |  | 316 h | 316 | Yes | 1.4.4.2 |  |  | 2002-11-04 16:45 | 2003-06-20 08:45 | NA
zzz$? | 201 | Pkg -1 Design/Build/Test/Implement | 100% | 479 h | 84.29 d | 2002-10-21 08:00 | 2003-02-14 14:15 | 100% |  | 554 h | 489 | Yes | 1.3 |  |  | 2002-10-21 08:00 | 2003-02-20 13:30 | NA
zzz$? | 250 | Pkg -1 Implementation | 100% | 25 h | 30.97 d | 2003-01-03 14:15 | 2003-02-14 14:15 | 100% |  | 55 h | 35 | Yes | 1.3.9 |  |  | 2003-01-03 14:15 | 2003-04-25 11:00 | NA
zzz$? | 303 | Security Support - David | 100% | 35 h | 51.77 d | 2002-12-19 14:45 | 2003-02-28 16:00 | 100% |  | 25 h | 35 | Yes | 1.4.2 |  |  | 2002-12-19 08:00 | 2003-05-30 13:30 | NA
zzz$? | 342 | AUI -Chgs for NECHO (TSD/TPD/UPD) | 100% | 115 h | 94.35 d | 2002-11-18 13:00 | 2003-03-28 16:15 | 100% |  | 40 h | 40 | Yes | 1.4.4.4 |  |  | 2002-11-18 13:00 | 2003-06-13 10:00 | NA
zzz$? | 346 | AUI -DLV Int Testing | 100% | 230 h | 66.84 d | 2003-01-06 08:00 | 2003-04-04 15:00 | 100% |  | 210 h | 210 | Yes | 1.4.4.5 |  |  | 2002-12-20 15:15 | 2003-06-20 08:45 | NA
zzz$? | 453 | NECHO - all Remaining Changes -(TPD) | 100% | 1,082 h | 51.32 d | 2003-02-03 08:00 | 2003-04-11 14:45 | 100% |  | 1,050 h | 1050 | Yes | 1.5.2.6 |  |  | 2003-02-03 08:00 | 2003-07-08 14:30 | NA
zzz$? | 451 | Pkg-3 NECHO Integration Testing | 100% | 120 h | 63 d | 2003-01-20 10:30 | 2003-04-15 10:44 | 100% |  | 120 h | 120 | Yes | 1.5.2.5 |  |  | 2003-01-20 10:30 | 2003-04-14 15:30 | NA
zzz$? | 421 | Host Addr Std/Terr | 100% | 60 h | 134.13 d | 2002-11-12 16:45 | 2003-05-16 16:15 | 100% |  | 60 h | 60 | Yes | 1.5.2.3 |  |  | 2002-11-12 16:45 | 2003-04-21 14:15 | NA
zzz$? | 307 | Test Environment Setup | 100% | 90 h | 111.58 d | 2002-12-23 16:15 | 2003-05-24 16:15 | 100% |  | 90 h | 90 | Yes | 1.4.3 |  |  | 2002-12-23 16:15 | 2003-04-30 11:30 | NA
zzz$? | 477 | Pkg-3 Consolidated Tech Doc | 100% | 6 h | 40.69 d | 2003-04-04 16:00 | 2003-05-30 10:23 | 100% |  | 6 h | 6 | Yes | 1.5.3 |  |  | 2003-03-28 14:45 | 2003-06-04 11:45 | NA
zzz$? | 408 | MQSeries | 97% | 145 h | 166.68 d | 2002-10-28 08:00 | 2003-06-13 11:45 | 84% |  | 145 h | 140 | Yes | 1.5.2.2 |  |  | 2002-10-28 08:00 | 2003-06-11 10:30 | NA
zzz$? | 417 | R10481 - MQ Regional Office MVS Dev Environment | 92% | 60 h | 81.68 d | 2003-02-24 10:45 | 2003-06-13 11:45 | 75% |  | 60 h | 55 | Yes | 1.5.2.2.3 |  |  | 2003-02-24 10:45 | 2003-06-24 17:00 | NA
zzz$? |  | Pkg-3 Perf Testing | 46% | 70 h | 30.48 d | 2003-05-05 08:00 | 2003-06-13 13:15 | 55% |  | 0 h | 0 | Yes | 1.5.4.6 |  |  | NA | 2003-07-01 15:45 | NA
zzz$? |  | Performance Testing Pkg-2 | 69% | 90 h | 74.45 d | 2003-03-05 11:45 | 2003-06-13 13:45 | 44% |  | 70 h | 57.5 | Yes | 1.4.4.6 |  |  | 2003-03-05 09:00 | 2003-07-08 14:30 | NA
zzz$? | 403 | NECHO - all Remaining Changes (TSD/TPD/UPD) | 99% | 2,164 h | 167.16 d | 2002-10-28 08:00 | 2003-06-13 16:30 | 87% |  | 2,108 h | 2091.5 | Yes | 1.5.2 |  |  | 2002-10-28 08:00 | 2003-05-09 08:30 | NA
zzz$? | 424 | NECHO - all Remaining Changes -(TSD) | 98% | 726 h | 154.77 d | 2002-11-13 08:00 | 2003-06-13 16:30 | 74% |  | 702 h | 690.5 | Yes | 1.5.2.4 |  |  | 2002-11-13 08:00 | 2003-05-22 15:00 | NA
zzz$? | 355 | Pkg -2 Communication | 67% | 45 h | 97.32 d | 2003-02-17 08:00 | 2003-06-27 10:15 | 89% |  | 45 h | 30 | Yes | 1.4.4.8 |  |  | 2002-12-31 08:00 | 2003-05-29 13:45 | NA
zzz$? | 480 | Pkg-3 Systems Acceptance Test (SAT) | 49% | 330 h | 151.68 d | 2003-01-06 14:00 | 2003-07-30 13:30 | 67% |  | 260 h | 130 | Yes | 1.5.4 |  |  | 2003-01-06 14:00 | 2003-08-11 16:15 | NA
zzz$? | 486 | Pkg-3 FIT Test (SAT) | 15% | 130 h | 151.68 d | 2003-01-06 14:00 | 2003-07-30 13:30 | 44% |  | 130 h | 20 | Yes | 1.5.4.7 |  |  | 2003-01-06 14:00 | 2003-06-11 10:30 | NA
zzz$? | 301 | Pkg -2 Design/Build/Test/Implement | 92% | 1,273 h | 201.81 d | 2002-10-28 08:00 | 2003-07-31 12:00 | 88% |  | 1,273 h | 1065.5 | Yes | 1.4 |  |  | 2002-10-28 08:00 | 2003-06-24 17:00 | NA
zzz$? | 313 | AUI - DLV | 91% | 1,148 h | 195.81 d | 2002-11-04 15:30 | 2003-07-31 12:00 | 83% |  | 1,148 h | 940.5 | Yes | 1.4.4 |  |  | 2002-11-04 15:30 | 2003-07-15 13:15 | NA
zzz$? | 365 | Pkg -2 Implementation | 0% | 65 h | 35 d | 2003-06-13 13:45 | 2003-07-31 12:00 | 0% |  | 65 h | 0 | Yes | 1.4.4.9 |  |  | 2003-04-21 15:45 | 2003-06-24 17:00 | NA
zzz$? | 4 | Project Admin & Cordination | 82% | 3,514 h | 342.35 d | 2002-05-06 08:00 | 2003-08-15 14:15 | 80% |  | 3,514 h | 2571.23 | Yes | 1.1.2 |  |  | 2002-05-06 08:00 | 2003-08-11 16:15 | NA
zzz$? | 492 | Pkg-3 Communication | 11% | 45 h | 72.42 d | 2003-05-12 08:00 | 2003-08-18 09:15 | 3% |  | 45 h | 5 | Yes | 1.5.5 |  |  | 2003-04-07 08:00 | 2003-08-11 16:15 | NA
zzz$? |  | IIA | 35% | 375 h | 230 d | 2002-10-07 08:00 | 2003-08-18 15:30 | 1% |  | 0 h | 131.25 | Yes | 1.1.5 |  |  | NA | 2003-08-18 15:00 | NA
zzz$? | 401 | Pkg -3 Design/Build/Test/Implement | 89% | 2,610 h | 238.84 d | 2002-10-28 08:00 | 2003-09-19 11:00 | 79% |  | 2,484 h | 2232.5 | Yes | 1.5 |  |  | 2002-10-28 08:00 | 2003-07-16 12:00 | NA
zzz$? | 504 | Pkg-3 Implementation | 0% | 65 h | 53 d | 2003-07-10 08:15 | 2003-09-19 11:00 | 0% |  | 65 h | 0 | Yes | 1.5.6 |  |  | 2003-05-30 13:30 | 2003-07-17 11:45 | NA
zzz$? | 2 | Planning/Admin/Meetings/Coordination | 79% | 4,287.01 h | 371.87 d | 2002-05-06 08:00 | 2003-09-25 10:00 | 74% |  | 4,287 h | 3080.48 | Yes | 1.1 |  |  | 2002-05-06 08:00 | 2003-08-05 08:30 | NA
zzz$? | 22 | SP/IP | 50% | 40 h | 280 d | 2002-09-06 08:00 | 2003-09-25 10:00 | 90% |  | 40 h | 20 | Yes | 1.1.4 |  |  | 2002-11-05 14:30 | 2003-08-11 16:15 | NA
zzz$? | 1 | Auto Necho - Auto Apps Efficiency | 87% | 10,779.01 h | 372.87 d | 2002-05-06 08:00 | 2003-09-26 09:45 | 82% |  | 10,709.01 h | 8921.48 | Yes | 1 |  |  | 2002-05-06 08:00 | 2003-08-18 15:00 | NA
zzz$? | 601 | Transition | 0% | 76 h | 25 d | 2003-08-25 08:00 | 2003-09-26 09:45 | 0% |  | 86 h | 0 | Yes | 1.6 |  |  | 2003-01-06 13:15 | 2003-08-18 15:00 | NA
NA
NA
Import Info
◄▬Menu

## SMP
Proj. 1234 | Schedule Maintenance Procedure
Project Planner will be responsible to keep Project Schedule updated with current status of tasks. Following procedure will be followed by all resource leads and the project planner. This procedure is intended to ensure that schedule with latest status is available to team members during weekly team meeting on Wednesday.
1 | Schedule maintenance cycle time will be of one week i.e. schedule maintenance tasks will happen on predetermined days and times.
2 | On every Monday between 2:30PM to 3:30PM, planner will send an email to team resource leads (henceforth called as leads). This email will have two attached files as described bellow.. File 1: An Excel file (henceforth to be refered as 'Status Excel' ) will have as many worksheet tabs as the number of leads. These worksheet tabs will have lead's name mentioned on it and will contain lists of tasks assigned to leads. Tasks included in each tab are the tasks for which current status is needed.
Link to see Sample of Status Excel format. This sample contains only one tab.
File 2: A .pdf file (henceforth to be refered as 'Schedule Status') and will contain schedule status to be used for reference by leads.
Link to see Sample of Schedule Status format. Though the format shown is in excel, actual file will be in pdf format.
Leads may save attachments (xls and pdf files) in a folder on their workstation's hard disk (C: or D:).
3 | The .xls file has several worksheet tabs having leads' name mentioned on these tabs. Please locate the named tab and open it. It will contain all tasks assigned to named lead. Pdf file contains Complete Schedule Status with tasks status as first column.
Link to see tasks status definitions (Defs tab)
4 | Task Status inputs are expected for all WIP tasks (tasks under execution), tasks that should have started by now but not started, and tasks that are going to start during next week. In the tasks list, tasks with yellow background color mean that status inputs are expected for these tasks. For other tasks, status inputs are not expected at that moment and should be ignored but not deleted from the list.
5 | Tasks status inputs should be provided by overwriting any cell with RED foreground color. It will help planner to identify the changes made by by leads. Otherwise, to identify changes, Planner has to compare whole worksheet with MS schedule file and this is not practical. Therefore, for updating inputs onto MS Schedule file, Planner will need that all changes are made with RED color.
6 | Changes may include start and end dates, work / duration estimates, and % work completed. However, the most important change is % work completion (%WC). If changes relate to start or end date, dependencies must be carefully studied for possible impacts on other tasks' start and end dates.
7 | A task will be treated as started when value of %WC becomes more than 0. Sometimes it happens that the task is started but leads forget to give this input. If leads do not know the exact amount of work done since the task is started and till the time of updating inputs in the excel, please assume a 5% figure. As soon as the %WC cell becomes more than 0, tasks is assumed to be started.
8 | When ready with tasks status update inputs, please open the .xls file and update tasks status & save the changes on to the same file i.e. please do not change the file name. If backup is needed , create a separate subfolder for this purpose.
9 | Mail this Excel as an attachment to planner on or before 2:30 PM on Tuesday. If planner does not receive reply mail with attached excel, leads will be reminded by 2:40PM on Tuesday.
10 | After mailing this excel, please deletion or retaining the excel file depend upon leads' needs. It is suggested that lead may retain it till next week i.e. Leads will have two excels at any time - one the most current one and other the previous one.
11 | Generally, planner will collect all these mails into a mail subfolder. On Tuesday, 3:30 PM, planner will save all these excels into a folder on D: drive. Then planner will copy MS Project file from N: drive to local workstation and rename it reflecting Tuesday's date. Next planner will open these excels one by one and make changes to MS Project file that has just copied from N: drive. After finishing this update exercise, planner will again copy this MS Project File to N: drive. In between, planner takes care of all backup requirements if any.
12 | This is the way the whole operations of collecting inputs from project team leads and updating to MS Project file will happen.

## WTP
Proj. 1234 | Weekly Tasks Plan
Day of Week | Task Name
Monday | 1) Extract Tasks assigned to each lead resource and put these extracted tasks into an excel. 2) Create Schedule Status Reports in pdf format. 3) Send this excel and pdf file to lead resources for getting schedule status update inputs (to be received by 2:30 PM on Tuesday).
Tueday | 1) Copy files of 'Current Status' folder on N: drive to 'Previous Status' folder on N: drive. 2) Update schedule status in "Current Status" folder. Resolve conflicts arising during updating schedule. 3) Identify status of tasks and update this status on MS schedule file. Definition of tasks status is given in sheet with tab as "Defs" 4) Create Schedule Status report in pdf format and save it to N: drive. 5) Analyze Schedule status and note down problems ahead for executing schedule. 6) Send schedule status reports in pdf format and analysis commnets to lead resources and project manager schedule. 7) Prepare for Wednesday's meeting.
Wednesday | 1) Attend Project meeting and do briefing to core team on Schedule Status. Take notes of feedback on Schedule Status given by core team. 2) Project Planning Work
Thursday | 1) Project Planning Work
Friday | 1) Project Planning Work

## Defs
Proj. 1234 | Schedule Tasks Status definitions
Status Code | Status Description | Status definitions
(blank) (scheduled for future | Tasks that are schedule to start in future. | Tasks which are scheduled to start in future. These tasks will have %work-completion as 0%. This is the default and initial value for status of any task.
SOF (Sliped on Finish) | WIP Tasks scheduled to complete this week but not completed: | Tasks having %work-completion less than 100% and schedule completion date less than or equal to this Wednesday's Date. This status gives warning signal to lead resource to remove all bottlenecks for immediately finishing these tasks. If a task with this status is on critical path and is a critical task, there is already impact on schedule finish date and lead resource should ensure that the impact is minimum.
SOS (Sliped on Start) | Tasks scheduled to start upto this week but not started: | Tasks having %work-completed as 0% and schedule start date is less than or equal to this Wednesday's date. This status is a warning signal to lead resource to remove all bottlenecks for immediately starting these tasks. If a task with this status is on critical path and is a critical task, lead resource should ensure that the impact on schedule finish date is minimum. There is all possibility that now task duration is to be reduced either by increasing resources or by extra working or by some other means.
SNW (Start Next week) | Tasks that are scheduled to start during next week: | Tasks having %work-completed as 0% and schedule start date is during next week (this Thursday to next Wednesday). This status will give a reminder to lead resource for ensuring that these tasks are start next week.
FNW (Finish Next Week) | Tasks that are scheduled to complete during next week: | Tasks having %work-completed as greater than 0% and planed completion date is during next week (this Thursday to next Wednesday). This status will give a reminder to lead resource for ensuring that these tasks are completed next week.
TIF (Task is Finished) | Tasks that are finished | Tasks having %work-completed as 100% will have this status. Also if a task is abondoned before its completion (I.e. during execution) , it will be marked as 100% complete and task status as TIF.

## SchStatus
Lead | Code | Task Name | %WC | Work | Duration | Start date | Finish date | Predecessor | Resources
Schedule Status 8-20-01
Last Updated Mon 8/20/01
Project Schedule Status
Gantt Chart
Project Manager:
Project Planner:

## Role
Proj. 1234 | Project Planner Role
Area | Tasks | Remarks
Organize & co-facilitate planning sessions: | Impact Analysis - Pre- Project Planning
Project Charter
Project Plan
| Work Breakdown Structure | MS Project / WBS tool
| Estimating Workbook | ? Excel
Network Diagram
| Schedule Development | MS Project Schedule
Facilitating Processes
Re-planning efforts
Earned Value: | Develop procedures for utilizing Earned Value | ? EVA excel
| Track project using Earned Value procedures | ?
| Present Earned Value statistics to appropriate parties | ?
Develop procedures for updating | Project schedules tasks status
Allocations and Authorizations in Plan View
Gather actuals start, Finish and worked hours for tasks
Analyze, update, and tract schedule: | Collecting Tasks status from leads and updating it on schedule | Excel
| Analyzing Critical Path, Slipped Tasks, Finish dates impacts etc | MS Project Schedule
Actuals (taken from resource tracking tool into schedule tool)
People Allocation Requests | Submit PARs
| Track PARs for allocations | PlanView
Team allocations /Authorizations | Monitor resource tracking tool for over allocations | MS project resourse usage
Update allocations as necessary
Resource Forecasting | Help in determining resources, tasks, hours, dates, and numbers for future phases
Status Meetings | Lead role for schedule and related issues
Prepare Reports | The schedule tool | R_DT_CD1 Actual and Remaining Hours
| The resource tracking pool | R_TR_001 Resourse Planned v/s Actual work
| Executive Summary | Word doc

## ProjEVA
Proj. 1234 |  | Earned Value Analysis
EVA Start date: |  | 2001-07-01 |  | EVA End date: |  |  | 2001-05-31 |  |  | Period: | Monthly
|  |  | Budgeted Hours |  |  |  | Earned Hours |  |  |  | Actual Hours
Till Date | Cummulative | [6 empty] | For the period
| BCWS | BCWP | ACWP | SV | CV | SPI | CPI | BCWS | BCWP | ACWP | SV | CV | SPI | CPI
2001-07-01 | 110 | 105 | 115 | -5 | -10 | 0.95455 | 0.91304 | 110 | 105 | 115 | -5 | -10 | 0.95455 | 0.91304
2001-08-01 | 373 | 335 | 437 | -38 | -102 | 0.89812 | 0.76659 | 263 | 230 | 322 | -33 | -92 | 0.87452 | 0.71429
2001-09-01 | 605 | 644 | 742 | 39 | -98 | 1.0645 | 0.86792 | 232 | 309 | 305 | 77 | 4 | 1.3319 | 1.0131
2001-10-01 | 962 | 994 | 1135 | 32 | -141 | 1.0333 | 0.87577 | 357 | 350 | 393 | -7 | -43 | 0.98039 | 0.89059
2001-11-01 | 1368 | 1393 | 1533 | 25 | -140 | 1.0183 | 0.90868 | 406 | 399 | 398 | -7 | 1 | 0.98276 | 1.0025
2001-12-01 | 1730 | 1704 | 1846.65 | -26 | -142.65 | 0.98497 | 0.92275 | 362 | 311 | 313.65 | -51 | -2.65 | 0.85912 | 0.99155
2002-01-01 | 2193 | 1809 | 2377.65 | -384 | -568.65 | 0.8249 | 0.76084 | 463 | 105 | 531 | -358 | -426 | 0.22678 | 0.19774
2002-02-01 | 2695 | 2288 | 2912.95 | -407 | -624.95 | 0.84898 | 0.78546 | 502 | 479 | 535.3 | -23 | -56.3 | 0.95418 | 0.89483
2002-03-01 | 4093 | 2467 | 3028.05 | -1626 | -561.05 | 0.60274 | 0.81472 | 1398 | 179 | 115.1 | -1219 | 63.9 | 0.12804 | 1.5552
2002-04-01 | 5314 | 0 | 0 | 0 | 0 | 0 | 0 | 1221 | 0 | 0 | 0 | 0 | 0 | 0
2002-05-01 | 5960 | 0 | 197.25 | -5960 | -197.25 | 0 | 0 | 646 | 0 | 197.25 | -646 | -197.25 | 0 | 0
2002-06-01 | 6554 | 0 | 447.5 | -6554 | -447.5 | 0 | 0 | 594 | 0 | 250.25 | -594 | -250.25 | 0 | 0
2002-07-01 | 7386 | 0 | 924.25 | -7386 | -924.25 | 0 | 0 | 832 | 0 | 476.75 | -832 | -476.75 | 0 | 0
2002-08-01 | 8237 | 0 | 1500.75 | -8237 | -1500.75 | 0 | 0 | 851 | 0 | 576.5 | -851 | -576.5 | 0 | 0
2002-09-01 | 8904 | 0 | 2183.25 | -8904 | -2183.25 | 0 | 0 | 667 | 0 | 682.5 | -667 | -682.5 | 0 | 0
2002-10-01 | 9666 | 0 | 2899.25 | -9666 | -2899.25 | 0 | 0 | 762 | 0 | 716 | -762 | -716 | 0 | 0
2002-11-01 | 10101 | 0 | 3692.5 | -10101 | -3692.5 | 0 | 0 | 435 | 0 | 793.25 | -435 | -793.25 | 0 | 0
2002-12-01 | 10404 | 0 | 4619.25 | -10404 | -4619.25 | 0 | 0 | 303 | 0 | 926.75 | -303 | -926.75 | 0 | 0
2003-01-01 | 10811 | 0 | 5565.9 | -10811 | -5565.9 | 0 | 0 | 407 | 0 | 946.65 | -407 | -946.65 | 0 | 0
2003-02-01 | 10893 | 0 | 6364.75 | -10893 | -6364.75 | 0 | 0 | 82 | 0 | 798.85 | -82 | -798.85 | 0 | 0

## Macros
Proj. 1234 | Macros Index
MacroName | What the macro does? | Instructions to use the macro
Import Tasks Status Info from MS Project file | This macro imports tasks status information in required format from Microsoft Project .mpp file. This process needs defining a MAP in MS Project. The extracted information includes Lead name, Task Code, Tasks name, % work completed, Work Efforts in Hours, Duration in days, Task Start date, Task Finish Date, % Duration completed, Successors, Baseline work, Earned Value, Summary(Y/N), Indenting Level,Predecesors, and Resource names. This macro does not do any thing further other than formating of few columns of sheet [AllTasks]. | How to create a MAP. To create a MAP, open Microsoft schedule file. Select "Save as" from file menu of microsoft project. Then select "Microsoft Excel" as file type to save. Next it will display a list of existing MAPs to select from. If the required MAP is not in this list, click on "New" button to create new MAP. It will open form for creating new MAP. Complete it and Save the form. MAP should contain columns of information as per tab "AllTasks" of this excel. Sequence and format of columns of MAP should be identical to sequence and format of columns of tab "AllTasks".
Mannual method to import Tasks Status info from MS Project File | Also you can mannually import Tasks Status information from MS Project .mpp file to sheet [AllTasks] of this excel by copy and paste technique as described here in. Mannual method is an alternate method. | - Open Microsoft schedule file in Gantt Chart view. Insert or hide columns to match sequence and contents of columns of tab "AllTasks" of the excel. Once you have created the desired view, copy all the rows into buffer by selecting and pressing Ctrl+C. - Go to excel on tab "AllTasks" and position cursor on cell "A3" and press Ctrl+V to paste the buffer content. - Inspect if pasting has been done correctly.
Update Tasks Status Summary | This macro extracts following information from schedule tasks imported into this excel. 1. Statistical information like total number of tasks, Number of finished tasks, Number of WIP tasks, Number of tasks slipped on finish, Number of tasks slipped on start, total schedule hours for all tasks etc. 2. For each resource lead, statistical information like number of assigned tasks, number of WIP tasks, number of finished tasks, number of tasks slipped on finish, number of tasks slipped on start, schedule estimated hours for assigned tasks, earned hours for completed work, cost performance index-CPI (earned/actual) 3. Extracts list of tasks that are due on finish / start as on now or one week from now. | This macro is run mostly once a week to generates information going into Weekly Project Status Report. 1. Create a view of MS Project schedule - Gantt Chart containing columns as Lead Resourse, Task Code, Tasks Name, % work completed, Work hours, Duration, Start Date, Finish date, %duration completion, predecesors, resource names. 2. Copy this information for all tasks from MS Project to "AllTasks" tab of this excel by simple cut paste. 3. On successful completion of step 2., Run the macro. 4. After running of macro is over, visually inspect the following sheets for desired results: - StatSum for point 1 of purpose - TasksSum for point 3 of purpose - DueTasks for point 2 of pupose
UpdMonthlyActualHours | This macro performs following functions: 1. Reads PlanView report R_DT_CD1 and insert resourcewise actual hours in a new column in sheet "ActHist". 2. Updates total actual hours for the project for the processing month in Sheet "EVA". This figure is required for Earned Value Analysis. | This macro is run only once a month. Do following in steps. 1. Generate report R_DT_CD1 for desired period by spefifying the period in Parameters of report menu of PlanView and export this report into excel file. 2. Open this generated excel file and cut - paste this sheet content onto sheet "RDTCD1" of Project Tracking template excel. 3. Run the macro. Go to sheet "ActHist" and varify that a new column is inserted and actual hours updated. Also varify the update in sheet "EVA" .
UpdWeeklyRemandActualHours
UpdResEVA

## SetupInstructions
Proj. 1234 | Steps to follow for using this excel by Project Planners.
Following are steps that a planner should understand for using this excel.
1 | Copy or Save the excel in a folder where mirosoft schedule .mpp file is also kept. However, you will learn it later that excel and .mpp files can be kept in different folders. After saving the excel, open it. While opening the excel, enable the macros.
2 | Click on tab "TabsIndex" and enter Release no in "R0nnnn - " format in cell "A1" and as-on-date in cell "D1".
3 | Click on Tab "AllTasks". Take a print of this sheet. Read the column information and sequence carefully.
4 | Open Microsoft schedule file. Create a MAP containing columns of information as per tab "AllTasks" of this excel. Sequence and format of columns of MAP should be identical to sequence and format of columns of tab "AllTasks". To create new MAP, select "Save as" from file menu of microsoft project. Select "Microsoft Excel" as file type to save. Next it will display a list of existing MAPs to select from. If the required MAP is not in this list, click on "New" button to create new MAP. It will open form for creating new MAP. Complete it and Save the form. Once the MAP is ready, you can run the macro to import information into tab "AllTasks" from mirosoft schedule.
5 | Step 4 is required only when you opt for importing "AllTasks" information from microsoft schedule using excel macro. However, you can import this information by copy and paste technique as described here in. - Open Microsoft schedule file in Gantt Chart view. Insert or hide columns to match sequence and contents of columns of tab "AllTasks" of the excel. Once you have created the desired view, copy all the rows into buffer by selecting and pressing Ctrl+C. - Go to excel on tab "AllTasks" and position cursor on cell "A3" and press Ctrl+V to paste the buffer content. - Inspect if pasting has been done correctly.
10 | Send this excel to all team members by using appropriate macro. Excel is sent to resources having "ActiveStatu" as 1 or 2. However, you can send the excel directly through outlook mannully. Following is a sample message text for the mail sending mails mannually.
Mail SubJect | Project Status Report - Status as on mm/dd/yyyy.
Mail Message Text | Attached is an excel for collecting tasks status updates from resource leads. This excel contains macros. Please disable the macros while opening the excel. Please open the excel, click on tab having your name on it, make the updates, save, and send it back to me. In case the task is not started and the schedule start date is already passed, please revise the start date. Similarly for cases where the task is started but not finished and the finish date is already passed, you should revise the finish date. You have to pay attention to tasks that are due. For easy identification, these tasks are shown with yellow background color. If you do not have any due tasks, you may not respond to this mail. However, you may always make and send the changes even though those tasks may be executed in future. Please refer to [ReadMe] tab in excel for useful information. This mail has been sent to resource leads who have some tasks assigned to them. Please feel free to ask questions or clarifications. Ashok kumar

## TabsIndex
Proj. 1234 | Auto Necho - Auto Apps Efficiency Status Tracking | 2003-06-10
Tab Name | Tab Description
RDTCD1 | R_DT_CD1 PlanView Report (Cummulative used hours)
RDTCD1MM | R_DT_CD1 PlanView Report (Monthly used hours)
RTR001 | R_TR_001 PlanView Report (Res x Work Entity wise Used & Remaining hrs)
PDTA10 | P_DT_A10 PalnView Report (Work Entity x Resource x Monthly used hours)
AllTasks | Import information of all tasks from Microsoft Shedule (.mpp file)
Team | Resource Status information
MileStones | Major MileStones Status Tracking
StatSum | Schedule Tasks Status Summary
DueTasks | Tasks that are due to finish / start by now or one week from now
UnFinished | UnFinished Tasks Status(Useful during project end phase)
PARTrns | PARs submitted Transactions
AllocStat | Resources Allocation Status
PAREFC | PAR hours extenstion Forecasting
TaskSum | Leadwise Tasks Statistical Summary
Sch_PV | Resourcewise schedule hours v/s PV allocation hours variance
EVAProject | Earned Value Analysis Project Level Sheet, (EVA Setup sheet is adjesent ot it)
ResEVA | Resourcewise Earned Value Analysis
AuditTrail | Track Tasks Status Changes
WEResAllocPlan | PlanView Work Entity x Resources Allocated Hours Plan
ReWEHrs | Resource x Work Entity wise Allocation, Used and Remaining hours
WEResHrs | PlanView Work Entity x Resources Schedule, Plan, Used & Rem Hours
ActHist | Resource x Period wise actual used hours history
ActHrs | Work Entity x Resource wise total actual used hours
RemHrs | Work Entity x Resource wise remaining hours
WRMHrs | Work Entity x Resource x Monthly used hours
Scratch | Sheet for temporary work - used as scratch pad
PTE | Time Estimation for Team meetings, Planner's Tasks
ResUses | Resourcewise Tasks Usage view of Microsoft Project
SMP | Schedule Maintenance Procedure
WTP | Weekly Task Plan for Project Planner
Defs | Schedule Tasks Status definitions
SchStatus | Schedule Status Template
Role | Project Planner's Role
Marocs | Information about macros used in this excel
Mail this excel to team
Note on A4: This update requires following tasks to be done. 1) Process R_DT_CD1 PlanView report for the whole duration of project. - In Parameters keep "From date" and "To date" fields blank. - Preview report - Export report into Excel format and store in the same folder in which this excel is stored. 2) Open this exported Excel and copy / paste this excel sheet on to Tab "RDTCD1". 3) Run the update macro which primarily updates the Team Status on tab "Team". It also puts "Upd Team" in column A of tab "RDTCD1" against each name. By inspecting column A, you can identify if new team members have been allocated in PlanView. In this case you have to re-run this macro one time more. 4) After this update, inspect the team status for correctness of update.
Note on A5: This update requires following tasks to be done. 1) Process R_DT_CD1 PlanView report for the desired period (Weekly or Bi-Weekly or Monthly selected from a list in Cell "C1" of tab "ActHist"). - In Parameters give correct values to "From date" and "To date" fields. - Preview report - Export report into Excel format and store in the same folder in which this excel is stored. 2) Open this exported Excel and copy / paste this excel sheet on to Tab "RDTCD1MM". 3) Run the update macro. Primarily this macro updates the Actual used hours history tab "ActHist". It will ask you if the report "RDTCD1MM" is for a new period or for the last (most recent) period. Respond appropriately. Depending upon the reponse, this macro adds a new column after column E or replaces values in an existing column F. If you have to replace values in a column corresponding to a past period, consider that the update is for a new period. After doing the update as explained in step 3), cut & paste values from column F onto the desired existing column. After this, delete the newly added column (Column F). 4) After this update, inspect tab "ActHist" for new additions of names.
Note on A6: This update requires following tasks to be done. 1) Process R_TR_001 PlanView report. - In Parameters, do not enter anything. - Preview report - Export report into Excel format and store in the same folder in which this excel is stored. 2) Open this exported Excel and copy / paste this excel sheet on to Tab "RTR001". 3) Run the update macro which will update following tabs. - ResWEHrs - WEResHrs - ActHrs - RemHrs 4) After this update, inspect these tabs for accuracy of update.
Note on A8: This macro does the following updates. 1) It imports Gantt Chart View of Microsoft Schedule through MAP onto tab "AllTasks" and indents tasks names in a way that matches the indenting by Microsoft Schedules. 2) Then it updates several sheets of this work book. - StatSum - DueTasks - Sch_PV - TaskSum - ResBLW - ResEVA 3) Before running this macro, run macro associated with RDTCD1 update.
Note on A9: Team Status information consisting of information like resource name, PAR status, actual used and remaining hours as per PlanView, Burn Rate, available rate, and schedules allocations etc. This information is used for identifying PAR extension requirements or hours by analyzing currect allocations, burn rate, and available rate. It is also used to identify and analyze variances between schedule allocations and actual time logged. This information is not available from Earned Value Ananlysis which give variances at summary tasks or project level i.e. not at resource level. (Though conceptually, the EVA concept can be used at resource level.):
Update
Update
Mail
Schedule
Update
Refresh
Refresh
Refresh
Refresh
Update
CreateStatusReports