## Instructions
Product Launch Checklist
Instructions
1. Data from the "Product Launch Checklist" tab automatically creates a Gantt Chart on the "Gantt Chart" tab.
2. Simply edit the Stage, Department, Task, Description, Owner, Start, Duration, End, and Status fields.
3. We have created drop-down lists to show you how to make this tool very user friendly. If you need help editing drop down lists or color coding, please visit: http://blog.demandmetric.com/category/excel-help/
4. Once you enter the Start date of a task and the Duration (# days), the End date will automatically be calculated.
5. You can use the filters at the top of each column on the "Product Launch Checklist" tab to drill down on specific items and create a custom report, such as what are all of our "Overdue" tasks.
6. If you have any difficulties, you can always contact product support at info@demandmetric.com

## Product Launch Checklist
Product Launch Checklist
Stage | Department | Task | Description | Owner | Start | Duration (Days) | End | Status
1 Market Problems | Product Team | Market Needs | Validate the understanding of Market Problems that this new product was developed to address | Sally | 2011-01-06 | 35 | 2011-02-10 | Completed
2 Customer Requirements | Technical | Requirements | Review the customer requirements that resulted in this product's feature set | Jim | 2011-02-10 | 35 | 2011-03-17 | On Track
2 Customer Requirements | Product Team | Feature Specs | Make sure that the Marketing and PR functions have the product specifications and feature detail to help craft supporting marketing materials, web pages, press releases, etc. | Michael | 2011-03-17 | 35 | 2011-04-21 | Overdue
2 Customer Requirements | Product Team | Support | Make sure that the Support function understands the new product's feature set to prepare needed documentation, training and support materials. | Tom | 2011-04-21 | 28 | 2011-05-19 | At Risk
3 Competitive Analysis | Marketing | Competition | Review the competitive analysis to understand the differentiation that exists in the new product. Make sure that the product launch marketing messages reflect this differentation. | Jim | 2011-04-21 | 21 | 2011-05-12 | Not Started
4 Positioning | Marketing | Positioning | Understand the market position that was determined for the new product. Verify that the Positioning is still valid and the product's differentation. | Sally | 2011-05-10 | 21 | 2011-05-31 | Not Started
4 Positioning | Product Team | Messaging | Work with Marketing, Sales and PR to make sure that all key product messages flow from the Positioning. | Paul | 2011-06-01 | 30 | 2011-07-01 | Not Started
4 Positioning | Executive | Alignment | Determine if the launch of this new product is still aligned with corporate strategy. If not, understand what must change - the product or the strategy - to not create market confusion or potential embarrassment when the product is launched. | Nancy | 2011-06-01 | 21 | 2011-06-22 | Not Started
5 Business Case | Finance | Business Case | Review the Business Case to understand all assumptions that must go into the pricing for the new product. See if anything has changed since the Business Case was approved that might require you to adopt different pricing. | Nancy | 2011-06-01 | 21 | 2011-06-22 | Not Started
5 Business Case | Product Team | Pricing | Work with Product Management and any other stakeholders to finalize launch pricing based on the Business Case. | Jim | 2011-06-15 | 28 | 2011-07-13 | Not Started
6 Product Roadmap | Technical | Roadmap | Review the Product Roadmap to ensure that all the planned features for the pending product release are in fact in the new product. If some features were omitted, make sure there are no references to them in launch and marketing materials. Determine if these new features have been deferred or canceled so you can update the Product Roadmap accordingly. | Sally | 2011-06-01 | 49 | 2011-07-20 | Not Started
7 Product Launch | Product Team | Set Goals | Set specific, measurable goals for this Product Launch. Most often, the goal of a Launch is to create sales momentum. | Tom | 2011-06-15 | 21 | 2011-07-06 | Not Started
7 Product Launch | Product Team | Pick Leader | Select someone to lead the Product Launch, ideally someone from the Product Management function. | Nancy | 2011-06-21 | 21 | 2011-07-12 | Not Started
7 Product Launch | Executive | Sponsorship | Ensure that the Launch team leader has executive sponsorship. | Sally | 2011-06-15 | 21 | 2011-07-06 | Not Started
7 Product Launch | Product Team | Build Team | Select members from each of the following functional areas to serve on the Launch team: Product Management, Marketing, Sales, R&D, Support/service, Channel Management. | Jim | 2011-07-06 | 21 | 2011-07-27 | Not Started
7 Product Launch | Product Team | Meetings | Begin meeting well in advance of the anticipated General Availability date for the new product. A new product launch typically takes 6 -12 months to properly plan and execute. Determine how frequently the team needs to meet. More frequent meetings are likely as the Launch date draws near. | Michael | 2011-07-15 | 21 | 2011-08-05 | Not Started
7 Product Launch | Product Team | Protocol | Decide on a set of communication protocols and frequency of regular communication between members of the Launch Team and those outside the Launch Team with a need to know. | Paul | 2011-07-15 | 21 | 2011-08-05 | Not Started
7 Product Launch | Product Team | To Do List | Using this template as your guide, develop a detailed checklist of all activities that must occur to successfully launch this new product. | Sally | 2011-07-21 | 28 | 2011-08-18 | Not Started
7 Product Launch | Marketing | Marketing Plan | Develop the pre and post-launch Marketing plan | Jim | 2011-07-30 | 35 | 2011-09-03 | Not Started
7 Product Launch | Marketing | Communications | Develop the pre and post-launch Communications plan. Consider both internal and external communications. What press activities are planned? Will you communicate the launch to your current customers differently that the general public? | Michael | 2011-08-05 | 28 | 2011-09-02 | Not Started
7 Product Launch | Marketing | Event Strategy | Develop your pre and post-launch events strategy (this can be part of the Marketing plan). | Nancy | 2011-08-05 | 28 | 2011-09-02 | Not Started
7 Product Launch | Technical | Release Milestones | Determine the product release milestones - working prototype, Alpha test, Beta test, General Availability. Document in the Launch Plan and develop a launch timeline around these dates. | Michael | 2011-04-10 | 35 | 2011-05-15 | Not Started
7 Product Launch | Technical | Testing | Stay in close communication with R&D and Manufacturing to determine if anything is occurring during testing that might delay the General Availability or Launch date. | Paul | 2011-05-01 | 63 | 2011-07-03 | Not Started
7 Product Launch | Product Team | Budget | After you've completed your detailed Launch Plan, develop a budget for the Launch and get it approved. | Jim | 2011-08-10 | 21 | 2011-08-31 | Not Started
7 Product Launch | Marketing | Metrics | Estimate how many impressions (exposures), leads, sales and profit will result from executing your Launch Plan | Tom | 2011-08-15 | 14 | 2011-08-29 | Not Started
7 Product Launch | Finance | ROI | Using the approved Launch budget and estimates from the previous step (or from the Business Case), develop an ROI projection for the Launch. | Sally | 2011-08-15 | 14 | 2011-08-29 | Not Started
7 Product Launch | Product Team | International | If you plan to launch in international markets, ensure that localization requirements, pricing and distribution are in place. | Jim | 2011-08-01 | 28 | 2011-08-29 | Not Started
7 Product Launch | Executive | Risk | Discuss as a team the risks to the Launch Plan, particularly those risks that might delay the launch or cause the launch to fail. Where possible, develop contingency plans against these risks. | Tom | 2011-08-01 | 21 | 2011-08-22 | Not Started
Formulas:
End = [Start]+[Duration (Days)]