- Review of the Dedicated Schools Grant Distribution Formula

- Project Brief and Outline Programme of Work

- Aim

The aim of the review is to develop a single transparent formula for the distribution of DSG which would be available for use from 2011-12 which:

  - support schools and local authorities to raise the educational achievement of all children and young people and to narrow the gap in educational achievement between all children, including those from low income and disadvantaged backgrounds;

  - distributes resources in line with relative need, recognising the different costs of educating particular groups of pupils and providing education in different areas;

  - is based on the principles of transparency, simplicity and stability.

- Scope

In Scope - The review will include the development of proposals on the distribution formula for DSG, consultation on the proposals and the development of final recommendations, so that Minsters can announce broad decisions by summer 2010 for implementation in the school funding settlement in autumn 2010 for 2011-12 onwards.  Scope for streamlining other grants into DSG will also be considered through the review.

Out of Scope – As Jim Knight announced in his statement on 31 January the review will start from the premise that the ring-fence on DSG will remain.  Consideration of the ring-fence on DSG is therefore out of scope.  The lead on decisions on the transfer of 16-18 funding to local authorities is with the 14-19 Reform Programme.  The level of resources which will be available for the school funding settlement from 2011-12, will be determined by the next Comprehensive Spending Review.  While the review will consider scope for streamlining other grants into DSG, the specific allocation of resources between the Dedicated Schools Grant and other funding streams in the settlement from 2011-12 is outside the scope of this review.

- Project Strands

Development Phase - There will be 9 key project strands in the development phase of the review:

- Calculating the Basic Unit of Funding per Pupil – This strand will focus on different models for calculating the basic unit of funding per pupil. Research will be commissioned into the feasibility of adopting an activity led approach to deriving the basic unit of funding, with the aim of reporting the findings to the Formula Review Group (FRG) in early 2009. In parallel with this we will also consider whether the basic unit of funding should be derived from the DSG total and weighted pupil numbers – as it was under the Schools FSS system.  We will consider the case for moving the pupil count for DSG from the January to the autumn School Census.

- Raising Attainment and Promoting Progression/Introducing incentives into the Funding System – Throughout the review we will examine the extent to which the developing proposals are likely to provide schools with the right resources and incentives to help to raise attainment and promote pupil progression.  We will review the scope for introducing incentives into the system, for example for pupil progression or through a premium for pupils from deprived backgrounds, and whether an element of funding could be based on outcomes achieved to reward success.

- Additional Educational Needs, SEN and Deprivation – This strand will look at the costs of meeting additional educational needs (AEN) and high cost SEN pupils.  We will conduct a brief review of the indicators of AEN, building on the technical note we published in 2006, to incorporate the Department’s new Tax Credit indicator and any other indicators that have recently become available.  Research will be commissioned into the costs to schools of meeting the needs of pupils with AEN and high cost SEN.   We will in particular look at interventions that have been shown to be effective in raising attainment and promoting pupil progression and how much these interventions cost.  We will also look at the scope for identifying funding for deprivation, as a subset of AEN, more clearly within overall allocations – to support continued progress towards fairer local formulae.  We will aim to report the findings to the FRG in early 2009.  We will also look at whether there is scope to fund high cost SEN pupils on a regional basis.  Finally, we will review whether there is evidence that pupil mobility should be reflected in the formula for distributing DSG.

- Area Costs/Sparsity and Small Schools – We will consider whether an area costs measure should be developed for schools, separate to the current methodology used in the Local Government Finance settlement.  We will look at two ways of assessing the additional costs to schools in high cost areas through analysis of data on wages areas and on house prices. We will aim to report the results of this research to FRG in early 2009.   This project strand will also take account of the review of area costs announced by Communities and Local Government and the review of teachers’ pay bands recommended by the School Teachers’ Review Body.  We will review the costs of sparsity and whether there is evidence that there should be a change before we have revised data from the 2011 Census; we will analyse the pupil postcode data from the School Census to assess the viability of using this as an alternative data source to the National Census data.  We will also look at the additional costs of small schools, and schools with rapidly falling rolls.

- Scope of DSG/Streamlining other School Grants – Consideration will be given to whether there should be greater flexibility in the use of DSG to support Every Child Matters outcomes and the implementation of the Children’s Plan.  We will look at the potential for streamlining grants into DSG, including Schools Standard Grant, School Development Grant and other Standards Fund grants.  We will review whether any changes are needed to the boundaries between local authority and school funding and whether the definition of what a school’s budget should cover is fit to deliver the 5 ECM outcomes.

- Early Years – Throughout the review we will consider the implications of the development of a new formula for early years funding.  We will also look at the implications for DSG distribution of the programme of changes on early years funding from 2008-11, including the change to count and fund children in the maintained sector according to the amount of provision they take up and the introduction of single local formula for funding the free entitlement.

- 14-19 Funding – This strand will look at the scope for introducing a common 14-19 funding system and how 11-14 funding would be aligned with this.  Given the consultation on the transfer of 16-18 funding to local authorities work on this strand will be completed first, with the aim of developing proposals by autumn 2008.

- Academies – We will review how the DSG formula should be adjusted to fund academies.  We will also look at the impact on local authorities where the majority of secondary schools will be academies and whether there should be a fixed cost element for small local authorities or those with significant numbers of academies.  Funding for pupils with individually assigned resources for SEN in academies will be reviewed.

- Local Authority and School Implementation/Transition Issues – Throughout the review we will model the impact of proposals on the development of local authority formulae.  We will review whether the minimum funding guarantee should continue and how it would operate.  With the introduction of a new formula, we will also consider whether it would be beneficial for local authority funding formulae to be simplified.  As proposals on a new formula take shape we will model the potential distributional changes amongst authorities and what transitional measures will be needed.

Developing Proposals for Consultation – Regular progress reports will be submitted to Ministers during the development phase of the review.  Towards the end of the development phase, the FRG will submit a report to Ministers with proposals on a new formula.  Following decisions by Ministers, proposals will be developed for consultation from January-March 2010.

Implementation of Proposals – Taking into account responses to the consultation, Ministers will take final decisions on the development of a new formula, in preparation for an announcement in summer 2010.  Proposals will be implemented in the autumn 2010 in the school funding settlement from 2011-12 onwards.

- Meeting Schedule for Formula Review Group

A draft programme of work for the review is attached at Annex A.  The meeting schedule takes into account the need to begin some project strands early because of inter-dependencies with other programmes of work (14-19 funding) or because of long lead in times to implement changes (timing of the pupil count).  Initial scoping papers for project strands will be submitted to the FRG.  Where it is proposed that research will be commissioned, time has been built into the schedule for procurement.  It is envisaged that where research projects are on-going that there will be regular progress reports to the FRG.

- Annex A - Draft Outline Progamme of Work for the Review

| Date | Schedule of Work |
| --- | --- |
| 26 February | 1st Meeting 1. Feedback from consultation/terms of reference for review 2. Past funding system/principles of a new formula 3. Project brief/schedule of work 4. Governance, role of the FRG, technical group 5. Communications & stakeholder management |
| 1 April | 2nd Meeting 1. Pupil count for DSG (January or autumn) 2. Scope for working towards a common 14-19 funding system 3. Introducing incentives into the funding system |
| Week beginning 12 May | 3rd Meeting 1. Activity-led funding - specification for research project |
| Week beginning 9 June | 4th Meeting 1. Additional education needs - specification for research project 2. SEN costs 3. Pupil mobility |
| Week beginning 14 July | 5th Meeting 1. Area Costs - specification for research project 2. Sparsity & small schools 3. Proposals on 14-19 funding |
| Week beginning 22 September | 6th Meeting 1. Greater flexibility in the use of DSG to support ECM 2. Review of boundaries of LA/school split |
| Week beginning 27 October | 7th Meeting 1. Academies funding |
| Week beginning 24 November | 8th Meeting TBA |
| 2009 Week beginning 26 January | 10th Meeting 1. Review of work on activity led funding 2. Streamlining of grants |
| Week beginning 23 February | 11th Meeting 1. Review of work on AEN |
| Week beginning 23 March | 12th Meeting 1. Review of work on ACA |
| Monthly Meetings from April - September | Further development of proposals on new formula and submission of a report to Ministers. |
| October- December | Development of consultation proposals. |
| 2010 January-March | Consultation on proposals. |
| April-June | Further development of proposals taking into account responses to the consultation. |
| July | Broad decisions announced by Ministers. |
| October/ November | School funding settlement for 2011-12. |