## Slide 1: PRECEDENCE DIAGRAM METHOD - PDM

## Slide 2: What is PDM?
Notes: The precedence diagramming method (PDM) is a technique used for constructing a schedule model

## Slide 3: What is PDM ?
A SCHEDULE MODEL
TECHNIQUE
Notes: The precedence diagramming method (PDM) is a technique used for constructing a schedule model

## Slide 4: What is PDM ?
ACTIVITY
ACTIVITY
i
j
ADM
PDM
Logical relationship
Logical relationship
Notes: The precedence diagramming method (PDM) is a technique used for constructing a schedule model in which activities are represented by nodes and are graphically linked by one or more logical relationships to show the sequence in which the activities are to be performed.

## Slide 5: Why?
Notes: Introduce in 1964

## Slide 6: Why Do We Need To Learn PDM?
6
Available on almost all commercial microcomputer-base on PMS.
Around 30% of contracting organization in Europe are using PDM
This technique is more versatile as compared to the other network planning.
Notes: Introduce in 1964

## Slide 7: Why Do We Need To Learn PDM?
6
Availability of lag has made this technique more adaptable to the planner’s needs.
This tool can guide managers in making critical decisions such as to deploy resources based on priority.
Can assist the client in determining the duration for extension of time.
Notes: Introduce in 1964

## Slide 8: ADVANTAGES & DISADVANTAGES
Fewer Activities
No Dummy Arrows
Quicker & Easier Logic
Complicates Manual Calculations
Updating and Managing change can be Challenging
May produce Different Dates on Diferent Software
No Restraints
Notes: Introduce in 1964

## Slide 9: ADVANTAGES & DISADVANTAGES
Activity A
Activity B
Activity C
Activity D
Activity E
Notes: Introduce in 1964

## Slide 10: Logical Relationship
FS
SS
SF
FF
Finish to Start
Start to Start
Finish to Finish
Start to Finish

## Slide 11: Logical Relationship
Activity A
Activity B
Finish to Start
F S
Notes: Activity A has to finish completely before starting activity B

## Slide 12: Logical Relationship
Activity A
Start to Start
SS
Activity B
Notes: Activity B has to start together with activity A

## Slide 13: Logical Relationship
Activity A
Fnish to Fnish
FF
Activity B
Notes: Activity B must finish together with activity A

## Slide 14: Logical Relationship
Activity A
Activity B
Start to Finish
SF
Notes: Activity B finish as soon as starting activity A

## Slide 15: Precedence Diagram’s Notation
LS – Lastest Start Time
EF - Earliest Finish Time
ES - Earliest Start Time
CF – Critical Path
TF – Total Float
LF – Lastest Finish Time
Notes: Introduce in 1964

## Slide 16: Precedence Diagram’s Notation
Total Float (TF) is the amount of time an activity can be delayed without delaying project end date.

## Slide 17: Precedence Diagram’s Notation
How to calculate Float?
Float = LS – ES or LF - EF
Activity A
ES
EF
LS
LF
FORWARD PASS
BACKWARD PASS

## Slide 18: Precedence Diagram’s Notation
Critical Path (CF) is the longest duration path in a network diagram.
And is the shortest time to complete project
It helps to determine the focus for project management efforts.
CF activities have Zero Float

## Slide 19: Schedule Model
TF=0
TF=0
TF=0
TF=0
Notes: Activity B finish as soon as starting activity A

## Slide 20: THANKS FOR YOUR ATTENTION