Statement of Work (SOW)

Writing Guide and Template

# Purpose of This Document

This document has been created in an effort to assist Commercial Services with the demands of the competitive procurement process, and in particular the demands associated with writing Statements of Work. Our hope is that it is of some benefit to university managers in their efforts to meet operational procurement requirements, while at the same time balancing the need to ensure compliance with the spirit and intent of University procurement and contracting policies. Questions or other enquiries may be directed to:

UNIVERSITY OF NEWCASTLE - COMMERCIAL SERVICES

Craig Lehman

Associate Director

Commercial Services

Telephone: (02) 4921 8839

Facsimile: (02) 4921 5152

E-Mail: Craig.Lehman@newcastle.edu.au

# Reminder Checklist

Remember to select the right “type” of SOW for your requirement:

  - Performance-based (for Operational Product and Services)

  - Detail/Design (for highly prescriptive requirements)

  - Quality Based Selection  (for Professional Services)

Try to write your SOW in a sufficiently detailed manner, so as to provide enough of a basis at a later stage when you will be required to extract relevant criteria that will be used to differentiate competing proposals. Remember that the selection criteria that you develop for your RFP must have a logical foundation within the text of the SOW - you cannot differentiate bidders on factors that have no relevance to the work itself (as described within the SOW), as this would be both meaningless and unfair.

If writing a Performance-based SOW, try not to “tie the Bidders’ hands” by being overly prescriptive in your description of the work and the manner in which it is to be undertaken. While care should always be taken to fully describe your requirement (as per above), try to balance this by leaving bidders with the flexibility in their proposals to offer innovative strategies, and to accept maximum responsibility and accountability for the results of their work. The primary risk in being overly prescriptive in your SOW is contractor “finger-pointing” and unwillingness to accept responsibility for results (“I did it the way you asked for it; if you don’t like the outcome, don’t blame me,...”).

When writing your SOW, try to think ahead to the contract management stage (once the winning bidder has been selected and the work is underway). In doing this, try to write your SOW in such a way as to ensure that the mutual expectations of the resulting contract will be adequately described and easily understood. Once the contract is underway, a well written SOW will go a long way to minimising potential misunderstandings and/or disputes with your Contractor. Remember to always use generic (non-proprietary) terminology and references in describing your requirements. This enables greater competition, and it also minimises the risk of a bid challenge or allegation that the requirements were slanted to a particular bidder.

Remember to use the present/active tense when writing your SOW, as the document needs to survive the RFP process and move forward intact into the contract itself. If the document is written in the present/active tense, it can be more easily interpreted at various points in time throughout the RFP/Contract cycle. The words “will” and “shall” have specific, legally interpreted meanings within a SOW. The word “Shall” is always used to convey a binding provision on the Contractor (i.e. “The Contractor shall supply ,...”). The word “Will” is always used to convey a declaration of future action by the Buyer (i.e. “The University will provide the Contractor with,...”).

Using the principles and examples provided within the SOW Writing Guide, group information as logically as possible within your SOW. There is an abundance of information associated with an SOW, and it is used by different audiences for different purposes, at different points in time. The SOW template has a place for everything, and a good SOW places everything in its proper place. Try to use plain and simple language in writing your SOW, and to avoid jargon, vague terms and rambling sentences. While there is a natural tendency to want to cover-off all possible contingencies in a SOW and to establish the basis for an irontight, no-risk, enforceable contract, this often leads to excessive “legalese” with the document, creating confusion, misunderstandings and contradictions. Ask yourself: “What would a reasonable person looking at this conclude?”. Remember to spell out acronyms and provide definitions for any technical or unique terms used within your SOW.

There is tremendous potential within a SOW for overlap, duplication, and/or contradiction with the Terms and Conditions (T’s & C’s) of the resulting Contract. Remember – the contents of the SOW are variable to define the requirement(s) at hand vs. the T’s & C’s which contain the standard terms and conditions of the resulting contract. If it’s covered-off in the T’s & C’s, you generally don’t need to worry about it in the SOW.

Above all, do your best in the SOW to convey to the Bidders what it will take on their part to complete the work to your satisfaction, and accordingly what it will take for them to ultimately have their work accepted and certified for payment.

Definitions

“Contractor”- An individual, partnership, company, corporation, association or other service, having a contract with the organisation for the design, development, manufacture, maintenance, modification, or supply of items or services under the terms of a contract.

“Bidder”- Any individual, firm, partnership, or corporation submitting a proposal for the statement of works contemplated, acting directly or through a duly authorised representative.

“Organisation”- The University of Newcastle

“Deliverable”- An aspect of a proposal that the provider commits to do or supply, usually and preferably clearly measurable. A product, service, or property that is a requirement of a contract or agreement.

# Scope of Works Template

1.	TITLE	5

2.	BACKGROUND	5

3.	OBJECTIVE	6

4.	ESTIMATED VALUE	6

5.	DEFINITIONS AND APPLICABLE DOCUMENTS	7

6.	BUSINESS AND/OR TECHNICAL ENVIRONMENT	8

7.	DESCRIPTION AND SCOPE OF WORK	9

8.	DELIVERABLES	11

9.	CONTRACTOR RESOURCE REQUIREMENTS AND QUALIFICATIONS (If required)	12

10.	APPROACH AND METHODOLOGY	14

11.	PERFORMANCE STANDARDS AND QUALITY ASSURANCE	15

12.	REPORTING AND COMMUNICATIONS	17

13.	RISKS AND CONSTRAINTS	17

14.	CONTRACTOR RESPONSIBILITIES	19

15.	UNIVERSITY OF NEWCASTLE REPRESENTATIVE AND SUPPORT	19

16.	LOCATION OF WORK AND TRAVEL	20

17.	SECURITY REQUIREMENTS	20

18.	INTELLECTUAL PROPERTY/COPYRIGHT	21

19.	GREEN PROCUREMENT AND SERVICES	21

20.	COMMENCEMENT, DURATION AND AWARD	21

21.	CONTRACTOR’S PROPOSAL	21

22.	INSURANCE/WARRANTIES	22

# TITLE

The Title clearly and succinctly summarises the name of the requirement being contracted for, and should, ‘at a glance’, answer the question: who is trying to buy what and via what form of contracting.

  - Briefly and clearly, identify the type of service being acquired, the organisation (Department, Faculty, Office, etc,..) acquiring the services.

# BACKGROUND

The Background section provides contextual information that plays a key role during the proposal solicitation stage by providing Bidders with an understanding of the organisation’s requirement, its objectives and key drivers for the work to be undertaken that can assist in determining whether to bid and in preparing a Proposal. The Background section should also support the organisation’s documentation of its business case, including the rationale for the work and the need to enter into Contract.

  - Describe the mandate of the organisation (Department, Faculty, Office, etc,...) acquiring the services.

  - As required, identify the authorised users of the resulting service/product. Describe the area within the organisation (Faculty, Division, etc,..) requiring the services. Similarly, identify whether the resulting service/product will be accessible by all areas within the organisation, or by only selected (and identified) authorised users.

  - Describe the specific commodity (type of service) being acquired.

  - At a high level, briefly describe the organisational program, project, or internal operational requirement for which the services are being acquired. The ‘need’ for the work to be completed must be clearly articulated – if possible, contextualise the project/requirement within the organisation/area’s overall business plan.

  - If needed, provide additional background/contextual information on the requirement and/or the organisation (Department/Faculty, Office, etc….).

  - If available, and if it would be helpful to Bidders in developing their proposals, provide publicly accessible informational URL’s .

  - Identify the reason the organisation needs to source the requirement externally (i.e. via Contractors). The first determination required is whether the requirement can be satisfied in-house. This subsection should articulate why the organisation (Department/Faculty, Office, etc….) feels that a contract is needed to meet this requirement.

  - Identify whether the requirement is recurring, the first in a series of similar upcoming requirements, a subsequent phase in a multi-phase program/initiative, or a ‘one off’ (i.e. one-time only) project. If the work to be undertaken consists of planning for or requirements definition in support of anticipated future work for which contracts will be established by the University at a later date, this should be clearly articulated, including any restrictions that may be placed on the resulting Contractor(s) from participating on the future work. This subsection can help to mitigate the risk of perceived bias and/or prior knowledge on the part of ‘incumbent’ Contractors, through the organisation’s proactive disclosure of its previous activities and future intentions.

# OBJECTIVE

The Objective section identifies the organisation’s overall outcome for the resulting contracted work, to provide a clear understanding and enforceable outcome for the work to be undertaken. The Objective also identifies the organisation’s anticipated outcome of the competitive bidding process, leading to the awarding of the resulting contract(s). Its primary role at the RFP stage is to provide Bidders with a clear understanding of the structure and number of resulting service/product(s) to be awarded.

  - Describe in outcomes-based terminology precisely what the organisation hopes to achieve as a result of this RFP.

  - Indicate if it is the organisation’s intent to award the resulting service/product(s) to one or multiple Contractors.

  - Identify whether the required type of Contractor consists of a firm or an individual providing services, or both.

# ESTIMATED VALUE

  - The Estimated Value section provides guidance to potential Bidders during the RFP stage in relation to the expected value of the resulting service/product(s). It can facilitate an understanding of the scale of the work to be undertaken, or can serve as guidance to identify the maximum budget within which the requirement must be fulfilled. The Estimated Value does not represent a commitment on the part of the University to enter into contract for a specified amount, but instead provides a framework within which potential Bidders may quote their proposed price/rates for the work.

Disclosure of the Estimated Value of the work is generally at the discretion of the organisation. The organisation may opt to remain silent on this point within the SOW. The risk in this approach is that Bidders will be given very little guidance, and there is a greater likelihood that resulting proposal values will be based on incomplete information or invalid assumptions, potentially penalising one or more Bidders. Not disclosing Estimate Value would generally be part of the Quality Based Selection (QBS) process.

How the Estimated Value is articulated within the SOW is also largely dependent upon the type of resulting service/product.

    - The Estimated Value of a Contract (i.e. a service/product with one (1) winner) can be expressed in several ways. At the RFP stage, value may be:

- fixed (the organisation encourages Bidders to compete by seeing who can propose ‘the most’ for a pre-specified, fixed amount);

- estimated (the organisation is unsure of the value of the work to be undertaken and is providing some guidance only; or

- an amount not to exceed (an upper limit to the resulting Contract that will not be exceeded in the resulting Award, but Proposals lower than this value would of course be acceptable).

  - In all cases, clearly identify whether the estimated value of the requirement is inclusive of GST, Travel and Living Expenses and/or Administrative Expenses or other direct costs.

# DEFINITIONS AND APPLICABLE DOCUMENTS

Definitions and Applicable Documents section provides contextual information at both the RFP and Contract stages to ensure clarity in the interpretation of the SOW and identification of overarching legislation, policies, procedures and guidelines that will govern the resulting work. The purpose of this section is to mitigate ambiguity and misunderstanding that could lead to poor proposals at the RFP stage, or default, breach or dispute at the Contract stage.

  - Define terms that may be unfamiliar and spell out acronyms. This includes terminology unique to the commodity, field of work, the organisation, or contracting.

  - Identify all applicable documentation or reference material that the Contractor(s) will require to complete the work, or that will provide useful background to Bidders in preparing their proposals. Referenced policies become enforceable in the resulting Contract. Applicable documents can be attached as an Annex to the SOW, via a publicly accessible URL where the documents may be obtained, or made available upon Award.

Provide only what is pertinent to the work and relevant for Bidders to understand the requirement and for resulting the Contractor(s) to complete the work correctly.

# BUSINESS AND/OR TECHNICAL ENVIRONMENT

Business and/or Technical Environment section provides contextual information to Bidders at the RFP stage to identify operational requirements of the work and programs, systems and infrastructure with which the Contractor(s) will be required to work in the Contract stage.

  - The Business Environment identifies the hours of operation for the organisation and identifies the contractual requirements for the Contractor(s) to provide service in accordance with or beyond regular operating hours. The requirements for Contractor service hours are enforceable at the Contract stage.

    - Identify the hours of operation for the organisation (e.g. normal working hours MF; extended or peak hours based on region of service delivery; or 24x7 operation).

    - Describe the organisation’s expectation for the Contractor’(s’) working hours. Identify whether the Contractor is expected to be available to provide service in accordance with the organisation’s hours of operation or whether additional hours of service (e.g. occasional after hours work; extended hours; 24x7) are required. As applicable, clearly identify if the Contractor’s extended hours differ from those of the organisation.

    - Requirements for Overtime Work: Identify whether the Contractor will be required to complete overtime work (i.e. will the organisation consume billable hours from individual Contractor resources in excess of the provincial norm, typically, more than 40 hours/week?). Clearly identify whether overtime is required on a continual basis, occasionally or not at all. The organisation’s definition for Overtime should be included in 5.1, Definitions.

To avoid dispute at the Contract stage, clearly identify whether the organisation is prepared to pay the Contractor a higher rate for Overtime hours worked. If Overtime will be reimbursed at a different rate, the organisation may specify a rate (e.g. time and a half, etc.) or may request Bidders to identify proposed

Overtime rates within the Financial Evaluation/Pricing Matrix of the RFP, for the purpose of evaluating Bidders on their Overtime rates.

    - Requirements for On-Call Service: Identify whether the Contractor is required to be available outside of the Contractor’s regular working hours (as defined in 6.1.2 above). Identify whether On-Call requirements are for routine services and/or for emergency response. To avoid dispute at the Contract stage, clearly identify whether the organisation will pay a different rate for On-Call Service requirements.

Additional charges for this service response may be specified by the organisation or Bidders may be requested to identify proposed rates for the purpose of Financial Evaluation.

    - Requirements for Emergency/Rush Service: Different service types, such as communications, HV supply etc., may have requirements for the Contractor to respond and deliver service/complete a deliverable in a time frame that is an exception to the normal response time or service standard (to be identified in 11) and/or when the organisation has requested greater than typical volumes of work from the Contractor within the same period of time. If included, this provision places an obligation on the Contractor to respond and deliver service in accordance with the Emergency/Rush parameter, when requested by the organisation and accepted by the Contractor, that becomes enforceable in the resulting Contract. Clearly identify whether Emergency/Rush service may be required and the conditions that must be in place for requirements to be deemed Emergency/Rush (i.e. shorter than normal response time).

To avoid dispute at the Contract stage, clearly identify how the organisation will pay for Emergency/Rush Service. Additional charges for this service response may be specified by the organisation (as an identified multiplier of the base rate of service or another method), or, Bidders may be requested to identify proposed rates for the purpose of Financial Evaluation. If Emergency/Rush Service is included, be sure to identify within 11 the normal and Emergency/Rush response times for work.

  - The Technical Environment provides a description of the technological infrastructure, systems and/or programs operant within the organisation. This section is optional, dependent upon the type of services being acquired (e.g. IT Services) and/or a requirement for the Contractor to work within the organisation’s existing technical standards or infrastructure. Inclusion of this section places an obligation on the Contractor to comply with the organisation’s standards that becomes enforceable in the resulting Contract.

    - As required, provide a description of the aspects of the organisation’s IT infrastructure/technical environment that are relevant to the work being undertaken.

    - Identify the specific obligation being placed on the Contractor. For example, the Contractor may be required to adapt the output of its work/ensure compatibility with the technical/technology within the organisation; and/or to ensure that its resources are properly trained and equipped to work with the organisation’s technology or equipment.

# DESCRIPTION AND SCOPE OF WORK

The Scope provides guidance at the RFP stage to assist Bidders in understanding the work to be undertaken and provide clarity in developing their Proposals. At the Contract stage, the Scope provides enforceable guidance to the Contractor as to where to focus its efforts in the resulting Contract to ensure the Contractor remains ‘in scope’ and focussed on issues, tasks and other activities that are relevant to the completion of the work.

The contents and structure of the Scope are influenced by the type of resulting service/product. The Scope will define typical activities and tasks to be undertaken.

  - The Scope section with a SOW describes the logical boundaries within which the work will take place (ie. what is the work, and what is it not?). In contrast to the Deliverables under the Contract (described in 8) which identify the specific, tangible items the Contractor must complete in order to receive payment, this section “sets the stage” for a later and more precise description of the deliverables, by first describing the work at a macro or conceptual framework level, and in more general terms.

Where Deliverables may be characterised as Outputs of the resulting Contract, the Scope identifies the Inputs (requirements of the broader field of work, specific activities, etc.) required to successfully complete the work.

To avoid contradiction or misunderstanding of the requirement, clearly identify the distinction between the Scope and the Deliverables sections of the SOW and direct Bidders/the Contractor to 8 for a listing of specific deliverables.

  - Frame the required work within the context of the professional discipline in which it is situated. Provide a brief description of the discipline to ensure understanding of the requirements to successfully undertake the work within this broader field.

  - Clearly describe the activities the Contractor is required to undertake that will lead to the production of the Deliverables (8), but that are not part of the content of the Deliverables themselves. To ensure the Contract remains “Performance-Based” do not over-specify the specific methodologies or approaches to be used in completing these required steps. Any organisational/requirement specific methodologies should be described in 10.

For each activity described, provide the scale and metrics (e.g. identify the frequency, quantity or volume of inputs the Contractor is required to make) for the successful completion of the work. For anticipatory service/product all Scope activities will be “as required”.

  - For Professional Services/Project Scopes of Work, identify the high level project phases/milestones. To avoid ambiguity or contradiction, direct Bidders/Contractors to 8 for identification of where the Deliverables fit within these phases/milestones. For Scopes of Work where deliverables are unknown, the Scope may be driven by the type of Resource Categories required. In this instance, describe the typical activities associated with each of the Resource Category types (as defined in 9).

  - As required, reserve the organisation’s right to amend the scope at a later date, to include additional related input or scope parameters, should the need arise due to a change in business or technical requirements. Inclusion of this right, as accepted by the Bidder in the submission of its Proposal, provides an enforceable legal option the organisation can exercise, where a legitimate need may arise in the future. Amendments to the scope of work are, by definition, a surprise. This provision identifies the potential for additional requirements to occur within the scope resulting contract, but must not be used to avoid competitive processes or bypass levels of delegated signing authority. Any item that is anticipated as a requirement at the time the RFP is developed should be included within the RFP document.

# DELIVERABLES

The Deliverables section clearly identifies the tangible products or outcomes that the Contractor is required to produce in order to receive payment (ie. “Outputs”). In accordance with Contracting Policy, payment should be made only for satisfactory completion of a concrete Deliverable or delivery of a service. Similar to the Scope of Work (7), the structure of Deliverables 8 is dependent upon the type of resulting service/product. Professional Services/Projects will have clearly defined Deliverables and delivery dates, whereas supply contracts will identify the anticipated types of deliverables associated with the work to be undertaken.

This section will link to any milestones/phases identified in the Scope of Work and intersect with the contract Basis of Payment. Clearly identify the structure of the resulting service/product - does the outcome of the work consist of:

- A reoccurring Deliverable(s) to be paid by one (1) invoice upon completion;

- A single Deliverable comprised of multiple milestones and thus multiple ‘progress payments’ against completed milestones; or

- More than one Deliverable, each of which may consist of more than one milestone with one or more invoice payments.

  - Clearly identify the required Deliverable(s). This should include the Deliverable Name, Description of its contents, the format in which it is required, number of units/deliveries/services, and the date or time period following Award when the delivery is required (if for Professional services/Projects).

  - For Deliverables with milestones, provide a description of the milestone, including a date or time period following Award when this milestone is required to be completed. To mitigate the potential for confusion or dispute at the Contract Stage, clearly identify when payment will occur and whether the organisation will dictate the amount of payment (as a percentage of the overall contract value) or whether Bidders are required to propose a percentage of the overall value that this delivery will be worth. This information provides the basis for evaluating Contractor performance against the completion of the work in the event of dispute or ‘stop work’ orders, to enable the organisation to clearly identify what has been received (and completed in accordance with the approach and methodology 10 and any required performance standards 11) and how much is owed to the Contractor.

  - Clearly identify when payment will occur for the Deliverables (i.e. at the end of the Contract; upon receipt of the Deliverable; upon completion of the milestone; monthly; or otherwise). Payment is always conditional upon the satisfactory acceptance of the Deliverable(s). Clearly state this condition here.

  - Direct the Bidders/Contractor(s) to the subsequent sections of the SOW that will govern how the work is to be completed (10). This enhances the enforceability of the resulting mechanism at the Contract stage by clearly linking the completion of the Deliverables to the required resource quality, approach, performance standards, communications requirements, etc. The subsequent sections are critical at the Contract stage and form an obligation on the Contractor in the successful completion of the work.

# CONTRACTOR RESOURCE REQUIREMENTS AND QUALIFICATIONS (If required)

Contractor Resource Requirements and Qualifications section identifies, in part, how the Contractor is required to undertake the work, by identifying the type of people (skill sets) the Contractor is required to deploy and accountabilities for activities associated with each of the Contractor’s resources for the completion of the work. At the RFP stage, this section provides guidance to the Bidders in relation to the organisation’s requirements and expectations; and it will also establish a foundation for developing selection and evaluation criteria within the RFP. At the Contract Stage it will be used to assess the suitability of the Contractor’s deployed resources, providing the organisation with a measure of enforceability for qualifications, in addition to providing enforceability for availability and replacement of named resources.

  - Clearly identify the Resource Category(ies) required (e.g. Supervisor, Leading Hand, Tradesman, Business Analyst, etc…) and their level of seniority in relation to the other Categories required. The number of resources required at Contract stage may differ from the number of resources Bidders are required to propose at RFP stage -dependent upon the length of the Contract, type of requirement and whether there is a need to identify named resources (see also 9.2 below).

Each Resource Category should be described in two (2) parts:

    - description of the Resource Category’s role and activities in the resulting work - This should NOT be written as a traditional “job description” (to avoid any appearance of an Employer-Employee relationship); and

    - a description of the minimum required qualifications for an individual within the Resource Category to successfully undertake the work - Try to highlight the actual qualifications, skills, experience and knowledge genuinely required by the Contractor’s key resources needed to successfully and competently undertake the work, as described within the SOW.

Note: In some cases, qualifications, experience and/or skill sets may not be specific to any one Resource Category. As needed, identify any specific skills/experience the Contractor, in general, is required to possess in order to complete the work. This information will also inform the development of the selection and evaluation criteria.

  - Clearly identify whether the resulting contract will allow for the completion of work by named resources only (i.e. only those individuals proposed and screened can complete the work) or whether any resource may be provided by the Contractor provided that he/she meets the established requirements. If the former, in the event these resources are unavailable, the Contractor will be ineligible to receive the Contract.

This decision will impact the development of the selection and evaluation criteria. A requirement for only specific named resources to undertake the work will necessitate a requirement for Bidders to identify specific individuals within their proposal(s) and for their qualifications to be evaluated by the organisation at the RFP Stage. Where resource identification will take place at a later stage (e.g. as in some anticipatory mechanisms), the minimum qualifications identified in 9.1.2 will set the bar for the future determination of the acceptability of these resources.

  - Identify whether the replacement of Contractor resources (whether due to illness or other unforeseen events, or based on flexibility of resource identity, as per decisions made in 9.2 above) is acceptable over the life of the resulting contract. Clearly identify whether resource replacements are only permissible in exceptional circumstances. If replacement resources will be allowed, prescribe the protocol by which resource changes and/or substitutions will be allowed; including definition of a time frame within which replacement resources will be available to commence the work, and any requirement for the Contractor to ensure continuity of service or knowledge transfer among its resources, and at whose cost (Contractor’s or organisation’s).  Regardless of circumstance, clearly state that the suitability and acceptability of Contractor resources is at the exclusive opinion of the organisation. Reserving this right can mitigate the potential for future dispute.

  - As required, for anticipatory mechanisms, identify any rights the organisation wishes to retain to add additional Resource Categories and/or additional named resources. Legal rights of the organisation should be specified in advance and are accepted by the Contractor (based on submission of their Proposal at the RFP stage). If needed, this option can provide flexibility to the contract to include additional related Resource Categories, as needs arise, over the duration of the Agreement.

# APPROACH AND METHODOLOGY

  - The Approach and Methodology describes how the Contractor will specifically go about the completion of the work under the resulting contract. Typically, in Performance-based SOW’s, and to mitigate the risk of liability for the organisation in the event of dispute or poor performance under the Contract, the Contractor is required to provide its own specific methodology for the completion of the tasks and deliverables. Bidders submit a proposed Approach and Methodology as part of their Proposal, which may be evaluated in the selection and evaluation criteria, and which, upon acceptance of the Proposal by the organisation, becomes enforceable in the resulting contract.

Dependent upon the requirement, there may be portions of the Approach and Methodology that need to be prescribed to ensure conformity of the Contractor’s work with existing government, industry, or discipline standards; or existing methodologies used within the organisation. Where this is the case, take care to ensure that only those portions of the method that are essential are prescribed, and that the Contractor retains creativity for innovation, and thus liability, for the implementation of its methodology and the resulting outputs.

    - Describe any obligation the organisation is imposing upon the Contractor with respect to the Approach and Methodology to be used in the resulting work.

    - Clearly identify whether the Contractor is required to fulfil the work in accordance with its own methodology and what portions of the work this method must address. Regardless of the flexibility provided to the Contractor/Bidders, all work must be completed in accordance with industry accepted methodologies and approaches.

  - Where the Contractor is required to provide its own approach and methodology, identify whether this must be included within the Contractor’s Proposal. If yes, selection and evaluation criteria can be developed to evaluate the aspects of the methodology that are of greatest risk to realisation and success.

  - Clearly identify the obligation on the Contractor to meet the requirements of the SOW, using this methodology (as described in 10.1 and 10.2 above) in a manner that is in compliance with the Performance Standards and Quality Assurance requirements of the resulting contract (described in 11). This strengthens the link between these elements of the SOW, and provides for enhanced enforceability of the resulting contract.

  - In addition to specific methodologies, approaches and standards, identify the Contractor’s obligation to ensure that all work undertaken is in compliance with all applicable legislation, Acts and codes.

  - Identify the Contractor’s obligation to ensure that its resources are adequately trained to fulfil their responsibilities under the contract and shall operate at all times in compliance with the law.

# PERFORMANCE STANDARDS AND QUALITY ASSURANCE

Beyond the physical completion of Deliverables (8) within the Scope (7) of the contract, the Performance Standards and Quality Assurance section of the SOW identifies the organisation’s expectations for the outcome of the work, or, the level of ‘performance’ required of the Contractor.

  - Within any contract, there is an inherent performance standard that failure on the part of the Contractor to complete the required Deliverables (as defined in 8) will result in the withholding of payment and/or determination of breach of contract and/or default on the part of the Contractor. Clearly identify this expectation and the associated role of the Contract Operator/Manager who is responsible for determining the compliance of Contractor Deliverables with the Performance Standard of responsiveness, timely completion and quality work. In the event of dispute, this section must be clear enough to enable the withholding of payment under the contract for poor performance.

The inherent Performance Standard is typically sufficient for most contract requirements. Dependent upon the nature of the requirement, additional Performance Standards and Quality Assurance requirements may be needed to define any processes whereby the Contractor may be provided with assessed penalties for failure to comply with the minimum requirements (e.g. service levels) of the work.

  - Penalties should only be assessed where failure on the part of the Contractor to meet the minimum baseline (defined Performance Standard) results in a real (generally financial) loss to the organisation due to reduced client service provision by the organisation, costs of re-work, or significant project delays resulting in increased expenditure by the organisation. Areas where Penalties may be applicable include:

- Speed/timeliness of service delivery or work completion;

- Technical conformity of the product/service/work to specification (i.e. functionality, accuracy and completeness);

- Accessibility of the Contractor (e.g. for Client Services contracts);

- Client satisfaction with the Contractor’s level of service (as assessed by a client satisfaction index).

    - Where a Penalty will be assessed, clearly describe the element of the Contractor’s service that will be measured. Describe the specific obligation for performance that is being imposed on the Contractor.

    - Clearly identify the benchmark or baseline level of service that is required in relation to the service element identified.

    - Describe when the Penalty will be applied. Is every transaction equally eligible for Penalty (transactional), or will performance be assessed against work completed over a defined period of time (cumulative)? If cumulative, identify at what interval (e.g. monthly, quarterly, etc.) the penalty could be applied.

    - Identify the compliance standard associated with the benchmark/baseline level of service. How often is the Contractor required to perform to baseline (i.e. every time or a defined percentage of times)?

    - Identify whether there are any exceptions that will be made to the application of a penalty due to circumstances beyond the Contractor’s/organisation’s control (for example, natural disaster, etc.).

    - Identify the amount the Contractor will be penalised for performance below compliance with the benchmark/baseline level of service. For Penalties, this should consist of a percentage of the overall value of the contract that is reasonable and directly related to the organisation’s actual loss sustained as a result of the Contractor’s performance failure. For Penalties that are cumulative (i.e. measured over a period of time - see 11.2.3 above), identify whether a given percentage of transactions within that time period will be assessed for the Penalty, or whether all transactions over the cumulative period will be assessed. Possible time penalties could be applied to reduce the contract term.

    - For Penalties, clearly identify the point at which failure on the part of the Contractor to perform to standard will constitute a breach of contract, and direct the Contractor/Bidder to the applicable section in the Terms and Conditions.

    - Prescribe the schedule within which the Contract Operator/Manager will undertake to verify the Contractor’s adherence to the Performance Standard (i.e. whether pre-defined time periods, or ‘periodically’).

    - Identify any obligation on the part of the Contractor to provide records or other data to support the organisation’s monitoring and measurement of Performance.

  - Identify any other industry, government or internal Performance Standard which must be followed in the course of the work. In addition to the requirement for Contractor Performance, there is an inherent Quality Assurance Standard associated with all Contracts.

  - Clearly state the Contractor’s Quality Assurance requirement for work to be completed in conformance with the Deliverables (8), in a timely fashion and in a reasonable manner, consistent with generally recognised standards for quality work in the field of the service requirement.

    - Dependent upon the work, identify any external Quality designation or certification required to provide assurance that any specialised Contractor’s quality processes will be enforced in the resulting contract.

    - As required, identify any specific aspects of the work to be undertaken for which the Contractor will be required to provide its own Quality Assurance methodology. This can be linked to the selection and evaluation criteria, wherein Bidders can be evaluated on their method for meeting this requirement.

# REPORTING AND COMMUNICATIONS

Reporting and Communications section describes the obligations on the Contractor to maintain contact with the organisation during the resulting contract. It also identifies any specific reports or other updates the Contractor will be required to provide during the course of the work, that are necessary to ensure product/service oversight and control, but are not in themselves, Deliverables as defined in 8.

  - Clearly identify the Contractor’s obligation to adhere to the Reporting and Communications Requirements, in addition to the Deliverables specified in 8.

  - Describe the Contractor’s general Reporting obligation to keep the organisation informed of progress, status and completion over the course of the work. Identify how these reports may be delivered (e.g. orally, written, etc.), and whether there is a specific timeline for submitting status reports.

  - As required, describe any special Reporting Requirements that are specific to the work being undertaken (e.g. timesheets; activity reports; financial statements; etc.). For each Report type required, clearly identify: the Report format (oral or written); frequency; and content. If Reporting Requirements must be completed in existing organisational templates, copies of these templates may be provided within an attachment of the SOW, or provided upon Award.

  - Clearly describe the Contractor’s general Communications obligation of accessibility, responsiveness, and the need to keep the organisation informed of any issues, as they arise.

  - Identify any specific requirements for Meetings with the Contract Operator/Manager that will take place during the resulting work. As required, identify meeting topics, timelines and locations.

# RISKS AND CONSTRAINTS

Just as there is an inherent opportunity for profit, the act of entering into a contract creates an inherent risk of loss on the part of the Contractor. This potential is understood by Bidders as part of the process in engaging in business.

The Risks and Constraints section of the SOW operates at the RFP stage to inform Bidders of any unusual or exceptional risks and/or constraints beyond those inherent in undertaking a contract. As required, be sure to identify in this section any unique or specific Risks and Constraints related to the work that are known or are reasonably expected to occur. Be careful not to overstate or understate the Risks of the work.

Overstating a Risk may potentially dissuade Bidders from submitting a Proposal or lead to inflated rates, while understating places a risk on the organisation for liability should the Risk later be incurred by the Contractor. If no Risks and/or Constraints are reasonably anticipated, remove this SOW section.

This section identifies potential risks (real or perceived) that could incur in undertaking the work, and any operational constraints that could impact the ability of the Contractor to complete the work and/or require consideration in the Contractor’s methodology. At the Contract stage, identification of any Risks and Constraints in the SOW provides a degree of legal protection for the organisation. Should any Risk that has been identified befall the Contractor, or should a Constraint impede the Contractor’s ability to complete the work; previous transparency and disclosure of these items in the SOW can mitigate the organisation’s liability, as the Contractor has been informed of their potential and has accepted this in its offer to enter into and acceptance of the contract.

  - Clearly define the terms Risk and Constraint. A Risk is an unusual or exceptional peril (e.g. legal, physical, financial) that could befall the Contractor in the course of undertaking the work. A Constraint is an operational reality within the organisation’s environment that may impede the Contractor’s ability to complete its work.

  - Describe the specific Risk(s) (e.g. risk of physical harm, risk of third party litigation, etc.) that has the potential to occur. Clearly identify the responsibility of the Contractor to take appropriate measures to mitigate the aforementioned risk.

  - Describe the specific Constraint(s) (e.g. restricted access, time constraints, etc.) that is known or likely to impede the Contractor’s work. Clearly identify the responsibility of the Contractor to take appropriate measures to work within the Constraint(s). If the Work under the resulting product/service consists of planning and scoping for a future contractual requirement, it may be necessary to restrict the Bidder’s ability to participate in any future related work.

As needed, include one or more of the following sections.

- Maintain standard contract terms and conditions relating to Confidentiality.

- If there is a requirement for specific measures relating to Confidentiality, Non-Conflict of

- Interest or Non-Participation, discuss your requirements with Legal Services.

  - Identify any special requirements for the Contractor to certify that it will maintain Confidentiality, maintain a Conflict of Interest Free status, and/or is precluded from bidding on future requirements.

# CONTRACTOR RESPONSIBILITIES

Beyond the Contractor’s responsibility to complete the work under the contract in accordance with any defined methodology, performance standards and constraints, there may be other specific items the Contractor is responsible to provide/ensure while completing the work. Contractor Responsibilities are itemised to help mitigate the risk to the organisation of an employer-employee relationship arising under the contract.

Please note: although the relationship between the organisation and the Contractor may be well defined in the SOW, it is critical to ensure that this risk is not incurred in how the relationship is operationalised in practice in the resulting contract.

  - Identify the Contractor Responsibilities related to coordination and management of the work under the resulting contract .  As required, these include: responsibility for own travel arrangements, coordination with organisation personnel and other stakeholders, coordination with other Contractors, etc.

  - Clearly identify and describe anything unique the Contractor is required to bring to the work. This could include requirements for the Contractor to provide its own special tools or equipment. Clearly identify who (Contractor or organisation) will be providing equipment, computers, software, databases, etc. to complete the work.

# UNIVERSITY OF NEWCASTLE REPRESENTATIVE AND SUPPORT

This section identifies the responsibilities or commitments on the part of the organisation to support the Contractor in the successful completion of the work. It identifies authorised representatives of the organisation to whom the Contractor will report during the period of the contract. Distinctions are often made between the “Contract Operator” and the “Contract Manager”. It also identifies any specific items or services the organisation will provide to the Contractor, as needed, to complete the work.

  - Describe the role, responsibilities and authorities of the Contract Manager and when this individual will be identified (e.g. upon Award)

  - Describe the role, responsibilities and authorities of the Project Operator and when this individual will be identified (e.g. upon Award).

  - Clearly identify any organisation-furnished equipment, facilities, information and personnel that will be made available to the Contractor in support of its work related to the contract.

# LOCATION OF WORK AND TRAVEL

Location of Work and Travel specifies the geographic location(s) where the organisation requires the delivery of services and whether/how any requirements for Contractor travel will be reimbursed by the organisation under the resulting contract.

  - Define where the Contractor’s work will take place (i.e. at either facilities identified by the organisation or at facilities of the Contractor’s choosing, or both). If work will take place at organisational facilities, describe their location.

  - Clearly identify any requirement for the Contractor to travel to locations other than the organisation’s place of business. If possible, specify anticipated locations, frequency, duration, number of resources, and schedule. Clearly describe any requirements for travel to locations that may be considered a Remote or ‘Hardship’ posting and any risks associated with such travel. If specific details are not yet known, provide enough information to identify the requirement. Identify whether no travel is anticipated under the resulting contract.

  - Identify whether the Contractor will be reimbursed for travel and/or living expenses to/from locations other than the organisation’s usual place of business. If travel is required, identify the Contractor’s obligation to comply with the Travel Policy with respect to the reimbursement of expenses.

  - Identify whether funding for travel will be added to the Contract upon Award or whether the Contractor’s Proposal will form an estimate for travel costs. (If the latter, amounts for travel can form part of the evaluation process).

# SECURITY REQUIREMENTS

This section of the SOW identifies requirements for the Contractor to comply with the organisation’s requirements under the Security Policy. A Security Requirements Checklist may also be required and it is suggested to contact Facilities Management to determine what is needed.

  - If required, identify the required level(s) of Security Clearance for Contractor Resources.

  - Identify any requirement for the Contractor to possess a screening and when this clearance is required. Identify whether Award of the contract is conditional upon the successful completion of this screening.

  - Describe any obligations on the part of the Contractor to safeguard organisational assets (documents, etc.) while conducting work on-site and/or off-site.

# INTELLECTUAL PROPERTY/COPYRIGHT

This section of the SOW indicates which party will own or have rights to the existing intellectual property used to complete the work (referred to as “Background” – normally what is supplied by either the Contractor or the Organisation), and which party will own or have rights to any new intellectual property created as a result of the work (referred to as “Foreground”).

As a variety or pre-defined and often highly technical clauses are used in this section, employees should always seek input from Legal prior to finalising this section.

# GREEN PROCUREMENT AND SERVICES

This section of the SOW identifies requirements for the Contractor to comply with the organisation’s requirements under the Guideline on Socially Responsible Procurement.

  - Identify any specific environmental requirements (e.g. use of recycled materials, etc.) for the Contractor’s work.

# COMMENCEMENT, DURATION AND AWARD

This section of the SOW identifies the legal time frame for the resulting contract product/service and the commencement of work under the agreement.

  - Identify the time period of the resulting product/service, from the date of legal Award to the specific end date or within a specified duration.

  - Identify any rights reserved by the organisation to extend the period of the resulting product/service, and for what duration.

# CONTRACTOR’S PROPOSAL

This section of the SOW incorporates the Contractor’s Proposal into the resulting contract. This ensures the organisation’s ability to enforce the Contractor’s commitments made at the RFP stage in the resulting Contract.

Example:

The Contractor’s proposal, insofar as it is not in variance with anything contained herein, shall apply to and form part of this Agreement.

# INSURANCE/WARRANTIES

This section of the SOW identifies any legal obligations imposed on the Contractor in the resulting product/service in relation to the need to indemnify the organisation (i.e. insurance), or the need to offer a warranty or guarantee. It is suggested to contact Legal Services to discuss any special requirements.

  - As required, describe the type of insurance required, and whether the Contractor is expected to indemnify the organisation, and to what extent.

  - As required, describe any limitation on Contractor liability under the resulting contract.

  - As required, identify any specific liabilities the Contractor will be required to accept in completing the work under the contract.

  - As required, for goods and/or maintenance services, etc. identify any specific warranty or guarantee requirements, what is covered under the warranty/guarantee, to what standard, and for what time period.