- Contractor Performance Report

#### Guidance notes

- This Contractor Performance Report (CPR) is designed to be completed electronically, with answer fields expanding as required, and rows able to be inserted when needed.  However, if respondent completes the form by hand, please use block letters.

- Electronic copies of this CPR Report are available online (see References):

- All amounts in this CPR report should be GST inclusive

- Please view the Index of construction documents to locate all documents referenced throughout this text.

- Contents

Contractor Performance Report	1

Contract Executive Comments	4

1. Contractor Performance Reporting (CPR) System Guidelines	5

2. Performance Scoring Methodology	6

3. Industry Data	8

4. Steps for completing a Contractor Performance Report (CPR)	8

5. CPR Criteria Assessment Guidelines	11

- References

Available on the ProcurePoint website

Contractor Performance Report

NSW Government Code of Practice for Procurement.

NSW Government Environmental Management System Guidelines

NSW Government Industrial Relations Management Guidelines

NSW Government OHS Management Systems Guidelines

NSW Government Procurement System for Construction

Procurement Practice Guide: GC21 meetings and workshops

Procurement Practice Guide: Performance Management

- Contractor Performance Report

### CONFIDENTIAL

### Contract Details

| Contract No: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Contract Title |  |  |  |  |
| Original Contract Price | $ |  |  |  |
| Date of Contract | / /20 . | Original Date for Completion |  | / /20 . |

### Contractor Details

| Contractor’s Company / Organisation name |  |  |  |  |
| --- | --- | --- | --- | --- |
| Contractor’s Representative | Name |  |  |  |
|  | Position |  |  |  |
|  | Tel |  | Mobile |  |
|  | Email |  |  |  |

- Client Agency Details

| Client Agency* |  |  |  |  |
| --- | --- | --- | --- | --- |
| Client Agency* contact person | Name |  |  |  |
|  | Position |  |  |  |
|  | Tel |  | Mobile |  |
|  | Email |  |  |  |

* For multiple agencies insert extra rows.

### Reporting Period

| This report to be delivered in 1st week Feb, May, Aug, Nov & as required in guidelines below |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Report Date (date at end of reporting period) | / /20 . |  |  | Percentage of total contract completed (at the Report Date) |  |  |  |  |  |  | % |  |
| Report Period ending |  | Feb |  | May |  |  | Aug |  | Nov |  |  | Special |
| Report Reason |  | 3 monthly |  |  |  |  | Unsatisfactory performance |  |  |  |  |  |
|  |  | Completion |  |  |  |  | Termination |  |  |  |  |  |
| ### 100% completion CPR is to cover the entire contract |  |  |  |  |  | ### (To check box: copy  and paste over ) |  |  |  |  |  |  |

### Cost

| Contract Price as Varied | $ |  |  |
| --- | --- | --- | --- |
| Predicted Final Contract Price | $ | Actual Final Contract Price | $ |
| Predicted Liquidated damages | $ | Actual Liquidated damages | $ |

### Time

| Total extensions of time approved | days | Extended Contractual Completion Date | / /20 . |
| --- | --- | --- | --- |
| Predicted Date for Completion | / /20 . | Actual Date of Completion | / /20 . |

Contractor Performance Report

| Contract No: |  |
| --- | --- |

Contractor’s Performance

CPR reports must be completed with reference to Section 5. CPR Criteria Assessment Guidelines

|  | #### Evaluation Criteria | N/A |  |  |  |  | Unsat |  |  | Marginal |  |  |  | Acceptable |  |  |  |  | Good |  |  | Superior |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Time Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Standard of Work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Quality Mgmt Systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Contractor’s Personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Subcontractor Mgmt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Contract Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Co-operative Relations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Work Health and Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Industrial Relations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Environmental Mgmt |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Contractor’s Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Aboriginal Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Overall Comments on Performance

| In my opinion: |  |  |
| --- | --- | --- |
| I have attached further information  |  |  |

Compliance with Code of Practice for Procurement

|  | No indication of a breach was identified |  | Evidence of a breach was identified |
| --- | --- | --- | --- |
|  |  | (Attach details) |  |
| In my opinion: |  |  |  |

Consultation with Contractor

| I confirm that I have consulted with the Contractor in the preparation of this report and that a copy of this completed report was sent to the Contractor on ……/ …… / 20.…… |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| The Contractor has advised that this report is: |  |  | Accepted |  | Not Accepted |  |
| Where the Contractor has not responded within 10 days, the report is to be deemed as accepted |  |  |  |  |  |  |
|  | When the Contractor and Reporting Officer are unable to resolve a disagreement as to the content of this report, the report is to be forwarded to the Contract Executive (for resolution). Please refer to details in the guidelines below. |  |  |  |  |  |

Contractor Performance Report

| Contract No: |  |
| --- | --- |

Industry Data

Note: This information is primarily recorded to give feedback for the NSW Government Procurement System for Construction.  It will not be directly utilised with respect to tender opportunities for particular Contractors.

|  | Aboriginal Participation information Number of Aboriginal workers who have worked on site for more than one week to date (including Contractors and Subcontractors). Cumulative working-hours for Aboriginal workers on site to date (including Contractors and Subcontractors). Cumulative working-hours for all workers both Aboriginal and non-Aboriginal on site to date (including Contractors and Subcontractors). |  |
| --- | --- | --- |
|  | Issues elevated beyond Authorised Person |  |  |  |  |  |  |  |  |
|  | Claim Reference Number* |  | Name or brief description of Issue |  |  | Total claimed value ($) | Resolved | If resolved: Total settlement value ($) |  |
|  |  |  |  |  |  | $ | Yes/No | $ |  |
|  |  |  |  |  |  | $ | Yes/No | $ |  |

* For more Issues insert extra rows.

Usage of Photographs

I confirm that any photos which I have emailed to the CPR Image Library abc@gmail.com have been taken by myself. I agree to allow full rights for their use by NSW Government.

Signature Block - Reporting Officer

|  | URGENCY OF REPORT This original CPR report should be completed and delivered to the Department of Finance & Services, at abc@gmail.com or the postal address indicated below, to arrive in the first week of Feb/May/Aug/Nov (depending on the reporting period, or otherwise when required by section 3.3 of the Performance Management System Guidelines). Your prompt submission of this report is essential to assist NSW Government Agencies to make procurement decisions based on the most up-to-date information. This may influence matters such as the offering of tendering opportunities; award of contracts; assessment of Prequalification and/or Best Practice accreditation status and the review of common performance issues extending to other projects. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  The CPR Criteria Assessment Guidelines (Section 5) were used in preparing this CPR |  |  |  |  |  |  |  |  |  |  |  |
| Comment on the usefulness of the CPR Criteria Assessment Guidelines: ……………………. |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  | Signature |  |  |  |  | / /20.… |  |
| Title |  |  |  |  | Organisation Name: |  |  |  |  |  |  |
| Email |  |  |  |  | Telephone |  |  | Mobile |  |  |  |

- Contractor Performance Report

|  | Contract No: |  |
| --- | --- | --- |

## Contract Executive Comments

#### Guidance notes

- This portion of the report is required to be completed by the Contract Executive when there is disagreement between the Contractor and the Reporting Officer

- The Reporting Officer must not use this page of the CPR form

- If there is disagreement between the Contractor and the Reporting Officer as to the content of the CPR Report, the Contract Executive is to assess the report and the supporting evidence and is to communicate with both parties to determine the performance.

Contract Executive’s Comments

| In my opinion: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| I have attached further information |  |  | Yes |  | No |  |

Signature Block – Contract Executive

|  | URGENCY OF REPORT This original CPR report should be completed and delivered to the Department of Finance & Services, at abc@gmaol.com or the postal address indicated below. Your prompt submission of this report is essential to assist NSW Government Agencies to make procurement decisions based on the most up-to-date information. This may influence matters such as the offering of tendering opportunities; award of contracts; assessment of Prequalification and/or Best Practice accreditation status and the review of common performance issues extending to other projects. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name |  |  |  |  | Signature |  |  |  |  | / /20.… |  |
| Title |  |  |  |  | Organisation Name: |  |  |  |  |  |  |
| Email |  |  |  |  | Telephone |  |  | Mobile |  |  |  |

Submit report to:

| Submit report to: |  | Senior Manager Department of Finance & Services Construction Category Management Unit Level 10W, McKell Building 2-24 Rawson Place Sydney NSW 2000 - Facsimile: (01) 2345 6789 - Email: abc@gmail.com |  |
| --- | --- | --- | --- |

## 1. Contractor Performance Reporting (CPR) System Guidelines

Objective of Performance Reporting

The objectives of performance reporting are to:

- encourage Contractors and consultants to implement a business culture of continuous improvement to benefit themselves and their clients;

- provide the Department of Finance & Services with performance data from past and current contracts to identify the best performing Contractors and consultants;

- ensure that the best performing prequalified Contractors and consultants are offered more tendering opportunities than other Contractors;

- share information with other NSW Government agencies on Contractor and consultant performance on current and past contracts; and

- facilitate the development of a more complete understanding of project procurement by identifying opportunities for improving future project stakeholder relationships and management practices.

CPR is not to be confused with or replaced by the Performance Measurement Systems of other organisations and is not to be confused with the GC21 Performance Evaluation Form (which is a team based system of “self-measurement” and “self-improvement”). Refer to Procurement Practice Guide: GC21 meetings and workshops for clarification (see References).

Informing Contractors

- Procurement Practice Guide: Performance Management provides guidance to performance reporting on construction Contractors and all categories of consultants.

- The system of reporting including this document should be conveyed to Contractors at, or prior to, the first contract meeting.

When Reports are Required

- For all contracts valued at $0.5M or more, CPR Reports are required:

- in the first week of February, May, August and November;

- at Completion for Minor Works and GC21 contracts;

- whenever a critical aspect of performance is unsatisfactory, for example if:

- a management system (WHS, environmental or quality) audit reports unsatisfactory performance; or

- the Contractor fails, within the time specified, to make good defects discovered after Completion; or

- at termination of a contract [if occurring].

- For contracts valued less than $0.5M, CPR Reports are required whenever a critical aspect of performance is unsatisfactory.

- Note that a CPR Report is not mandatory in the first 2 months of the contract (unless unsatisfactory performance is recorded on any item in which case a full report on all criteria is to be completed).

Completing CPRs

- Note that clarity, completeness and timely response in submitting CPR Reports are evaluation criteria for Project Manager Performance Reports.

## 2. Performance Scoring Methodology

- The performance scoring methodology is provided to enable Contractors to understand the influence of gradings on overall performance scores including the potential to influence ranking (refer to ranking below).

- The Reporting Officer is not required to calculate CPR scores.

- Completed CPR Reports on a Contractor include assessed criteria from which a performance score is generated. The approach to generate the score is outlined below

#### Definition and Relative Weighting of Gradings

| - Grading | - Definition | - Rating* |
| --- | --- | --- |
| - Superior | - Standard well above the acceptable standard of performance | - 10 |
| - Good | - Standard often exceeds the acceptable standard of performance | - 7 |
| - Acceptable | - Meets the acceptable standard of performance | - 5 |
| - Marginal | - Mostly meets the acceptable standard of performance but has some weakness. | - 3 |
| - Unsatisfactory | - Well below the acceptable standard of performance | - 0 |

- The CPR performance score for a report on a Contractor on a contract is based on the weighted ratings from the report.

#### Example 1: Weighted Performance from a report

| - Evaluation Criteria | - Weight - (a) |  | - Grading | - Rating - (b) | - Weighted Rating - (a) x (b) | - Max. possible weighted rating - (a) x 10 |
| --- | --- | --- | --- | --- | --- | --- |
| - Time Management | - 5 |  | - Good | - 7 | - 35 | - 50 |
| - Standard of Work | - 5 |  | - Acceptable | - 5 | - 25 | - 50 |
| - Quality Mgmt Systems | - 2 |  | - Acceptable | - 5 | - 10 | - 20 |
| - Contractor’s Personnel | - 3 |  | - Good | - 7 | - 21 | - 30 |
| - Subcontractor Mgmt | - 3 |  | - Good | - 7 | - 21 | - 30 |
| - Contract Admin | - 3 |  | - Good | - 7 | - 21 | - 30 |
| - Co-operative Relations | - 3 |  | - Good | - 7 | - 21 | - 30 |
| - WHS | - 5 |  | - Acceptable | - 5 | - 25 | - 50 |
| - Industrial Relations | - 3 |  | - Good | - 7 | - 21 | - 30 |
| - Environmental Mgmt | - 4 |  | - Good | - 7 | - 28 | - 40 |
| - Training Management | - 3 |  | - Good | - 7 | - 21 | - 30 |
| - Contractor’s Design | - 3 |  | - Good | - 7 | - 21 | - 30 |
| - Aboriginal Participation | - 5 |  | - Good | - 7 | - 35 | - 50 |
|  |  |  | - Totals |  | - 305 (c) | - 470 (d) |
|  |  |  | - CPR score = 100 x (c)/(d) = 100 x (305/470) = 64.9% |  |  |  |

- The final performance score for a Contractor on a contract is based on the average of all CPR Reports for that contract. The completion report is given additional importance and this is reflected by being considered as equivalent to 2 reports for the same contract.

#### Example 2

- Demonstrating the overall scoring of a Contractor for a contract:

- First CPR = 55%,

- Second CPR = 55%,

- Third CPR = 60% ,

- Completion CPR = 65%

- CPR score for whole project = (55 + 55 + 60 + 65 x 2) / 5 = 60%

Performance Ranking

Prequalified Contractors are ranked based on recent performance scores. Ranking may be used to differentiate the higher performing Contractors from those with lesser performance or those with no recent performance history.  Ranked lists are used by the Department of Finance & Services in the selective tendering process to guide Tenderer Selection Committees when making decisions in the selection of Contractors to be offered opportunities to tender on future work.

Ranking is subject to ongoing change as new CPR Reports are received and as older reports are discarded from consideration. Reports which are within two (2) years of the specified reporting period are considered for ranking purposes.

Definitions used in Contractor Performance Report

#### Client Agency

The government agency funding the project, or the agency that will own the completed facility and/or will operate the facility when completed.

#### Client Agency contact person

The senior member of staff of the Client agency with executive responsibility for the project during construction.

#### Completion

Completion in the case of GC21 contracts and Minor Works contracts.

#### Contract Executive

A senior person within the Reporting Officer’s organisation with executive responsibility for the delivery of the project. This may be the Senior Executive (or equivalent) on the Contract or the Regional Procurement Adviser.

#### Contractor’s Representative

The direct employee of the Contractor’s organisation with responsibility for the project.

#### Date of Contract

Date of Contract for GC21 contracts; and Date of Acceptance of Tender for Minor Works contracts.

#### Extended Contractual Completion Date

Extended Contractual Completion Date for GC21 contracts; the extended Completion date in the case of Minor Works contracts.

#### Original Date for Completion

The original date for Completion at the Date of Contract.

#### Reporting Officer

The Principal’s authorised person for GC21 contracts; and Principal’s Representative for Minor Works based contracts.  (This may be a Private Sector project manager.)

## 3. Industry Data

Apart from being an instrument for maintaining Contractor Performance data, the CPR provides an opportunity for the Department of Finance & Services to monitor industry trends and related data. Whilst derived from specific contracts, such information will not be directly utilised with respect to tender opportunities for particular Contractors. The data is valuable to the Department of Finance & Services in maintaining a contemporary suite of contracts and contract management guides and in providing industry-wide key performance indicators.

### Aboriginal Participation Information

Data is required on the number of Aboriginal persons given the opportunity to work on Government construction projects. Aboriginal persons working more than 1 week (continuous or non-continuous) on the project should be counted. The number of working-hours worked by Aboriginal workers can be compared with the total number of working -hours worked by all workers on the site to give a percentage of Aboriginal participation. This information is useful for the NSW Government to measure the success of strategies to encourage Aboriginal Participation in construction. The percentage of Aboriginal Participation on the Contract does not directly affect the Contractor’s CPR score. It is the Contractor’s performance against its tendered commitments to Aboriginal Participation and/or against its requirements under the Contract in relation to Aboriginal Participation that are reflected in the CPR score.

### Issues elevated

The number of Issues elevated does not affect the Contractor’s CPR score. The information is valuable to the Department of Finance & Services in maintaining a contemporary suite of contracts and contract management guides. Therefore, where Issues have occurred on the Contract, follow up questions may be asked, such as the Contract clause numbers relevant to the Issue.

## 4. Steps for completing a Contractor Performance Report (CPR)

### Access and use of blank CPR Reports

- Use the latest version of this CPR Report.  Electronic copies are available on the Internet (see References):

- All CPR Reports are to be completed electronically whenever possible.  Otherwise, all responses are to be typed or handwritten in block letters so as to minimise risk of misinterpretation of comments and to promote focused communications.

- Please note when completing this form that there are 2 types of Check boxes used:

- large “table based” check box: insert a tick or a cross while retaining the “box”;

- small “symbol based” check box: is replaced by: “”

### Reporting Officer’s responsibilities

- Meet face to face with the Contractor’s Representative to discuss the Contractor’s performance.

- Welcome and encourage proactive communications with the Contractor’s Representative in promoting the scheduling of meetings to meet CPR reporting requirements.

- Discuss the Contractor’s performance with the Contractor’s Representative including each criteria item and the reasons for any differences in views on performance.

- Consult with the Contractor’s representative and attempt to reach an agreement on the rating of each criterion in a manner that accurately reflects performance on the contract.

- Complete the CPR in consultation with the Contractor’s Representative and preferably during the face-to-face meeting.

- Provide the Contract Details including the full identification of all contact persons.

- Grade the Contractor’s performance for each criterion.

- Tick boxes in NA (not applicable) column of matrix when it is too early in the project to assess Performance Evaluation Criteria, or, when the criteria do not apply to the specific contract.

- Tick all applicable Performance Evaluation Criteria boxes.  Nominate only one grading against each evaluation criteria after taking into account matters beyond the Contractor’s reasonable control.

- Complete the Reporting Officer’s overall comments portion of the CPR report. Ensure that aspects of Unsatisfactory and Marginal performance are clearly described. Aspects of Superior, Good and Acceptable performance are also to be noted especially when any contentious issues are likely to arise.  Please ensure that comments are congruent with the ratings given for each criterion. Additional detailed comments and information may be attached.

- Advise whether further information has been attached.

- Complete the assessment of compliance with the Code for Procurement.

- Insert date when a copy of the CPR report was sent to the Contractor.

- Sign the CPR report.

- Provide contact details in full.

### Report Attachments

- Attachments to CPR Reports are encouraged to clarify any key issues related to performance. Attachments may consist of type written text including extracts of relevant documents and correspondences.

### Photos of Project Status and work in progress

- If provided, photographic images illustrating progress on the site are to be Emailed as JPEG or TIF files to the Department of Finance & Services at

### Report copied to the Contractor and the Department of Finance & Services

- The Reporting Officer is to provide a copy of the completed report to the Contractor for review. The areas to be completed include:

- Page one in it’s entirety

- Page two (with the exclusion of the check boxes on the Contractor’s advice on acceptance)

- The Reporting Officer is also to provide the completed report to the Department of Finance & Services at the address shown below.

### Contractor’s disagreement with the Report

- If the Contractor disagrees, the Contractor should within 21 days of the date of the report, discuss any areas of concern with the Reporting Officer and try to resolve any disagreement that arises regarding the CPR report.

- Following an unsuccessful attempt to resolve a disagreement, the Contractor may within a further 14 days, elect to raise the matter to the Contract Executive for resolution. The Contractor is to request the Reporting Officer to advise the Contract Executive of the disagreement.

### The Contract Executive’s responsibilities

- If the Contractor disagrees with the CPR report, the disagreement is to be resolved by the Contractor referring the report, with written reasons for the disagreement, to the Contract Executive.

- The Contract Executive is required to meet with the Contractor and the Reporting Officer to consider the report and reasons, decide on the disagreement, recommend changes, if necessary, to the report and forward any amended report to the Manager, Supplier Management Systems, at the address given below.

- The disagreement is to be resolved at the earliest opportunity and preferably within 21 calendar days of the Contractor’s contact with the Contract Executive.

- Following the assessment of the matters raised by the Contractor, the Contract Executive is to determine the Contractor’s performance on the contract.

- Additional detailed comments, information and all correspondence are to be included with the CPR report in the form of attachments.

- The Contract Executive is to sign the Contract Executive’s section of the report.

- The Contract Executive is to provide contact details in full.

### Submission of the completed report

- Submit the completed CPR Report including all attachments to:

Senior Manager Department of Finance & Services Construction Category Management Unit Level 10W, McKell Building 2-24 Rawson Place Sydney NSW 2000 Facsimile: Email:

## 5. CPR Criteria Assessment Guidelines

The assessment of Contractor performance is supported by the following CPR Criteria Assessment Guidelines. The guidelines have been developed to enhance accuracy, consistency, clarity, objectivity and transparency in the assessment process.

CPR Criteria Assessment Guidelines are required to be used for the February 2012 reporting period and onwards for all Contractor Performance Reports.

Note that the CPR Criteria Assessment Guidelines are NOT required to be marked up or submitted with a completed CPR Report.

Instructions for Evaluation

For each performance criterion:

- Consider whether the Contractor’s performance during the reporting period was Acceptable based on the sub-criteria shown in the following table. If a sub-criterion is not applicable to the contract, or does not apply during the reporting period, do not take it into account in assessing whether performance is acceptable. Mark ‘N/A’ in the Acceptable column.

- If the Contractor’s performance was Acceptable for all sub-criteria, consider whether it met the criteria for a Good grading.

- If so, consider whether a Superior grading applies.

- If the Contractor’s performance during the reporting period did NOT meet all the requirements for an Acceptable grading, it will be graded Marginal at best.

- Consider whether an Unsatisfactory grading is applicable, based on the sub-criteria shown.

Principles for Evaluation

Note the following principles underlying the evaluation framework:

- Reports are to be delivered to the Department on a quarterly basis in the first week of February, May, August and November.

- The ‘reporting period’ is the period for which the Contractor Performance Report is applicable. For the ‘3 monthly’ report the period covers the 3 months prior to the ‘Report Date’.

- Except for the CPR prepared at completion of construction, all gradings apply to performance DURING the reporting period.

- Acceptable performance complies with contract requirements.

- For an Acceptable, Good or Superior gradings, EVERY ONE of the sub-criteria must be met.

- A Marginal or Unsatisfactory grading is given if ANY ONE of the sub-criteria applies.

| Unsatisfactory | Marginal | Acceptable | Good | Superior |
| --- | --- | --- | --- | --- |
| ANY ONE of the following occurred: | ANY ONE of the following applied | ALL of the following applied | In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied: | In addition to the requirements for a ‘Good’ grading ALL of the following applied: |
| #### Time Management |  |  |  |  |
| - The required program has not been submitted - The program was not updated within 10 business days after a request from the Principal - Work is not meeting scheduled progress AND it is unlikely that completion will be achieved by the approved completion date(s) - There was little or no activity on site in the last two weeks & the Contractor has not provided a reasonable explanation - The Contractor made no attempt to manage delays to mitigate their effects | - The Contractor failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | - The program (including any updates submitted during the period) met contract requirements - The Contractor reviewed progress regularly, rescheduled work activities to meet the program and updated the program - Updated programs were submitted within the time specified or requested - Any updated programs accurately reflected actual progress - Work was managed in accordance with the program | - The program (including any updates submitted during the period) met all contract requirements, including showing when action is required by the Principal - The Contractor submitted program updates when any milestone completion date changed, without waiting for a request from the Principal - Updated programs provided early warning of potential delays (if applicable) - The program(s) consistently demonstrated that approved completion date(s) would be met - The Contractor allocated resources based on project needs - The Contractor mitigated the effects of delays by rescheduling & reallocating resources | - The Contractor strictly adhered to the program, updating & resubmitting it whenever the sequencing of tasks changed - The Contractor made outstanding efforts to maintain progress & avoid delays - The Contractor mitigated the effects of anticipated delays by rescheduling & reallocating resources |
| #### Standard of Work |  |  |  |  |
| - There was no evidence that the Contractor has a system for identifying & rectifying defects; the Contractor relied on the Principal to identify defects - At every site inspection the Principal identified defects that were not being addressed - The number of defects continued to increase as work progressed, with many outstanding for more than a month - The Contractor refused to acknowledge & rectify defects identified by the Principal | - The Contractor failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | - The Contractor adhered to contract specifications - The Contractor consistently identified & rectified defects progressively as work proceeded - Whenever inspected, the work had only a few minor defects & rectifying them did not affect the progress of the work - The Contractor rectified defects identified by the Principal within the agreed timetable for rectification (unless prevented by circumstances beyond the Contractor’s control) | - The Contractor achieved better than specified tolerances & consistent high standards of workmanship - The Contractor provided detailed records of defect identification & rectification - The Contractor rectified defects identified by the Principal within 10 working days (unless prevented by circumstances beyond the Contractor’s control) | - The Contractor demonstrated that it considered defects to be unacceptable - During inspections, the Principal did not identify any defects that were not already being actioned - Defect-free Completion was achieved (or appears likely to be achieved) by the approved completion date(s) |
| #### Quality Management System |  |  |  |  |
| - The Contractor submitted a QMP that failed to meet many of the requirements in Appendix D of the Guidelines & required major amendments & additions - Work commenced on an activity before the required ITP was submitted - The work was not ready for inspection at the notified time & as a result, the Principal had to re-visit the site - Overall audit assessment was Unsatisfactory, OR - Overall audit assessment was Marginal & the Contractor did not address all non-conformances - The Contractor did not carry out its own inspections & audits but relied on the Principal to identify non-conformances - The same non-conformance occurred two or more times | - The Contractor failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | - The QMP complied with Appendix D of the Guidelines. - The Contractor implemented the QMP - All ITPs were submitted on time - ITPs & checklists were used while activities were being carried out - Work was ready for inspection at notified times for witness points and hold points - If a 2nd or 3rd party quality audit was carried out, the overall audit assessment was Acceptable & the Contractor addressed all non-conformances - The Contractor carried out its own site quality audits & regular inspections and provided evidence, within 14 days after the date of the audit, of both the immediate response and any system improvements proposed to close out all audit non-conformances - The Contractor’s quality system identified & dealt with most non-conformances without the Principal’s input | - The Contractor provided an internal audit schedule early in the contract period, updated it as necessary & adhered to the dates stated - If a 2nd or 3rd party quality audit was carried out, the overall audit assessment was Good and the Contractor addressed all non-conformances within 14 days | - If a 2nd or 3rd party quality audit was carried out, the overall audit assessment was Superior & no non-conformances were identified - The Contractor demonstrated a quality-oriented culture through routine involvement by senior managers in quality management on site, independent of any request from the Principal |
| #### Contractor’s Personnel |  |  |  |  |
| - Key personnel were not appropriately skilled - There was no supervisor on site and the Principal had to deal directly with workers on more than two (2) occasions - There were insufficient resources to manage the work - On more than one occasion, the Principal found it difficult to contact appropriate personnel to discuss matters of concern - Personnel were unfamiliar with the contract & rarely referred to it - The Contractor submitted RFIs when the information was in the contract; more than 3 times, the Principal’s responses simply identified relevant contract requirements - Site rules and procedures have not been established - Workers provided statutory evidence of not being paid | - The Contractor failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | - All personnel had appropriate skills for their tasks - The Contractor’s personnel ensured that workers followed contract requirements, with minimal intervention required from the Principal - The level of resources was adequate for the work activities - The Contractor established & maintained effective lines of communication with the Principal, minimising delays & re-work - Key management personnel showed a good knowledge of contract requirements & followed specified procedures on most occasions - Site rules and procedures were established, together with measures to ensure they were followed - The Contractor did not rely on the Principal’s expertise to inspect & verify specialist work - There was an appropriately skilled supervisor on site at all times | - All the Contractor’s personnel demonstrated knowledge and understanding of the parts of the contract relevant to their areas of responsibility requiring no intervention from the Principal - Site rules and procedures were in place & were followed without exception - The Contractor arranged for appropriate experts to inspect & verify specialist work, where the Contractor did not have the necessary expertise | - All the Contractor’s personnel demonstrated superior skills, more than adequate experience and a high level of professional courtesy when dealing with the Principal and the Client - The contract & the site were exceptionally well managed & the work proceeded efficiently, without any intervention from the Principal |
| #### Subcontractor Management |  |  |  |  |
| - Subcontractors & consultants were not competent to undertake the work, causing re-work & delays - There was no supervisor on site and the Principal had to deal directly with Subcontractors on more than two (2) occasions - The Contractor entered into subcontracts that did not include the specified provisions (eg for payment, dispute resolution, insurance) - The Contractor relied on the Principal to review documents prepared by Subcontractors - Poor Subcontractor coordination/ supervision caused delays or significant re-work or poor quality completed work - The quality systems of Subcontractors & the Contractor were inconsistent, causing poor work quality - Subcontractor(s) were unaware of the WHS, environmental, IR, Aboriginal participation & training objectives in the contract - A Subcontractor provided statutory evidence of not being paid entitlements | - The Contractor failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | - All Subcontractors & consultants were suitably competent & experienced - All subcontracts reviewed by the Principal included the required provisions - Design & fabrication activities were well managed, with minimal non-conformances required to be resolved by the Principal except for faults in the Principal’s documents - The quality systems of the Subcontractors & the Contractor were integrated to achieve satisfactory work quality - Subcontractor coordination issues caused only minor re-work, with no impact on contract time or the quality of the completed work - The Contractor reviewed all claims from Subcontractors & established that there was an entitlement & that the amounts claimed were reasonable before passing them on to the Principal - The Contractor ensured that Subcontractors complied with the WHS, environmental, IR, Aboriginal participation & training objectives | - All activities carried out by Subcontractors were well managed, with no coordination problems apparent to the Principal - The quality, safety and environmental management systems of the Contractor & all Subcontractors were seamlessly integrated - The Contractor ensured all Subcontractor claims were reviewed by people with relevant expertise; those passed on to the Principal were presented clearly & included all information required for assessment - Subcontractors demonstrated commitment to the quality, WHS, environmental, IR, Aboriginal participation & training objectives in the contract | - All subcontracts reviewed included ‘back to back’ provisions with those in the contract - Subcontractor relationships were exceptionally harmonious & the Principal observed an open collaborative relationship and communication between Subcontractors, consultants & the Contractor |
| #### Contract Administration |  |  |  |  |
| - The Contractor did not notify a change to its authorised person for more than 2 days after the change occurred - Key contact personnel were changed without notifying the Principal - More than 2 RFIs notifying ambiguities were submitted too late to avoid delays - More than 2 claims for price or time adjustments were submitted more than a month after the related work was completed - More than 2 claims for adjustment did not include the required information, eg: - correct identification of the entitlement - updated program - evidence of costs - More than one payment claim did not include all the required information, including records of compliance - More than one progress report was received late or did not provide the required information | - The Contractor failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | - The Contractor advised changes in contract personnel before they occurred (on the day they occurred if unforeseeable) - The Contractor provided proposals for variations by the specified time - 80% of RFIs notifying ambiguities were submitted within the specified time - The Contractor gave all notices (eg for adverse Site Conditions) within the specified times - All claims for adjustments were submitted by the specified times, identified the entitlement (by reference to applicable contract provisions) & included relevant information - Payment claims were made in accordance with the contract, supported by the required information - The Contractor provided the required compliance documents on time, with only minor omissions that were readily corrected - Progress reports included adequate information & were received on time | - The Contractor consistently provided proposals for variations before the specified time - All RFIs notifying ambiguities were submitted within the specified time - Claims for adjustments were submitted within the specified time, correctly identified the source of the entitlement & included all the information required for assessment - Payment claims did not include claims for adjustments that had not been agreed | - The Contractor did not submit any documentation later than the specified time - The Principal has not requested the Contractor to provide any additional information for any claim, including payment claims - All compliance documents were accurate & correct & none required amendment or resubmission |
| #### Co-operative Relationships |  |  |  |  |
| - The Contractor demonstrated an adversarial approach & was unwilling to cooperate or communicate openly - The Contractor communicated only at specified meetings & through formal RFIs & claims - The Contractor cancelled or deferred more than 2 scheduled meetings without a reasonable explanation OR refused to attend for sufficient time to discuss critical matters - The Contractor refused to comply with a direction of the Principal, including: - refusing to remove a person from the site when instructed, due to their inappropriate behaviour - The Contractor’s senior executive refused to meet to discuss formal issues OR was unavailable to meet within the specified time without good reason - More than one payment claim was more than 20% above the value of work assessed by the Principal - 50% or more of the Contractor’s claims for adjustment were more than 25% above an independent estimate - For more than one claim for adjustment, the Contractor refused to provide additional justification OR refused to participate in negotiations - The Contractor initiated court action before specified issue resolution processes were implemented | - The Contractor failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | - The Contractor cooperated in all matters relating to the contract, eg accommodating the needs of the Principal, including those occupying the site - The Contractor acted within 1 day after any request to remove from the site a person who behaved inappropriately - Communication between Contractor & Principal was open & effective - The Contractor gave early warning of events significantly affecting the contract & worked with the Principal to achieve resolution - All payment claims were discussed with the Principal and a reasonable value agreed for the completed work - 80% of claims for adjustment were approved within 10% of the initial claim - The Contractor demonstrated commitment to informal dispute resolution processes, including a willingness of the senior executive to meet promptly to resolve issues | - The Contractor notified the Principal as soon as practicable, of all events that could affect the contract or the work & worked with the Principal to resolve the matter with minimal effects on contract time & price - All payment claims were reasonable & were paid in full - All claims for price & time adjustments were reasonable; 90% were paid in full, as initially claimed, AND agreement was reached on the quantum of the remainder by negotiation within 3 months after receipt - The Contractor’s senior executive took a pro-active approach to preventing formal issues from arising, including attending meetings as necessary & maintaining a good relationship with the Principal’s senior executive - The Contractor showed commitment to informal dispute resolution processes; all issues & disputes were resolved within 3 months | - The Contractor’s cooperation with the Principal & the Client has been outstanding & the Client has not notified the Principal of a single complaint - The Contractor managed the work, including all changes & delays, to minimise additional costs to the Client - The Contractor’s senior executive showed exemplary leadership by: - attending start up workshop and close out workshop (if applicable) - attending sufficient monitoring & contract administration meetings to maintain a good working relationship, - regularly visiting the site - maintaining frequent contact with the Principal’s senior executive, & - initiating discussions to resolve emerging issues |
| #### Work Health and Safety (WHS) |  |  |  |  |
| - Site work started before the WHS Management Plan was submitted - The Contractor submitted an WHS Management Plan with major omissions &/ or without site-specific risks or late - The Contractor failed to comply with WHS regulations - 2nd party site reviews identified a breach that put workers at serious risk - 2nd or 3rd party audit reports &/or reviews showed major non-conformance(s) - The Contractor did not carry out its own audits & site safety reviews but relied on the Principal to identify non-conformances - A notifiable WHS incident occurred - A Prohibition Notice was imposed by regulatory authorities - WHS monthly reports were not provided | - The Contractor submitted an WHS Management Plan with a few omissions that were readily rectified without causing delays - 2nd party site reviews showed minor breaches - 2nd or 3rd party audit reports showed minor non-conformances - WHS monthly reports were submitted late &/or included incomplete information - An WHS incident was not reported to the Principal within 24 hrs after it occurred - An Improvement Notice was issued by a regulatory authority | - The WHS Management Plan met all contract requirements - WHS management complied with the contract, including the relevant NSW Government Management Systems guidelines & legislative requirements - The site was kept clean & tidy & free of uncontrolled safety hazards - No non-conformances were identified during 2nd party site reviews - If a 2nd or 3rd party WHS audit was carried out the audit report showed satisfactory performance - There was no notifiable incident - WHS monthly reports were submitted on time & met contract requirements | - There has been no lost time injury - The Contractor demonstrated commitment to the highest WHS standards & the safety of everyone on the site - The Contractor implemented a regular internal review process - The Contractor’s project manager regularly conducts safety walks and was involved in safety events such as tool box talks, safety meetings | The Contractor has demonstrated safety leadership through: - adopting a partnering approach with clients, Subcontractors & WorkCover - the Contractor’s executive involvement in safety management on site - 2nd or 3rd party audits were conducted and there were no non-conformances identified - comprehensive WHS management reporting demonstrating a safety culture (nil harm) |
| #### Industrial Relations |  |  |  |  |
| - The Contractor has not submitted the required IR information / IR Plan - The Contractor submitted IR information / an IR Plan with major omissions OR that did not comply when resubmitted after the Principal’s review - The Contractor did not comply with the IR Plan (if applicable) - The Contractor breached the Code of Practice for Procurement or the National Code of Practice (where applicable) - Non-compliance with employment law obligations was identified (including a non-compliance by a Subcontractor) - An IR incident, which could have been avoided if the Contractor had taken reasonable, timely action, caused delays | - The Contractor failed to meet one of the criteria required for an ‘Acceptable’ grading - A minor IR incident occurred, which could have been avoided if the Contractor had taken reasonable, timely action | - The required IR information / IR Plan was submitted on time - The IR information / IR Plan complied with the contract, including the IR Management Guidelines - The Contractor complied with the IR Plan (if required by the contract) & legal IR obligations - The Contractor maintained a cooperative workplace environment - The Contractor identified & resolved any IR issues within the Contractor’s control | - The Contractor promptly identified & resolved any IR issues, minimising delays to the work - The Contractor demonstrated an understanding & took practical steps towards building a productive workplace culture with cooperative relations, effective communication & consultation - No non-conformances were identified during 2nd and 3rd party audits (if applicable) | - There have been no industrial relations issues - The Contractor has demonstrated leadership in industrial relations management through: - Senior management involvement on site for IR matters - a productive workplace culture with cooperative relations, effective communication and consultation - implementing a documented IR Management System demonstrating innovative functions & capability - maintaining a strong internal review process |
| #### Environmental Management |  |  |  |  |
| - The EMP was submitted late - The Contractor submitted an EMP with major omissions &/ or without site-specific risks - The Contractor failed to comply with environmental regulations - The Contractor did not carry out its own inspections & audits but relied on the Principal to identify non-conformances - Site reviews identified non-conformances with potential for regulatory intervention or Penalty Infringement Notices - 2nd or 3rd party audit reports &/or reviews showed major non-conformance(s) - A serious pollution incident occurred - A Penalty Infringement Notice was imposed by regulatory authorities - Monthly reports were not provided (if required) | - The Contractor submitted an EMP with a few omissions that were readily rectified without causing delays - 2nd party site reviews showed minor infringements & /or room for improvements - 2nd or 3rd party audit reports showed minor non conformances - Monthly reports were submitted late &/or included incomplete information | - The EMP met the requirements of the contract - The Contractor complied fully with the EMP & legislative requirements - The site was kept clean & tidy, with appropriate environmental controls, regularly maintained - No non-conformances were identified during 2nd party site reviews - If a 2nd or 3rd party Environmental audit was carried out the audit report showed satisfactory performance - There was no notifiable environmental incident - Monthly reports (if required) were provided on time & met contract requirements | - There have been no environmental incidents - The Contractor demonstrated an understanding & took practical steps towards sustainability - The Contractor implemented a regular internal review process - The Contractor’s project manager regularly conducts environmental inspections and was involved in increasing environmental awareness through tool box talks and meetings | - The Contractor has demonstrated leadership in environmental management through: - a clear commitment to reaching new goals for environmental practices - achieving new levels of sustainability - senior management involvement in environmental matters on site - implementing innovative environmental controls - comprehensive environmental management reporting demonstrating an environmentally aware culture - 2nd or 3rd party audits were conducted and did not identify any non-conformances |
| #### Training Management (if required by the contract) |  |  |  |  |
| - The TMP was submitted late - The Contractor submitted a TMP that did not comply with the Guidelines - The TMP was not implemented - By a quarter of the way through the contract: - the training target was not achieved OR - the apprentice target was not achieved - For more than 25% of the part of the reporting period that fell between 25% & 90% completion, the Contractor did not achieve: - the training target OR - the apprentice target - The Contractor did not propose corrective action to remedy its failure to achieve the targets - The Contractor did not implement measures to monitor Subcontractor compliance with training & apprentice targets | - The Contractor submitted a TMP with a few omissions that were rectified without delaying the work - The TMP was not implemented in a consistent or sustained manner - For up to 25% of the part of the reporting period that fell between 25% & 90% completion, the Contractor did not achieve: - the training target OR - the apprentice target was not achieved - The Contractor did not submit specified reports on training - The Contractor did not take corrective action to remedy its failure to achieve the training or apprentice targets - The Contractor did not consistently monitor & assess Subcontractor compliance with training & apprenticeship targets | - The TMP complied with the Guidelines & specific contract requirements - The Contractor implemented the TMP in a consistent & sustained manner - For the part of the reporting period that fell between 25% & 90% completion: - no less than 20% of the total project workforce participated in structured training - apprentices undertook 20% of the trade work involved - The Contractor submitted the specified reports on training targets & outcomes - The Contractor implemented consistent & effective measures to monitor & assess Subcontractor compliance with training & apprentice targets | - The Contractor has established a cooperative relationship with training providers, Subcontractors & employer organisations - The Contractor’s senior management actively supported, training programs - For the part of the reporting period that fell between 25% & 90% completion: - More than 20% of the total project workforce participated in structured training - Apprentices undertook more than 20% of the trade work involved - The Contractor reported regularly on training outcomes & proposed improvements - The Contractor worked with Subcontractors to ensure they prepared & implemented their own effective TMPs | - The Contractor’s achievements in implementing training management initiatives are recognised by the community - For the part of the reporting period that fell between 25% & 90% completion: - More than 25% of the total project workforce participated in structured training - Apprentices undertook more than 25% of the trade work involved - The Subcontractors delivered training & apprenticeship employment exceeding their TMP targets |
| #### Contractor’s Design (if required by the contract) |  |  |  |  |
| - The Contractor’s design was submitted late & delayed the work - The Contractor submitted a design that had major non-compliances with the contract requirements, requiring significant input from the Principal - Revision of the submitted design after review by the Principal delayed the work - User groups were dissatisfied with the Contractor’s consultation process, which did not identify their needs The Contractor’s design did not take into account the identified needs of user groups - Constructability issues in the Contractor’s design required redesign and caused delay during construction - The Contractor did not eliminate or minimise risk in the design, so far as practicable, for those who construct, use, maintain or demolish the structure | - The Contractor failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | - The Contractor’s design was submitted within the specified time - The Contractor’s design was submitted in packages that facilitated review & minimised the risk of delay - The Contractor’s design generally complied with the contract; only minor amendments were required following review by the Principal & these did not delay the work - No part of the Contractor’s design needed to be revised after the Contractor responded to the Principal’s initial review - The Contractor consulted sufficiently with user groups (where required) to ascertain their needs and minimise safety risks, so these groups requested only minor enhancements to the design initially submitted to the Principal - The Contractor provided evidence of the application of the principles of safe design and eliminated or minimised, so far as is reasonably practicable, the risk arising from the design | - The Contractor’s design was submitted in sufficient time to allow for review, comment & revision before it was required for construction - The Contractor engaged in an effective consultation & review process with user groups (where required), ensuring that they were satisfied that the Contractor’s design met the Principal’s design brief and safety risks were eliminated or minimised - The Contractor provided comprehensive documentation to communicate information on hazards and controls to everyone involved in the life cycle of the asset - Innovative design technology e.g BIM was used to ensure: - Constructability - Compliance with the Principal’s design, and - Value for money - Safe design | - The Principal’s review of the design initially submitted by the Contractor identified no amendments necessary for compliance with the contract - The Contractor’s design improved on the Principal’s design, with the agreement of the Principal, for the Client’s benefit (eg providing capital cost savings, operational efficiency or improved safety) - The Contractor showed initiative in identifying key user groups & developing an effective consultation process - User groups were very complimentary about the Contractor’s consultation process |
| #### Aboriginal Participation (if required by the contract) |  |  |  |  |
| - The Contractor made no effort to implement Aboriginal participation - The local Aboriginal community complained about the Contractor’s attitude - The Contractor submitted an Aboriginal Participation Plan that did not propose reasonable strategies or targets - The Contractor did not develop appropriate KPIs to measure Aboriginal participation - The Contractor achieved less than 50% of the proposed/ required targets for Aboriginal participation OR provided less than 50% of the proposed/ required training - The Contractor did not propose any corrective action, despite repeated requests to do so - The Contractor did not report on Aboriginal participation | - The Contractor did not engage with the local Aboriginal community in seeking to develop strategies & meet Aboriginal participation targets - The Contractor submitted an Aboriginal Participation Plan that did not - meet the specific contract requirements OR - propose strategies likely to be effective OR - establish targets likely to be achieved - The Contractor established reasonable KPIs, but did not achieve more than 80% of the target participation levels or provide more than 80% of the proposed training - The Contractor did not implement corrective action to remedy its failure to achieve the targets for Aboriginal participation or training - The measures proposed by the Contractor to retain Aboriginal workers were not effective - The Contractor provided limited reporting, based only on the achievement of KPIs | - The Contractor implemented Aboriginal participation requirements in a culturally sensitive manner - The Aboriginal Participation Plan met specific contract requirements, complied with the Guidelines & proposed reasonable strategies & targets for Aboriginal participation - The Contractor established reasonable KPIs to monitor Aboriginal participation & training - The Contractor achieved at least 90% of its commitments for Aboriginal participation & training OR provided a reasonable explanation & proposed corrective action that is likely to be effective - The Contractor established & implemented measures to retain Aboriginal workers - The Contractor reported against the KPIs & on the outcomes achieved & the measures undertaken to retain Aboriginal workers | - The Contractor established a comprehensive set of KPIs & targets for Aboriginal participation & consistently met or exceeded those targets - The Contractor has established a cooperative relationship with Aboriginal community representatives - The Contractor has established demonstrably effective measures to retain Aboriginal workers & increase Aboriginal participation | - The Contractor always exceeded the targets for Aboriginal participation & training - The Contractor is actively developing more effective measures for increasing Aboriginal participation - The Contractor’s achievements in ensuring Aboriginal participation are recognised by the community - The Contractor is committed to Aboriginal participation & extends implementation of these initiatives to contracts for other Clients when their contracts do not require it |

END OF DOCUMENT