## Index
DASHBOARD
STATUS
GANTT
NOTES
TIMELINE
TASKS
TEAM
LISTS
HOLIDAYS
LABELS
HELP?
3 Projects Completed
PREFERENCES

## Index Calc (hidden)
Index Calculations
| PROJECTS PROGRESS | 3 Projects Completed
| PROJECTS | 6 | TOTAL PROJECTS: 6
| Completed | 3 | Projects
| Pending | 3
| TOTAL ACTIVITIES | 5 | 121 | TOTAL ACTIVITIES: 121
| Index | Activity | Activity Count | Completed
| 1 | Projects | 6 | 3
| 2 | Phases | 12 | 3
| 3 | Milestones | 0 | 0
| 4 | Tasks | 91 | 18
| 5 | Subtasks | 12 | 0
| 6 |  | 0 | 0
| 7 |  | 0 | 0
| 8 |  | 0 | 0
| 9 |  | 0 | 0
| 10 |  | 0 | 0

## Dashboard
Your Company Name |  | Dashboard
Projects Summary
Projects: 6
Phases: 12
Milestones: 0
Tasks: 91
Subtasks: 12
PROJECT NAME 1 | PROJECT NAME 1 - Tasks
Tasks
PROJECTS |  |  |  | TASKS
SNO | PROJECT | STATUS | PROGRESS | ACTIVITIES | COMPLETED | PROGRESS
SNO | LEVEL1 | STATUS LEVEL1 | PROGRESS LEVEL1 | ACTIVITIES | COMPLETED | PROGRESS
1 | PROJECT NAME 1 | Completed | 100% | 14 | 6 | 61.43%
2 | PROJECT NAME 2 | In Progress | 70% | 14 | 0 | 18.57%
3 | PROJECT NAME 3 | Completed | 100% | 14 | 6 | 61.43%
4 | PROJECT NAME 4 | In Progress | 70% | 18 | 1 | 20%
5 | PROJECT NAME 5 | Completed | 100% | 14 | 5 | 57.86%
6 | PROJECT NAME 6 | In Progress | 30% | 17 | 0 | 13.75%
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
H
3 COMPLETED
6 PROJECTS
3 IN PROGRESS
6 COMPLETED
6 IN PROGRESS
14 TOTAL TASKS
78%
61%

## Dashboard Calc (hidden)
Dashboard Calculations
OVERALL SUMMARY
| Level 1 Metrics |  |  |  |  | Total Activities
|  | Projects | 6 | 6 PROJECTS |  | Index | Activity | Count
|  | Completed | 3 | 3 COMPLETED |  | 1 | Projects | 6 | Projects: 6
|  | In Progress | 3 | 3 IN PROGRESS |  | 2 | Phases | 12 | Phases: 12
[6 empty] | 3 | Milestones | 0 | Milestones: 0
| Overall Progress | Completed | Pending |  |  | 4 | Tasks | 91 | Tasks: 91
|  | 78.33% | 21.67% |  |  | 5 | Subtasks | 12 | Subtasks: 12
[6 empty] | 6 |  | 0 | : 0
[6 empty] | 7 |  | 0 | : 0
| User Selection |  |  |  |  | 8 |  | 0 | : 0
| Level 1 | PROJECT NAME 1 | PROJECT NAME 1 | PROJECT NAME 1 |  | 9 |  | 0 | : 0
| Activity | Tasks | Tasks | 4 |  | 10 |  | 0 | : 0
| Activity Metrics | Header | PROJECT NAME 1 - Tasks
| Activities | TOTAL Tasks | 14 | 14 TOTAL TASKS
|  | Completed | 6 | 6 COMPLETED
|  | In Progress | 6 | 6 IN PROGRESS
|  | PROGRESS | 61.43% | 61% PROGRESS
38.57%
|  | TIMELINE | Mandays
| MANDAYS | PLANNED | 204
|  | BASELINE | 237
|  | ACTUAL | 247
| Projects and Progress |  |  | %Progress | #Tasks
|  | 0% | 0% | 0% | 2
|  | 1% | 10% | 1%-10% | 1
|  | 11% | 20% | 11%-20% | 0
|  | 21% | 30% | 21%-30% | 2
|  | 31% | 40% | 31%-40% | 0
|  | 41% | 50% | 41%-50% | 2
|  | 51% | 60% | 51%-60% | 0
|  | 61% | 70% | 61%-70% | 0
|  | 71% | 80% | 71%-80% | 0
|  | 81% | 90% | 81%-90% | 1
|  | 91% | 99% | 91%-99% | 0
|  | 100% | 100% | 100% | 6

## Status
| Your Company Name | [9 empty] | Status Report | [14 empty] | Tasks
| Actual Timelines | [5 empty] | Week Offset |  |  |  | 0 |  | From | 2022-08-22 |  |  | to | 2022-08-28 |  |  |  |  | Projects ¦ Tasks Due This Week & Status
| Actual Timelines | [5 empty] | Month Offset |  |  |  | 0 |  | From | 2022-08-01 |  |  | to | 2022-08-31 |  |  |  |  | Projects ¦ Tasks Due This Month & Status
| Planned Timelines | [5 empty] | Year Offset |  |  |  | 0 |  | From | 2022-01-01 |  |  | to | 2022-12-31 |  |  |  |  | Projects ¦ Tasks Due 2022 Year Calendar
| 2022 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | JAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | FEB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | MAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | APR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | MAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JUN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | JUL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | AUG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | SEP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | OCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | NOV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | DEC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | CUMULATIVE | [7 empty] | Projects ¦ Tasks Due 2022 Year Calendar
| 2022 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | JAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | FEB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | MAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | APR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | MAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JUN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | JUL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | AUG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | SEP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | OCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | NOV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | DEC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H

## Status_Calc (hidden)
Status Calculations
Planned Timelines
Planned Timelines
PLAN END
[5 empty] | User Selection | [5 empty] | Offset | 0
[5 empty] | Level 1 | 0 | * | Projects
[5 empty] | Activity | Tasks | Tasks | 4 |  |  | Tasks Due This Month & Status |  | Total Tasks | 0
Projects ¦ Tasks
| Actual Timelines | ACTUAL END | [8 empty] | 2022-01-01
| Planned Timelines | PLAN END | [8 empty] | 2022-12-31
| Baseline Timelines | BASELINE END
| Actual Timelines | ACTUAL END
Projects ¦ Tasks Due This Week & Status
| Offset | 0 | Projects ¦ Tasks - Due This Week |  | 2022-08-23
| Day | Date | Space | Total Projects ¦ Tasks Due | Completed | In Progress | Not Started | Other
| 2022-08-22 | 2022-08-22 |  | 0 | 0 | 0 | 0 | 0
| 2022-08-23 | 2022-08-23 |  | 0 | 0 | 0 | 0 | 0
| 2022-08-24 | 2022-08-24 |  | 0 | 0 | 0 | 0 | 0
| 2022-08-25 | 2022-08-25 |  | 0 | 0 | 0 | 0 | 0
| 2022-08-26 | 2022-08-26 |  | 0 | 0 | 0 | 0 | 0
| 2022-08-27 | 2022-08-27 |  | 0 | 0 | 0 | 0 | 0
| 2022-08-28 | 2022-08-28 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | Projects ¦ Tasks - Scheduled to finish by Today |  | Reamining Tasks to by Completed by Today | Projects ¦ Tasks Status of Overdue Tasks
|  | Over Due | 73 | TOTAL DUE | Completed | Remaining | Total Overdue Tasks | In Progress | Not Started | Other
|  |  |  | 91 | 18 | 73 | 73 | 34 | 34 | 5
Actual Timelines
| Actual Timelines | ACTUAL END |  | Projects ¦ Tasks Due This Month & Status
| Offset | 0
|  | 2022-08-31 | Date | Total Tasks Due | Completed | In Progress | Not Started | Other
|  |  | 2022-08-01 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-02 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-03 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-04 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-05 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-06 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-07 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-08 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-09 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-10 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-11 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-12 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-13 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-14 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-15 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-16 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-17 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-18 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-19 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-20 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-21 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-22 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-23 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-24 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-25 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-26 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-27 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-08-28 | 0 | 0 | 0 | 0 | 0
|  | 2022-08-29 | 2022-08-29 | 0 | 0 | 0 | 0 | 0
|  | 2022-08-30 | 2022-08-30 | 0 | 0 | 0 | 0 | 0
|  | 2022-08-31 | 2022-08-31 | 0 | 0 | 0 | 0 | 0

## Gantt
|  | Project |  | Act. STATUS |  | Act. COMPLEXITY |  | Start From Task: |  | Filter |  | TIMELINE
|  | PERSON |  | Act.PROGRESS <= |  | Due in (ACTUAL END) |  | No. of Tasks to Show: |  | Gantt Label |  | ACTUAL TIMELINES
| i | Showing 50 Records/ out of 121
Formula |  | WBS | ACTIVITY TITLE | ACTUAL START | ACTUAL DURATION | ACTUAL COMPLETED | ACTUAL PENDING | ACTUAL PROGRESS | ACTUAL END | Custom Field | Gantt Duration | Gantt Complete | Gantt Pending
SNO | MATCH | WBS | Tasks | START | DURATION | COMPLETED | PENDING | PROGRESS | END | CUSTOM FIELD | Gantt Duration | Gantt Completed | Gantt Pending
1 | 1 | 1 | Project Name 1 | 2020-03-03 | 70 | 70 | 0 | 100% | 2020-06-08 |  | 98 | 98 | 0
2 | 2 | 2 | P1 Phase 1 | 2020-03-02 | 35 | 35 | 0 | 100% | 2020-04-17 |  | 47 | 47 | 0
3 | 3 | 3 | P1 Ph1 Task 1 | 2020-03-06 | 6 | 6 | 0 | 100% | 2020-03-13 |  | 8 | 8 | 0
4 | 4 | 4 | P1 Ph1 Task 2 | 2020-03-07 | 10 | 10 | 0 | 100% | 2020-03-19 |  | 13 | 13 | 0
5 | 5 | 5 | P1 Ph1 Task 3 | 2020-03-15 | 14 | 14 | 0 | 100% | 2020-04-01 |  | 18 | 18 | 0
6 | 6 | 6 | P1 Ph1 Task 4 | 2020-03-12 | 19 | 19 | 0 | 100% | 2020-04-07 |  | 27 | 27 | 0
7 | 7 | 7 | P1 Ph1 Task 5 | 2020-03-22 | 9 | 9 | 0 | 100% | 2020-04-01 |  | 11 | 11 | 0
8 | 8 | 8 | P1 Ph1 Task 6 | 2020-04-02 | 15 | 15 | 0 | 100% | 2020-04-22 |  | 21 | 21 | 0
9 | 9 | 9 | P1 Phase 2 | 2020-04-15 | 32 | 16 | 16 | 50% | 2020-05-28 |  | 44 | 22 | 22
10 | 10 | 10 | P1 Ph2 Task 1 | 2020-04-21 | 24 | 21.6 | 2.4 | 90% | 2020-05-22 |  | 32 | 29 | 3
11 | 11 | 11 | P1 Ph2 Task 2 | 2020-04-17 | 10 | 5 | 5 | 50% | 2020-04-30 |  | 14 | 7 | 7
12 | 12 | 12 | P1 Ph2 Task 3 | 2020-04-22 | 17 | 8.5 | 8.5 | 50% | 2020-05-14 |  | 23 | 12 | 11
13 | 13 | 13 | P1 Ph2 Task 4 | 2020-04-19 | 37 | 11.1 | 25.9 | 30% | 2020-06-08 |  | 51 | 15 | 36
14 | 14 | 14 | P1 Ph2 Task 4 Sub task 1 | 2020-04-24 | 36 | 10.8 | 25.2 | 30% | 2020-06-12 |  | 50 | 15 | 35
15 | 15 | 15 | P1 Ph2 Task 4 Sub task 2 | 2020-04-20 | 14 | 8.4 | 5.6 | 60% | 2020-05-07 |  | 18 | 11 | 7
16 | 16 | 16 | P1 Ph2 Task 4 Sub task 3 | 2020-04-22 | 20 | 0 | 20 | 0% | 2020-05-19 |  | 28 | 0 | 28
17 | 17 | 17 | P1 Ph2 Task 5 | 2020-04-20 | 10 | 1 | 9 | 10% | 2020-05-01 |  | 12 | 1 | 11
18 | 18 | 18 | P1 Ph2 Task 6 | 2020-04-17 | 41 | 12.3 | 28.7 | 30% | 2020-06-12 |  | 57 | 17 | 40
19 | 19 | 19 | P1 Ph2 Task 7 | 2020-04-19 | 29 | 0 | 29 | 0% | 2020-05-27 |  | 39 | 0 | 39
20 | 20 | 20 | P1 Ph2 Task 8 | 2020-04-24 | 6 | 0 | 6 | 0% | 2020-05-01 |  | 8 | 0 | 8
21 | 21 | 21 | Project Name 2 | 2020-03-13 | 68 | 47.6 | 20.4 | 70% | 2020-06-16 |  | 96 | 67 | 29
22 | 22 | 22 | P2 Phase 1 | 2020-03-11 | 38 | 11.4 | 26.6 | 30% | 2020-05-01 |  | 52 | 16 | 36
23 | 23 | 23 | P2 Ph1 Task 1 | 2020-03-26 | 11 | 4.4 | 6.6 | 40% | 2020-04-09 |  | 15 | 6 | 9
24 | 24 | 24 | P2 Ph1 Task 2 | 2020-03-15 | 7 | 2.1 | 4.9 | 30% | 2020-03-23 |  | 9 | 3 | 6
25 | 25 | 25 | P2 Ph1 Task 3 | 2020-04-04 | 17 | 13.6 | 3.4 | 80% | 2020-04-27 |  | 24 | 19 | 5
26 | 26 | 26 | P2 Ph1 Task 4 | 2020-03-29 | 23 | 9.2 | 13.8 | 40% | 2020-04-28 |  | 31 | 12 | 19
27 | 27 | 27 | P2 Ph1 Task 5 | 2020-04-29 | 10 | 5 | 5 | 50% | 2020-05-12 |  | 14 | 7 | 7
28 | 28 | 28 | P2 Ph1 Task 6 | 2020-05-20 | 14 | 2.8 | 11.2 | 20% | 2020-06-08 |  | 20 | 4 | 16
29 | 29 | 29 | P2 Phase 2 | 2020-05-28 | 36 | 0 | 36 | 0% | 2020-07-16 |  | 50 | 0 | 50
30 | 30 | 30 | P2 Ph2 Task 1 | 2020-05-20 | 27 | 0 | 27 | 0% | 2020-06-25 |  | 37 | 0 | 37
31 | 31 | 31 | P2 Ph2 Task 2 | 2020-05-20 | 13 | 0 | 13 | 0% | 2020-06-05 |  | 17 | 0 | 17
32 | 32 | 32 | P2 Ph2 Task 3 | 2020-05-14 | 22 | 0 | 22 | 0% | 2020-06-12 |  | 30 | 0 | 30
33 | 33 | 33 | P2 Ph2 Task 4 | 2020-06-06 | 37 | 0 | 37 | 0% | 2020-07-27 |  | 52 | 0 | 52
34 | 34 | 34 | P2 Ph2 Task 4 Sub task 1 | 2020-05-24 | 37 | 0 | 37 | 0% | 2020-07-13 |  | 51 | 0 | 51
35 | 35 | 35 | P2 Ph2 Task 4 Sub task 2 | 2020-04-28 | 21 | 0 | 21 | 0% | 2020-05-26 |  | 29 | 0 | 29
36 | 36 | 36 | P2 Ph2 Task 4 Sub task 3 | 2020-05-13 | 25 | 0 | 25 | 0% | 2020-06-16 |  | 35 | 0 | 35
37 | 37 | 37 | P2 Ph2 Task 5 | 2020-06-12 | 10 | 0 | 10 | 0% | 2020-06-25 |  | 14 | 0 | 14
38 | 38 | 38 | P2 Ph2 Task 6 | 2020-05-16 | 39 | 0 | 39 | 0% | 2020-07-08 |  | 54 | 0 | 54
39 | 39 | 39 | P2 Ph2 Task 7 | 2020-06-09 | 32 | 0 | 32 | 0% | 2020-07-22 |  | 44 | 0 | 44
40 | 40 | 40 | P2 Ph2 Task 8 | 2020-06-05 | 8 | 0 | 8 | 0% | 2020-06-16 |  | 12 | 0 | 12
41 | 41 | 41 | Project Name 3 | 2020-06-02 | 70 | 70 | 0 | 100% | 2020-09-07 |  | 98 | 98 | 0
42 | 42 | 42 | P3 Phase 1 | 2020-05-30 | 34 | 34 | 0 | 100% | 2020-07-15 |  | 47 | 47 | 0
43 | 43 | 43 | P3 Ph1 Task 1 | 2020-07-20 | 6 | 6 | 0 | 100% | 2020-07-27 |  | 8 | 8 | 0
44 | 44 | 44 | P3 Ph1 Task 2 | 2020-06-03 | 14 | 14 | 0 | 100% | 2020-06-22 |  | 20 | 20 | 0
45 | 45 | 45 | P3 Ph1 Task 3 | 2020-07-01 | 15 | 15 | 0 | 100% | 2020-07-21 |  | 21 | 21 | 0
46 | 46 | 46 | P3 Ph1 Task 4 | 2020-07-11 | 21 | 21 | 0 | 100% | 2020-08-07 |  | 28 | 28 | 0
47 | 47 | 47 | P3 Ph1 Task 5 | 2020-06-02 | 10 | 10 | 0 | 100% | 2020-06-15 |  | 14 | 14 | 0
48 | 48 | 48 | P3 Ph1 Task 6 | 2020-07-27 | 16 | 16 | 0 | 100% | 2020-08-17 |  | 22 | 22 | 0
49 | 49 | 49 | P3 Phase 2 | 2020-07-01 | 34 | 17 | 17 | 50% | 2020-08-17 |  | 48 | 24 | 24
50 | 50 | 50 | P3 Ph2 Task 1 | 2020-07-19 | 27 | 24.3 | 2.7 | 90% | 2020-08-24 |  | 37 | 33 | 4
Formulas:
END = IF([MATCH]="","",INDEX(INDIRECT("tbl_Tasks["&AJ199&"]"),[MATCH]))
START = IF([MATCH]="","",INDEX(INDIRECT("tbl_Tasks["&AE199&"]"),[MATCH]))
H

## Gantt_Calc (hidden)
Gantt Chart Calculations
| OFFSET | 0 |  |  | Chart Note
Showing 50 Records/ out of 121
[5 empty] | Project Display Offset | ALL
| Valid Task Rows | 121 |  |  | Range | 1
| Valid Filtered Rows | 50 |  |  | 1 | 12
| Tasks to Show | ALL | 121 |  | 2 | 24
|  | 0 |  |  | 3 | 36
[5 empty] | 4 | 48
[5 empty] | 5 | 61
| Gantt Filters |  | 7 |  | 6 | 73
|  | Filter String | Calc String |  | 7 | 85
| Person | 0 | * |  | 8 | 97
| Project | 0 | * |  | 9 | 109
| Status | 0 | * |  | 10 | 121
| Act.PROGRESS <= | 0 | 0
| Complexity | 0 | *
| Due | All
| Act. PROGRESS >= | 0 | 0
| Act.PROGRESS <= | 0
| Item LevelB | 0 | 0 | 11
| Gantt View | ACTUAL TIMELINES
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 3 | ACTUAL TIMELINES | ACTUAL START | ACTUAL DURATION | ACTUAL COMPLETED | ACTUAL END | ACTUAL PENDING | ACTUAL PROGRESS
| 1 | PLANNED TIMELINES | PLAN START | PLAN DURATION | PLAN COMPLETED | PLAN END | PLAN PENDING | PLAN PROGRESS
| 2 | BASELINE TIMELINES | BASELINE START | BASELINE DURATION | BASELINE COMPLETED | BASELINE END | BASELINE PENDING | BASELINE PROGRESS
| 3 | ACTUAL TIMELINES | ACTUAL START | ACTUAL DURATION | ACTUAL COMPLETED | ACTUAL END | ACTUAL PENDING | ACTUAL PROGRESS
Due Ranges
[6 empty] | 2020-03-13 | 2021-02-25
| Gantt Custom Filed Offset | 2 |  |  | Today | 2022-08-23 | 2022-08-23
[5 empty] | This Week | 2022-08-22 | 2022-08-28
[5 empty] | Last Week | 2022-08-15 | 2022-08-21
[5 empty] | Next Week | 2022-08-29 | 2022-09-04
[5 empty] | This Month | 2022-08-01 | 2022-08-31
[5 empty] | Last Month | 2022-07-01 | 2022-07-31
[5 empty] | Next Month | 2022-09-01 | 2022-09-30
[5 empty] | This Year | 2022-01-01 | 2022-12-31
[5 empty] | Last Year | 2021-01-01 | 2021-12-31
[5 empty] | Next Year | 2023-01-01 | 2023-12-31
[5 empty] | All | 2020-03-13 | 2021-02-25
| 0 | [="]";[<>"]General
CF Formats | Field | Format Type
1 | WBS | [=""]"";[<>""]General
2 | ACTIVITY | [=""]"";[<>""]General
3 | ACTIVITY TITLE | [=""]"";[<>""]General
4 | RESPONSIBLE | [=""]"";[<>""]General
5 | PLAN START | dd-mm-yy
6 | PLAN DURATION | [=1]0" day";[>1]0" days"
7 | BASELINE START | dd-mm-yy
8 | BASELINE DURATION | [=1]0" day";[>1]0" days"
9 | ACTUAL START | dd-mm-yy
10 | ACTUAL DURATION | [=1]0" day";[>1]0" days"
11 | ACTUAL PROGRESS | 0%
12 | ACTUAL STATUS | [=""]"";[<>""]General
13 | ACTUAL COMPLEXITY | [=""]"";[<>""]General
14 | REMARKS | [=""]"";[<>""]General
15 | PLAN END | dd-mm-yy
16 | BASELINE END | dd-mm-yy
17 | ACTUAL END | dd-mm-yy
18 | PLAN COMPLETED | [=1]0" day";[>1]0" days"
19 | BASELINE COMPLETED | [=1]0" day";[>1]0" days"
20 | ACTUAL COMPLETED | [=1]0" day";[>1]0" days"
21 | TIMELINE | dd-mm-yy
22 | Item LevelA
23 | Item LevelB

## Timeline
Your Company Name |  |  | Project Timeline
Project |  |  | Activities | Projects |  | TIMELINE
| Project | Projects |  | ACTUAL START | ACTUAL END
SNO | PROJECT | ACTIVITY | RESPONSIBLE | START | DUE | ACTUAL STATUS | ACTUAL PROGRESS | MATCH | POSITION
1 | Project Name 1 | Project Name 1 | Person 1 | 2020-03-03 | 2020-06-08 | Completed | 100% | 1 | 3
2 | Project Name 2 | Project Name 2 | Person 1 | 2020-03-13 | 2020-06-16 | In Progress | 70% | 21 | 4
3 | Project Name 3 | Project Name 3 | Person 1 | 2020-06-02 | 2020-09-07 | Completed | 100% | 41 | 5
4 | Project Name 4 | Project Name 4 | Person 1 | 2020-08-17 | 2020-11-24 | In Progress | 70% | 61 | 6
5 | Project Name 5 | Project Name 5 | Person 1 | 2020-07-28 | 2020-11-06 | Completed | 100% | 82 | 7
6 | Project Name 6 | Project Name 6 | Person 1 | 2020-09-29 | 2021-01-07 | In Progress | 30% | 102 | 8
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Formulas:
START = IF(tbl_Timeline[[#This Row],[MATCH]]<>"",INDEX(INDIRECT("tbl_Tasks["&'Timeline Calc'!$I38&"]"),tbl_Timeline[[#This Row],[MATCH]]),"")
DUE = IF(tbl_Timeline[[#This Row],[MATCH]]<>"",INDEX(INDIRECT("tbl_Tasks["&'Timeline Calc'!$L38&"]"),tbl_Timeline[[#This Row],[MATCH]]),"")
H

## Timeline Calc (hidden)
Timeline Calculations
|  |  |  | TimeLine HeightFactor | 10
| Total PTItems | 2 |  | Projects
|  |  |  | Projects Start > | #NAME? | -3
| Project | 0 | * | Projects < End | #NAME? | -3
| Activities | Projects | 1
| MATCH TCount | 6
| MATCH Count | 6
| Items to Show |  | 10
All Project
| TimeLine | 0 | All Project - ACTUAL TIMELINES
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 3 | ACTUAL TIMELINES | ACTUAL START | ACTUAL DURATION | ACTUAL COMPLETED | ACTUAL END | ACTUAL PENDING | ACTUAL PROGRESS
| 1 | PLANNED TIMELINES | PLAN START | PLAN DURATION | PLAN COMPLETED | PLAN END | PLAN PENDING | PLAN PROGRESS
| 2 | BASELINE TIMELINES | BASELINE START | BASELINE DURATION | BASELINE COMPLETED | BASELINE END | BASELINE PENDING | BASELINE PROGRESS
| 3 | ACTUAL TIMELINES | ACTUAL START | ACTUAL DURATION | ACTUAL COMPLETED | ACTUAL END | ACTUAL PENDING | ACTUAL PROGRESS
No Records
| 1 |  | Found No Records | - | #NAME? | #NAME?

## Team
Your Company Name |  | Projects Team
|  | DASHBOARD CALCULATIONS |  | PROJECT NAME 1
Tasks
SNO | Person Name | All Assignments | Completed Assignments | Activities Assigned | Activities Completed | Activity Progress
1 | Person 1 | 12 | 6 | 1 | 1 | 100%
2 | Person 2 | 12 | 6 | 1 | 1 | 100%
3 | Person 3 | 6 | 3 | 1 | 1 | 100%
4 | Person 4 | 6 | 3 | 1 | 1 | 100%
5 | Person 5 | 6 | 3 | 1 | 1 | 100%
6 | Person 6 | 6 | 2 | 1 | 1 | 100%
7 | Person 7 | 0 | 0 | 0 | 0
8 | Person 8 | 18 | 0 | 2 | 0 | 50%
9 | Person 9 | 12 | 0 | 2 | 0 | 40%
10 | Person 10 | 13 | 1 | 2 | 0 | 25%
11 | Person 11 | 6 | 0 | 1 | 0 | 30%
12 | Person 12 | 6 | 0 | 0 | 0
13 | Person 13 | 6 | 0 | 0 | 0
14 | Person 14 | 6 | 0 | 0 | 0
15 | Person 15 | 6 | 0 | 1 | 0 | 0%
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
H

## Tasks
Your Company Name |  |  | Projects & Tasks
PROJECT TASKS & RESPONSIBILITIES |  |  |  | PLANNED TIMELINES |  | BASELINE TIMELINES |  | ACTUAL TIMELINES |  |  |  |  | OTHER | DO NOT CHANGE: Formula/Calculations
WBS | ACTIVITY | ACTIVITY TITLE | RESPONSIBLE | PLAN START | PLAN DURATION | BASELINE START | BASELINE DURATION | ACTUAL START | ACTUAL DURATION | ACTUAL PROGRESS | ACTUAL STATUS | ACTUAL COMPLEXITY | REMARKS | PLAN END | BASELINE END | ACTUAL END | PLAN COMPLETED | BASELINE COMPLETED | ACTUAL COMPLETED | TIMELINE | Item LevelA | Item LevelB | LEVEL 1 | CUM LEVEL1 | CFGC FILTERED TASKS | CFGC FILTERED SHOW | DB FILTER | PT FILTER | CUM PT FILTER | ST FILTER
1 | Project | Project Name 1 | Person 1 | 2020-02-28 | 65 | 2020-03-03 | 69 | 2020-03-03 | 70 | 100% | Completed | Level 2 | Important Notes Here | 2020-05-28 | 2020-06-05 | 2020-06-08 | 65 | 69 | 70 | 2020-06-08 | 1 | 1 | Project Name 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | Phase | P1 Phase 1 | Person 2 | 2020-02-29 | 30 | 2020-03-03 | 33 | 2020-03-02 | 35 | 100% | Completed | Level 2 |  | 2020-04-09 | 2020-04-16 | 2020-04-17 | 30 | 33 | 35 | 2020-04-17 | 2 | 2 | Project Name 1 |  | 1 | 2 | 1 |  |  | 1
3 | Task | P1 Ph1 Task 1 | Person 1 | 2020-03-03 | 4 | 2020-03-06 | 7 | 2020-03-06 | 6 | 100% | Completed | Level 2 |  | 2020-03-06 | 2020-03-16 | 2020-03-13 | 4 | 7 | 6 | 2020-03-13 | 4 | 4 | Project Name 1 |  | 1 | 3 | 1 |  |  | 1
4 |  | P1 Ph1 Task 2 | Person 2 | 2020-03-02 | 5 | 2020-02-27 | 10 | 2020-03-07 | 10 | 100% | Completed | Level 1 |  | 2020-03-06 | 2020-03-11 | 2020-03-19 | 5 | 10 | 10 | 2020-03-19 | 0 | 4 | Project Name 1 |  | 1 | 4 | 1 |  |  | 1
5 |  | P1 Ph1 Task 3 | Person 3 | 2020-03-13 | 10 | 2020-03-15 | 13 | 2020-03-15 | 14 | 100% | Completed | Level 2 |  | 2020-03-26 | 2020-03-31 | 2020-04-01 | 10 | 13 | 14 | 2020-04-01 | 0 | 4 | Project Name 1 |  | 1 | 5 | 1 |  |  | 1
6 |  | P1 Ph1 Task 4 | Person 4 | 2020-03-08 | 15 | 2020-03-12 | 18 | 2020-03-12 | 19 | 100% | Completed | Level 3 |  | 2020-03-26 | 2020-04-06 | 2020-04-07 | 15 | 18 | 19 | 2020-04-07 | 0 | 4 | Project Name 1 |  | 1 | 6 | 1 |  |  | 1
7 |  | P1 Ph1 Task 5 | Person 5 | 2020-03-18 | 8 | 2020-03-16 | 11 | 2020-03-22 | 9 | 100% | Completed | Level 2 |  | 2020-03-27 | 2020-03-30 | 2020-04-01 | 8 | 11 | 9 | 2020-04-01 | 0 | 4 | Project Name 1 |  | 1 | 7 | 1 |  |  | 1
8 |  | P1 Ph1 Task 6 | Person 6 | 2020-03-28 | 10 | 2020-03-28 | 13 | 2020-04-02 | 15 | 100% | Completed | Level 3 |  | 2020-04-09 | 2020-04-14 | 2020-04-22 | 10 | 13 | 15 | 2020-04-22 | 0 | 4 | Project Name 1 |  | 1 | 8 | 1 |  |  | 1
9 | Phase | P1 Phase 2 | Person 8 | 2020-04-13 | 30 | 2020-04-13 | 32 | 2020-04-15 | 32 | 50% | In Progress | Level 3 |  | 2020-05-22 | 2020-05-26 | 2020-05-28 | 30 | 32 | 16 | 2020-05-28 | 2 | 2 | Project Name 1 |  | 1 | 9 | 1 |  |  | 1
10 | Task | P1 Ph2 Task 1 | Person 8 | 2020-04-16 | 20 | 2020-04-18 | 21 | 2020-04-21 | 24 | 90% | In Progress | Level 2 |  | 2020-05-13 | 2020-05-15 | 2020-05-22 | 20 | 21 | 21.6 | 2020-05-22 | 4 | 4 | Project Name 1 |  | 1 | 10 | 1 |  |  | 1
11 |  | P1 Ph2 Task 2 | Person 9 | 2020-04-15 | 8 | 2020-04-12 | 10 | 2020-04-17 | 10 | 50% | In Progress | Level 1 |  | 2020-04-24 | 2020-04-23 | 2020-04-30 | 8 | 10 | 5 | 2020-04-30 | 0 | 4 | Project Name 1 |  | 1 | 11 | 1 |  |  | 1
12 |  | P1 Ph2 Task 3 | Person 10 | 2020-04-19 | 16 | 2020-04-16 | 18 | 2020-04-22 | 17 | 50% | In Progress | Level 2 |  | 2020-05-08 | 2020-05-11 | 2020-05-14 | 16 | 18 | 8.5 | 2020-05-14 | 0 | 4 | Project Name 1 |  | 1 | 12 | 1 |  |  | 1
13 |  | P1 Ph2 Task 4 | Person 11 | 2020-04-15 | 32 | 2020-04-20 | 33 | 2020-04-19 | 37 | 30% | In Progress | Level 3 |  | 2020-05-28 | 2020-06-03 | 2020-06-08 | 32 | 33 | 11.1 | 2020-06-08 | 0 | 4 | Project Name 1 |  | 1 | 13 | 1 |  |  | 1
14 | Subtask | P1 Ph2 Task 4 Sub task 1 | Person 12 | 2020-04-21 | 32 | 2020-04-23 | 37 | 2020-04-24 | 36 | 30% | In Progress | Level 2 |  | 2020-06-03 | 2020-06-12 | 2020-06-12 | 32 | 37 | 10.8 | 2020-06-12 | 5 | 5 | Project Name 1 |  | 1 | 14 | 1 |  |  | 1
15 |  | P1 Ph2 Task 4 Sub task 2 | Person 13 | 2020-04-15 | 12 | 2020-04-12 | 17 | 2020-04-20 | 14 | 60% | In Progress | Level 3 |  | 2020-04-30 | 2020-05-04 | 2020-05-07 | 12 | 17 | 8.4 | 2020-05-07 | 0 | 5 | Project Name 1 |  | 1 | 15 | 1 |  |  | 1
16 |  | P1 Ph2 Task 4 Sub task 3 | Person 14 | 2020-04-20 | 16 | 2020-04-16 | 20 | 2020-04-22 | 20 | 0% | Not Started | Level 3 |  | 2020-05-11 | 2020-05-13 | 2020-05-19 | 16 | 20 | 0 | 2020-05-19 | 0 | 5 | Project Name 1 |  | 1 | 16 | 1 |  |  | 1
17 | Task | P1 Ph2 Task 5 | Person 8 | 2020-04-19 | 8 | 2020-04-15 | 10 | 2020-04-20 | 10 | 10% | In Progress | Level 3 |  | 2020-04-28 | 2020-04-28 | 2020-05-01 | 8 | 10 | 1 | 2020-05-01 | 4 | 4 | Project Name 1 |  | 1 | 17 | 1 |  |  | 1
18 |  | P1 Ph2 Task 6 | Person 9 | 2020-04-15 | 36 | 2020-04-17 | 38 | 2020-04-17 | 41 | 30% | In Progress | Level 3 |  | 2020-06-03 | 2020-06-09 | 2020-06-12 | 36 | 38 | 12.3 | 2020-06-12 | 0 | 4 | Project Name 1 |  | 1 | 18 | 1 |  |  | 1
19 |  | P1 Ph2 Task 7 | Person 10 | 2020-04-16 | 28 | 2020-04-21 | 30 | 2020-04-19 | 29 | 0% | Not Started | Level 3 |  | 2020-05-25 | 2020-06-01 | 2020-05-27 | 28 | 30 | 0 | 2020-05-27 | 0 | 4 | Project Name 1 |  | 1 | 19 | 1 |  |  | 1
20 |  | P1 Ph2 Task 8 | Person 15 | 2020-04-21 | 4 | 2020-04-23 | 5 | 2020-04-24 | 6 | 0% | Not Started | Level 3 |  | 2020-04-24 | 2020-04-29 | 2020-05-01 | 4 | 5 | 0 | 2020-05-01 | 0 | 4 | Project Name 1 |  | 1 | 20 | 1 |  |  | 1
21 | Project | Project Name 2 | Person 1 | 2020-03-09 | 66 | 2020-03-07 | 67 | 2020-03-13 | 68 | 70% | In Progress | Level 1 |  | 2020-06-08 | 2020-06-08 | 2020-06-16 | 66 | 67 | 47.6 | 2020-06-16 | 1 | 1 | Project Name 2 | 2 | 1 | 21 |  | 1 | 2 | 1
22 | Phase | P2 Phase 1 | Person 2 | 2020-03-10 | 33 | 2020-03-05 | 37 | 2020-03-11 | 38 | 30% | In Progress | Level 2 |  | 2020-04-23 | 2020-04-24 | 2020-05-01 | 33 | 37 | 11.4 | 2020-05-01 | 2 | 2 | Project Name 2 |  | 1 | 22 |  |  |  | 1
23 | Task | P2 Ph1 Task 1 | Person 1 | 2020-03-23 | 9 | 2020-03-21 | 11 | 2020-03-26 | 11 | 40% | In Progress | Level 3 |  | 2020-04-02 | 2020-04-03 | 2020-04-09 | 9 | 11 | 4.4 | 2020-04-09 | 4 | 4 | Project Name 2 |  | 1 | 23 |  |  |  | 1
24 |  | P2 Ph1 Task 2 | Person 2 | 2020-03-12 | 6 | 2020-03-08 | 11 | 2020-03-15 | 7 | 30% | In Progress | Level 1 |  | 2020-03-19 | 2020-03-20 | 2020-03-23 | 6 | 11 | 2.1 | 2020-03-23 | 0 | 4 | Project Name 2 |  | 1 | 24 |  |  |  | 1
25 |  | P2 Ph1 Task 3 | Person 3 | 2020-04-02 | 12 | 2020-04-05 | 13 | 2020-04-04 | 17 | 80% | In Progress | Level 2 |  | 2020-04-17 | 2020-04-21 | 2020-04-27 | 12 | 13 | 13.6 | 2020-04-27 | 0 | 4 | Project Name 2 |  | 1 | 25 |  |  |  | 1
26 |  | P2 Ph1 Task 4 | Person 4 | 2020-03-28 | 18 | 2020-03-25 | 21 | 2020-03-29 | 23 | 40% | In Progress | Level 3 |  | 2020-04-21 | 2020-04-22 | 2020-04-28 | 18 | 21 | 9.2 | 2020-04-28 | 0 | 4 | Project Name 2 |  | 1 | 26 |  |  |  | 1
27 |  | P2 Ph1 Task 5 | Person 5 | 2020-04-27 | 9 | 2020-04-26 | 12 | 2020-04-29 | 10 | 50% | In Progress | Level 3 |  | 2020-05-07 | 2020-05-11 | 2020-05-12 | 9 | 12 | 5 | 2020-05-12 | 0 | 4 | Project Name 2 |  | 1 | 27 |  |  |  | 1
28 |  | P2 Ph1 Task 6 | Person 6 | 2020-05-17 | 13 | 2020-05-19 | 14 | 2020-05-20 | 14 | 20% | In Progress | Level 1 |  | 2020-06-02 | 2020-06-05 | 2020-06-08 | 13 | 14 | 2.8 | 2020-06-08 | 0 | 4 | Project Name 2 |  | 1 | 28 |  |  |  | 1
29 | Phase | P2 Phase 2 | Person 8 | 2020-05-23 | 32 | 2020-05-25 | 37 | 2020-05-28 | 36 | 0% | Not Started | Level 1 |  | 2020-07-06 | 2020-07-14 | 2020-07-16 | 32 | 37 | 0 | 2020-07-16 | 2 | 2 | Project Name 2 |  | 1 | 29 |  |  |  | 1
30 | Task | P2 Ph2 Task 1 | Person 8 | 2020-05-16 | 23 | 2020-05-20 | 28 | 2020-05-20 | 27 | 0% | Not Started | Level 2 |  | 2020-06-16 | 2020-06-26 | 2020-06-25 | 23 | 28 | 0 | 2020-06-25 | 4 | 4 | Project Name 2 |  | 1 | 30 |  |  |  | 1
31 |  | P2 Ph2 Task 2 | Person 9 | 2020-05-15 | 10 | 2020-05-12 | 13 | 2020-05-20 | 13 | 0% | Not Started | Level 3 |  | 2020-05-28 | 2020-05-28 | 2020-06-05 | 10 | 13 | 0 | 2020-06-05 | 0 | 4 | Project Name 2 |  | 1 | 31 |  |  |  | 1
32 |  | P2 Ph2 Task 3 | Person 10 | 2020-05-09 | 17 | 2020-05-06 | 18 | 2020-05-14 | 22 | 0% | Not Started | Level 1 |  | 2020-06-01 | 2020-05-29 | 2020-06-12 | 17 | 18 | 0 | 2020-06-12 | 0 | 4 | Project Name 2 |  | 1 | 32 |  |  |  | 1
33 |  | P2 Ph2 Task 4 | Person 11 | 2020-06-04 | 33 | 2020-06-03 | 35 | 2020-06-06 | 37 | 0% | Not Started | Level 2 |  | 2020-07-20 | 2020-07-21 | 2020-07-27 | 33 | 35 | 0 | 2020-07-27 | 0 | 4 | Project Name 2 |  | 1 | 33 |  |  |  | 1
34 | Subtask | P2 Ph2 Task 4 Sub task 1 | Person 12 | 2020-05-21 | 36 | 2020-05-18 | 37 | 2020-05-24 | 37 | 0% | Not Started | Level 3 |  | 2020-07-09 | 2020-07-07 | 2020-07-13 | 36 | 37 | 0 | 2020-07-13 | 5 | 5 | Project Name 2 |  | 1 | 34 |  |  |  | 1
35 |  | P2 Ph2 Task 4 Sub task 2 | Person 13 | 2020-04-25 | 16 | 2020-04-24 | 18 | 2020-04-28 | 21 | 0% | Not Started | Level 1 |  | 2020-05-15 | 2020-05-19 | 2020-05-26 | 16 | 18 | 0 | 2020-05-26 | 0 | 5 | Project Name 2 |  | 1 | 35 |  |  |  | 1
36 |  | P2 Ph2 Task 4 Sub task 3 | Person 14 | 2020-05-10 | 21 | 2020-05-07 | 26 | 2020-05-13 | 25 | 0% | Not Started | Level 2 |  | 2020-06-05 | 2020-06-11 | 2020-06-16 | 21 | 26 | 0 | 2020-06-16 | 0 | 5 | Project Name 2 |  | 1 | 36 |  |  |  | 1
37 | Task | P2 Ph2 Task 5 | Person 8 | 2020-06-08 | 9 | 2020-06-09 | 11 | 2020-06-12 | 10 | 0% | Not Started | Level 3 |  | 2020-06-18 | 2020-06-23 | 2020-06-25 | 9 | 11 | 0 | 2020-06-25 | 4 | 4 | Project Name 2 |  | 1 | 37 |  |  |  | 1
38 |  | P2 Ph2 Task 6 | Person 9 | 2020-05-15 | 37 | 2020-05-12 | 39 | 2020-05-16 | 39 | 0% | Not Started | Level 1 |  | 2020-07-06 | 2020-07-03 | 2020-07-08 | 37 | 39 | 0 | 2020-07-08 | 0 | 4 | Project Name 2 |  | 1 | 38 |  |  |  | 1
39 |  | P2 Ph2 Task 7 | Person 10 | 2020-06-05 | 29 | 2020-06-08 | 34 | 2020-06-09 | 32 | 0% | Not Started | Level 2 |  | 2020-07-15 | 2020-07-23 | 2020-07-22 | 29 | 34 | 0 | 2020-07-22 | 0 | 4 | Project Name 2 |  | 1 | 39 |  |  |  | 1
40 |  | P2 Ph2 Task 8 | Person 15 | 2020-05-31 | 6 | 2020-05-28 | 11 | 2020-06-05 | 8 | 0% | Not Started | Level 3 |  | 2020-06-05 | 2020-06-11 | 2020-06-16 | 6 | 11 | 0 | 2020-06-16 | 0 | 4 | Project Name 2 |  | 1 | 40 |  |  |  | 1
41 | Project | Project Name 3 | Person 1 | 2020-05-28 | 67 | 2020-05-29 | 68 | 2020-06-02 | 70 | 100% | Completed | Level 2 |  | 2020-08-28 | 2020-09-01 | 2020-09-07 | 67 | 68 | 70 | 2020-09-07 | 1 | 1 | Project Name 3 | 3 | 1 | 41 |  | 1 | 3 | 1
42 | Phase | P3 Phase 1 | Person 2 | 2020-05-29 | 31 | 2020-05-29 | 32 | 2020-05-30 | 34 | 100% | Completed | Level 2 |  | 2020-07-10 | 2020-07-13 | 2020-07-15 | 31 | 32 | 34 | 2020-07-15 | 2 | 2 | Project Name 3 |  | 1 | 42 |  |  |  | 1
43 | Task | P3 Ph1 Task 1 | Person 1 | 2020-07-16 | 5 | 2020-07-13 | 10 | 2020-07-20 | 6 | 100% | Completed | Level 2 |  | 2020-07-22 | 2020-07-24 | 2020-07-27 | 5 | 10 | 6 | 2020-07-27 | 4 | 4 | Project Name 3 |  | 1 | 43 |  |  |  | 1
44 |  | P3 Ph1 Task 2 | Person 2 | 2020-05-31 | 9 | 2020-05-26 | 11 | 2020-06-03 | 14 | 100% | Completed | Level 1 |  | 2020-06-10 | 2020-06-09 | 2020-06-22 | 9 | 11 | 14 | 2020-06-22 | 0 | 4 | Project Name 3 |  | 1 | 44 |  |  |  | 1
45 |  | P3 Ph1 Task 3 | Person 3 | 2020-06-26 | 13 | 2020-06-30 | 16 | 2020-07-01 | 15 | 100% | Completed | Level 2 |  | 2020-07-14 | 2020-07-21 | 2020-07-21 | 13 | 16 | 15 | 2020-07-21 | 0 | 4 | Project Name 3 |  | 1 | 45 |  |  |  | 1
46 |  | P3 Ph1 Task 4 | Person 4 | 2020-07-06 | 20 | 2020-07-06 | 23 | 2020-07-11 | 21 | 100% | Completed | Level 3 |  | 2020-07-31 | 2020-08-05 | 2020-08-07 | 20 | 23 | 21 | 2020-08-07 | 0 | 4 | Project Name 3 |  | 1 | 46 |  |  |  | 1
47 |  | P3 Ph1 Task 5 | Person 5 | 2020-06-01 | 9 | 2020-06-01 | 14 | 2020-06-02 | 10 | 100% | Completed | Level 2 |  | 2020-06-11 | 2020-06-18 | 2020-06-15 | 9 | 14 | 10 | 2020-06-15 | 0 | 4 | Project Name 3 |  | 1 | 47 |  |  |  | 1
48 |  | P3 Ph1 Task 6 | Person 6 | 2020-07-26 | 15 | 2020-07-30 | 16 | 2020-07-27 | 16 | 100% | Completed | Level 3 |  | 2020-08-13 | 2020-08-20 | 2020-08-17 | 15 | 16 | 16 | 2020-08-17 | 0 | 4 | Project Name 3 |  | 1 | 48 |  |  |  | 1
49 | Phase | P3 Phase 2 | Person 8 | 2020-06-27 | 33 | 2020-06-25 | 34 | 2020-07-01 | 34 | 50% | In Progress | Level 3 |  | 2020-08-11 | 2020-08-11 | 2020-08-17 | 33 | 34 | 17 | 2020-08-17 | 2 | 2 | Project Name 3 |  | 1 | 49 |  |  |  | 1
50 | Task | P3 Ph2 Task 1 | Person 8 | 2020-07-15 | 25 | 2020-07-16 | 29 | 2020-07-19 | 27 | 90% | In Progress | Level 2 |  | 2020-08-18 | 2020-08-25 | 2020-08-24 | 25 | 29 | 24.3 | 2020-08-24 | 4 | 4 | Project Name 3 |  | 1 | 50 |  |  |  | 1
51 |  | P3 Ph2 Task 2 | Person 9 | 2020-06-14 | 12 | 2020-06-16 | 13 | 2020-06-16 | 17 | 50% | In Progress | Level 1 |  | 2020-06-29 | 2020-07-02 | 2020-07-08 | 12 | 13 | 8.5 | 2020-07-08 | 0 | 4 | Project Name 3 |  | 1 | 51 |  |  |  | 1
52 |  | P3 Ph2 Task 3 | Person 10 | 2020-07-18 | 20 | 2020-07-21 | 23 | 2020-07-22 | 24 | 50% | In Progress | Level 2 |  | 2020-08-13 | 2020-08-20 | 2020-08-24 | 20 | 23 | 12 | 2020-08-24 | 0 | 4 | Project Name 3 |  | 1 | 52 |  |  |  | 1
53 |  | P3 Ph2 Task 4 | Person 11 | 2020-07-14 | 37 | 2020-07-17 | 41 | 2020-07-18 | 40 | 30% | In Progress | Level 3 |  | 2020-09-02 | 2020-09-11 | 2020-09-10 | 37 | 41 | 12 | 2020-09-10 | 0 | 4 | Project Name 3 |  | 1 | 53 |  |  |  | 1
54 | Subtask | P3 Ph2 Task 4 Sub task 1 | Person 12 | 2020-05-21 | 33 | 2020-05-21 | 34 | 2020-05-25 | 34 | 30% | In Progress | Level 2 |  | 2020-07-06 | 2020-07-07 | 2020-07-09 | 33 | 34 | 10.2 | 2020-07-09 | 5 | 5 | Project Name 3 |  | 1 | 54 |  |  |  | 1
55 |  | P3 Ph2 Task 4 Sub task 2 | Person 13 | 2020-08-28 | 15 | 2020-08-27 | 20 | 2020-09-01 | 16 | 60% | In Progress | Level 3 |  | 2020-09-17 | 2020-09-23 | 2020-09-22 | 15 | 20 | 9.6 | 2020-09-22 | 0 | 5 | Project Name 3 |  | 1 | 55 |  |  |  | 1
56 |  | P3 Ph2 Task 4 Sub task 3 | Person 14 | 2020-07-04 | 18 | 2020-07-05 | 19 | 2020-07-05 | 20 | 0% | Not Started | Level 3 |  | 2020-07-28 | 2020-07-29 | 2020-07-30 | 18 | 19 | 0 | 2020-07-30 | 0 | 5 | Project Name 3 |  | 1 | 56 |  |  |  | 1
57 | Task | P3 Ph2 Task 5 | Person 8 | 2020-08-02 | 11 | 2020-07-28 | 15 | 2020-08-06 | 13 | 10% | In Progress | Level 3 |  | 2020-08-14 | 2020-08-17 | 2020-08-24 | 11 | 15 | 1.3 | 2020-08-24 | 4 | 4 | Project Name 3 |  | 1 | 57 |  |  |  | 1
58 |  | P3 Ph2 Task 6 | Person 9 | 2020-07-14 | 39 | 2020-07-14 | 43 | 2020-07-16 | 43 | 30% | In Progress | Level 3 |  | 2020-09-04 | 2020-09-10 | 2020-09-14 | 39 | 43 | 12.9 | 2020-09-14 | 0 | 4 | Project Name 3 |  | 1 | 58 |  |  |  | 1
59 |  | P3 Ph2 Task 7 | Person 10 | 2020-07-15 | 33 | 2020-07-11 | 36 | 2020-07-16 | 38 | 0% | Not Started | Level 3 |  | 2020-08-28 | 2020-08-28 | 2020-09-07 | 33 | 36 | 0 | 2020-09-07 | 0 | 4 | Project Name 3 |  | 1 | 59 |  |  |  | 1
60 |  | P3 Ph2 Task 8 | Person 15 | 2020-07-20 | 8 | 2020-07-19 | 12 | 2020-07-25 | 10 | 0% | Not Started | Level 3 |  | 2020-07-29 | 2020-08-03 | 2020-08-06 | 8 | 12 | 0 | 2020-08-06 | 0 | 4 | Project Name 3 |  | 1 | 60 |  |  |  | 1
61 | Project | Project Name 4 | Person 1 | 2020-08-16 | 69 | 2020-08-14 | 71 | 2020-08-17 | 72 | 70% | In Progress | Level 1 |  | 2020-11-18 | 2020-11-20 | 2020-11-24 | 69 | 71 | 50.4 | 2020-11-24 | 1 | 1 | Project Name 4 | 4 | 1 | 61 |  | 1 | 4 | 1
62 | Phase | P4 Phase 1 | Person 2 | 2020-06-18 | 34 | 2020-06-19 | 36 | 2020-06-21 | 36 | 30% | In Progress | Level 2 |  | 2020-08-04 | 2020-08-07 | 2020-08-07 | 34 | 36 | 10.8 | 2020-08-07 | 2 | 2 | Project Name 4 |  | 1 | 62 |  |  |  | 1
63 | Task | P4 Ph1 Task 1 | Person 1 | 2020-08-05 | 12 | 2020-08-10 | 15 | 2020-08-10 | 17 | 40% | In Progress | Level 3 |  | 2020-08-20 | 2020-08-28 | 2020-09-01 | 12 | 15 | 6.8 | 2020-09-01 | 4 | 4 | Project Name 4 |  | 1 | 63 |  |  |  | 1
64 |  | P4 Ph1 Task 2 | Person 2 | 2020-07-05 | 7 | 2020-07-03 | 12 | 2020-07-06 | 9 | 30% | In Progress | Level 1 |  | 2020-07-13 | 2020-07-20 | 2020-07-16 | 7 | 12 | 2.7 | 2020-07-16 | 0 | 4 | Project Name 4 |  | 1 | 64 |  |  |  | 1
65 |  | P4 Ph1 Task 3 | Person 3 | 2020-08-30 | 15 | 2020-08-30 | 17 | 2020-09-01 | 17 | 80% | In Progress | Level 2 |  | 2020-09-17 | 2020-09-21 | 2020-09-23 | 15 | 17 | 13.6 | 2020-09-23 | 0 | 4 | Project Name 4 |  | 1 | 65 |  |  |  | 1
66 |  | P4 Ph1 Task 4 | Person 4 | 2020-08-10 | 22 | 2020-08-13 | 26 | 2020-08-14 | 23 | 40% | On Hold | Level 3 |  | 2020-09-08 | 2020-09-17 | 2020-09-15 | 22 | 26 | 9.2 | 2020-09-15 | 0 | 4 | Project Name 4 |  | 1 | 66 |  |  |  | 1
67 |  | P4 Ph1 Task 5 | Person 5 | 2020-06-21 | 13 | 2020-06-17 | 15 | 2020-06-22 | 16 | 50% | On Hold | Level 3 |  | 2020-07-07 | 2020-07-07 | 2020-07-13 | 13 | 15 | 8 | 2020-07-13 | 0 | 4 | Project Name 4 |  | 1 | 67 |  |  |  | 1
68 |  | P4 Ph1 Task 6 | Person 6 | 2020-09-29 | 16 | 2020-09-30 | 18 | 2020-10-04 | 21 | 20% | In Progress | Level 1 |  | 2020-10-20 | 2020-10-23 | 2020-10-30 | 16 | 18 | 4.2 | 2020-10-30 | 0 | 4 | Project Name 4 |  | 1 | 68 |  |  |  | 1
69 | Phase | P4 Phase 2 | Person 8 | 2020-08-31 | 34 | 2020-08-26 | 36 | 2020-09-05 | 35 | 0% | Not Started | Level 1 |  | 2020-10-15 | 2020-10-14 | 2020-10-22 | 34 | 36 | 0 | 2020-10-22 | 2 | 2 | Project Name 4 |  | 1 | 69 |  |  |  | 1
70 | Task | P4 Ph2 Task 1 | Person 8 | 2020-07-05 | 24 | 2020-07-08 | 25 | 2020-07-07 | 25 | 0% | Cancelled | Level 2 |  | 2020-08-05 | 2020-08-11 | 2020-08-10 | 24 | 25 | 0 | 2020-08-10 | 4 | 4 | Project Name 4 |  | 1 | 70 |  |  |  | 1
71 |  | P4 Ph2 Task 2 | Person 9 | 2020-10-02 | 12 | 2020-10-04 | 16 | 2020-10-05 | 16 | 0% | Not Started | Level 3 |  | 2020-10-19 | 2020-10-23 | 2020-10-26 | 12 | 16 | 0 | 2020-10-26 | 0 | 4 | Project Name 4 |  | 1 | 71 |  |  |  | 1
72 |  | P4 Ph2 Task 3 | Person 10 | 2020-09-06 | 20 | 2020-09-07 | 21 | 2020-09-09 | 22 | 0% | Cancelled | Level 1 |  | 2020-10-01 | 2020-10-05 | 2020-10-08 | 20 | 21 | 0 | 2020-10-08 | 0 | 4 | Project Name 4 |  | 1 | 72 |  |  |  | 1
73 |  | P4 Ph2 Task 4 | Person 11 | 2020-09-02 | 36 | 2020-08-30 | 41 | 2020-09-03 | 40 | 0% | Not Started | Level 2 |  | 2020-10-21 | 2020-10-23 | 2020-10-28 | 36 | 41 | 0 | 2020-10-28 | 0 | 4 | Project Name 4 |  | 1 | 73 |  |  |  | 1
74 |  | P4 Ph2 Task 5 | Person 12 | 2020-09-08 | 40 | 2020-09-04 | 43 | 2020-09-09 | 42 | 0% | Not Started | Level 3 |  | 2020-11-02 | 2020-11-03 | 2020-11-05 | 40 | 43 | 0 | 2020-11-05 | 0 | 4 | Project Name 4 |  | 1 | 74 |  |  |  | 1
75 |  | P4 Ph2 Task 6 | Person 13 | 2020-11-01 | 17 | 2020-11-05 | 20 | 2020-11-06 | 22 | 0% | Not Started | Level 1 |  | 2020-11-23 | 2020-12-02 | 2020-12-07 | 17 | 20 | 0 | 2020-12-07 | 0 | 4 | Project Name 4 |  | 1 | 75 |  |  |  | 1
76 |  | P4 Ph2 Task 7 | Person 14 | 2020-09-07 | 25 | 2020-09-04 | 29 | 2020-09-09 | 29 | 0% | Not Started | Level 2 |  | 2020-10-09 | 2020-10-14 | 2020-10-19 | 25 | 29 | 0 | 2020-10-19 | 0 | 4 | Project Name 4 |  | 1 | 76 |  |  |  | 1
77 |  | P4 Ph2 Task 8 | Person 8 | 2020-09-06 | 13 | 2020-09-01 | 14 | 2020-09-09 | 16 | 0% | Not Started | Level 3 |  | 2020-09-22 | 2020-09-18 | 2020-09-30 | 13 | 14 | 0 | 2020-09-30 | 0 | 4 | Project Name 4 |  | 1 | 77 |  |  |  | 1
78 |  | P4 Ph2 Task 9 | Person 9 | 2020-07-04 | 42 | 2020-07-04 | 45 | 2020-07-05 | 47 | 0% | Not Started | Level 1 |  | 2020-08-31 | 2020-09-03 | 2020-09-07 | 42 | 45 | 0 | 2020-09-07 | 0 | 4 | Project Name 4 |  | 1 | 78 |  |  |  | 1
79 |  | P4 Ph2 Task 10 | Person 10 | 2020-09-18 | 31 | 2020-09-18 | 34 | 2020-09-23 | 33 | 0% | Not Started | Level 2 |  | 2020-10-30 | 2020-11-04 | 2020-11-06 | 31 | 34 | 0 | 2020-11-06 | 0 | 4 | Project Name 4 |  | 1 | 79 |  |  |  | 1
80 |  | P4 Ph2 Task 11 | Person 15 | 2020-10-08 | 10 | 2020-10-11 | 11 | 2020-10-11 | 13 | 0% | Not Started | Level 3 |  | 2020-10-21 | 2020-10-23 | 2020-10-27 | 10 | 11 | 0 | 2020-10-27 | 0 | 4 | Project Name 4 |  | 1 | 80 |  |  |  | 1
81 |  | P4 Ph2 Task 12 | Person 10 | 2020-10-05 | 33 | 2020-10-09 | 37 | 2020-10-09 | 35 | 100% | Completed | Level 2 |  | 2020-11-18 | 2020-11-30 | 2020-11-26 | 33 | 37 | 35 | 2020-11-26 | 0 | 4 | Project Name 4 |  | 1 | 81 |  |  |  | 1
82 | Project | Project Name 5 | Person 1 | 2020-07-27 | 71 | 2020-07-25 | 72 | 2020-07-28 | 74 | 100% | Completed | Level 2 |  | 2020-11-02 | 2020-11-02 | 2020-11-06 | 71 | 72 | 74 | 2020-11-06 | 1 | 1 | Project Name 5 | 5 | 1 | 82 |  | 1 | 5 | 1
83 | Phase | P5 Phase 1 | Person 2 | 2020-07-28 | 33 | 2020-07-28 | 38 | 2020-07-30 | 35 | 100% | Completed | Level 2 |  | 2020-09-10 | 2020-09-17 | 2020-09-16 | 33 | 38 | 35 | 2020-09-16 | 2 | 2 | Project Name 5 |  | 1 | 83 |  |  |  | 1
84 | Task | P5 Ph1 Task 1 | Person 1 | 2020-09-14 | 9 | 2020-09-10 | 13 | 2020-09-18 | 13 | 100% | Completed | Level 1 |  | 2020-09-24 | 2020-09-28 | 2020-10-06 | 9 | 13 | 13 | 2020-10-06 | 4 | 4 | Project Name 5 |  | 1 | 84 |  |  |  | 1
85 |  | P5 Ph1 Task 2 | Person 2 | 2020-07-30 | 14 | 2020-07-25 | 15 | 2020-08-01 | 19 | 100% | Completed | Level 2 |  | 2020-08-18 | 2020-08-13 | 2020-08-26 | 14 | 15 | 19 | 2020-08-26 | 0 | 4 | Project Name 5 |  | 1 | 85 |  |  |  | 1
86 |  | P5 Ph1 Task 3 | Person 3 | 2020-08-25 | 15 | 2020-08-30 | 20 | 2020-08-26 | 17 | 100% | Completed | Level 3 |  | 2020-09-14 | 2020-09-24 | 2020-09-17 | 15 | 20 | 17 | 2020-09-17 | 0 | 4 | Project Name 5 |  | 1 | 86 |  |  |  | 1
87 |  | P5 Ph1 Task 4 | Person 4 | 2020-09-04 | 21 | 2020-09-02 | 24 | 2020-09-05 | 22 | 100% | Completed | Level 2 |  | 2020-10-02 | 2020-10-05 | 2020-10-05 | 21 | 24 | 22 | 2020-10-05 | 0 | 4 | Project Name 5 |  | 1 | 87 |  |  |  | 1
88 |  | P5 Ph1 Task 5 | Person 5 | 2020-07-31 | 11 | 2020-08-04 | 12 | 2020-08-05 | 15 | 100% | Completed | Level 3 |  | 2020-08-14 | 2020-08-19 | 2020-08-25 | 11 | 12 | 15 | 2020-08-25 | 0 | 4 | Project Name 5 |  | 1 | 88 |  |  |  | 1
89 |  | P5 Ph1 Task 6 | Person 6 | 2020-09-24 | 20 | 2020-09-23 | 24 | 2020-09-26 | 24 | 50% | In Progress | Level 3 |  | 2020-10-21 | 2020-10-26 | 2020-10-28 | 20 | 24 | 12 | 2020-10-28 | 0 | 4 | Project Name 5 |  | 1 | 89 |  |  |  | 1
90 | Phase | P5 Phase 2 | Person 8 | 2020-08-26 | 34 | 2020-08-28 | 38 | 2020-08-29 | 35 | 90% | In Progress | Level 2 |  | 2020-10-12 | 2020-10-20 | 2020-10-15 | 34 | 38 | 31.5 | 2020-10-15 | 2 | 2 | Project Name 5 |  | 1 | 90 |  |  |  | 1
91 | Task | P5 Ph2 Task 1 | Person 8 | 2020-09-13 | 29 | 2020-09-15 | 34 | 2020-09-17 | 30 | 50% | In Progress | Level 1 |  | 2020-10-21 | 2020-10-30 | 2020-10-28 | 29 | 34 | 15 | 2020-10-28 | 4 | 4 | Project Name 5 |  | 1 | 91 |  |  |  | 1
92 |  | P5 Ph2 Task 2 | Person 9 | 2020-08-13 | 17 | 2020-08-14 | 22 | 2020-08-14 | 19 | 50% | In Progress | Level 2 |  | 2020-09-04 | 2020-09-14 | 2020-09-09 | 17 | 22 | 9.5 | 2020-09-09 | 0 | 4 | Project Name 5 |  | 1 | 92 |  |  |  | 1
93 |  | P5 Ph2 Task 3 | Person 10 | 2020-09-16 | 21 | 2020-09-15 | 24 | 2020-09-17 | 26 | 30% | In Progress | Level 3 |  | 2020-10-14 | 2020-10-16 | 2020-10-22 | 21 | 24 | 7.8 | 2020-10-22 | 0 | 4 | Project Name 5 |  | 1 | 93 |  |  |  | 1
94 |  | P5 Ph2 Task 4 | Person 11 | 2020-09-12 | 39 | 2020-09-07 | 40 | 2020-09-14 | 42 | 30% | In Progress | Level 2 |  | 2020-11-04 | 2020-10-30 | 2020-11-10 | 39 | 40 | 12.6 | 2020-11-10 | 0 | 4 | Project Name 5 |  | 1 | 94 |  |  |  | 1
95 | Subtask | P5 Ph2 Task 4 Sub task 1 | Person 12 | 2020-07-20 | 35 | 2020-07-23 | 38 | 2020-07-23 | 36 | 60% | In Progress | Level 3 |  | 2020-09-04 | 2020-09-14 | 2020-09-10 | 35 | 38 | 21.6 | 2020-09-10 | 5 | 5 | Project Name 5 |  | 1 | 95 |  |  |  | 1
96 |  | P5 Ph2 Task 4 Sub task 2 | Person 13 | 2020-10-27 | 18 | 2020-10-27 | 20 | 2020-10-29 | 20 | 0% | Not Started | Level 3 |  | 2020-11-19 | 2020-11-23 | 2020-11-25 | 18 | 20 | 0 | 2020-11-25 | 0 | 5 | Project Name 5 |  | 1 | 96 |  |  |  | 1
97 |  | P5 Ph2 Task 4 Sub task 3 | Person 14 | 2020-09-02 | 23 | 2020-09-07 | 28 | 2020-09-04 | 28 | 10% | In Progress | Level 3 |  | 2020-10-02 | 2020-10-14 | 2020-10-13 | 23 | 28 | 2.8 | 2020-10-13 | 0 | 5 | Project Name 5 |  | 1 | 97 |  |  |  | 1
98 | Task | P5 Ph2 Task 5 | Person 8 | 2020-10-01 | 14 | 2020-10-03 | 17 | 2020-10-04 | 17 | 30% | In Progress | Level 3 |  | 2020-10-20 | 2020-10-26 | 2020-10-26 | 14 | 17 | 5.1 | 2020-10-26 | 4 | 4 | Project Name 5 |  | 1 | 98 |  |  |  | 1
99 |  | P5 Ph2 Task 6 | Person 9 | 2020-09-12 | 41 | 2020-09-12 | 45 | 2020-09-13 | 46 | 0% | Not Started | Level 3 |  | 2020-11-06 | 2020-11-12 | 2020-11-13 | 41 | 45 | 0 | 2020-11-13 | 0 | 4 | Project Name 5 |  | 1 | 99 |  |  |  | 1
100 |  | P5 Ph2 Task 7 | Person 10 | 2020-09-13 | 34 | 2020-09-08 | 36 | 2020-09-17 | 39 | 0% | Not Started | Level 3 |  | 2020-10-28 | 2020-10-27 | 2020-11-10 | 34 | 36 | 0 | 2020-11-10 | 0 | 4 | Project Name 5 |  | 1 | 100 |  |  |  | 1
101 |  | P5 Ph2 Task 8 | Person 15 | 2020-09-25 | 9 | 2020-09-29 | 14 | 2020-09-29 | 11 | 70% | In Progress | Level 1 |  | 2020-10-07 | 2020-10-16 | 2020-10-13 | 9 | 14 | 7.7 | 2020-10-13 | 0 | 4 | Project Name 5 |  | 1 | 101 |  |  |  | 1
102 | Project | Project Name 6 | Person 1 | 2020-09-26 | 71 | 2020-09-25 | 75 | 2020-09-29 | 73 | 30% | In Progress | Level 2 |  | 2021-01-01 | 2021-01-07 | 2021-01-07 | 71 | 75 | 21.9 | 2021-01-07 | 1 | 1 | Project Name 6 | 6 | 1 | 102 |  | 1 | 6 | 1
103 | Phase | P6 Phase 1 | Person 2 | 2020-11-13 | 39 | 2020-11-17 | 44 | 2020-11-17 | 42 | 40% | In Progress | Level 3 |  | 2021-01-06 | 2021-01-15 | 2021-01-13 | 39 | 44 | 16.8 | 2021-01-13 | 2 | 2 | Project Name 6 |  | 1 | 103 |  |  |  | 1
104 | Task | P6 Ph1 Task 1 | Person 1 | 2020-09-28 | 13 | 2020-09-30 | 15 | 2020-09-29 | 16 | 30% | In Progress | Level 1 |  | 2020-10-14 | 2020-10-20 | 2020-10-20 | 13 | 15 | 4.8 | 2020-10-20 | 4 | 4 | Project Name 6 |  | 1 | 104 |  |  |  | 1
105 |  | P6 Ph1 Task 2 | Person 2 | 2020-10-24 | 8 | 2020-10-23 | 9 | 2020-10-26 | 9 | 80% | In Progress | Level 2 |  | 2020-11-03 | 2020-11-04 | 2020-11-05 | 8 | 9 | 7.2 | 2020-11-05 | 0 | 4 | Project Name 6 |  | 1 | 105 |  |  |  | 1
106 |  | P6 Ph1 Task 3 | Person 3 | 2020-11-03 | 16 | 2020-11-07 | 18 | 2020-11-04 | 18 | 40% | In Progress | Level 3 |  | 2020-11-24 | 2020-12-01 | 2020-11-27 | 16 | 18 | 7.2 | 2020-11-27 | 0 | 4 | Project Name 6 |  | 1 | 106 |  |  |  | 1
107 |  | P6 Ph1 Task 4 | Person 4 | 2020-09-29 | 25 | 2020-10-01 | 30 | 2020-10-03 | 27 | 50% | In Progress | Level 3 |  | 2020-11-02 | 2020-11-11 | 2020-11-09 | 25 | 30 | 13.5 | 2020-11-09 | 0 | 4 | Project Name 6 |  | 1 | 107 |  |  |  | 1
108 |  | P6 Ph1 Task 5 | Person 5 | 2020-11-23 | 15 | 2020-11-25 | 19 | 2020-11-25 | 17 | 20% | In Progress | Level 1 |  | 2020-12-11 | 2020-12-21 | 2020-12-17 | 15 | 19 | 3.4 | 2020-12-17 | 0 | 4 | Project Name 6 |  | 1 | 108 |  |  |  | 1
109 |  | P6 Ph1 Task 6 | Person 6 | 2020-10-25 | 18 | 2020-10-21 | 21 | 2020-10-28 | 21 | 0% | Not Started | Level 1 |  | 2020-11-17 | 2020-11-18 | 2020-11-25 | 18 | 21 | 0 | 2020-11-25 | 0 | 4 | Project Name 6 |  | 1 | 109 |  |  |  | 1
110 | Phase | P6 Phase 2 | Person 8 | 2020-11-12 | 37 | 2020-11-16 | 39 | 2020-11-14 | 38 | 0% | Not Started | Level 2 |  | 2021-01-01 | 2021-01-07 | 2021-01-05 | 37 | 39 | 0 | 2021-01-05 | 2 | 2 | Project Name 6 |  | 1 | 110 |  |  |  | 1
111 | Task | P6 Ph2 Task 1 | Person 8 | 2020-10-12 | 27 | 2020-10-08 | 28 | 2020-10-13 | 32 | 0% | Not Started | Level 3 |  | 2020-11-17 | 2020-11-16 | 2020-11-25 | 27 | 28 | 0 | 2020-11-25 | 4 | 4 | Project Name 6 |  | 1 | 111 |  |  |  | 1
112 |  | P6 Ph2 Task 2 | Person 9 | 2020-11-15 | 16 | 2020-11-14 | 20 | 2020-11-19 | 17 | 0% | Not Started | Level 1 |  | 2020-12-04 | 2020-12-10 | 2020-12-11 | 16 | 20 | 0 | 2020-12-11 | 0 | 4 | Project Name 6 |  | 1 | 112 |  |  |  | 1
113 |  | P6 Ph2 Task 3 | Person 10 | 2020-11-11 | 21 | 2020-11-15 | 25 | 2020-11-13 | 23 | 0% | Not Started | Level 2 |  | 2020-12-09 | 2020-12-17 | 2020-12-15 | 21 | 25 | 0 | 2020-12-15 | 0 | 4 | Project Name 6 |  | 1 | 113 |  |  |  | 1
114 |  | P6 Ph2 Task 4 | Person 11 | 2020-09-18 | 40 | 2020-09-19 | 42 | 2020-09-20 | 41 | 0% | Not Started | Level 3 |  | 2020-11-12 | 2020-11-16 | 2020-11-13 | 40 | 42 | 0 | 2020-11-13 | 0 | 4 | Project Name 6 |  | 1 | 114 |  |  |  | 1
115 |  | P6 Ph2 Task 4 Sub task 1 | Person 12 | 2020-12-26 | 41 | 2020-12-28 | 42 | 2020-12-29 | 43 | 0% | Not Started | Level 1 |  | 2021-02-19 | 2021-02-23 | 2021-02-25 | 41 | 42 | 0 | 2021-02-25 | 0 | 4 | Project Name 6 |  | 1 | 115 |  |  |  | 1
116 |  | P6 Ph2 Task 4 Sub task 2 | Person 13 | 2020-11-01 | 22 | 2020-10-31 | 26 | 2020-11-02 | 27 | 0% | Not Started | Level 2 |  | 2020-11-30 | 2020-12-04 | 2020-12-08 | 22 | 26 | 0 | 2020-12-08 | 0 | 4 | Project Name 6 |  | 1 | 116 |  |  |  | 1
117 |  | P6 Ph2 Task 4 Sub task 3 | Person 14 | 2020-11-30 | 29 | 2020-12-04 | 32 | 2020-12-02 | 33 | 0% | Not Started | Level 3 |  | 2021-01-07 | 2021-01-18 | 2021-01-15 | 29 | 32 | 0 | 2021-01-15 | 0 | 4 | Project Name 6 |  | 1 | 117 |  |  |  | 1
118 |  | P6 Ph2 Task 5 | Person 8 | 2020-11-11 | 15 | 2020-11-07 | 20 | 2020-11-12 | 17 | 0% | Not Started | Level 1 |  | 2020-12-01 | 2020-12-03 | 2020-12-04 | 15 | 20 | 0 | 2020-12-04 | 0 | 4 | Project Name 6 |  | 1 | 118 |  |  |  | 1
119 |  | P6 Ph2 Task 6 | Person 9 | 2020-11-12 | 46 | 2020-11-13 | 48 | 2020-11-16 | 48 | 0% | Not Started | Level 2 |  | 2021-01-14 | 2021-01-19 | 2021-01-20 | 46 | 48 | 0 | 2021-01-20 | 0 | 4 | Project Name 6 |  | 1 | 119 |  |  |  | 1
120 |  | P6 Ph2 Task 7 | Person 10 | 2020-11-24 | 33 | 2020-11-22 | 34 | 2020-11-27 | 38 | 0% | Not Started | Level 3 |  | 2021-01-07 | 2021-01-06 | 2021-01-19 | 33 | 34 | 0 | 2021-01-19 | 0 | 4 | Project Name 6 |  | 1 | 120 |  |  |  | 1
121 |  | P6 Ph2 Task 8 | Person 15 | 2020-11-25 | 13 | 2020-11-27 | 16 | 2020-11-27 | 18 |  |  |  |  | 2020-12-11 | 2020-12-18 | 2020-12-22 | 13 | 16 | 0 | 2020-12-22 | 0 | 4 | Project Name 6 |  | 1 | 121 |  |  |  | 1
122 | [20 empty] | 0 | 4 | Project Name 6
123 | [20 empty] | 0 | 4 | Project Name 6
124 | [20 empty] | 0 | 4 | Project Name 6
125 | [20 empty] | 0 | 4 | Project Name 6
126 | [20 empty] | 0 | 4 | Project Name 6
127 | [20 empty] | 0 | 4 | Project Name 6
128 | [20 empty] | 0 | 4 | Project Name 6
129 | [20 empty] | 0 | 4 | Project Name 6
130 | [20 empty] | 0 | 4 | Project Name 6
131 | [20 empty] | 0 | 4 | Project Name 6
132 | [20 empty] | 0 | 4 | Project Name 6
133 | [20 empty] | 0 | 4 | Project Name 6
134 | [20 empty] | 0 | 4 | Project Name 6
135 | [20 empty] | 0 | 4 | Project Name 6
136 | [20 empty] | 0 | 4 | Project Name 6
137 | [20 empty] | 0 | 4 | Project Name 6
138 | [20 empty] | 0 | 4 | Project Name 6
139 | [20 empty] | 0 | 4 | Project Name 6
140 | [20 empty] | 0 | 4 | Project Name 6
141 | [20 empty] | 0 | 4 | Project Name 6
142 | [20 empty] | 0 | 4 | Project Name 6
143 | [20 empty] | 0 | 4 | Project Name 6
144 | [20 empty] | 0 | 4 | Project Name 6
145 | [20 empty] | 0 | 4 | Project Name 6
146 | [20 empty] | 0 | 4 | Project Name 6
147 | [20 empty] | 0 | 4 | Project Name 6
148 | [20 empty] | 0 | 4 | Project Name 6
149 | [20 empty] | 0 | 4 | Project Name 6
150 | [20 empty] | 0 | 4 | Project Name 6
151 | [20 empty] | 0 | 4 | Project Name 6
152 | [20 empty] | 0 | 4 | Project Name 6
153 | [20 empty] | 0 | 4 | Project Name 6
154 | [20 empty] | 0 | 4 | Project Name 6
155 | [20 empty] | 0 | 4 | Project Name 6
156 | [20 empty] | 0 | 4 | Project Name 6
157 | [20 empty] | 0 | 4 | Project Name 6
158 | [20 empty] | 0 | 4 | Project Name 6
159 | [20 empty] | 0 | 4 | Project Name 6
160 | [20 empty] | 0 | 4 | Project Name 6
161 | [20 empty] | 0 | 4 | Project Name 6
162 | [20 empty] | 0 | 4 | Project Name 6
163 | [20 empty] | 0 | 4 | Project Name 6
164 | [20 empty] | 0 | 4 | Project Name 6
165 | [20 empty] | 0 | 4 | Project Name 6
166 | [20 empty] | 0 | 4 | Project Name 6
167 | [20 empty] | 0 | 4 | Project Name 6
168 | [20 empty] | 0 | 4 | Project Name 6
169 | [20 empty] | 0 | 4 | Project Name 6
170 | [20 empty] | 0 | 4 | Project Name 6
171 | [20 empty] | 0 | 4 | Project Name 6
172 | [20 empty] | 0 | 4 | Project Name 6
173 | [20 empty] | 0 | 4 | Project Name 6
174 | [20 empty] | 0 | 4 | Project Name 6
175 | [20 empty] | 0 | 4 | Project Name 6
176 | [20 empty] | 0 | 4 | Project Name 6
177 | [20 empty] | 0 | 4 | Project Name 6
178 | [20 empty] | 0 | 4 | Project Name 6
179 | [20 empty] | 0 | 4 | Project Name 6
180 | [20 empty] | 0 | 4 | Project Name 6
181 | [20 empty] | 0 | 4 | Project Name 6
182 | [20 empty] | 0 | 4 | Project Name 6
183 | [20 empty] | 0 | 4 | Project Name 6
184 | [20 empty] | 0 | 4 | Project Name 6
185 | [20 empty] | 0 | 4 | Project Name 6
186 | [20 empty] | 0 | 4 | Project Name 6
187 | [20 empty] | 0 | 4 | Project Name 6
188 | [20 empty] | 0 | 4 | Project Name 6
189 | [20 empty] | 0 | 4 | Project Name 6
190 | [20 empty] | 0 | 4 | Project Name 6
Formulas:
DO NOT CHANGE: Formula/Calculations = IFERROR(IF(tbl_Tasks[[#This Row],[PLAN START]]="","",WORKDAY.INTL(tbl_Tasks[[#This Row],[PLAN START]],tbl_Tasks[[#This Row],[PLAN DURATION]]-1,rngWH_Weekends, rngWH_Holidays)),"")
BASELINE END = IFERROR(IF(tbl_Tasks[[#This Row],[BASELINE START]]="","",WORKDAY.INTL(tbl_Tasks[[#This Row],[BASELINE START]],tbl_Tasks[[#This Row],[BASELINE DURATION]]-1,rngWH_Weekends, rngWH_Holidays)),"")
ACTUAL END = IFERROR(IF(tbl_Tasks[[#This Row],[ACTUAL START]]="","",WORKDAY.INTL(tbl_Tasks[[#This Row],[ACTUAL START]],tbl_Tasks[[#This Row],[ACTUAL DURATION]]-1,rngWH_Weekends, rngWH_Holidays)),"")
TIMELINE = IF(Gantt_Calc!$L39=Gantt_Calc!$L40,tbl_Tasks[[#This Row],[PLAN END]],IF(Gantt_Calc!$L39=Gantt_Calc!$L41,tbl_Tasks[[#This Row],[BASELINE END]],tbl_Tasks[[#This Row],[ACTUAL END]]))
H

## Notes
Your Company Name |  |  | Important Notes
+ | COMPANY DETAILS
| Name of the Organization | Your Company Name |  |  |  | NAME
| DATE |  |  | LAST UPDATED |  | EMAIL
| Project Description |  |  |  |  | Project Notes
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
+ | PROJECT SPECIFICATIONS
| Project Specification |  |  |  |  | Project Deliverables
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
| Brief description about project … |  |  |  |  | Brief description about project …
+ | PROJECT CONTACTS
| MANAGERS | Details |  |  | TEAM LEADERS | CLIENTS | Details | STAKEHOLDERS
| Name of the Manager | NAME |  |  | Name of the Team Leader | Name of the Client 1 | NAME | Name of the Stakeholder 1
| Email address | Email |  |  | Email address | Email address | Email | Email address
| Phone Number Primary | Office Number |  |  | Phone Number Primary | Phone Number Primary | Office Number | Phone Number Primary
| Phone Number Secondary | Mobile Number |  |  | Phone Number Secondary | Phone Number Secondary | Mobile Number | Phone Number Secondary
| Name of the Developer | NAME |  |  | Name of the Analyst | Name of the Client 2 | NAME | Name of the Stakeholder 2
| Email address | Email |  |  | Email address | Email address | Email | Email address
| Phone Number Primary | Office Number |  |  | Phone Number Primary | Phone Number Primary | Office Number | Phone Number Primary
| Phone Number Secondary | Mobile Number |  |  | Phone Number Secondary | Phone Number Secondary | Mobile Number | Phone Number Secondary
| Name of the Tester | NAME |  |  | Name of the Approver | Name of the Client 3 | NAME | Name of the Stakeholder 3
| Email address | Email |  |  | Email address | Email address | Email | Email address
| Phone Number Primary | Office Number |  |  | Phone Number Primary | Phone Number Primary | Office Number | Phone Number Primary
| Phone Number Secondary | Mobile Number |  |  | Phone Number Secondary | Phone Number Secondary | Mobile Number | Phone Number Secondary
H

## Lists
Lists
Calculations
SNO | Project Status | Project Complexity | Project Progress | DB SUMMARY STATUS | DB ACTIVITY STATUS | ST ACTIVITY STATUS
1 | Not Started | Level 1 | 0% | 0 | 2 | 34
2 | In Progress | Level 2 | 10% | 3 | 6 | 34
3 | Completed | Level 3 | 20% | 3 | 6 | 18
4 | On Hold |  | 30% | 0 | 0 | 2
5 | Cancelled |  | 40% | 0 | 0 | 2
6 |  |  | 50%
7 |  |  | 60%
8 |  |  | 70%
9 |  |  | 80%
10 |  |  | 90%
11 |  |  | 100%
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Always leave the first row of this Lists Table as Blank
H

## Weekends - Holidays
Weekends & Holidays
Company Weekends |  | Company Holidays
|  | Required | Optional
DAY | WEEKEND? | Date | [Description]
MONDAY | No | 2020-01-01 | New Year
TUESDAY | No
WEDNESDAY | No
THURSDAY | No
FRIDAY | No
SATURDAY | Yes
SUNDAY | Yes
H

## Calculation (hidden)
| Date | Position
Project Start | 0 | 4
Project End | 0 | 4
Selected Structure | List Row | Row | Items
Model - 4 | 16 | 32 | 5
DAY | WEEKEND |  | Start Day of Week
MONDAY | 0 |  | 2018-01-01 | 2 | Mon
TUESDAY | 0 |  | 2018-01-02 | 3 | Tue
WEDNESDAY | 0 |  | 2018-01-03 | 4 | Wed
THURSDAY | 0 |  | 2018-01-04 | 5 | Thu
FRIDAY | 0 |  | 2018-01-05 | 6 | Fri
SATURDAY | 1 |  | 2018-01-06 | 7 | Sat
SUNDAY | 1 |  | 2018-01-07 | 1 | Sun
0000011
Template String | /AT-?X!-ATPMS-!X?-AT/
Status Labels
Completed | Completed
In Progress | In Progress
Not Started | Not Started

## Preferences
Preferences
Project Structure | Model - 4 | << Required First Time
Model - 1 | Items | Plural | 2
| Project | Projects
| Tasks | Tasks
Model - 2 | Items | Plural | 3
| Project | Projects
| Milestone | Milestones
| Task | Tasks
Model - 3 | Items | Plural | 4
| Project | Projects
| Milestone | Milestones
| Task | Tasks
| Subtask | Subtasks
Model - 4 | Items | Plural | 5
| Project | Projects
| Phase | Phases
| Milestone | Milestones
| Task | Tasks
| Subtask | Subtasks
Custom | Items* | Plural* | 10
Top Level
Secondary Level 1
Secondary Level 2
Secondary Level 3
Secondary Level 4
Secondary Level 5
Secondary Level 6
Secondary Level 7
Secondary Level 8
Secondary Level 9
H

## Label Manager
Your Company Name |  |  | Template Labels
Sheet Name | Object | Object Default Label | New Label | Label
Index | Doughnut Chart | TOTAL PROJECTS: 6 |  | TOTAL PROJECTS: 6
Index | Doughnut Chart | 3 Projects Completed |  | 3 Projects Completed
Index | Bar Chart | TOTAL ACTIVITIES: 121 |  | TOTAL ACTIVITIES: 121
Index | Column Chart | PROJECTS PROGRESS |  | PROJECTS PROGRESS
Index | Left Menu Item | DASHBOARD |  | DASHBOARD
Index | Left Menu Item | STATUS |  | STATUS
Index | Left Menu Item | GANTT |  | GANTT
Index | Left Menu Item | TIMELINE |  | TIMELINE
Index | Left Menu Item | TEAM |  | TEAM
Index | Left Menu Item | TASKS |  | TASKS
Index | Left Menu Item | NOTES |  | NOTES
Index | Left Menu Item | LISTS |  | LISTS
Index | Left Menu Item | HOLIDAYS |  | HOLIDAYS
Index | Left Menu Item | PREFERENCES |  | PREFERENCES
Index | Left Menu Item | LABELS |  | LABELS
Index | Left Menu Item | HELP? |  | HELP?
Dashboard | Top Header | Dashboard |  | Dashboard
Dashboard | Section 1 - Title | Projects Summary |  | Projects Summary
Dashboard | Section 1 - Bar Chart | Activities Assigned by Person |  | Activities Assigned by Person
Dashboard | Section 1 - Column Chart | Projects - Status |  | Projects - Status
Dashboard | Section 2 - Title | PROJECT NAME 1 - Tasks |  | PROJECT NAME 1 - Tasks
Dashboard | Section 2 - Doughnut Chart | PROJECT NAME 1 - Tasks: Progress |  | PROJECT NAME 1 - Tasks: Progress
Dashboard | Section 2 - Bar Chart 1 | PROJECT NAME 1 - Tasks: Man-days |  | PROJECT NAME 1 - Tasks: Man-days
Dashboard | Section 2 - Column Chart | PROJECT NAME 1 - Tasks: Status |  | PROJECT NAME 1 - Tasks: Status
Dashboard | Section 2 - Bar Chart 2 | PROJECT NAME 1 - Tasks: Progress |  | PROJECT NAME 1 - Tasks: Progress
Dashboard | Section 2 - Bar Chart 3 | PROJECT NAME 1 - Tasks by Person |  | PROJECT NAME 1 - Tasks by Person
Dashboard | Section 2 - Bar Chart 4 | PROJECT NAME 1 - Tasks Progress by Person |  | PROJECT NAME 1 - Tasks Progress by Person
Status | Top Header | Status Report |  | Status Report
Status | Section 1 - Column Chart 1 | Projects ¦ Tasks by Status |  | Projects ¦ Tasks by Status
Status | Section 1 - Column Chart 2 | Projects ¦ Tasks - Scheduled to finish by Today |  | Projects ¦ Tasks - Scheduled to finish by Today
Status | Section 1 - Column Chart 3 | Projects ¦ Tasks Status of Overdue Tasks |  | Projects ¦ Tasks Status of Overdue Tasks
Status | Section 2 - Title | Projects ¦ Tasks Due This Week & Status |  | Projects ¦ Tasks Due This Week & Status
Status | Section 3 - Title | Projects ¦ Tasks Due This Month & Status |  | Projects ¦ Tasks Due This Month & Status
Status | Section 4 - Title | Projects ¦ Tasks Due 2022 Year Calendar |  | Projects ¦ Tasks Due 2022 Year Calendar
Gantt | Bar Chart | ACTUAL TIMELINES |  | ACTUAL TIMELINES
Timeline | Top Header | Project Timeline |  | Project Timeline
Timeline | XY Chart | ALL PROJECT - ACTUAL TIMELINES |  | ALL PROJECT - ACTUAL TIMELINES
TEAM | Top Header | Projects Team |  | Projects Team
Tasks | Top Header | Projects & Tasks |  | Projects & Tasks
Notes | Top Header | Important Notes |  | Important Notes
Lists | Top Header | Lists |  | Lists
Weekends Holidays | Top Header | Weekends & Holidays |  | Weekends & Holidays
Preferences | Top Header | Preferences |  | Preferences
Label Manager | Top Header | Template Labels |  | Template Labels
Help | Top Header | Help? |  | Help?
H

## Help
Help?
Please follow the below instructions and same order while entering the data.
1 | Enter the project team details in 'Team' sheet
2 | Enter the project, phases, task details in the 'Tasks' sheet as shown in the sample records
H